## Work Plan
ESTI TECH FELLOW – 1-YEAR WORK PLAN
African Union – Science, Technology and Innovation Strategy for Africa (STISA-2034)
Phase | Task | Key Deliverables | Status | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Phase 1 Discovery & Planning | Conduct ESTI website audit | Website audit report (content gaps, structure issues, missing sections) | Planned | █
| Stakeholder consultations (ESTI divisions) | Requirements document for portal + tracking system | Planned | █
| Define STISA-2034 indicators framework (with teams) | Draft tracking framework aligned with AU priorities | Planned | █ | █
| Map innovation ecosystem (hubs, institutions, partners) | Database of hubs across 5 AU regions | Planned |  | █
| Develop overall system architecture | Concept note for portal + tracking + networking platform | Planned |  | █
Phase 2 Website Enhancement | Restructure ESTI website content | New sitemap + improved content sections (Programs, Youth, Innovation, Events, Publications) | Planned |  | █ | █
| Update and upload content | Updated pages reflecting divisions, initiatives, and impact | Planned |  |  | █ | █
| Introduce content workflow system | Template for divisions to submit updates regularly | Planned |  |  | █
| Improve media & storytelling | News, highlights, and featured stories added | Planned |  |  | █ | █ | █
Phase 3 Portal Development | Design centralized ESTI portal UI/UX | Wireframes and system design prototype | Planned |  |  | █ | █
| Develop portal (MVP) integrated with AU web infrastructure | Functional portal with sections for STI, Space, Education, Innovation | Planned |  |  |  | █ | █ | █
| Add content modules (documents, initiatives, dashboards) | Fully structured portal content system | Planned |  |  |  |  | █ | █
| Testing and internal validation | Tested and refined portal (internal use) | Planned | [5 empty] | █
Phase 4 STISA-2034 Tracking | Design reporting framework for Member States | Reporting templates and submission format | Planned |  |  |  |  | █ | █
| Develop tracking dashboard (MVP) | Basic dashboard for monitoring implementation | Planned | [5 empty] | █ | █
| Pilot with selected Member States | Pilot feedback report | Planned | [6 empty] | █ | █
| Improve and finalize system | Refined tracking system ready for rollout | Planned | [7 empty] | █ | █
Phase 5 Innovation Hub Networking | Design networking platform structure | Platform concept (profiles, connections, collaboration features) | Planned | [5 empty] | █ | █
| Develop platform (MVP) | Functional networking system linking hubs | Planned | [6 empty] | █ | █ | █
| Upload hub profiles and data | Active database of innovation hubs | Planned | [7 empty] | █ | █
| Enable basic interaction features | Messaging / connection / collaboration features | Planned | [8 empty] | █ | █
Phase 6 Visibility & Engagement | Launch LinkedIn engagement strategy | Monthly content calendar + ESTI visibility posts | Planned |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
| Produce "30 Seconds with ESTI" videos | 2–4 videos per month (staff awareness series) | Planned |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █
| Cover events and initiatives digitally | Event posts, highlights, storytelling | Planned |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █
Phase 7 Integration & Optimization | Integrate portal + tracking + networking systems | Unified ecosystem platform | Planned | [8 empty] | █ | █
| Improve system performance and usability | Optimization report and updates | Planned | [9 empty] | █ | █
| Develop user guidelines | Manuals for ESTI staff and Member States | Planned | [9 empty] | █ | █
Phase 8 Finalization & Handover | Full system deployment | Live ESTI portal with tracking + networking features | Planned | [10 empty] | █
| Training sessions for ESTI teams | Capacity-building workshops | Planned | [10 empty] | █ | █
| Final report and sustainability plan | 1-year impact report + roadmap for scale | Planned | [11 empty] | █

## AI Integration Plan
POSSIBLE AI INTEGRATION PLAN FOR ESTI SYSTEM
Proposed AI capabilities to enhance the ESTI portal, tracking system, and networking platform
System / Module | AI Feature | What It Does | How It Works
1. Divisional Portal (Website & Knowledge Hub) | A. Document Summarization | Auto-generate short summaries for reports, policies, and publications. | Use existing ESTI documents (PDFs, reports) → process with AI → store summaries at the top of each document page.
| B. AI Knowledge Assistant (Chat) | Users can ask questions about ESTI, programs, and policies. | Use ESTI website content + uploaded documents as the knowledge base → connect to a chatbot (RAG system).
2. STISA-2034 Tracking & Reporting System | A. Report Summarization | Automatically extract key insights from Member State submissions. | Use submitted country reports → AI generates highlights, challenges, and recommendations → display in dashboard.
| B. Progress Classification | Categorize countries (e.g., "On Track / Needs Attention"). | Use reporting data and indicators → apply AI-based text + data analysis → assign simple performance labels.
3. Innovation Hub Networking Platform | A. Smart Matching System | Connect hubs, partners, and institutions automatically. | Use hub profiles (sector, location, focus areas) → AI suggests relevant partnerships.
| B. Recommendation Engine | Suggest opportunities, hubs, and collaborations. | Use platform activity + hub data → AI recommends similar organizations and relevant programs.

## Summary Dashboard
WORK PLAN – SUMMARY DASHBOARD
Phase | Start Month | End Month | # Tasks | Status
Phase 1 – Discovery & Planning | 1 | 2 | 5 | Planned
Phase 2 – Website Enhancement | 2 | 5 | 4 | Planned
Phase 3 – Portal Development | 3 | 6 | 4 | Planned
Phase 4 – STISA-2034 Tracking | 5 | 9 | 4 | Planned
Phase 5 – Innovation Hub Networking | 6 | 10 | 4 | Planned
Phase 6 – Visibility & Engagement | 3 | 12 | 3 | Ongoing
Phase 7 – Integration & Optimization | 9 | 11 | 3 | Planned
Phase 8 – Finalization & Handover | 11 | 12 | 3 | Planned
TOTAL