## How to use
Training roadmap (v1.1)
Yellow cells are yours to fill in. Grey cells work themselves out.
Part | What to do
Goals | Record up to five goals, with a measure, baseline, target and owner. The capacity is not a recommended goal count. Keep fixed codes G1 to G5. A goal may need a workplace action rather than training; document that decision.
Initiatives | Record up to 20 initiatives, using fixed IDs 1 to 20. Link to a listed goal or All for shared groundwork. Complete audience, owner, measure, priority and status. Do not change the ID cells or sort individual columns.
People and hours | People must be positive whole numbers; hours each must be positive; cost must be zero or positive. Cost is planned external expenditure in the currency at C9, excluding staff salaries. A firm-wide average is not each learner’s workload; check cohort and facilitator time separately.
Quarters | Use Q1 to Q4 with end not before start. State the year and quarter basis. Example uses calendar 2027: Q1 Jan-Mar, Q2 Apr-Jun, Q3 Jul-Sep, Q4 Oct-Dec. Hours/cost spread evenly across active quarters; this is an allocation assumption, not cash-flow or delivery scheduling.
Depends on | One prerequisite ID per initiative. Lookup uses the ID, not its position. Missing, duplicate, self or invalid references are flagged. Same-quarter dependencies need actual-date checks; this file only clears a prerequisite ending in an earlier quarter. Do not use it to certify a complex dependency network.
Limits | Set budget, staff, learning-hour allowance and concurrent-initiative review threshold. Counts do not measure team capacity. Checks flag missing inputs, incomplete goals, uncovered goals, ordering questions, budget excess and average hours above the allowance. Checks clear means review the plan, not approval or proof of feasibility.
Review | Record a review point with a measure and owner. Revisit needs, audience availability, actual spend and work outcomes after the first phase. All sample organisations, targets, dates, hours and costs are fictional planning assumptions.

## Roadmap
Training roadmap (v1.1)
Start from the business goals. Every initiative should trace back to one.
Organisation |  | Fictional professional services firm, 80 staff |  |  |  |  | Total cost |  | 38000
Year |  | 2027 (calendar year) |  |  |  |  | Budget left |  | Over by 3,000
Staff |  | 80 |  |  |  |  | Learner hours |  | 1824
Budget |  | 35000 |  |  |  |  | Hours per person |  | 22.8 of 40
Hours per person (allowance) |  | 40 |  |  |  |  | Goals with no initiative |  | 0
Concurrent initiatives: review threshold |  | 4 |  |  |  |  | Rows needing inputs |  | 0
Currency |  | AUD |  |  |  |  | Dependencies to fix |  | 1
Quarter basis |  | Calendar year: Jan-Dec |  |  |  |  | Quarters above threshold |  | 1
[7 empty] | Plan checks |  | Review dependencies
Code | Business goal | Measure |  | Now | Target | Owner |  | Count | Status
G1 | Keep more clients | Client retention |  | 72% | 80% | Head of client services |  | 2 | Recorded
G2 | Cut rework on client reports | Reports returned for rework |  | 18% | 10% | Practice leads |  | 1 | Recorded
G3 | Get new starters productive sooner | Weeks to first billable project |  | 8 | 5 | HR manager |  | 1 | Recorded
G4 | Complete required refresher training | Completion of required refreshers |  | 64% | 100% by 30 June | Compliance manager |  | 1 | Recorded
G5
Qtr | Initiatives running | Learner hours | Cost | Limit
Q1 | 3 | 312 | 750 | OK
Q2 | 4 | 640 | 11250 | OK
Q3 | 5 | 552 | 19250 | Over by 1
Q4 | 2 | 320 | 6750 | OK
Total |  | 1824 | 38000
# | Initiative | Goal | Audience | People | Hours each | Learner hours | Cost | Start | End | Q1 | Q2 | Q3 | Q4 | Depends on (#) | Order check | Owner | Measure | Priority | Status |  |  |  | Input status
1 | Needs analysis with heads of department | All | Heads of department | 8 | 4 | 32 | 0 | Q1 | Q1 | ■ | [5 empty] | L&D lead | Needs list signed off | Must | Planned | 1 | 32 | 0 | OK
2 | Report writing and review course | G2 | Consultants | 40 | 6 | 240 | 6000 | Q2 | Q2 |  | ■ |  |  | 1 | OK | L&D lead | Rework rate | Must | Planned | 1 | 240 | 6000 | OK
3 | New starter academy, six stages | G3 | New starters | 12 | 20 | 240 | 9000 | Q2 | Q3 |  | ■ | ■ |  | 1 | OK | HR manager | Weeks to first billable project | Must | Planned | 2 | 120 | 4500 | OK
4 | Client conversations workshop series | G1 | Client-facing staff | 30 | 8 | 240 | 12000 | Q3 | Q4 |  |  | ■ | ■ | 6 | Same quarter: check dates | Head of client services | Client retention | Should | Planned | 2 | 120 | 6000 | OK
5 | Privacy and AML refresher | G4 | All staff | 80 | 2 | 160 | 0 | Q1 | Q2 | ■ | ■ |  |  |  |  | Compliance manager | Completion by 30 June | Must | In progress | 2 | 80 | 0 | OK
6 | Coaching skills for team leaders | G1 | Team leaders | 10 | 10 | 100 | 8000 | Q3 | Q3 |  |  | ■ |  | 1 | OK | L&D lead | Observed coaching conversations against agreed criteria | Should | Planned | 1 | 100 | 8000 | OK
7 | Self-paced tools library | All | All staff | 80 | 10 | 800 | 3000 | Q1 | Q4 | ■ | ■ | ■ | ■ |  |  | L&D lead | Hours used per person | Could | Planned | 4 | 200 | 750 | OK
8 | Review after the report-writing course | All | Leadership team | 6 | 2 | 12 | 0 | Q3 | Q3 |  |  | ■ |  | 2 | OK | CEO | Roadmap updated | Must | Planned | 1 | 12 | 0 | OK
9
10
11
12
13
14
15
16
17
18
19
20

## Roadmap or plan
Roadmap, plan, calendar or path?
Working descriptions; document names and time horizons overlap. Choose the detail needed for the decision.
Document | Covers | Time span | Answers
Training roadmap | The organisation or a department | Chosen planning horizon | Which initiatives, in what order, for which goals
Training plan | A team or one programme | Weeks to a year | Who takes which training, by when
Training calendar | Everyone attending sessions | Weeks to months | Dated sessions, rooms and trainers
Learning path | A role or one learner | Days to months | The order of courses one person works through
Curriculum map | A programme or qualification | The whole programme | Which course covers which outcome

## Sample sales academy
Sample: sales academy
Separate fictional programme, not a component of the annual firm example. Timings and checks are planning assumptions; confirm role-specific requirements before delivery.
Stage | When | Audience | Hours each | Measure
1 Product and market | Week 1 | New reps | 6 | Quiz pass
2 Our sales process | Week 2 | New reps | 4 | Process walkthrough
3 Discovery calls | Weeks 3 to 4 | New reps | 8 | Recorded role play
4 Demos and objections | Weeks 5 to 6 | New reps | 8 | Observed demo
5 Live calls with a buddy | Weeks 7 to 10 | New reps | 12 | Buddy feedback
6 Sign-off | Week 12 | New reps | 2 | Team-lead sign-off
Total hours each |  |  | 40

## Sample hospitality
Sample: hospitality
Separate fictional programme, not a component of the annual firm example. Timings and checks are planning assumptions; confirm role-specific requirements before delivery.
Stage | When | Audience | Hours each | Measure
Food safety and allergen procedures | Before relevant duties | All new staff | 1 | Approved knowledge and practical checks
Week 2 Service standards | Week 2 | Front of house | 1 | Manager check on shift
Allergen questions: supervised practice | After initial instruction, before independent duties | All staff | 1 | Observed use of approved information and referral
Week 4 Complaints and recovery | Week 4 | Front of house | 1 | Observed role play
Total hours each |  |  | 4

## Sample compliance path
Sample: compliance path
Separate fictional programme, not a component of the annual firm example. Timings and checks are planning assumptions; confirm role-specific requirements before delivery.
Stage | When | Audience | Hours each | Measure
1 Current rules | Q1 | All staff | 2 | Assessment pass
2 The firm's obligations | Q2 | All staff | 2 | Attestation
3 Upcoming changes | Q3 | Managers | 1 | Briefing attended
Total hours each |  |  | 5