CIPP Evaluation Plan Template

Plan context, input, process and product evaluation for one training programme or curriculum, with the decision each part should inform.

From the Coursebox blog: coursebox.ai/blog/cipp-model-for-training-evaluation

How to use this template

Fill in Part 1 with the people who asked for the evaluation before you collect any data. It sets who the evaluation is for and when they get findings.

You do not have to run all four parts, or run them in order. Pick the parts that match the decision in front of you.

Run a part during the programme to improve it (formative), and after to judge it (summative). The same question often serves both.

Write the decision each part informs. If no decision depends on a finding, you probably do not need to collect it.

Part 1. Agreement and audiences

| Item | Your answer |
| --- | --- |
| Programme or curriculum being evaluated |  |
| Who asked for the evaluation, and why now |  |
| Decisions the evaluation should inform |  |
| Stakeholders to involve (learners, managers, facilitators, funders, others) |  |
| Who receives findings, in what format |  |
| Reporting dates (formative updates and final report) |  |
| Budget and time available for the evaluation |  |
| Who reviews the evaluation itself (metaevaluation) |  |

Part 2. The four evaluations

One row per question. The example rows use the onboarding programme for new aged-care support workers from the article; replace them with your own.

| Part | Question | Evidence and source | Who and when | Decision it informs |
| --- | --- | --- | --- | --- |
| Context | What do new starters need to do safely in their first month, and does it differ by site? | Incident reports, supervisor interviews, exit interviews | Training lead, before design | Programme goals and priorities |
| Context |  |  |  |  |
| Input | Which delivery plan fits our budget, rosters and three sites best? | Two or three costed options, roster data, facilitator availability | Training lead and site managers, before build | Which plan to adopt |
| Input |  |  |  |  |
| Process | Is the programme being delivered as planned at every site? | Platform progress data, buddy-shift logs, facilitator notes | Training coordinator, weekly in the first cohort | Fixes during delivery |
| Process |  |  |  |  |
| Product | Did the right people get the training, and did their practice change? | Enrolment vs new-starter list, competency sign-offs, supervisor observation | Site managers, at day 30 and day 90 | Continue, change or stop |
| Product |  |  |  |  |

Part 3. Product evaluation in four parts

Stufflebeam's 2007 checklist splits product evaluation into four questions. Use the ones that matter for your decision.

| Sub-part | The question | Your measure | When |
| --- | --- | --- | --- |
| Impact | Did the programme reach the people it was meant for? |  |  |
| Effectiveness | Did it meet their needs and produce the intended outcomes, and any unintended ones? |  |  |
| Sustainability | Are the gains and the programme lasting, with ownership and funding in place? |  |  |
| Transportability | Could it work in another site, team or setting? |  |  |

Part 4. Findings log

| Date | Part | Finding | Shared with | Decision or action | Owner |
| --- | --- | --- | --- | --- | --- |

Before the final report, ask someone outside the programme to read the plan and the findings log and say where the evidence is thin. Stufflebeam calls this a metaevaluation.