## How to use
Customer onboarding templates (v1.1)
Yellow cells are yours to fill in. Grey cells work themselves out.
1. Handoff: sales records the purchase, goals and promises before the first onboarding meeting.
2. Intake form: send it to the customer before the kickoff. It collects the details setup needs.
3. Kickoff agenda: run the first meeting from it. It ends with first value and its date written down.
4. Onboarding plan: every task with a side (us, customer or both), an owner and a due date. Status is worked out against the 'as at' date at the top: Done, Blocked, Overdue or Open.
5. Training plan: enter a positive whole-number People count and Completed from 0 to People. Enter 0 when nobody has finished. Completion records attendance or course progress, not a skills assessment.
6. Welcome emails: adapt five messages to your dates and product. Check the stated progress and results before sending.
First value is an agreed early customer result. This workbook measures time from kickoff. Change the restaurant-specific questions, courses and dates for your own product.

## Onboarding plan
Onboarding plan
50 task rows (14 to 63). Replace the example with your tasks. Calculated columns: A, I, J and the summary.
As at |  | 2026-10-19 |  |  | Tasks | 0
Kickoff |  |  |  |  | Done | 0
First value |  |  |  |  | Done (%)
Target date |  |  |  |  | Overdue: us | 0
Actual date |  |  |  |  | Overdue: customer | 0
[5 empty] | Blocked | 0
Days to target
[5 empty] | Time to first value (days) | Not reached yet
# | Stage | Task | Side | Owner | Due | Done | Blocked by | Status | Days late

## Handoff
Sales to onboarding handoff
Sales fills this in before the kickoff. Write what the customer said, not what we hope.
Question | Answer
Customer
Contract start
What they bought
Why they bought, in their words
What success looks like in 90 days
Decision maker
Day-to-day contact
Systems to connect
Promises made in the sale
Risks
Deadline that cannot move

## Training plan
Customer training plan
15 role rows (6 to 20). Enter People and Completed, including zero completed. Status uses the As at date.
As at | 2026-10-19
Role | People | Must be able to | Course or session | Format | Length | Due | Completed | Done (%) | Status

## Intake form
Customer intake form
Send this to the customer before the kickoff. It collects what setup needs.
Question | Answer
Business name and venues
Opening hours for each venue
Where the current menu lives
POS system and who manages it
Website platform and who can edit it
Who approves menu and price changes
Staff who will use the system, by role
Busiest times to avoid for launch
Payments

## Kickoff agenda
Kickoff agenda (60 minutes)
Suggested 60-minute meeting. Adjust the timings and record the agreed decisions below.
Min | Item | Owner | Output
5 | Introductions and roles on both sides | Onboarding manager | Named contact for each task
10 | What the customer bought and why (from the handoff) | Account executive | Customer confirms the goal in their words
10 | Agree first value and its date | Onboarding manager | First value and target date written down
15 | Walk through the onboarding plan, task by task | Onboarding manager | Owners and due dates accepted
10 | Training: who needs what, by role | Onboarding manager | Training plan agreed
10 | Risks, deadlines and the next meeting | Both | Risks logged; next check-in booked
60 | Total minutes
| Decisions made at the kickoff |  | Answer
First value
Target date for first value
Venue admins named
Launch order

## Welcome emails
Welcome email sequence
Five suggested messages. Replace brackets, dates, role names and timings. Confirm every stated result before sending.
When | Subject | Email
Day 0, after signing | Welcome, and what happens next | Hi [Name], welcome aboard. I'm [Onboarding manager], and I'll look after your onboarding. Our first step is a 60-minute kickoff to agree your first goal, target date and responsibilities. Book a time: [Booking link]. Before then, fill in the intake form: [Intake link].
Day 1, before the kickoff | Before our kickoff on [date] | Hi [Name], looking forward to [date]. Please bring the person who will run the system day to day at each venue. We'll leave the call with a first goal, a date and a named owner for every task.
Day 3, during setup | Your setup: three things from your side | Hi [Name], your menus are in. To keep to [target date], we need three things from your team: [task 1], [task 2], [task 3]. The full plan, with who does what, is here: [link].
Day 10, training | Training for your team: 5 to 15 minutes each | Hi [Name], your team's training is ready. Admins: [Admin course link] (15 minutes). Kitchen: [Kitchen course link] (5 minutes). Front of house: [Front-of-house course link] (8 minutes). Please finish by [Due date]. These are the example roles and timings; replace them before sending.
Day 30, check-in | 30 days in: how is it going? | Hi [Name], let's review your first month. Your current progress is [Verified result or remaining tasks]. Please book a 30-minute check-in: [Check-in link]. We'll review the result, open questions and next steps.