## How to use
Customer onboarding templates (v1.1)
Fictional software company and three-venue restaurant group. Yellow cells are editable; grey cells calculate.
1. Handoff: sales records the purchase, goals and promises before the first onboarding meeting.
2. Intake form: send it to the customer before the kickoff. It collects the details setup needs.
3. Kickoff agenda: run the first meeting from it. It ends with first value and its date written down.
4. Onboarding plan: every task with a side (us, customer or both), an owner and a due date. Status is worked out against the 'as at' date at the top: Done, Blocked, Overdue or Open.
5. Training plan: enter a positive whole-number People count and Completed from 0 to People. Enter 0 when nobody has finished. Completion records attendance or course progress, not a skills assessment.
6. Welcome emails: adapt five messages to your dates and product. Check the stated progress and results before sending.
First value is an agreed early customer result. This workbook measures time from kickoff. Change the restaurant-specific questions, courses and dates for your own product.

## Onboarding plan
Onboarding plan
50 task rows (14 to 63). Replace the example with your tasks. Calculated columns: A, I, J and the summary.
As at |  | 2026-10-19 |  |  | Tasks | 20
Kickoff |  | 2026-10-01 |  |  | Done | 12
First value |  | First 50 online orders processed through the new system across all three venues |  |  | Done (%) | 60
Target date |  | 2026-10-30 |  |  | Overdue: us | 0
Actual date |  |  |  |  | Overdue: customer | 2
[5 empty] | Blocked | 1
[5 empty] | Days to target | 11
[5 empty] | Time to first value (days) | Not reached yet
# | Stage | Task | Side | Owner | Due | Done | Blocked by | Status | Days late
1 | Handoff | Account executive completes the handoff form | Us | Account executive | 2026-09-29 | 2026-09-29 |  | Done | 0
2 | Handoff | Onboarding manager reviews the handoff and books the kickoff | Us | Onboarding manager | 2026-09-30 | 2026-09-30 |  | Done | 0
3 | Kickoff | Kickoff call held; first value agreed and dated | Both | Onboarding manager | 2026-10-01 | 2026-10-01 |  | Done | 0
4 | Kickoff | Customer names an admin at each venue | Customer | Operations manager | 2026-10-02 | 2026-10-02 |  | Done | 0
5 | Setup | Menus imported for all three venues | Us | Implementation specialist | 2026-10-06 | 2026-10-05 |  | Done | 0
6 | Setup | Payment account verified in the payments portal | Customer | Owner | 2026-10-07 | 2026-10-09 |  | Done | 2
7 | Setup | Delivery zones and opening hours set for each venue | Customer | Venue admins | 2026-10-09 | 2026-10-08 |  | Done | 0
8 | Setup | Printers and tablets installed at venue 1 | Us | Field technician | 2026-10-12 | 2026-10-12 |  | Done | 0
9 | Setup | Printers and tablets installed at venues 2 and 3 | Us | Field technician | 2026-10-14 | 2026-10-14 |  | Done | 0
10 | Setup | Online ordering link added to the customer's website | Customer | Owner | 2026-10-14 |  |  | Overdue | 5
11 | Setup | POS integration switched on | Us | Implementation specialist | 2026-10-16 |  | Waiting for the POS provider's access key | Blocked
12 | Training | Venue admins complete the 15-minute admin course | Customer | Venue admins | 2026-10-13 | 2026-10-13 |  | Done | 0
13 | Training | Kitchen staff complete the 5-minute order-handling course | Customer | Venue admins | 2026-10-16 |  |  | Overdue | 3
14 | Training | Live questions session for venue managers | Us | Onboarding manager | 2026-10-15 | 2026-10-15 |  | Done | 0
15 | Training | Front-of-house staff complete the refunds course | Customer | Venue admins | 2026-10-21 |  |  | Open
16 | First value | Soft launch at venue 1 | Both | Onboarding manager | 2026-10-19 | 2026-10-19 |  | Done | 0
17 | First value | Launch at venues 2 and 3 | Both | Onboarding manager | 2026-10-23 |  |  | Open
18 | First value | First 50 online orders processed | Customer | Owner | 2026-10-30 |  |  | Open
19 | Check-in | Day 30 check-in: orders, support tickets, what is next | Both | Onboarding manager | 2026-11-02 |  |  | Open
20 | Check-in | Handover to the account manager | Us | Onboarding manager | 2026-11-06 |  |  | Open

## Handoff
Sales to onboarding handoff
Sales fills this in before the kickoff. Write what the customer said, not what we hope.
Question | Answer
Customer | A restaurant group with three venues
Contract start | 28 September 2026
What they bought | Online ordering for three venues, with POS integration
Why they bought, in their words | "We lose orders on the phone on Friday nights."
What success looks like in 90 days | Most takeaway orders come in online, and phone orders drop on weekends
Decision maker | Owner
Day-to-day contact | Operations manager
Systems to connect | Existing POS at all three venues
Promises made in the sale | Live at venue 1 before the end of October
Risks | The POS provider is slow to issue access keys
Deadline that cannot move | School holidays from 19 December (their busiest weeks)

## Training plan
Customer training plan
15 role rows (6 to 20). Enter People and Completed, including zero completed. Status uses the As at date.
As at | 2026-10-19
Role | People | Must be able to | Course or session | Format | Length | Due | Completed | Done (%) | Status
Venue admins | 3 | Update menus, hours and delivery zones; pause online orders | Admin course | Online course | 15 min | 2026-10-13 | 3 | 100 | Done
Venue managers | 3 | Read the daily orders report; handle a missed order | Live questions session | Live, online | 30 min | 2026-10-15 | 3 | 100 | Done
Kitchen staff | 12 | Accept, time and complete an order on the tablet | Order-handling course | Online course | 5 min | 2026-10-16 | 10 | 83 | Overdue
Front of house | 18 | Process a refund and answer a customer's order question | Refunds course | Online course | 8 min | 2026-10-21 | 7 | 39 | Open

## Intake form
Customer intake form
Send this to the customer before the kickoff. It collects what setup needs.
Question | Answer
Business name and venues | Restaurant group; three venues
Opening hours for each venue | 11:00 to 22:00, closed Mondays at venue 3
Where the current menu lives | PDF menus on the website
POS system and who manages it | Existing POS; managed by the operations manager
Website platform and who can edit it | Website builder; the owner edits it
Who approves menu and price changes | Owner
Staff who will use the system, by role | 3 admins, 3 managers, 12 kitchen, 18 front of house
Busiest times to avoid for launch | Friday and Saturday nights; school holidays
Payments | Set up by the owner in the payments portal. We never ask for bank details by email.

## Kickoff agenda
Kickoff agenda (60 minutes)
Suggested 60-minute meeting. Adjust the timings and record the agreed decisions below.
Min | Item | Owner | Output
5 | Introductions and roles on both sides | Onboarding manager | Named contact for each task
10 | What the customer bought and why (from the handoff) | Account executive | Customer confirms the goal in their words
10 | Agree first value and its date | Onboarding manager | First value and target date written down
15 | Walk through the onboarding plan, task by task | Onboarding manager | Owners and due dates accepted
10 | Training: who needs what, by role | Onboarding manager | Training plan agreed
10 | Risks, deadlines and the next meeting | Both | Risks logged; next check-in booked
60 | Total minutes
| Decisions made at the kickoff |  | Answer
| First value |  | First 50 online orders processed through the new system across all three venues
| Target date for first value |  | 30 October 2026
| Venue admins named |  | One per venue, by 2 October
| Launch order |  | Venue 1 first, then venues 2 and 3

## Welcome emails
Welcome email sequence
Five suggested messages. Replace brackets, dates, role names and timings. Confirm every stated result before sending.
When | Subject | Email
Day 0, after signing | Welcome, and what happens next | Hi [Name], welcome aboard. I'm [Onboarding manager], and I'll look after your onboarding. Our first step is a 60-minute kickoff to agree your first goal, target date and responsibilities. Book a time: [Booking link]. Before then, fill in the intake form: [Intake link].
Day 1, before the kickoff | Before our kickoff on [date] | Hi [Name], looking forward to [date]. Please bring the person who will run the system day to day at each venue. We'll leave the call with a first goal, a date and a named owner for every task.
Day 3, during setup | Your setup: three things from your side | Hi [Name], your menus are in. To keep to [target date], we need three things from your team: [task 1], [task 2], [task 3]. The full plan, with who does what, is here: [link].
Day 10, training | Training for your team: 5 to 15 minutes each | Hi [Name], your team's training is ready. Admins: [Admin course link] (15 minutes). Kitchen: [Kitchen course link] (5 minutes). Front of house: [Front-of-house course link] (8 minutes). Please finish by [Due date]. These are the example roles and timings; replace them before sending.
Day 30, check-in | 30 days in: how is it going? | Hi [Name], let's review your first month. Your current progress is [Verified result or remaining tasks]. Please book a 30-minute check-in: [Check-in link]. We'll review the result, open questions and next steps.

## Sample enterprise rollout
Sample: enterprise rollout
A high-touch implementation for a 2,000-person customer, in stages over 12 weeks.
When | Stage | What happens | Owner
Week 0 | Handoff | Sales hands over the contract, goals and promises made | Account executive
Weeks 1 to 2 | Kickoff and plan | Steering group meets; first value and the go-live date agreed | Onboarding lead
Weeks 2 to 6 | Setup and integration | Single sign-on, user import and data checks | Implementation team
Weeks 5 to 8 | Pilot | Train the pilot group, launch one department and resolve issues before wider rollout | Customer project lead
Weeks 8 to 10 | Training | Admins trained live; users get a short course by role | Onboarding lead
Week 10 | Go-live | All departments live; first value measured | Both
Week 12 | Review and handover | Results against the goal; handover to the account manager | Onboarding lead

## Sample self-serve
Sample: self-serve
Illustrative self-serve sequence. Days are suggested review points; send only when the trigger applies.
Day | Trigger | What they get | Goal
0 | Account created | Welcome email with one first step and a 3-minute video | Log in again
1 | First step not done | Reminder with the most important first step | First step done
3 | First step done | Short course in the customer academy: the core feature | Use the core feature
7 | Core feature not used | Email with a customer example and a booking link for help | Use the core feature
14 | Core feature used 3 times | Invite to the advanced course and the community | Return to the core task
30 | Any | Check-in email with their usage and one next step | Agree the next useful step

## Sample client intake
Sample: client intake
An agency or accounting practice taking on a new client.
Section | What to ask | Why
Contacts | Who decides, who approves, who sends us information | No waiting on the wrong person
Goals | What a good result looks like in 3 months | Agree success before work starts
Access | Accounts and logins we need, shared through a password manager | Never by email
Documents | Contracts, brand files or last year's records | Everything in one place on day one
Ways of working | How often to meet, how to report, response times | No surprises in month one