One-Page Training Program Plan

A one-page plan for building a training program backwards: the business number first, then the behaviour, the objective, the assessment, the lessons and practice, the schedule, the on-the-job support and the evaluation plan. Page 2 is filled in with a contact-centre refund example (all numbers illustrative). Page 3 is blank for your program. It is a planning aid, not a validated instrument, and it gives no score.

From the Coursebox blog: coursebox.ai/blog/how-to-design-and-deliver-training-programs

How to use it

Fill the rows from top to bottom. Do not write a lesson until the assessment row is done.

If row 2 says training is not the answer, stop and fix the system, the tool or the incentive instead.

Write the actual artefact in each row: the real assessment item, the real checklist, the real dates.

Agree rows 1 and 10 with the manager who owns the number before you build anything.

Review the plan with that manager after the first evaluation date and change what did not work.

Worked example: refund calls in a 40-agent contact centre

Illustrative example. The policy: refunds within 30 days of the purchase date in the CRM (day 30 is eligible); after 30 days decline voluntary change-of-mind refunds only; faults and statutory rights use the approved remedies process; over $200 goes to a team leader before the agent promises money; the agent checks the date in the CRM; the agent records the outcome and reason.

| Plan field | What goes here |
| --- | --- |
| 1. Business problem and number | Refund calls that break policy. Baseline: 18 of 100 sampled calls in last quarter's QA audit. Target: 5 of 100 in the first QA audit after launch. |
| 2. Is training the answer? | Partly. A 10-question check of 10 agents: 6 could not state the $200 escalation rule, so train. Check whether agents can find and interpret the CRM date; its presence alone does not rule out a usability problem. Call-speed bonus reviewed with the team manager. |
| 3. Audience | 40 contact-centre agents who take refund calls. |
| 4. Objective | Given a change-of-mind call, the approved policy and CRM, check facts, decide and explain the action without an unapproved promise. A 9-of-10 score prompts further checking; demonstrate every essential rule. |
| 5. Assessment | 10 scenario items, pass mark 9 of 10. Sample: a customer no longer wants a working $89 blender bought 40 days ago. Decline the voluntary change-of-mind refund. If a fault is reported, use the separate approved remedies process. |
| 6. Outline | Lessons (3): the refund rule; the CRM fields to check; the escalation script. Practice (4): scenario calls in pairs; branching call simulation; spot the error in an anonymised QA call note; script rehearsal. Assessment (1): the 10 scenarios. |
| 7. Format and schedule | Day 1: online lessons, the branching call simulation and spot the error, about 30 minutes. Day 2: live paired calls, script rehearsal and the assessment, 45 minutes. Short scenario quizzes on days 3, 10 and 24. First week back on calls: on-the-job support. |
| 8. On-the-job support | Team leaders listen to two refund calls per agent in week 2 with a three-item checklist: checked the purchase date in the CRM; applied the 30-day rule; escalated over $200 before promising money. |
| 9. Evaluation plan | Level 4: agree a business outcome, baseline and review period, such as avoidable complaint cost. Level 3: policy breaches per 100 comparable calls and the week-2 listening checklist. Level 2: scenario assessment score, course report, day 2. Level 1: two-question reaction survey, end of day 2. |
| 10. Owner and review date | Contact-centre manager. Review after the first QA audit following launch. |

Your training program plan

| Plan field | Your answer |
| --- | --- |
| 1. Business problem and number (baseline, target, date) |  |
| 2. Is training the answer? (yes / partly / no, and any non-training fix) |  |
| 3. Audience |  |
| 4. Objective (an observable behaviour) |  |
| 5. Assessment (one sample item, pass mark) |  |
| 6. Outline (lessons / practice / assessment) |  |
| 7. Format and schedule |  |
| 8. On-the-job support (who, what checklist, when) |  |
| 9. Evaluation plan (Levels 1 to 4: measure, source, date) |  |
| 10. Owner and review date |  |

Rows 1 and 10 belong to the manager who owns the number. Agree them before you build anything.