Review Calendar by Retention Horizon

Plan repeated reviews for one course, with dates, tasks and a named owner. The worked cleaning example is hypothetical. Findings from a one-review fact-learning study inform the planning questions, not a validated workplace timetable. Check critical actions before independent work, and retain site procedures and required job aids.

From the Coursebox blog: coursebox.ai/blog/spaced-repetition-and-how-to-practice

How to use this calendar

Step 1: list when each item is first needed and how long it must remain usable. An annual refresher date is not a reason to delay an early performance check.

Step 2: check initial performance and observe routine work. Give rarely used rules delayed practice; daily use does not prove correct use.

Step 3: use the study results as context, then propose a first gap that fits the task, prior knowledge and consequences of forgetting. Check safety-critical actions before independent work.

Step 4: attach every review to an event the team already holds, such as a shift start, a monthly meeting or a quarterly toolbox talk, and name the person who runs it.

Step 5: write new questions for every review: the same rule in a new situation, answered from memory, with one line of feedback that names the rule.

| How long it must last | Proposed first review | Later reviews (design extrapolation) | What the study found |
| --- | --- | --- | --- |
| About a week | 2 to 3 days after the course | None if the job uses it every day | Best gap about 3 days for a test 7 days later |
| About a month | About a week after | One more before the check if rarely used | Best gap about 8 days for a test 35 days later |
| About a quarter | 10 to 14 days after | Every few weeks until the check | Best gap about 12 days for a test 70 days later |
| About a year | 3 to 4 weeks after | About monthly at first, then wider, up to the refresher | Best gap about 27 days for a test 350 days later |
| Several years | Several months after | Months apart | A delayed review of at least several months |

Source: Cepeda, Vul, Rohrer, Wixted and Pashler (2008), Psychological Science 19(11), pp. 1095 to 1102: interpolated best gaps (p. 1099) and the cost of too-short gaps (p. 1101). Trivia facts learned online, one review; not tested on procedures or physical skills.

Content by horizon: worked example

Hypothetical example; the company, its rules and its dates are illustrative. A commercial cleaning contractor in Brisbane has about 140 cleaners on night shifts across 60 office and medical-centre sites. It is moving to a wall-mounted dispensing system with four colour-coded products. Every cleaner does a 30-minute phone course, "Safe chemical use on our sites", at the start of a paid shift on Monday 1 February 2027, the day the dispensers go live.

The contractor's six rules (its own procedure, not a legal standard; first aid and spills follow the product's safety data sheet (SDS) and the supervisor):

1. Use the colour for the job: green for general surfaces, blue for glass, red for bathrooms, yellow for the medical-centre disinfectant.

2. Fill spray bottles only from the wall dispenser. Never decant into a drink bottle or an unmarked container.

3. Label every bottle with the product name and colour before it leaves the cleaners' room.

4. Never mix products. The red bathroom cleaner and the yellow disinfectant must never go in the same bucket, bottle or drain at the same time.

5. Gloves for every product; gloves and safety glasses for red and yellow.

6. If there is a spill or a splash: stop work, keep others away and alert the supervisor immediately. Follow the product's SDS and the site emergency procedure. Use a spill kit only if you are trained, equipped and it is safe to do so.

Before using the new products, the supervisor checks correct selection, filling, labelling, protective gear and the locations of the SDS and spill kit. Correct any missed safety step before independent work.

| Content | Example item | How long it must last | How often the job uses it | Review plan |
| --- | --- | --- | --- | --- |
| Colour codes (rule 1) | Blue for glass, red for bathrooms | About a week, then daily use keeps it fresh | Every shift | Check before use and on day 2; observe correct use on shift |
| Filling, labelling and protective gear (rules 2, 3 and 5) | Fill only at the dispenser; label every bottle; gloves for every product | Until the first quarterly audit, about 12 weeks | Every shift, but easy to skip | Early observed check, first-quarter reviews and continuing site checks |
| Rare events (rules 4 and 6) | Never mix red and yellow; spill and splash steps | 12 months, to the annual refresher | Rarely, maybe never | Reviews across the whole year; rules 4 and 6 only after the first quarter |

The calendar: worked example

All gaps are in days. Each review uses new scenarios, so none repeats within the year: at least three for most rules, and more for rules 4 and 6, which come up in every review.

| Date | Day | Gap since last | What learners do (minutes) | Rules covered | Carried by (existing event) | Who runs it | Channel |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mon 1 Feb 2027 | 0 | none | The course (30) | 1 to 6 | Shift start, paid time | Supervisor | Phone |
| Wed 3 Feb 2027 | 2 | 2 | 3 questions: which colour for which job (2) | 1 | Shift start | Supervisor | Phone |
| Mon 1 Mar 2027 | 28 | 26 | Review 1: 5 scenario questions (5) | 2 to 6, at least one each on 4 and 6 | Monthly team meeting | Supervisor | Phone, at the meeting |
| Mon 29 Mar 2027 | 56 | 28 | Review 2: 5 new scenario questions (5) | 2 to 6 | Monthly team meeting | Supervisor | Phone, at the meeting |
| Mon 26 Apr 2027 | 84 | 28 | Review 3: 5 new scenario questions (5); the site audit checks rules 2 and 3 | 2 to 6 | Quarterly toolbox talk and audit | Supervisor | Phone, at the toolbox talk |
| Mon 26 Jul 2027 | 175 | 91 | Review 4: 5 scenario questions, rare events only (5) | 4 and 6 | Quarterly toolbox talk | Supervisor | Phone, at the toolbox talk |
| Mon 25 Oct 2027 | 266 | 91 | Review 5: 5 scenario questions, rare events only (5) | 4 and 6 | Quarterly toolbox talk | Supervisor | Phone, at the toolbox talk |
| Tue 1 Feb 2028 | 365 | 99 | Annual refresher and check (10) | 1 to 6 | Annual compliance calendar | Supervisor | Phone |

The six planned reviews take about 27 minutes in total. These dates are illustrative workload choices, not tested intervals. Correct missed rules immediately and bring them back sooner. The proposed 10-minute annual refresher must fit organisational requirements and observed performance.

Check after each review: worked example

Three plain questions after every review. There is no score: the answers decide the next gap and who needs help.

| Question | What it tells you | Example decision (cleaning course) |
| --- | --- | --- |
| Which items did most people miss? | Which rules are fading before the next review | Most of a site misses the mixing question in Review 4: rules 4 and 6 come back monthly until Review 5 |
| Does the next gap stay the same, shrink or widen? | Whether the schedule fits this group | Everyone answers the colour questions correctly on day 2: no more colour reviews before the refresher |
| Who needs a conversation rather than another quiz? | Where the problem is the job, not memory | A cleaner answers the drink-bottle question correctly but the audit finds unlabelled bottles on their trolley: the supervisor talks to them on site |

Planning aid only. A review that happens on the right date shows the schedule is running; delayed review answers show what they recalled on those checks.

Your check after each review

| Review | Items most people missed | Next gap: same, shorter or longer? | Who needs a conversation? |
| --- | --- | --- | --- |

Planning aid only. Questions that come back on set dates put spacing into a course; delayed answers show recall on those checks, not causal improvement.

Your content by horizon

Course: ______________________   Go-live date: ______________   Reviews owned by: ______________

| Content | Example item | How long it must last | How often the job uses it | Review plan |
| --- | --- | --- | --- | --- |

Your calendar

| Date | Day | Gap since last | What learners do (minutes) | Items covered | Carried by (existing event) | Who runs it | Channel |
| --- | --- | --- | --- | --- | --- | --- | --- |