## Decision Tool
Phase | Check | Owner | Evidence | Go / no-go | Rollback trigger | Status | Notes
Inventory | Apps, workers, schedules, add-ons, domains, certificates |  |  |  |  | Not started
Inventory | Data stores, queues, files, backups |  |  |  |  | Not started
Inventory | Secrets, access, dependencies |  |  |  |  | Not started
Build | AWS account, network, identity, encryption |  |  |  |  | Not started
Build | Build and release path |  |  |  |  | Not started
Build | Logs, metrics, traces, alerts |  |  |  |  | Not started
Rehearsal | Production-like data and traffic |  |  |  |  | Not started
Rehearsal | Restore and rollback |  |  |  |  | Not started
Rehearsal | Business transaction checks |  |  |  |  | Not started
Cutover | Write and job strategy |  |  |  |  | Not started
Cutover | DNS and certificate plan |  |  |  |  | Not started
Cutover | Support communication and stop conditions |  |  |  |  | Not started
After cutover | Data and transaction reconciliation |  |  |  |  | Not started
After cutover | Performance, errors, cost, alerts |  |  |  |  | Not started
After cutover | Legacy environment retention and closure |  |  |  |  | Not started