# Request for Proposals

# Title: Design of training manual and conduct capacity building on implementation of land use plan in NW Liberia.

RFP No: CIL-2026-CONSULTANCY-02

Date of Issuance: May 5, 2026

## Background

Conservation International (CI) has been protecting nature for the benefit of all for over 30 years. Through science, policy, and partnerships, CI is helping build a healthier, more prosperous, and more productive planet. CI is a global organization that has been active in Liberia for about 20 years, working closely with communities, the private sector, government, and civil society leaders to support conservation and sustainable development. Liberia is at a vital point in its development history with an enormous wealth of natural resources. It has an opportunity to encourage investors and promote development initiatives that support economic growth and development while maintaining Liberia’s critical natural capital for future generations. Proper stewardship of Liberia’s resources may prove to be the key to the future well-being of the Liberian people.

To this end, CI Liberia, in collaboration with the Environment Protection Agency (EPA,) is implementing a Global Environment Facility (GEF) funded Food Systems, Land Use, and Restoration (FOLUR)Project.

## Project Overview

The Project is based on the growing recognition that food production systems and land use must improve for the benefit of peoples' health, planet, and economies. The FOLUR project titled "Reducing deforestation from palm oil and cocoa value chains,” aims "to promote biodiversity conservation and sustainable food systems for enhanced livelihood opportunities in Northwest Liberia Landscape through land use planning, restoration of degraded lands, and strengthening governance, policies, and market incentives for nationally replicable models of deforestation- free cocoa and palm oil value chains."

The FOLUR project is being implemented in the Northwest (NW) Liberia landscape (Grand Cape Mount, Bong, Bomi, Lofa, and Gbarpolu) Counties by Conservation International in partnership with Fauna and Flora International (FFI), Royal Society for the Protection of Birds (RSPB), and Society for the Conservation of Nature of Liberia (SCNL).

The project has four components, and they are as follows:

Component 1: Development, adoption, and implementation of National and NW Liberia Landscape

Component 2: Promotion of sustainable production practices for food crops, palm oil, and cocoa, supported by responsible value chains.

Component 3: Biodiversity loss reduction and restoration of natural habitats.

Component 4: Coordination, collaboration, and Monitoring and Evaluation.

Pursuant to the above, Conservation International and the Environmental Protection Agency are seeking the services of a consultancy firm to develop land use plans – coarse national land use plan and a detailed landscape (NW Liberia) land use plan.)

## Terms of Reference, Deliverables and Deliverables Schedule

The consultancy firm will utilize the validated LUP for NW Liberia to design training manual and conduct capacity building on Land Use Plan implementation in NW Liberia landscape. This will include working with all ten (10) clans across the FOLUR landscape.

## Key tasks

The consultant will work closely with CI, Liberia Land Authority (LLA), EPA, and partners (FFI, RSPB and SCNL) to undertake the following tasks:

  - Conduct comprehensive desktop review of existing documents including the validated LUP, the Liberia Land Rights Act, relevant laws, policies, strategies, and initiatives to identify gaps in land use planning implementation in Liberia generally and specifically in NW Liberia landscape.

  - Assess the capacity of existing Community Land Development and Management Committee (CLDMC) and design training programs to enhance capacity on the implementation of the LUP. In areas that lack CLDMC, establish one and strengthen their capacities.

  - Review and adopt existing training manual on climate-smart agriculture and restoration, linked to the LUP implementation. This should include thorough review and update of existing land use/land cover maps to current realities.

  - Develop a gender-sensitive monitoring, and evaluation system and an action plan for the NW Liberia land use plan implementation

  - Conduct gender sensitive training on conflict resolution and livelihood activities linked to existing conservation agreement initiatives in the FOLUR landscape. This should include working closely with the project’s Livelihood and Gender and Safeguards team.

  - Ensure that all established and functional CLDMCs are linked to the current Multistakeholder Platform in the project landscape. Create awareness and sensitization campaigns on the relevance of the LUP and its implementation in NW Liberia.

## Deliverable schedules

| Deliverables | Description | Deadline |
| --- | --- | --- |
| Inception report | The inception report should include methodologies, approaches, and tools to conduct a comprehensive review of existing documents including the validated LUP, the Liberia Land Rights Act, relevant laws, policies, strategies, and initiatives to identify gaps in land use planning implementation in Liberia generally and specifically in NW Liberia landscape. | July 15, 2026 |
| Desktop review report | The desktop review report should include an analysis of existing documents and/or gaps including relevant laws, policies, strategies, and initiatives on LUP implementation in Liberia. Specific emphasis should be placed on highlighting the gaps in current CLDMC structures and other project implementation modalities across the project landscape. | Aug 1, 2026 |
| Comprehensive training manual and updated LUP maps for the landscape | The report should include a comprehensive training manual that encompasses a review and adoption of existing training manual on climate-smart agriculture and restoration programs, linked to the LUP implementation. This should include thorough review and update of existing land use/land cover maps to match current realities. | Aug. 30, 2026 |
| Training Report | This report should include training on climate-smart agriculture, restoration, conflict resolution and livelihood programs linked to the LUP implementation. It should also include a gender-sensitive monitoring, and evaluation system for the NW Liberia land use plan implementation | Sept 30, 2026 |
| Validated action plan | Validate the action plan to implement the LUP in the NW Liberia landscape | Oct. 30, 2026 |
| Final Report | A comprehensive report that covers all other deliverables including awareness raising materials. | Nov. 30, 2026 |

- Submission Details

- Deadline. Proposals must be received no later than June 29, 2026, at 5:00PM GMT. Late submissions will not be accepted. Proposals must be submitted via email to hrliberia@conservation.org. All proposals are to be submitted following the guidelines listed in this RFP.

- Validity of bid. 120 days from the submission deadline

- Clarifications. Questions may be submitted to hrliberia@conservation.org by the specified date and time in the timeline below. The subject of the email must contain the RFP number and title of the RFP. CI will respond in writing to submitted clarifications by the date specified in the timeline below. Responses to questions that may be of common interest to all bidders will be posted   to   the   CI   website   and/or   communicated   via   email.

- Amendments. At any time prior to the deadline for submission of proposals, CI may, for any reason, modify the RFP documents by amendment which will be posted to the CI website and/or communicated via email.

## Minimum Requirements

The successful Consultant or organization will have team members with the following minimum requirements:

## Education:

Master’s degree in environmental and social sciences, Economics, physical planning, or related fields with proven experience in qualitative and quantitative data collection and analysis, land use planning, climate change modelling, environmental policy and GIS and Remote Sensing. The Team Leader should have a PhD in any of the above fields.

- Experience in conducting biophysical and socio-economic modeling.

- Experience in landscape planning, specifically the development of land use plans and maps

- Good understanding of livelihoods and conservation of natural resources

- Fluency in English

- Excellent analytical and report writing skills.

- Proactive and able to work with minimal supervision and high degree of initiative, reliability, flexibility, and self-motivation.

- Professionalism: flexibility to make ad-hoc changes as and when the need arises; ability to perform under stress;	willingness	to	keep	flexible	working	hours.

## Proposal Documents to Include

- Signed cover page on bidder’s letterhead with the bidder’s contact information.

- Signed Representation of Transparency, Integrity, Environmental and Social Responsibility (Attachment 3) Technical Proposal.

  - Corporate Capabilities, Experience, Past Performance, and 3 client references. Please include descriptions of similar projects or assignments and at least three client references.

  - Qualifications of Key Personnel. Please attach CVs that demonstrate how the team proposed meets the minimum requirements listed in section 5 (Minimum Requirements).

4) Technical Approach, Methodology and Detailed Work Plan. The Technical Proposal should describe in detail how the bidder intends to carry out the requirements described in the Terms of Reference (indicate Section 3)

3) Financial Proposal. Offerors shall use the cost proposal template (Attachment 2).

## Evaluation Criteria

In evaluating proposals, CI will seek the best value for money considering the merits of the technical and costs proposals. Proposals will be evaluated using the following criteria:

| Evaluation Criteria | Score (out of 100) |
| --- | --- |
| Is the proposed approach and methodology appropriate to the assignment and practical in the prevailing project circumstances? | 20%/ Max points |
| Is the presentation clear and is the sequence of activities and the planning logical, realistic and promise efficient implementation to the project? | 10%/ Max points |
| Does the bidder’s past performance demonstrate recent proven experience doing similar work? | 20%/ Max points |
| Does the bidder and the proposed personnel have the specific technical expertise for the assignment? | 30%/ Max points |
| Cost: Costs proposed are reasonable and realistic, reflect a solid understanding of the assignment. | 20%/ Max points |

## Proposal Timeline

| RFP Issued | May 5, 2026 |
| --- | --- |
| Clarifications submitted to CI | June 18, 2026 |
| Clarifications provided to known bidders | June 22, 2026 |
| Complete proposals due to CI | June 29, 2026 |
| Final selection | July 5, 2026 |

- Resulting Award

CI anticipates entering into an agreement with the selected bidder by June 29, 2026. Any resulting agreement will be subject to the terms and conditions of CI’s Services Agreement. A model form of agreement can be provided upon request.

This RFP does not obligate CI to execute a contract, nor does it commit CI to pay any costs incurred in the preparation or submission of the proposals. Furthermore, CI reserves the right to reject any and all offers, if such action is considered to be in the best interest of CI. CI will, in its sole discretion, select the winning proposal and is not obligated to share individual evaluation results.

## Confidentiality

All proprietary information provided by the bidder shall be treated as confidential and will not be shared with potential or actual applicants during the solicitation process. This includes but is not limited to price quotations, cost proposals and technical proposals. CI may, but is not obliged to, post procurement awards on its public website after the solicitation process has concluded, and the contract has been awarded. CI’s evaluation results are confidential, and applicant scoring will not be shared among bidders.

## Code of Ethics

All Offerors are expected to exercise the highest standards of conduct in preparing, submitting and if selected, eventually carrying out the specified work in accordance with CI’s Code of Ethics [for GCF-funded projects only, add: “and the Green Climate Fund’s Policy on Prohibited Practices”]. Conservation International’s reputation derives from our commitment to our values: Integrity, Respect, Courage, Optimism, Passion and Teamwork. CI’s Code of Ethics (the “Code”) provides guidance to CI employees, service providers, experts, interns, and volunteers in living CI’s core values, and outlines minimum standards for ethical conduct which all parties must adhere to. Any violation of the Code of Ethics, as well as concerns regarding the integrity of the procurement process and documents should be reported to CI via its Ethics Hotline at www.ci.ethicspoint.com.

- Attachments:

# Attachment 1: Representation of Transparency, Integrity, Environmental and Social Responsibility Attachment 2: Cost Proposal Template

## Attachment 1: Representation of Transparency, Integrity, Environmental and Social Responsibility

RFP No. CIL-2026-CONSULTANCY-02

UEI Number (if applicable): XXX-XXX-XXX

All Offerors are expected to exercise the highest standards of conduct in preparing, submitting and if selected,

eventually carrying out the specified work in accordance with CI’s Code of Ethics. CI’s Code of Ethics provides

guidance to CI employees, service providers, experts, interns, and volunteers in living CI’s core values, and outlines minimum standards for ethical conduct which all parties must adhere to. Any violations of the Code of Ethics should be reported to CI via its Ethics Hotline at www.ci.ethicspoint.com.

CI relies on the personal integrity, good judgment and common sense of all third parties acting on behalf, or providing services to the organization, to deal with issues not expressly addressed by the Code or as noted below.

## With respect to CI’s Code of Ethics, we certify:

  - We understand and accept that CI, its contractual partners, grantees and other parties with whom we work are expected to commit to the highest standards of Transparency, Fairness, and Integrity in procurement.

## With respect to social and environmental standards, we certify:

  - We are committed to high standards of ethics and integrity and compliance with all applicable laws across our operations, including prohibition of actions that facilitate trafficking in persons, child labor, forced labor, sexual abuse, exploitation or harassment. We respect internationally proclaimed human rights and take no action that contributes to the infringement of human rights. We protect those who are most vulnerable to infringements of their rights and the ecosystems that sustain them.

  - We fully respect and enforce the environmental and social standards recognized by the international community, including the fundamental conventions of International Labour Organization (ILO) and international conventions for the protection of the environment, in line with the laws and regulations applicable to the country where the contract is to be performed.

## With respect to our eligibility and professional conduct, we certify:

  - We are not and none of our affiliates [members, employees, contractors, subcontractors, and consultants] are in a state of bankruptcy, liquidation, legal settlement, termination of activity, or guilty of grave professional misconduct as determined by a regulatory body responsible for licensing and/or regulating the offeror’s business

  - We have not and will not engage in criminal or fraudulent acts. By a final judgment, we were not convicted in the last five years for offenses such as fraud or corruption, money laundering or professional misconduct.

  - We are/were not involved in writing or recommending the terms of reference for this solicitation document.

  - We have not engaged in any collusion or price fixing with other offerors.

  - We have not made promises, offers, or grants, directly or indirectly to any CI employees involved in this procurement, or to any government official in relation to the contract to be performed, with the intention of unduly influencing a decision or receiving an improper advantage.

  - We have taken no action nor will we take any action to limit or restrict access of other companies, organizations or individuals to participate in the competitive bidding process launched by CI.

  - We have fulfilled our obligations relating to the payment of social security contributions or taxes in accordance with the legal provisions of the country where the contract is to be performed.

  - We have not provided, and will take all reasonable steps to ensure that we do not and will not knowingly provide, material support or resources to any individual or entity that commits, attempts to commit, advocates, facilitates, or participates in terrorist acts, or has committed, attempted to commit, facilitate, or participated in terrorist acts, and we are compliant with all applicable

Counter-Terrorist Financing and Anti-Money Laundering laws (including USA Patriot Act and U.S. Executive Order 13224).

  - We certify that neither we nor our directors, officers, key employees or beneficial owners are included in any list of financial or economic sanctions, debarment or suspension adopted by the United States, United Nations, the European Union, the World Bank, or General Services

Administration’s List of Parties Excluded from Federal Procurement or Non-procurement programs

in accordance with E.O.s 12549 and 12689, “Debarment and Suspension”. [Include additional sanctions lists of the country of a public donor, if required by the donor.]

Name:

Signature:

Title:

Date:

## Attachment 2: Cost Proposal Template

The cost proposal must be all-inclusive of profit, fees or taxes. Additional costs cannot be included after award, and revisions to proposed costs may not be made after submission unless expressly requested by CI should the offerors proposal be accepted. Nevertheless, for the purpose of the proposal, Offerors must provide a detailed budget showing major expense line items. Offers must show unit prices, quantities, and total price. All items, services, etc. must be clearly labeled and included in the total offered price. All cost information must be expressed in [USD].

If selected, Offeror shall use its best efforts to minimize the financing of any taxes on goods and services, or the importation, manufacture, procurement or supply thereof. If Offeror is eligible to apply for refunds on taxes paid, Offeror shall do so. Any tax savings should be reflected in the total cost.

Cost Breakdown by Deliverable

| Deliverable | Price (Lump Sum, All Inclusive) |
| --- | --- |
| Insert deliverable 1 from Section 3 or attached TOR |  |
| Insert deliverable 2 from Section 3 or attached TOR |  |
| Insert deliverable 3from Section 3 or attached TOR |  |
| Insert deliverable 4 from Section 3 or attached TOR |  |
| Insert deliverable 5 from Section 3 or attached TOR |  |

Cost Breakdown by Cost Component (example only)

| Description | Unit of measure (day, month etc) | Total period of engagement | Unit cost/rate | Total Cost for the Period |
| --- | --- | --- | --- | --- |
| Consultant 1 |  |  |  |  |
| Consultant 2 |  |  |  |  |
| Sub-total Personnel |  |  |  |  |
| Travel Costs (if applicable) |  |  |  |  |
| Other related Costs (please specify) |  |  |  |  |
| Total Cost of Financial Proposal |  |  |  |  |