GBFF CEO Endorsement REQUEST Template

TABLE OF CONTENTS

General Project Information	3

Project Summary	4

Project Description Overview	5

project outline	18

A.	Changes compared to PPG Request	18

B.	Project Rationale	23

C.	Project Description	35

Institutional Arrangement and Coordination with Ongoing Initiatives and Project.	51

Core Indicators	59

Risks to Project Implementation	60

D.	Alignment with Programming strategies and country/regional priorities	67

E.	Policy requirements	69

Gender Equality and Women’s Empowerment:	69

Stakeholder Engagement	69

Private Sector	70

Environmental and Social Safeguards	70

F.	Other requirements	70

Knowledge management	70

Socio-economic Benefits	71

Annex a: FINANCING TABLES	72

Total GEF Financing Table	72

Project Preparation Grant (PPG)	72

Action Area Elements	72

Confirmed Co-financing for the project, by name and type	72

ANNEX b: EndorsementS	74

Letter of Endorsement	74

ANNEX C: Project results framework	75

ANNEX D: status of utilization of Project Preparation Grant (PPG)	82

annex E: project map and coordinates	82

ANNEX F: Environmental and Social Safeguards documents including Rating	84

ANNEX G: Budget Table	92

ANNEX H: Blended-finance relevant annexes	92

ANNEX I:  MONITORING AND EVALUATION PLAN	93

ANNEX J: MEx30x30 site details	105

ANNEX k: alignment of MEx30x30 with the enbiomex	121

# General Project Information

| Project Title: | MEx30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |
| --- | --- | --- | --- |
| Region: |  | GEF Project ID: | 11510 |
| Country(ies): | Mexico |  |  |
| GEF Agency(ies): |  | GEF Agency Project ID: |  |
| Project Executing Entity(s) and Type: | Fondo Mexicano para la Conservación de la Naturaleza A.C. |  |  |
| GEF Focal Area(s): |  | Submission Date: |  |
| Type of Trust Fund: |  | Project Duration (Months) | 60 |
| GEF Project Grant: (a) | 16,672,477 | GEF Project Non-Grant (b) |  |
| Agency Fee(s) Grant: (c) | 1,500,523 | Agency Fee(s) Non-Grant: (d) |  |
| Total GEF Financing: (a+b+c+d) | 18,173,000 | Total Co-financing: | 115,549,532 |
| PPG Amount (e): | 300,000 | PPG Agency Fee(s) (f): | 27,000 |
| Total GEF Resources (a+b+c+d+e+f) | 18,500,000 |  |  |
| Project Tags: | Support to IP&LCs Blended finance Contributions to the implementation of: GBF Target 1 GBF Target 2 GBF Target 3 GBF Target 4 GBF Target 5 GBF Target 6 GBF Target 7 GBF Target 8 GBF Target 9 GBF Target 10 GBF Target 11 GBF Target 12 GBF Target 13 GBF Target 14 GBF Target 15 GBF Target 16 GBF Target 17 GBF Target 18 GBF Target 19 GBF Target 20 GBF Target 21 GBF Target 22 GBF Target 23 |  |  |
| Rio Markers |  |  |  |
| - Climate Change Mitigation | No Contribution (0) Significant Objective (1) Principal Objective (2) |  |  |
| - Climate Change Adaptation | No Contribution (0) Significant Objective (1) Principal Objective (2) |  |  |
| - Biodiversity | No Contribution (0) Significant Objective (1) Principal Objective (2) |  |  |
| - Land Degradation | No Contribution (0) Significant Objective (1) Principal Objective (2) |  |  |

### Project Summary

MEx30x30 will advance biodiversity conservation by strengthening protected area (PA) financing in Mexico. Mexico´s federal PA system faces an estimated annual financing gap of US$87 million. In addition, the National Commission for Protected Areas (CONANP) has increasingly certified Areas Voluntarily Designated for Conservation (ADVCs) in response to requests from Indigenous Peoples and local communities (IP&LCs) who want to conserve their lands and need support. Consequently, these areas remain vulnerable to threats rooted in pressure for economic development and exacerbated by climate change; the resultant deforestation and degradation erodes ecosystem services that are vital for biodiversity and rural livelihoods. To reinforce conservation management, MEx30x30 will strengthen the capacity of CONANP to pursue diverse financing options; use the Project Finance for Permanence (PFP) approach to secure funding from other sources while public financing flows are developed; and invest in conservation, restoration and sustainable management of recently established PAs and ADVCs. Supporting enhanced IPLC management of conservation areas is of particular importance as 51% of the land in Mexico belongs to IP&LCs and harbors 83% of biodiversity; thus, IP&LCs will be vital for further progress towards the 30x30 target.

The project aligns closely with GBFF Action Areas 1, 2 and 4, and will achieve GEF Core Indicator targets as follows: improve management effectiveness for 3,665,666 ha of terrestrial PAs and 22,241,504 ha of marine PAs; mitigate 9.43 million MtCO2e of greenhouse gas emissions; and generate inclusive, gender-equitable socioeconomic benefits for 163,293 people (50% women). The project will be transformative by improving the effectiveness of all PAs, catalyzing progress towards Mexico’s 30x30 target and putting in place the financial and institutional foundation to reach this target and then ensure robust management of the 30% of the country under conservation.

### Project Description Overview

| Project Objective: | To help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). Indicators (Targets): a. Terrestrial protected areas under improved management effectiveness (Target: 3,665,666 ha) b. Marine protected areas under improved management effectiveness (Target: 22,241,504 ha) c. Greenhouse gas emissions mitigated (Target: 5.7 million tons) d. Number of people experiencing socioeconomic benefits (male/female) (Target: 163,293 people; 50% female) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Project Components | Component Type | Project Outcomes | Project Outputs | Trust Fund | (in $) |  |
|  |  |  |  |  | GEF Project Financing | Co-financing |
| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. | Technical Assistance | Outcome 1.1: CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. Indicator 1.1: % decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams. Target 1.1: 10% decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams. | Output 1.1.1: New revenue streams to increase CONANP's budget are identified. Indicator 1.1.1: # of feasibility reports and action plans for accessing new revenue streams completed. Target 1.1.1: 1 feasibility report and action plan for accessing new revenue streams completed. Output 1.1.2: New revenue streams to increase CONANP's budget are accessed. Indicator 1.1.2: # of new revenue streams accessed and contributing to CONANP budget. Target 1.1.2: At least one new revenue stream accessed and contributing to CONANP budget. Output 1.1.3: The institutional capacity of CONANP is enhanced through expanding the Protected Areas Learning Community (community of practice). Indicator 1.1.3a: % improvement in CONANP institutional capacity assessment score. Target 1.1.3a: 15% improvement in CONANP institutional capacity assessment score. Indicator 1.1.3b: Increase in Protected Areas Learning Community membership (disaggregated by gender and IPLC membership). Target 1.1.3b: At least 100 new members are part the Protected Areas Learning Community, of whom at least 50% are women. |  | 1,690,290 | 100,000,000 |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. | Technical Assistance | Outcome 2.1: Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years. Indicator 2.1: Percentage of required funding for a Transition Fund to cover PA financing gaps for 15 years. Target 2.1: 100% required Funding pledged for phase one for a Transition Fund. | Output 2.1.1: Funding pledged to address identified financial gaps. Indicator 2.1.1: Amount of donor funding pledged to address financing gap for phase one during transition period. Target 2.1.1 100% of required funding for phase one pledged to address financing gap during transition period (amount to be confirmed in step 5 and 6 of long-term sustainable finance mechanism design process). Output 2.1.2: Long-term sustainable finance mechanism/PFP is designed. Indicator 2.1.2: Number of long-term sustainable finance mechanism designed and ready for closing. Target 2.1.2: One long-term sustainable finance mechanism designed and ready for closing. |  | 1,516,539 | 500,000 |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. | Technical Assistance | Outcome 3.1: PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. Indicator 3.1a: % improvement in PA management effectiveness score, as measured by i-effectiveness evaluation. Target 3.1a: For PAs with a rating of “Highly Effective” or “Outstanding”: Maintained or increased management effectiveness score. For PAs with a rating of “Ineffective” or “Partially Effective”: i-effectiveness score increased by at least 15 points. Indicator 3.1b: # people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (disaggregated by gender and IP&LCs). Target 3.1b: 163,200 people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (at least 50% female, desegregated by gender and IP&LCs). | Output 3.1.1: Five-year plans, and associated Annual Operating Plans (POAs), developed for PAs and ADVCs through an inclusive participatory process coordinated by CONANP. Indicator 3.1.1: # of gender-responsive and inclusive POAs prepared and implemented. Target 3.1.1: 1 gender-responsive and inclusive POAs prepared and implemented per PA or ADVC per year of the project (6 total). Output 3.1.2: Gender-responsive and inclusive training provided to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation and restoration practices. Indicator 3.1.2: # of people trained in sustainable land management, conservation and restoration practices (disaggregated by gender, recording level of Indigenous participation). Target 3.1.2: At least 100 people per PA or ADVC trained in sustainable land management, conservation and restoration practices (at least 50% women; level of Indigenous participation proportional to Indigenous percentage of local population). Output 3.1.3: IP&LCs and local organizations implement gender-responsive and inclusive conservation, restoration and sustainable management actions defined in POAs. Indicator 3.1.3: % of targets reached in POAs, which include gender-responsive and inclusive management actions implemented by IP&LCs and local organizations in PAs and ADVCs. Target 3.1.3: At least 80% of targets reached in POAs Output 3.1.4: Emergency fund expanded to support emergency-response brigades. Indicator 3.1.4: % of valid emergency funding requests that result in financial support within 72 hours. Target 3.1.4: at least 90% of funding requests resulting in delivery of financial support within 72 hours. |  | 12,146,999 | 14,100,000 |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. | Technical Assistance | Outcome 4.1: MEx30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. Indicator 4.1: # of scale-up strategy documents based on MEx30x30 experience. Target 4.1: 1 scale-up strategy document based on MEx30x30 experience. Outcome 4.2: Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. Indicator 4.2: PIR, MTR and TE ratings. Target 4.2.: PIR, MTR and TE ratings scored as “Satisfactory” to “Highly Satisfactory” | Output 4.1.1: Ongoing lessons learned from MEx30x30 and other long-term sustainable finance mechanisms and PA scaling experiences documented and disseminated. Indicator 4.1.1: Number of lessons-learned knowledge products prepared and shared (including products with a focus on gender and inclusion). Target 4.1.1: At least 4 lessons-learned knowledge products prepared and shared (including at least one with a focus on gender and one with a focus on IP&LCs). Output 4.1.2: National workshop and dissemination event held to finalize scale-up strategy document based on MEx30x30 experience. Indicator 4.1.2a: # of national workshop and dissemination events held. Target 4.1.2a: 1 national workshop and dissemination event held. Indicator 4.1.2b: # of people participating in national workshop and dissemination event (disaggregated by gender, recording level of Indigenous participation). Target 4.1.2b: 400 people participating in national workshop and dissemination event (at least 50% women, disaggregated by indigenous groups). Output 4.2.1: Clear and robust gender-responsive and inclusive Monitoring and Evaluation framework created and implemented. Output 4.2.2: Project Implementation Reports, Mid-term Review, and Terminal Evaluation completed. Indicator 4.2.2: % of required reports submitted to CI GEF Agency on time and determined to be satisfactory. Target 4.2.2: 100% of required reports. |  | 524,722 | 447,000 |
| Subtotal |  |  |  |  | 15,878,550 | 115,047,000 |
| Project Management Cost (PMC)*** ***If amount requested is above limits, a pop-up menu should open for the Agency to provide an explanation*** |  |  |  |  | 793,927 | 502,532 |
| Total Project Cost |  |  |  |  | 16,672,477 | 115,549,532 |

# project outline

## Changes compared to PPG Request

The Project design remains consistent with the PPG Request that was endorsed by the Global Environment Facility (GEF). Outcomes and Outputs have been slightly reorganized and reworded as captured in the table below, but in substance of project remains unchanged in terms of Objective, Components, and the associated outcomes and outputs to achieve the targets.

|  | PPG Request | GEF CEO ER/ Prodoc | Rationale |
| --- | --- | --- | --- |
| Project Objective and Components |  |  |  |
| Project Objective | To support Mexico to reach an effective management of the existing protected areas and contribute to conserve 30% of the territory by 2030 that is of global importance for biodiversity and of key priority in ecosystem services. This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan, ENBioMex. | To help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). | Slightly edits of wording for clarity and to focus overall project objective. New Annex K to detail alignment with EnBioMex. |
| Core Indicator 1: Terrestrial protected areas created or under improved management (hectare) | 3,802,036 ha | 3,665,666 ha | The total area of the 5 terrestrial protected areas under improved management was further refined after using official data of ANP polygons from CONANP, leading to a small downward adjustment. |
| Core Indicator 6: Greenhouse Gas Emissions Mitigated (metric ton of CO2e) | 8.3 MtCO2 eq | 5.7 MtCO2eq | The total indicator was modified to include conservation activities and using EX-ACT. The final calculation therefore -5.7MtCO2eq. |
| Component 2 |  | Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. | Slight change in wording |
| Component 3 |  | Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. | Slight change in wording |
| Component 4 | Knowledge Management for scaling impact. | Knowledge management, monitoring and evaluation for scaling-up impact. | Component 4 was revised to make explicit the need for knowledge management and emphasize the intent to catalyze scaling up. Two outputs were separated, where 4.1 is focused on Knowledge management and 4.2 on M and E |
| Project Outcomes |  |  |  |
| Outcome 2.1 | New funding to cover the financial gap has been mobilized. | Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years. | Outcome 2.1 was revised to give additional details about funding gap to be covered and over what time frame. |
| Outcome 3.1 | PAs and ADVs are effectively managed, benefiting IP&LCs directly. | PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. | Outcome 3.1 was revised to reflect the project’s prioritization of inclusive, gender-equitable benefits for IP&LCs. |
| Outcome 4 .1 | Project monitoring and reporting system is efficient and utilized. | MEx30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. | M&E moved to Outcome 4.2, so that 4.1 focuses on knowledge management with this new Outcome 4.1. The initial project did not contain a gender-responsive and inclusive learning and knowledge sharing outcome, leading to its addition for the final project's M&E system. |
| Outcome 4.2 | None | Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | M&E moved to new Outcome 4.2, and corresponding outputs reworded to emphasize gender, inclusion and adaptive management. This new reflects the requirement of GEF Policy of a dedicated M&E budget., as expressed in pp11 of the policy “budgetary resources should be allocated separately for monitoring and evaluation activities”. |
| Project Outputs |  |  |  |
| Output 1.1.1 | New revenue streams to increase CONANP's budget are identified and accessed. | New revenue streams to increase CONANP's budget are identified. | Given the complexity of identifying and accessing new revenue streams, this output was split into two – the revised Output 1.1.1, and the new Output 1.1.2. |
| Output 1.1.2 | The institutional capacities of CONANP to address the increase in the budget are enhanced. | New revenue streams to increase CONANP's budget are accessed. | With the revision of Output 1.1.1., accessing new funds was given its own separate output here. capacity is now addressed under Output 1.1.3. |
| Output 1.1.3 | Gender-responsive and inclusive learning exchange increased through a community of practice. | The institutional capacity of CONANP is enhanced through expanding the Protected Areas Learning Community (community of practice). | Gender-responsive and inclusive learning exchange outputs were placed in Component 4, while capturing the need for CONANP to increase its institutional capacity to absorb the increased budget (former Output 1.1.2) was put here with slightly revised wording. |
| Output 2.1.1 | Funding mobilized to address identified financial gaps | Funding pledged to address identified financial gaps. | This output was revised to focus on and specify funds pledged (rather than mobilized) to cover the financing gap in CONANP’s budget. |
| Output 2.1.2 | Transition fund designed is under implementation | Long-term sustainable finance mechanism/PFP is designed. | Output was revised to more accurately capture the need for a long-term finance mechanism or PFP to cover CONANP’s financing gap and create more flexibility in development of the overall mechanism, which is more than the Transition Fund. |
| Output 3.1.1 | Gender-responsive and inclusive Annual Operating plans for conservation, restoration and sustainable development of PAs and ADVCs, derived from five-year planning that will result from a participatory process developed by CONANP. | Five-year plans, and associated Annual Operating Plans (POAs), developed for PAs and ADVCs through an inclusive, participatory process coordinated by CONANP. | Output was slightly revised for clarity and to make explicit the emphasis on inclusive participatory processes. |
| Output 3.1.2 | Gender-responsive and inclusive conservation, restoration and sustainable management initiatives implemented in ANP and ADVCs that yield environmental and socioeconomic benefits. | Gender-responsive and inclusive training provided to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation and restoration practices. | Former Outputs 3.1.2 and 3.1.3 were reordered to first focus on enhancement of skills and knowledge through training, prior to implementation of management initiatives. |
| Output 3.1.3 | People from local communities in PAs and ADVCs trained to enhance their skills and knowledge in sustainable land management, conservation and restoration practices. | IP&LCs and local organizations implement gender-responsive and inclusive conservation, restoration and sustainable management actions defined in POAs. | See above. Output 3.1.3 also slightly revised for clarity. |
| Output 3.1.4 | None | Emergency fund expanded to support emergency-response brigades. | Stakeholder engagement on Component 3 identified the need for a financial mechanism to support emergency response brigades, ensuring that project conservation and restoration outcomes can be sustainably maintained. |
| Output 4.1.1 | Progress on project workplan is measured according to M&E protocols. | Ongoing lessons learned from MEx30x30 and other long-term sustainable finance mechanisms and PA scaling experiences documented and disseminated. | With new Component 4, this output was added to capture how the project will promote learning and knowledge sharing in the areas of PA scaling and long-term sustainable finance mechanisms. |
| Output 4.1.2 | None | National workshop and dissemination event held to finalize scaleup strategy document based on MEx30x30 experience. | As part of new Component 4, this output was added to ensure finalization of Mex30x30’s scale-up strategy document, with broad-based national buy-in. |
| Output 4.2.1 | None | Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | Output was moved and revised to capture the need for a Monitoring and Evaluation framework that is gender-responsive and inclusive. |
| Output 4.2.2 | None | Project Implementation Reports, Mid-term Review, and Terminal Evaluation completed. | Output 4.2.2 was added to ensure PIR, MTR and TE project requirements are included as explicit key outputs of the M&E system. |
| GEF Budget |  |  |  |
|  | Component 1: 1,750,000 Component 2: 1,750,000 Component 3: 12,051,639 M&E: 326,911 PMC: 793,927 Total: 16,672,477 | No change | Changes to include additional monitoring and evaluation activities that were previously under Component 1 and 2 are now included in Component 4. Component 1: 1,690,290 Component 2: 1,516,539 Component 3: 12,146,999 Component 4: 524,722 PMC: 793,927 Total: 16,672,477 |
| Co-financing |  |  |  |
|  | Component 1:100,000,000 Component 2: 1,750,000 Component 3: 14,100,000 M&E: 317,000 Total: 115,167,000 | No change | Revised to include co-financing to C4 and PMC, plus co-financing from CI. C1: 100,000,000 C2: 500,000 C3: 14,100,000 C4: 447,000 PMC: 502,532 Total: 115,549,532 |

## Project Rationale

Mexico’s vast territory, geographic location (including the longest coastline of any Latin American country) and altitudinal gradients give the country an enormous diversity of climates, with multiple biomes including deserts, scrublands, numerous rainforest types, temperate forests, alpine regions and mangroves. As a result, Mexico is one of the world’s 15 megadiverse countries, home to between approximately 10-12% of all global biodiversity. This includes ranking third globally in mammal diversity (over 564 species, 30% of which are endemic) and second for reptiles (over 860 species, 45% of which are endemic). The country is the genetic center of 118 crop species (notably maize) (CONABIO, 2017) comprising 15% of the human diet, and over 5,000 species of Mexico’s flora are used by indigenous and local communities for a wide range of traditional uses, including over 3,000 medicinal plant species (BIOFIN 2023). Given its wealth of biodiversity, several international classifications validate its importance, including: three of Conservation International’s “Hotspots” (Mesoamerica, California Floristic Province and Madrean Pine-Oak Woodlands), 122 of WWF’s Global 200 ecoregions, and 275 Key Biodiversity Areas (KBAs) (CEPF 2023; Olson et al. 2000; CBD 2021).

To safeguard its globally important biodiversity, Mexico has enacted a diverse set of ambitious initiatives over the last three decades, including the recent record in the expansion of the country’s protected areas. At the beginning of 2024, approximately 14.6% of Mexico’s total land and inland waters area (over 28.6 million ha) was under some form of protection, while over 21.5% of Mexico’s total marine and coastal territory (70.8 million ha) was protected (UNEP-WCMC 2024). A significant majority of Mexico’s protected areas (over 93 million ha) is managed by the federal Commission of Protected Natural Areas (CONANP), which as of the beginning of 2024 was responsible for 226 federal terrestrial and marine protected areas.

Recognizing the importance of community participation, CONANP champions the creation of “Areas Voluntarily Destined for Conservation” (Spanish Acronym ADVC). ADVCs are established and officially recognized by CONANP at the request of communities or landowners, and are designated for both conservation management and sustainable productive practices such as sustainable forestry, climate-smart agriculture, regenerative livestock and ecotourism. These areas, situated on private or communal land, serve a vital public interest function and are officially established through CONANP certification. Positioned in proximity to PAs, ADVCs contribute to connectivity of natural ecosystems and preservation of crucial environmental services, with a pivotal role in facilitating the movement of species and maintaining ecological flow. By the end of 2023, Mexico had legally recognized 395 legally ADVCs as part of its official protected area system, encompassing over 701,000 ha (CONANP 2024). The government has set a target of reaching 1 million hectares by 2030, as outlined in the National Determined Contributions (NDC) of 2022, underscoring a commitment to sustainable practices and the importance of community involvement.

Global biodiversity problem to be addressed

The objective of the MEx30x30 Project is to advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas. This objective is aligned with the targets of the Global Biodiversity Framework Fund (GBFF) as well as Mexico's National Biodiversity Strategy and Action Plan (NBSAP). The design of MEx30x30 responds to two critical factors facing biodiversity conservation in Mexico: the current status of financing for protected areas (PAs), and the crucial role of Indigenous Peoples and local communities  (IP&LCs) in Mexico’s efforts to achieve the 30x30 target.

Current status of financing for PAs

The annual budget allocation from the central government to CONANP reached a record US$92 million in 2023 and expects to reach US$100 million in 2024. The Protected Areas Fund (FANP) -a public-private partnership between CONANP, the Mexican Fund for the Conservation of Nature (FMCN) (the national Conservation Trust Fund (CTF) of Mexico), was established with GEF support 26 years ago. FANP complements CONANP’s budget with annual support for PA management totaling US$10 million. However, a preliminary gap analysis conducted by CONANP suggests that US$197 million per year will be needed over the next six years to meet the 30x30 goal. This leaves an annual shortfall of US$87 million. Consequences of this shortfall include: insufficient resources for effective management of existing PAs; and virtually no budget for newly created PAs, a problem that will grow as Mexico extends protected status to additional areas in pursuit of the 30x30 target. This shortfall of financing endangers the commitment of the government of Mexico to achieve 30x30 goal, as the present administration has the record of more new PAs decreed in the history of Mexico.

Crucial role of IP&LCs

Mexico is a multiethnic and multicultural country with more than 68 Indigenous groups identified in the 2020 Population and Housing Census produced by the National Institute of Statistics and Geography (INEGI); approximately 23 million people aged three years or above self-identify as Indigenous in Mexico, 19.4% of the country's total population (IWGIA 2023). Most of Mexico’s 226 PAs are home to IP&LCs with deep cultural connections to the land and livelihoods that depend on effective PA management to maintain critical ecosystem services (see Figure 1 below). These communities play a critical role in conserving biodiversity due to their traditional ecological knowledge and management practices, and supporting sustainable livelihood options is essential to ensure biodiversity conservation. Forest ecosystems play a particularly outsized role in the economies of rural and Indigenous communities, with over 20 million Mexicans relying on forests for part or all their livelihood, and 5 million Indigenous people living in forested areas (World Bank 2018). Moreover, given the considerable additional area under PAs and ADVCs needed to reach the 30x30 target and the fact that IP&LCs may own more than half of Mexico’s land (RRI 2015), adequate financing for appropriate involvement of IP&LCs in PA and ADVC creation and management will be essential.

Figure 1. Overlap between Indigenous Groups and PAs

Project Sites supported under component 3

To achieve 30x30, Mexico is in the process of expanding its system of protected areas and ADVCs. In addition to addressing the challenge of CONANP financing shortfalls, under Component 3 MEx30x30 will ensure that three recently created PAs (Balam-Kú, Bajos del Norte, and Tecuani), two previously created but under-resourced PA (Cuenca Alimentadora del Distrito Nacional de Riego 043 and Papigochic), and one set of 8 ADVCs (Chimalapas cluster), totaling 4,969,780 ha, meet the criteria of effective management. These areas were selected by CONANP as focal areas for MEx30x30 for their biological importance, the presence of IP&LCs, and diversity of regions and thus ecosystems. IP&LCs inhabit, use, and protect ecosystems in and around all the PAs and ADVCs included under Component 3. MEx30x30 will facilitate IPLC conservation initiatives to ensure sustainable resource use and strengthen protected areas management through two approaches:

1) ADVCs are areas in which the legitimate owners are communities or individuals. The Chimalapas complex is a region where IP&LC are the owners of eight ADVCs. These IP&LCs committed to protecting and sustainably managing their land; in return, the owners receive a federally administered certification issued by the Ministry of the Environment and Natural Resources (SEMARNAT). In ADVCs, the decision-making process is typically collective and democratic, involving the participation of all community members with land rights. Decisions are usually taken in the General Assembly, the highest decision-making body, composed of all adult members of the community. These assemblies are typically held regularly, often monthly or quarterly, and serve as fora for discussing and deciding essential matters. In many ejidos and communities, decisions are reached through consensus rather than a majority vote. This means that all members are encouraged to express their opinions and concerns, and efforts are made to find acceptable solutions. Before making decisions, members of the ejido or community engage in thorough discussions and debates to ensure that all viewpoints are considered. This process can be time-consuming but is essential for reaching agreements that reflect the interests of the entire community. While all members have the right to participate in decision-making, ejidos and communities may also elect representatives or delegates to negotiate on behalf of the community in certain situations, such as dealing with external entities or government agencies. Given that ejidos and communities typically manage collectively owned land and natural resources, decisions often revolve around their sustainable use and conservation. It may involve agreements on farming practices, forestry management, water allocation, or other resource-related issues.

2) Mexico is also unique because most protected areas (PAs) are home, under an established communal land tenure system, to indigenous peoples and local communities (IP&LC) with deep cultural connections to the land. These communities play a critical role in conserving biodiversity due to their traditional ecological knowledge and management practices. Protected Area Advisory Councils (and similar participatory bodies) provide a mechanism through which IP&LC and other stakeholders can be aware, participate, advise, and support decision-making of the pertinent strategies to address the priority needs of the PAs. The Project will ensure that PA Advisory Councils or similar participatory bodies will be used as platforms to engage IP&LC in developing the PA Annual Operating Plans (POAs for its Spanish acronym) and implementing the POAs' conservation, restoration, and sustainable management practices, creating community-based brigades and accessing capacity-building initiatives, job opportunities, and community-driven development projects for sustainable and equitable outcomes, particularly for women and indigenous peoples.  Many of the POA activities includes actions that improve socioeconomic wellbeing increased income from sustainable use and productive restoration supported, increased employment trough monitoring and fire brigades, increase governance and social cohesion through training.

See below for summary descriptions of each area supported under Component 3 and Figure 2 for a map, as well as summary information in Table 1; further details are provided in Annex J.

Balam-Kú

Balam Kú is a 463,441.76-hectare Biosphere Reserve (BR) in the state of Campeche on the border with Guatemala. The word balam kú is composed of the Maya words: balam, 'jaguar'; and kú, 'temple'. It alludes to the three jaguars that are represented in the archaeological zone located within the BR. Balam Kú is a contiguous neighbor of the Selva Maya Biosphere Reserve decreed in 1990, which has almost half a million hectares. Balam Kú is one of the potential areas to be supported by the GEF-8 Forest Biomes Project; the GBFF resources will be focused on financing the operational costs, while GEF-8 complement with communications, early warning systems, local governance structures, local training of CONANP staff, equipment. CONANP will coordinate both investments, to ensure complementarity. The Selva Maya, shared by Belize, Guatemala and Mexico, represents one of the most important ecological systems at a global level, because it is considered the largest continuous massif of humid and sub-humid tropical forest in Mesoamerica and the second largest tropical forest in America, after the Amazon Rainforest. Balam Kú is linked by bioclimatic corridors with Balam Kin Ecological Conservation Zone and the federal Calakmul Biosphere Reserve. Balam Kú is home to 889 people and two agrarian nuclei with indigenous households in Kilometer 120 and Hecelchakán. The vegetation in this area consists mainly of low deciduous and sub-deciduous forests and wetlands. In the most arid zones, the vegetation can be xerophytic and be formed by thorny scrub and cacti. The conditions of the area allow the development of other types of vegetation characteristic of this zone such as the "bajos", which are generally low flooded areas that present distinctive plant associations. A number of species are endemic to the region, including 8 reptile species, 4 species of mammals, and 660 (76 endemic) species of vascular plants. There are also a number of species that are priorities for conservation in Mexico, including the colorless juil (Rhamdia guatemalensis), the striped spiny iguana (Ctenosaura similis), the Yucatan spiny-tailed iguana (C. defensor), the swamp crocodile (Crocodylus moreletii), the masked duck (Nomonyx dominicus), sad pigeon (Patagioenas nigrirostris), blue-crowned parrot (Amazona farinosa) and dusky-headed parrot (Pyrilia haematotis). There are 19 species of amphibians, which represents 83 % of the state's amphibian diversity, and the area contains 21 % of the bat species distributed in Mexico. Main threats to the area include deforestation and illegal logging, forest fires, introduction of invasive exotic species, and climate change.

Bajos del Norte

Bajos del Norte is a national marine park in the Gulf of Mexico, covering 1,304,115 hectares. The reef areas of the northeastern end of the Yucatan Peninsula are transition zones between the Gulf of Mexico and the Caribbean Sea, therefore, this is considered a region of ecological connection and, therefore, of high biodiversity. The Bajos del Norte reefs are the second most relevant site as a larval source for areas in the northern, western and central Gulf of Mexico for several key fishery species for the region's economy. The area is characterized by its upwelling system and the so-called "loop current", both of which are responsible for the balance of nutrients in the Gulf of Mexico shelf and for the genetic connectivity and biological exchange of reef species, especially those of fishery value. It is one of the main grouper fish (Epinephelinae) reproduction sites in the Gulf of Mexico. Species richness represents 6 % and 25 % of the species recorded for the Gulf of Mexico and the Mexican Caribbean, respectively. Five species of sea turtles are present: loggerhead (Caretta caretta), white (Chelonia mydas), hawksbill (Eretmochelys imbricata), olive ridley (Lepidochelys kempii) and leatherback (Dermochelys coriacea), which are listed as Endangered, as well as being priority species for conservation in Mexico. The area also hosts the threatened rocky star coral (Orbicella annularis). The area is important to the 68,944 people (6% of whom are indigenous) that belong to fishing communities on the Yucatán coast. Two coastal fishing municipalities are relevant to Bajos del Norte: Progreso and Dzilam de Bravo. Main threats include pressure on fish stocks due to overfishing capture of the reproductive stock of larger and more fecund females in deep areas, and climate change.

Chimalapas

Los Chimalapas is a set of 8 Areas Voluntarily Destined for Conservation (ADVCs) in the State of Oaxaca, totaling 438,662.66 hectares. It is an ancestral indigenous territory of the Zoque people, and is home to 16,286 people, 38% of which are indigenous. The protection of biocultural resources in the Los Chimalapas Region is important for generating important biological corridors with other nearby Protected Areas, in addition to protecting the area from mining and fossil fuel extraction. Important species include felines like Puma (Puma concolor), Ocelot (Leopardus pardalis), Tigrillo (Leopardus wiedii) and Jaguar (Panthera onca); quetzal; various species of parrots, macaws, and eagles, toucans (Rampasthus sulfurathos) and pajuil (Penelopina nigra); endemic plant species; endemic amphibians including Eleutherodactylus Lineatus macdougalli, Hyla sumichrasti, and Pseudoeurycea parva; and endemic reptiles such as Abronia bogerti, Abronia ornelasi, Adelphicos latifasciatus, Ctenosaura pectinata, Sceloporus internasalis, Anolis breedlovei, Anolis compressicaudua, Scincella gemmingeri, and Heloderma horridum. Main threats to the area include deforestation and land use change, forest fires caused by agricultural burning, and poaching. Additionally, there are historical land tenure disputes in the border strip with the state of Chiapas.

Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit

The 2,192,656.37-hectare Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit is a natural protected area in the states of Jalisco, Sinaloa, Durango  and Nayarit. More than 50% of the area is covered by oak-pine and pine-oak forests, providing important hydrological environmental services. Distrito Nacional de Riego 043 (Riego 043) is a large PA that has received GEF funding under the Conservation of Coastal Watersheds in the Context of Climate Change (known as C6 for its Spanish abbreviation) project. This support led to a 225,398 ha Biosphere Reserve decree in 2024 within Riego 043, which covers 2,192,657 ha. While C6 endowment funds will continue supporting the Biosphere Reserve, MEx30x30 will enable improved management in the full protected area of Riego 043 with technical and financial resources. The protected area’s forests are essential for water catchment and the recharge of aquifers for supplying population centers such as Puerto Vallarta and Bahía de Banderas. This watershed is also important for maintaining Marismas Nacional in Nayarit, which includes extensive mangrove areas. The water from this protected area makes agricultural and livestock farming possible and provides drinking and industrial water to 38 municipalities in Jalisco and Nayarit. Home to 52,498 people, nearly 50% of the population is indigenous, belonging to the Huicot or Gran Nayar region. Two of the four polygons that make up this protected area coincide with CONABIO's priority terrestrial regions, RTP-62 Sierra Vallejo-Río Ameca and RTP-60 Sierra Los Huicholes, as well as with the priority hydrological region: Río Baluarte - Marismas Nacionales. There are six areas of importance for bird conservation (AICAS): Quebradas de Sinaloa Nayarit and Durango, Guacamayita, La Michilia, Sierra de Valparaíso, El Carricito and Sierra Fría. The area hosts at least 15 endemic birds; around 80 species of mammals, with more than 15 endemic to Mexico and eight protected by Official Mexican Norms (NOM in Spanish) 059; more than 60 species of reptiles and 16 species of amphibians, more than half endemic to Mexico and at least ten threatened. Main threats to the area include deforestation, land use change, forest fires, presence of forest pests and diseases (e.g., defoliator, bark stripper, and parasitic plants), expansion of unsustainable extensive cattle ranching activities, illegal extraction of flora and fauna, soil degradation, presence of invasive exotic species, and climate change.

Papigochic

Papigochic is a 222,763.85-ha protected area in the state of Chihuahua, established in 2003. The type of vegetation that characterizes Papigochic is mixed conifer and oak forests. It has some of the last relics of old-growth forests in the world. The area coincides with CONABIO's priority terrestrial regions, Alta Tarahumara-Barrancas and Bassaseachic, and the priority hydrological region, Río Yaqui - Bassaseachic Waterfall. In addition, there is an area of importance for bird conservation (AICAS): Papigochic. Although only 10% of its population of 6,907 people is indigenous, this protected area is the only one decreed on Rarámuri (Tarahumara) lands. The area is important for tourism and recreation and provides natural resources for local population, mainly related to the use of timber forest species for the construction of houses, fences, commercial purposes and fuel. Additionally, non-timber resources such as mushrooms and wild plants are used for food and medicine, and grasses, shoots and foliage are used for fodder. Main threats include deforestation, habitat modification or loss (reduction, fragmentation), natural phenomena (snowfall, north winds, hailstorms, cold fronts, rainfall, drought), forest fires, land cover conversion for the development of productive activities (forest exploitation, mining exploration and exploitation, agriculture, livestock), presence of forest pests, and population growth near forested lands.

Sierra Tecuani BR

The 348,140.97 hectare Sierra de Tecuani Biosphere Reserve, in the state of Guerrero, is a biological corridor for the jaguar in Mexico. The term tecuani is of Nahuatl origin and refers to the "man-eater", in allusion to the various species of felines identified in the area. The Sierra Madre del Sur is in the transition zone of the Nearctic and Neotropical regions, which favors the presence of a great diversity of species, including several microendemic vertebrates such as the tree frog (Charadrahyla tecuani), the Guerrero rattlesnake (Crotalus ericsmithi), the short-crested coquette (Lophornis brachylophus) and the tropical shrew of the Sierra Madre del Sur (Cryptotis goldmani), among others. It is considered a zone of high endemism that harbors viable populations of different species with some degree of threat. Twenty-five species of fungi, 338 plant species, 16 invertebrate species, and 120 vertebrate species are endemic. 28% of the species at risk in the entire Sierra Madre del Sur are present in Tecuani. The 18 ejidos and communities (population: 17,768) that are part of the protected area have diverse populations, including indigenous peoples. There is a high level of marginalization in some of the communities. Land-use change is one of the most significant threats to the area. The expansion of avocado plantations and cattle ranching exert considerable pressure on the forests, as they involve the clearing of large areas, from the lowlands to the mountain forests. Forest fires are another cause of changes in vegetation cover, in addition to timber extraction.

Figure 2: PAs (Balam-Kú, Riego043, Papigochic, Bajos del Norte, and Tecuani) and ADVCs (Chimalapas) where MEx30x30 will work.

Table 1. Summary of Protected Areas and ADVCs supported under Project Component 3

| PA/ADVC | Mexico Category | IUCN Category | Terrestrial | Marine | Hectares | Key Biodiversity Areas (KBA) | Important Bird Areas (IBA) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Balam-Kú | Biosphere Reserve (BR) | Protected area with sustainable use of natural resources | X |  | 463,441.76 |  |  |
| Bajos del Norte | National Park (NP) | Strict Nature Reserve (Core Zone) |  | X | 1,304,114.89 |  |  |
| Chimalapas cluster | Areas Voluntarily Designated for Conservation (ADVC) | Protected area with sustainable use of natural resources | X |  | 438,662.66 | X | X |
| Cuenca Alimentadora del Distrito Nacional de Riego 043 Estado de Nayarit | Natural Resource Protection Area (NRPA) | Protected landscape/seascape | X |  | 2,192,656.37 | X | X |
| Papigochic | Flora and Fauna Protection Area (APFF) | Habitat/species management areas | X |  | 222,763.85 | X | X |
| Tecuani | Biosphere Reserve (BR) | Strict Nature Reserve (Core Zone) | X |  | 348,140.97 | X | X |

Environmental Problem: Root Cause, Drivers and Barriers

The root cause of threats to Mexico’s protected areas, in the absence of management capacity reinforced through enhanced financing, is pressure for economic development throughout the country and especially in poor and marginalized rural areas. This pressure leads to land use change and degradation, driven by deforestation, overgrazing, overharvesting of natural resources, agricultural conversion, and urbanization. These drivers, exacerbated by poor soil conditions in many areas as well as impacts of climate change (Ortiz García et al. 2022; see below), can take the form of encroachment on protected areas, undermining sustainable resource use and biodiversity conservation. While the Federal Government has made important commitments towards conservation and natural resource management, including the GBF 30x30 target, funding for federal environmental agencies is not sufficient to fulfill the growing commitments and address climatic and environmental challenges.

For example, although the annual rate of forest loss has decreased over the last few decades, Mexico continues to lose forest cover at a 0.2 - 0.3% per year, with over 179,000 ha of forest lost in 2022 alone (Global Forest Watch 2023). Between 2001 and 2022, Mexico lost 4.66 million ha of tree cover (around 8.8% of the total), equivalent to 1.88 Gt of CO₂e emissions (Global Forest Watch 2023). Another example of pressure on ecosystems is land degradation, with about 12% of the country experiencing “severe or extreme soil degradation,” and nearly 60% experiencing impacts of desertification (Etchevers et al. 2020; CONAFOR-UACh 2013; Granados-Sánchez et al. 2013). Land degradation is a particular challenge for small family farms, which make up around 80% of all farmers on roughly 70% of land under cultivation. The high levels of poverty of many of these farms preclude investments in soil conservation or restoration, instead leading to clearing of new areas (Ortiz García et al. 2022). These deforestation and degradation trends pose a persistent threat to PAs as local resource users seek new areas for cultivation, livestock grazing, and resource extraction. One indication of the negative impact of such trends on Mexico’s biodiversity is that at least 2,606 species are deemed threatened or at risk of extinction (CONABIO 2017; NOM-059-SEMARNAT-2010).

As noted, climate change further exacerbates pressure on Mexico’s ecosystems. Its position between two oceans, topography and reliance on agriculture leave the country particularly vulnerable, notably to extreme meteorological events such as Hurricane Otis in October 2023 which caused sudden and widespread damage to Acapulco, Guerrero and surrounding areas. Climate change forecasts for Mexico show increased and more frequent extreme weather events (World Bank Climate Change Knowledge Portal 2023); rural and high poverty areas, notably in Mexico’s southern states, are particularly susceptible to impacts from climate change, and their ability to mitigate and recover is low (Islam and Winkel 2017). Although the national government has moved forward on increasing Mexico’s readiness for the impacts of climate change, Notre Dame’s Adaptation Initiative (ND-GAIN) currently ranks Mexico as 88th out of 185 countries in terms of readiness to address the impacts from climate change, indicating substantial room for improvement (ND-GAIN 2024).

Among the most urgent needs in order to respond to these trends is enhanced ability on the part of CONANP to mount an effective PA management response, ranging from monitoring and enforcement to disaster response to community engagement and support for sustainable livelihoods. Without the MEx30x30 project, the result of persistent budget shortfalls will be that: a. existing PAs and ADVCs experience continued and growing inadequacy to management responses, and b. new PAs and ADVCs established to meet the 30x30 area target will exist as paper parks without effective management. This in turn will lead to continued erosion of ecosystem services driven by encroachment, conversion and unsustainable resource use. Habitat loss and degradation will put biodiversity at ever greater risk and undermine rural livelihoods that depend on natural resources.

The principal barrier to enabling CONANP to apply effective management to the entirety of Mexico’s PA system is its budget shortfall, estimated at US$87 million per year until 2030. This barrier is linked to capacity constraints of CONANP with respect to conservation finance strategies, including both mobilization of new revenue streams and optimization of the use of available funding. To address this barrier, MEx30x30 will pursue the following Outcomes:

Outcome 1.1:	CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased

Outcome 2.1:	Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years.

Outcome 3.1:	PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LC.

The proposed Project approach of MEx30x30 leverages several enabling factors: alignment with country priorities and strong political will and leadership, reflected in Mexico’s 30x30 commitment; global recognition of need to increase funding to address the global biodiversity crisis together with the climate crisis; and global recognition of the important role of IP&LC in achieving global biodiversity and climate change mitigation goals. Combined with their strong record of mobilizing conservation finance (as seen in the success of FANP), FMCN and CONANP are confident that the Outcomes summarized above will result in financial and institutional sustainability that ensures Mexico’s enduring contribution to the GBF 30x30 target.

Project Stakeholders

Making the Project work requires active participation of the following stakeholders:

National Commission for Protected Areas (CONANP): CONANP oversees 226 terrestrial and marine PAs throughout Mexico, encompassing over 90 million ha. The PAs encompass 14.6% of the land territory and 21.5% of Mexico´s oceans. They are managed by a 1,680 staff that work daily with 35,000 members of local communities. As the federal agency leading this project, CONANP will ensure that the project is aligned with policy commitments and national strategies. The project will enhance the capacity of CONANP to close the financial gap for the system of federal protected areas by 2030, through a variety of revenue streams, as well as increasing CONANP’s capacity to efficiently use this budget. Monitoring by CONANP will be strengthened, while prevention and rapid response to fires, droughts and hurricanes will be developed through a consolidation of a learning community of managers and rangers.

Fondo Mexicano para la Conservación de la Naturaleza, A.C.(FMCN): A national conservation trust fund, FMCN has 30 years of experience in supporting conservation efforts in Mexico, including improved management of nearly 30 million ha of land (including 70 PAs through the 26-year-old Fund for Protected Areas, a public-private partnership with CONANP) and promoting the wellbeing of almost 80,000 people through its $200+ million endowment and additional sinking funds. Its work includes large, landscape-scale projects in all regions of the country with partners as diverse as the Government of Mexico, the GEF, World Bank and the Green Climate Fund, from which it was the first Mexican organization to receive accreditation. FMCN projects are supported by multi-lateral funds, bi-lateral funds such as the Development Bank KfW and private foundations such as the Packard, Summit and Walton Foundations. It has implemented three successful projects (FANP 1, FANP 2 and Conservation of Coastal Watersheds in the Context of Climate Change Project), has one project under implementation (CONECTA) and has one project in the pipeline corresponding to the GEF-8 allocation (ORIGEN). In total FMCN has received more than US$70 million from GEF. FMCN has been supported by 146 donors and participates actively in conservation finance networks, such as Mexico Conservation Funders, the Latin American and Caribbean Network of Environmental Funds (RedLAC) and a network of Mexican foundations. FMCN will serve as the Executing Agency, leading resource mobilization under Component 2 and managing the endowment for Component 3.

Conservation International-GEF Implementing Agency (CIGEF): As an Implementing Agency for GEF since 2013, CIGEF has a portfolio of more than 300 million USD mobilized across GEF focal areas and regions. In Mexico, the Agency has been working in GEF-funded projects since 2016 with a portfolio of 4 projects. (i) Maintaining and Increasing Carbon Stocks in Agro-silvopastoral Systems in Rural Communities of the Selva Zoque — Sumidero Canyon Complex as a Climate Change Mitigation Strategy (GEF 5 project- closed); (ii) Conservation and sustainable use of biological diversity in priority landscapes of Oaxaca and Chiapas (GEF 6 project in its last year of implementation); and (iii) ORIGEN: Restoring Watersheds for Ecosystems and Communities (GEF 8 project in PPG phase with FMCN as Executing Agency) and now the first GBFF project in Mexico with FMCN as EA,  and the support of  together with CONANP.

Indigenous Peoples and local communities (IP&LC): IP&LC inhabit, use, and protect ecosystems in and around allll the PAs and ADVCs included in Component 3.  ADVCs are areas in which the legitimate owners are local communities or individuals. The Chimalapas complex is a region where IP&LC are the owners of eight ADVCs. These IP&LC committed to protecting and sustainably managing their land; in return, the owners receive a federally administered certification issued by the Ministry of the Environment and Natural Resources (SEMARNAT). Additionally, all Protected Areas in Mexico have an Advisory Council or similar participatory body, through which government institutions, civil society, academic and research entities, and representatives of the people living in the area (e.g., ejidos, communities, indigenous groups, and women) can be aware, participate, advise, and support decision-making of the pertinent strategies to address the priority needs of the PAs. The Advisory Councils or similar participatory bodies will be used as platforms to engage IP&LC in developing the PA Annual Operating Plans (POAs for its Spanish acronym) and implementing priority actions. Mex30x30 will build on lessons learned through the PAs Advisory Councils that date back to 1996 and through which IP&LCs participate in the management of the PAs. The project will strengthen the organizational capacity of IP&LCs for conserving and sustainably managing areas and territories under their stewardship and governance.

Legally Constituted Local Organizations (OLLCs): Legally constituted local associations, groups or organizations with the capacity to receive, manage and apply resources will act as intermediaries between FMCN and CONANP to administer the annual plans (POAs) for Protected Areas in Component 3. The Fund for Protected Areas Committee established since 1996 will select local organizations through a call for proposals process. The local organizations will work with CONANP to break the POAs into weekly plans, spend funds accordingly, prepare administrative reports and support CONANP with technical reports.

Other Donors: Using a long term-finance mechanism following the Project Finance for Permanence (PFP) approach, the project will attract and mobilize funding to establish a transition fund to cover the financial gap in protected areas while public funding reaches its target. This funding will be from additional donors, mainly philanthropy.

Landscape of relevant recent and ongoing initiatives

FMCN and CONANP have more than two decades of shared collaboratives experiences in improving protected area management effectiveness, securing financial sustainability and strengthening and expanding CONANP’s institutional capacity. Recent and ongoing collaborative initiatives include:

Fund for Protected Areas (FANP), 1997-Present (endowment) (USD165 million): Initially started in 1997 with USD16.48 million in GEF funding, the Protected Areas Fund (FANP in its Spanish acronym) is a public-private partnership between FMCN, CONANP and 20 additional donors. At the beginning of 2024, FANP is supporting 70 PAs (55 with endowment funds), including activities in biological monitoring, restoration, fire management, and productive projects. Its total endowment has increased to US$165 million owing to the contributions of 21 donors from the multilateral, bi-lateral, philanthropic and private sector. FANP has been widely recognized as “best practice” example, as PAs with additional operational financing by FANP in Mexico avoided up to 23% forest loss from 2001 to 2012 (Hansen et al.). Currently, FANP contributes $10 million in additional funding CONANP’s US$92 million annual budget, allowing CONANP to cover operating costs, provide additional staff and support to local communities and lower CONANP’s annual financial gap to US$87 million.

Monarch Butterfly Fund, 2000-Present (endowment) (USD7.5 million): The Monarch Butterfly Fund is a public-private collaboration to support conservation and restoration of core area forests in the 56,259 ha Monarch Butterfly Biosphere Reserve in central Mexico, which is managed by CONANP. As part of FANP endowment, the US$8.6 million endowment fund is administered by FMCN in collaboration CONANP, the World Wildlife Fund (WWF), the governments of the states of Mexico and Michoacán, and the National Forestry Commission (CONAFOR, acronym in Spanish). The annual return of the endowment provides payments for ecosystem services to the IP&LCs that support the ecological integrity of the Reserve.

Sustainable Financing for New Protected Areas (FINANP), 2021-2026 (endowment) (Eur22 million): The Sustainable Financing for New Protected Areas (FINANP, acronym in Spanish) is a project funded by the KfW Development Bank with the collaboration of the International Union for the Conservation of Nature (IUCN), FMCN and CONANP. Phase I involves IUCN support for effective management of ADVCs. Phase II includes US$14.1 million in endowment funds that are part of FANP. The annual return supports CONANP’s effective management of three federal marine PAs covering over 22 million ha. This project provides beyond a 1:1 match in endowment funds to Component 3 of Mex30x30.

Biodiversity Conservation in the Sierra Madre Oriental and Gulf of Mexico (Sierra y Mar), 2019-endowment (Eur15 million) The Sierra y Mar project is a collaborative effort between KfW Development Bank, FMCN and CONANP to ensure effective conservation of 14 protected areas and ecological corridors. Principal activities include strengthening the management capacity of the 14 protected areas and productive capacity of local communities, securing financial sustainability for management activities and improving CONANP's capacity in critical cross-cutting issues, such as communications and monitoring and evaluation. It consists of an endowment managed by FMCN as part of FANP.

Connecting Watershed Health with Sustainable Livestock and Agroforestry Production (CONECTA, acronym in Spanish), 2021-2026 (USD 13.76 million). A Child Project under the GEF-7 funded Food Systems, Land Use and Restoration (FOLUR) Impact Program, CONECTA’s main objective is to improve integrated landscape management and promote climate-smart production practices in 450,000 ha of selected watersheds in the states of Chiapas, Chihuahua, Jalisco, and Veracruz. Through a landscape-based approach, the project is focused on interventions in watersheds vulnerable to land use change, climate change and impacts of soil erosion. Principal activities include promoting productive and environmentally compatible practices that increase forest areas under sustainable landscape management and improve livelihoods, water quality, and biodiversity. The project is supported by National Institute of Ecology and Climate Change (INECC, acronym in Spanish), with FMCN overseeing fiduciary aspects and CONANP being a member of the governance structure’s Coordinating Committee, which will scale CONECTA’s impact by aligning public and private investments with project activities. CONECTA´s funding is matched by the RIOS project (US$9 million), which is the first Green Climate Fund (GCF) project in Mexico with FMCN as accredited entity. RIOS shares the institutional arrangements of CONECTA and complements funding in CONECTA´s watersheds by restoring rivers as a mean to address adaptation to climate change.

CONECTA was built off the GEF financed Coastal Watersheds Conservation in the Context of Climate Change Project (C6), 2014-2019 (USD 39.52 million). Undertaken collaboratively by INECC, CONAFOR, CONANP, and FMCN, all of which served as members of the governance structure’s Project Committee, the C6 project successfully consolidated 1.1 million ha of protected areas and improved land and forest management, allowing for reduced carbon emissions in 1.027 million ha of watersheds. Six strategic watersheds successfully developed and implemented Integrated watershed/sub-watershed action plans (IWAPs) (World Bank 2019). Two Regional Funds, FONNOR in Jalisco and the Gulf of Mexico Fund (Fondo Golfo de México, FGM) in Veracruz were created by the project to undertake coordination and training activities in priority areas.

Enhancing Political Will for Sustainable Protected Areas Financing (USD2 million). The GEF financing and United Nations Environment Program as IA, and Conservation Council of Nations as EA, focuses on creating the necessary conditions in the legislative branch to increase the budget for PAs. It will complement MEx30x30 by supporting the required changes in legislation identified in Component 1.

Forest biomes of Mesoamerica. Mexico National Project – Mayan Rainforest (USD13.3 million). This GEF financing, IUCN as IA, will be implemented during 2025-2029. It eeks to support the transformative change towards the conservation of the Mayan rainforest by a set of interventions addressing the main drivers of deforestation and degradation. It is structured around four components: 1) Adoption of enabling policies and planning frameworks; 2) Accelerating the implementation of actions for forest protection and restoration; 3) Increased investment in rainforest landscapes; and 4) Enhanced regional coordination and cooperation. oth projects will work within the Balam Kú PA, an therefore the alignment of activities for conservation and sustainable use is expected to synergize.  Forest Biomes is expected to begin in 2025. It will contribute to the following complementary efforts (not included in MEx30x30): (i) Strengthening of local and national governance structures to increase the effectiveness of primary forest protection and conservation; (ii) Early warning systems for timely transmission of alerts to field staff, (iii) Training of PA's staff; (iv) Procurement of tools and equipment and (v) Regional assessment of collapse risk. As CONANP participates in both projects, this will ensure that there is synergy with this project and the activities included in POAs under MEX30x30 Component 3.

Lessons learned from previous projects

The project will build on 26 years of successful public-private collaboration between CONANP and FMCN through the Protected Areas Fund (FANP). The following best-practices have been developed and will be applied to this project:

- FMCN is well-positioned to manage funds for federal PAs administered by CONANP so that resources are used for strategic conservation activities in the territory. It has been found that PAs with additional operational financing by FANP in Mexico avoided up to 23% forest loss from 2001 to 2012 (Hansen et al.).

- The Protected Areas Learning Community (CAAP) is an effective model for strengthening capacities of PA managers and local organizations through the exchange of experiences and peer-to-peer learning.

- Long-term monitoring of biological and socioeconomic indicators as well as management effectiveness is critical for assessing protected areas. CONANP and FANP have successfully developed monitoring protocols for PAs that may be adapted for ADVCs.

- The development of an emergency fund and community brigades has been instrumental in successful rapid response to fires, hurricanes, and other emergencies, which, according to climate change projections, are expected to increase in the project areas.

A central feature of the MEx30x30 project is using a long-term financing using the Project for Permanence (PFP) model to structure a transition fund that will cover CONANP’s funding gap until federal funds can be secured to support longer-term protected area system costs. Cabrera et al. (2021), defined the PFP model as “an approach or single initiative that secures important policy changes, and all funding necessary to meet specific conservation goals of a program over a defined long-term timeframe, with the ultimate aim of achieving the ecological, social, political, organizational, and financial sustainability of that program.”

A 2023 PFP evaluation commissioned by Enduring Earth (EE), a global collaboration between The Nature Conservancy, The Pew Charitable Trusts, World Wildlife Fund and ZOMALAB, concluded that the PFP model offers a number of advantages that enable it to help countries achieve large-scale conservation commitments, including reaching 30x30 targets. The evaluation highlighted the model’s ability to (EcoAdvisors 2023):

- achieve compromise among diverse stakeholder interests in furtherance of ambitious-scale conservation and sustainable development

- empower Indigenous-led conservation

- reinforce institutions that champion and facilitate large-scale conservation

- help make protected areas and conservation management resilient against adverse political pressure

- enable the application of long-term perspectives to protected area planning and management

- promote livelihoods and enterprise development grounded in sustainable resource management

The transition fund mechanism that FMCN and CONANP will use for the MEx30x30 project will draw on lessons learned from other PFP applications to achieve large-scale conservation outcomes. The model will mainly use lessons learned from Latin America from Brazil, Colombia, Costa Rica and Peru. For example, in Brazil a PFP structure was used to create a US$210 million sinking to support the country’s Amazon Region Protected Areas Program (ARPA), the world’s largest protected area system, until federal funds are available as of 2039 to cover the system’s management costs. To date, ARPA has allowed Brazil to create over 62 million ha of protected and sustainable use areas (roughly 9% of the entire Amazon) and support the consolidation of over 40 million ha of protected and sustainable use areas (EcoAdvisors 2023).

The MEx30x30 project design reflects lessons and best practices for PFPs distilled from the experiences noted above. This includes:

- Design, establishment and operation of PFP mechanisms must be grounded in participatory multi-stakeholder processes to cultivate broad-based buy-in and support.

- The financing solutions provided by a PFP must be paired with technical capacity building for institutions responsible for conservation and sustainable resource management.

- Safeguard policies and plans should be introduced from the beginning of the design process to be fully integrated into the long-term financial mechanisms (rather than grafted on afterwards as seen in some PFP processes), with the required allocation of budget and expertise.

- For PFPs with IP&LCs as a major constituency, meaningful governance roles in the PFP mechanisms are necessary to ensure social legitimacy as well as responsiveness to IPLC needs and priorities.

- The ability of PFPs to involve civil society and strengthen civil society capacity with respect to advancing and participating in conservation and protected area management reflects untapped potential.

- The scale at which PFPs operate may limit the extent to which design and launch processes can be truly inclusive, particularly on an ambitious timeline; this trade-off needs to be explicitly recognized and planned for, with a concerted outreach effort early in implementation.

- The transition fund approach needs to be accompanied by other strategies to safeguard permanence: government commitments, cultivating a broad multi-stakeholder constituency to hold parties to their commitments, and advancing a diversified set of financing solutions to reduce vulnerability to changes in government priorities.

Provisions for knowledge management (KM) in MEx30x30 will incorporate the following lessons from other projects:

- Knowledge sharing should be founded on a demand-driven process where the needs of stakeholders are prioritized, as well as themes and experiences with the best potential for replication and scaling up.

- Traditional knowledge in the management of natural resources is often overlooked, therefore knowledge management and sharing and capacity building should also draw from diverse sources, including traditional knowledge of local communities.

- Projects should build on and link to existing structures for learning and knowledge management. Opportunities for collaboration and cost sharing with other initiatives and existing platforms should be taken when appropriate.

- Diverse, easily accessible and culturally and technologically appropriate dissemination mediums in multiple languages (publications, websites, workshops, webinars) should be employed to ensure broad and inclusive access to multiple audiences.

- In-person and virtual knowledge-sharing and exchanges should have clear objectives and understanding of participants’ expectations, with appropriate translation provided. Robust and inclusive working stakeholder networks should be cultivated to allowing for regular exchanges of knowledge and experiences from multiple sources (local, traditional, customary, scientific, etc).

## Project Description

Theory of Change

As part of the Kunming Montreal Biodiversity Framework, Mexico has committed to effective protection of 30% of its territory by 2030. Accomplishing this goal will conserve the country’s enormous wealth of biodiversity but requires increased financial support to close the financing gap for Mexico’s PA system, including ADVCs, as well as a central role for IP&LCs. Therefore, the Theory of Change for MEx30x30 posits that:

If federal PA management is strengthened by mobilizing adequate funding and IP&LCs are directly involved in and benefit from implementation of gender-responsive and inclusive conservation initiatives in PAs and ADVCs, then the ecosystem services, the ecological integrity, and the overall conservation of globally significant biodiversity will be ensured.

The proposed interventions reflect this Theory of Change as follows:

| Theory of Change | Project Components |
| --- | --- |
| If federal PA management is strengthened by mobilizing adequate funding | Component 1 (Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively) will enhance the capacity of CONANP to reduce the financing gap for PA management by developing new revenue streams, and Component 2 (Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target) will apply the Project Finance for Permanence approach to mobilize funding that addresses the PA financing gap during a transition period in which CONANP develops the new revenue streams. |
| and IP&LCs are directly involved in and benefit from implementation of gender-responsive and inclusive conservation initiatives in PAs and ADVCs | Component 3 (Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories) will focus on IPLC roles in ADVCs and PA management, captured in Annual Operating Plans; provide training on sustainable management to IP&LCs such that they are able to fulfill these roles; and implement sustainable management initiatives that reinforce training and generate socioeconomic benefits for IP&LCs. |
| then the ecosystem services, the ecological integrity, and the overall conservation of globally significant biodiversity will be ensured. | Component 4 (Monitoring, evaluation, and knowledge management for scaling) will verify conservation of globally significant biodiversity through protected areas under improved management effectiveness (3,665,666 ha terrestrial and 22,241,504 ha marine) and 9.43 million tons of greenhouse gas emissions mitigated (as well as socioeconomic benefits for 163,293 people, 50% of whom will be women). |

Collectively the components summarized above will ensure enduring outcomes by putting in place the long-term financing required for Mexico’s national protected area system. Although economic pressure for development and the accompanying threats of deforestation, degradation, agricultural conversion, and unsustainable resource use are expected to persist, full funding for the nation’s protected area system in perpetuity will provide a lasting foundation for sustaining CONANP’s capacity to work with IP&LCs to ensure effective management of PAs and ADVCs and respond to these threats.

Figure 3 below illustrates how the project design reflects this Theory of Change:

Figure 3: MEx30x30 Theory of Change

Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively.

MEx30x30 will technically and financially support CONANP in closing its financial gap for existing federal protected areas through a variety of revenue streams, including federal appropriations, entrance and users’ fees, payment for ecosystem services, and compensations. The aim will be to have public resources cover the overall costs of PA management and ADVCs within fifteen years. Furthermore, CONANP will also increase its institutional capacity commensurate with the increase in the budget. Monitoring and evaluation of the federal PA system by CONANP will be strengthened, as will prevention of and rapid response to fires, droughts and hurricanes. Learning will be accelerated through the PA management community of practice established by FANP to encompass ADVCs. The incremental contributions of Component 1 will be to achieve critical expansion in CONANP’s capacity with respect to generating and managing funds, and better integration of ADVCs into management systems for the national PA network.

Outcome 1.1: CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased.

Under this outcome, CONANP will undertake a two-pronged process of both increasing its budget and gradually closing its funding gap by leveraging additional financial resources. Potential sources of additional revenue include (but are not limited to) further growth in federal appropriations, creating and/or updating frameworks for setting and collecting PA entrance and other user fees, expanding the application of Payment for Ecosystem Services (PES), and exploring the rapidly developing market for nature credits. Mex30x30 will coordinate activities with the GEF funded project “Enhancing Political Will for Sustainable Protected Areas Financing” implemented by the United Nations Environment Program and executed by the Conservation Council of Nations, which focuses on creating the necessary conditions in the legislative branch to increase the budget for PAs. Also, the project will collaborate where possible with Conservation International global and national initiatives related to conservation finance. Expanding the size and scope of revenue streams will require investment in capacity with respect to financing tools and financial management, as well as commensurate strengthening of CONANP’s institutional and technical capacity to accommodate growth in the national PA system and expanding use of ADVCs as Mexico pursues its 30x30 national goal.

Indicator 1.1: % decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams

Target 1.1: 10% decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams.

Output 1.1.1: New revenue streams to increase CONANP's budget are identified.

CONANP’s annual budget of approximately US$110 million currently relies on several revenue streams, including federal appropriations, user and entrance fees from PAs, various PES schemes, international donations, environmental compensation payments and around US$10 million per year from FANP. To close the budget gap of approximately US$87 million per year, new and augmented existing revenue streams are needed.  For Output 1.1.1, CONANP and FMCN will undertake an assessment to identify and analyze potential new revenue streams as well as options for increasing existing revenue streams to address the budget gap. Results of the assessment will be compiled into an action plan detailing steps to unlock the most promising (in terms of feasibility and yield) revenue streams to secure the projected budget needed to accommodate Mexico’s 30x30 goal. To identify and structure these new revenue streams, the project will explore potential collaboration with the United Nations Development Program Finance for Biodiversity BIOFIN and CI conservation finance work including nature credits initiative.

Indicator 1.1.1: # of feasibility reports and action plans for accessing new revenue streams completed.

Target 1.1.1: 1 feasibility report and action plan for accessing new revenue streams completed.

Output 1.1.2: New revenue streams to increase CONANP's budget are accessed.

Once finalized the feasibility report, CONANP will work closely with FMCN to operationalize the revenue action plan, developing and securing the most likely target revenue sources identified in the feasibility assessment (Output 1.1.2). Recognizing that some revenue streams will take longer to develop than others, CONANP and FMCN will initially prioritize those sources that could be developed relatively quickly based on existing institutional and financial management capacity (such as increases in PA entrance and user fees), with longer-term sources developed later in the action plan’s implementation in tandem with activities to install the requisite capacity (Output 1.1.3).

Indicator 1.1.2: # of new revenue streams accessed and contributing to CONANP budget.

Target 1.1.2: At least one new revenue stream accessed and contributing to CONANP budget.

Output 1.1.3: The institutional capacity of CONANP is enhanced through expanding the Protected Areas Learning Community (community of practice).

As CONANP’s budget accesses new and augmented revenue sources, a commensurate effort will be made to increase and strengthen its institutional capacity. The avenue by which the project will deliver Output 1.1.3 is Mexico’s existing PA Learning Community’s (Comunidad de Aprendizaje de Áreas Naturales – CAAP, acronym in Spanish), which will be expanded to increase its inclusion, reach and impact. Since 2012, CONANP and FMCN have promoted the CAAP through FANP, as a network of CONANP’s PA managers and local organizations to facilitate knowledge sharing and strengthen the capacities of its members to improve PA management and community development outcomes. Under this project, increased gender-responsive and inclusive learning and knowledge sharing approaches will be incorporated into CAAP, thereby allowing for greater participation and access to resources to a wider spectrum of stakeholders. Output 1.1.3 will include a particular focus on increasing participation of women from IP&LCs. Progress will be measured through CONANP’s existing institutional capacity assessment scoring system, using the first year of implementation as the baseline. Priority areas for increased capacity will include: roles relating to revenue generation; improvement of Mexico’s PA monitoring and evaluation system (including an adapted i-effectivity model for ADVCs); improved mainstreaming of key topics such as gender, safeguards, governance and IP&LCs; and augmented institutional capacity to prevent and respond to natural disasters and extreme weather events, including fires, droughts and hurricanes.

Indicator 1.1.3a: % improvement in CONANP institutional capacity assessment score.

Target 1.1.3a: 15% improvement in CONANP institutional capacity assessment score.

Indicator 1.1.3b: Increase in Protected Areas Learning Community membership (disaggregated by gender and IPLC membership).

Target 1.1.3b: At least 100 new members are part the Protected Areas Learning Community, of whom at least 50% are women.

Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target.

MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding. The PFP is intended at a national level but the number of PAs included will be confirmed as the work starts in the proposed steps. A preliminary exercise conducted by FMCN determined that FANP already meets most requirements to serve as the home for a financing mechanism within a PFP framework, thereby making the application of the PFP approach relatively straightforward. To raise additional revenues to close the funding gap, CONANP and FMCN will build on the strong track record of their 26-year partnership, which has attracted a growing number of donors to raise US$165M in endowment funds. Using networks and lessons learned from their shared FANP experience, CONANP and FMCN offer a strong basis for establishing a transition fund to support the financial gap of existing PAs that is approximately US$200 million in (the capitalization target will be finalized based on financial analysis and modeling planned for the start of the implementation period, see steps 5 and 6 Output 2.1.2). Once this transition fund is established, it is anticipated that it will support PA and ADVC management costs for 15 years, as CONANP works to close its budget gap (the timeline also will be solidified through the aforementioned financial analysis and modeling). The clear and critical incremental contribution of Component 2 is that it will overcome the barrier of PA financing shortfalls and enable effective management of PAs while additional revenue streams are developed.

Outcome 2.1: Donor support is secured to cover the financing gap for effective PA management over the next 15 years.

CONANP and FMCN have a well-established track record spanning 26+ years in effective fundraising, raising over US$165 million for the FANP. Using both its established network of prior and current donors, as well as using its proven record of success in attracting new donors, FMCN will develop and implement a strategic outreach plan to generate interest and commitments from likely donors. Given the financial gap of existing PAs, bi- and multi-lateral donors (national governments, multi-lateral institutions) will be critical funding partners, as will donors from the private and philanthropic sectors, notably large foundations and high net worth individuals. MEx30x30 will allocate a portion (US$1 million) of its GBFF-funding as the initial contribution to the transition fund, to signal a starting contribution to an existing solid mechanism ready to grow. This mechanism will incorporate gender and inclusion considerations and may have one of more phases, depending on the financial gap identified under Output 2.1.2.

Indicator 2.1: Percentage of required funding for a Transition Fund to cover PA financing gaps for 15 years.

Target 2.1:  100% required Funding secured for phase one for a Transition Fund.

Output 2.1.1: Funding pledged to address identified financial gaps.

FMCN’s will develop and execute the strategic outreach plan to secure donor commitments for the PFP. The intent is to secure pledges in advance as per other examples of the PFP approach, in which each donor commits to a simultaneous joint contribution to formally launch the PFP. In preparing the full design and financing model for the PFP (Output 2.1.2 below), CONANP and FMCN will determine the balance between the single close and continued post-launch capitalization work, reflecting the lesson from other PFPs that a single close does not eliminate the need for additional fundraising effort for MEx30x30. The activities include to develop outreach plan for each type of donors, obtain pledges from them, and to mobilize funds into the transition fund. The Transition Fund is a sinking fund with multiple donors, that as part of the PFP process it is expected to cover the financial gap while the public funding sources rump up.

Indicator 2.1.1: Amount of donor funding pledged to address financing gap for phase one during transition period.

Target 2.1.1: 100% of required funding for phase one to address financing gap during transition period (amount to be confirmed in step 5 and 6 of the long-term sustainable finance mechanism design process; see below).

Output 2.1.2: Long-term sustainable finance mechanism/PFP is designed.

CONANP and FMCN will apply the PFP approach to develop a long-term financing mechanism to support management of the existing national protected area system. The long-term financing mechanism will incorporate gender and inclusion considerations (e.g., gender mainstreamed in conservation, restoration and sustainable development in PAs and ADVCs, through the conservation plan). Using their shared experience with FANP and FMCN’s expertise in developing and implementing effective conservation finance mechanisms, they will define the most appropriate structure for an effective and efficient financing mechanism, including governance and safeguards considerations. The priority design objective for the transition fund will be to direct funding to PA management in a timely and efficient manner. Key steps for the PFP design will include:

- Setting up the transition fund with USD 1 M. FMCN will create a dedicated account that will compose the transition fund for Mexico-PFP as a sinking fund. FCMN will use its own guidelines to manage the corresponding investment.

- Formation of a coalition of institutions. A coalition will be formed to support and oversee the design of the PFP process.

- Hiring and designation of a Mexico- design team. The design of a long-term financial mechanism following the PFP approach is a complex and time-consuming process. For this reason, FMCN will hire a team to be designated by the coalition as responsible for bringing the design process ready for the signing of the PFP agreement.

- Development of a shared conservation vision. Members of the coalition will discuss and agree on a shared conservation vision for the PFP aiming at attracting other partners and funders.

- Financial gap estimation. Under component 1, experts will review and strengthen the financial gap estimation for the existent PAs. This will then input the PFP work.

- Design of a financial model and/or plan. A technical working group will be formed by the coalition to lead the PFP financial plan that will include: PA Network and ADVCs cost analysis, required funds for the transition fund and a strategy to generate revenues to fill the financial gap (complemented with the gap analysis from step v) and determine the transition fund amount required for a first phase to be implemented under this project.

- Design of a conservation plan. A technical working group will be formed by the coalition to lead the preparation of a PFP conservation plan in a participatory process, particularly at a local level. This plan will include specific actions that consider gender and inclusion dimensions and associated budget. The plan has a national scope, the number of PAs involved will be confirmed depending on the agreements after the financial gap estimation and financial model work are completed.

- Design the institutional arrangements for the adequate implementation of the initiative. The coalition will engage in the discussion of the PFP governance, focusing mainly in the organizational structure required by Mexico-PFP and will clearly define the roles of all participating institutions.

- Diagnosis, strategy, and development of domestic mechanisms sustainable financing. This activity will focus on supporting CONANP with complementary budget to develop prioritized sustainable financing mechanisms that can bring durability to Mexico-PFP transformative actions.

- Design and implementation of a communications strategy. Mexico-PFP will require a sound communications strategy for its different phases. During the design phase it will be focused mainly in: generating political buy-out, awareness at the local level, and fundraising.

Indicator 2.1.2: Number of long-term sustainable finance mechanisms designed and ready for closing.

Target 2.1.2: One long-term sustainable financing mechanism designed and ready for closing.

Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories.

Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for areas under conservation - three recently decreed PAs, two PA decreed prior to the present administration, and one complex of eight ADVCs recently established in the Chimalapas region of Oaxaca, an area with the highest biodiversity levels in all of Mexico. Specific PAs and ADVCs include Balam-Kú, Riego 043, Papigochic, Bajos del Norte, and Tecuani, located in five indigenous regions These areas were selected by CONANP for their biological importance, presence of IP&LCs, degraded areas eligible for restoration, regional and ecosystem diversity, and a mix of new and existing PAs. Advisory Councils or similar participatory bodies will be used as platforms to engage stakeholders in developing the Annual Operating Plans (POAs for its Spanish acronym) for the PAs and ADVCs (Output 3.1.1), with implementation of specific activities by IP&LCs and local organizations (Output 3.1.3). Training will be provided to IP&LCs in PAs and ADVCs (Output 2.1.2) to support implementation. With dedicated funding from the endowment, these PAs and ADVCs will serve as models for how biodiversity conservation can contribute to improved livelihoods through community management, with ADVCs in particular benefiting from technical assistance and financing to improve gender-responsive and inclusive sustainable use of natural resources and conservation activities. The incremental contribution of Component 3 will be to ensure effective management of 5 PAs and an ADVC complex of 8 certified areas that otherwise would remain paper parks. Moreover, this will provide the basis for replication and scale up of MEx30x30 outcomes as CONANP will apply the lessons learned from these areas by establishing new PAs and ADVCs with provisions for strong, gender-responsive and inclusive community management, helping propel Mexico to its 30x30 goal. During project implementation, CONANP and FMCN will assess whether to continue operating this allocation as an endowment fund or if it will be integrated into the transition fund.

Outcome 3.1: PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs.

An endowment managed by FMCN will ensure funding to support management of Balam-Kú, Riego043, Papigochic, Bajos del Norte, Tecuani, and Chimalapas ADVCs. During the establishment of the Transition Fund, depending on pledges from donors and increase in CONANP budget, FMCN and CONANP will analyze the suitability of using part or all of the endowment as a contribution to the Transition Fund at a later stage. This decision will be based on careful financial analysis and modeling with clear indicators as part of the design under Component 2.  Outcome 3.1 seeks to meet the requirement that these PAs are under effective management (for the 3,665,666 ha, including robust Annual Operating Plans prepared as Output 3.1.1 and disaster response through Output 3.1.4) and thus contribute to the 30x30 target. It also seeks to ensure that they deliver environmental and socioeconomic benefits from sustainable resource management, including ecosystem services provided by conservation management and income from productive activities with positive social and private returns grounded in sustainable resource use. These benefits will be achieved through training activities (Output 3.1.2) and implementation of sustainable management initiatives (Output 3.1.3). Through these efforts, 163,200 people will experience socioeconomic and/or environmental benefits (at least 50% female, disaggregated by gender and IP&LCs) in the long term. Although PA management effectiveness is readily measured using CONANP’s i-effectiveness tool (analogous to METT scores), this tool was not designed for ADVCs; under the project, CONANP and FMCN will adapt the i-effectiveness tool to ADVCs.

Indicator 3.1a: % improvement in PA management effectiveness score, as measured by i-effectiveness.

Target 3.1a: For PAs with high rating: Management effectiveness score maintained; For PAs with medium or low rating: Management effectiveness score improved.

Indicator 3.1b: # people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (disaggregated by gender and IP&LCs).

Target 3.1c: 163,293 people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (at least 50% female, desegregated by gender and IP&LCs).

Output 3.1.1: Five-year plans, and associated Annual Operating Plans (POAs), developed for PAs and ADVCs through an inclusive participatory process coordinated by CONANP.

Using inclusive, participatory processes that it has successfully used across Mexico’s PA system, CONANP will engage PA managers, IP&LCs and other important stakeholders, with outcomes of the processes being used to develop Annual Operating Plans for each area. Most Protected Areas in Mexico have an Advisory Council, through which government institutions, civil society, academic and research entities, and representatives of the people who inhabit, work, and use the ecosystems (e.g., ejidos, communities, indigenous groups, and women) can be aware, participate, advise, and support decision-making of the pertinent strategies to address the priority needs of the PAs. The Advisory Councils or similar participatory bodies will be used as platforms to engage stakeholders in developing the Annual Operating Plans (POAs for its Spanish acronym). Priority components for each operating plan will include how the PAs and ADVCs can ensure conservation of their respective areas through adoption of sustainable development practices, and where appropriate, restoration activities that can be implemented to both improve biodiversity and key ecosystem services. The plans will include monitoring indicators, and budget aligning the different public policy instruments that affect the PA, such as its Management Program, CONANP 2040 Strategy, and the National Program for Protected Areas. Plans will also ensure that gender-responsive and inclusive elements are integrated into every aspect of the POA, with particular emphasis on how the plans can benefit women and marginalized members of the focal IP&LCs. Plans will be implemented under Outputs 3.1.2 and 3.1.3.

Indicator 3.1.1: # of gender-responsive and inclusive Annual Operating Plans prepared and implemented.

Target 3.1.1: 1 gender-responsive and inclusive Annual Operating Plan prepared and implemented per PA or ADVC per year of the project (6 total).

Output 3.1.2: Gender-responsive and inclusive training provided to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation and restoration practices.

Using both its prior capacity-building experience with IP&LCs in Mexico’s PA system and the gender-responsive and inclusive components of the Annual Operating Plans, CONANP and partners will carry out training sessions with the IP&LCs in the focal PAs and ADVCs, focusing on how conservation in each respective area can best be achieved by building skills and knowledge in sustainable land use practices and, where appropriate, restoration activities. While some training contents will be common across all the protected area (e.g., regulatory requirements, management principles, etc.), others will be tailored to each context, based on local needs and opportunity assessments conducted with the Advisory Councils or similar participatory bodies. Emphasis will be given to ensuring training sessions are gender-responsive and inclusive, particularly with Indigenous People who use PAs and ADVCs to support their livelihoods. This may include translating to indigenous languages and using inclusive language in all communications, using communication channels and spaces that are relevant to women, and conducting women-only training sessions.

Indicator 3.1.2: # of people trained in sustainable land management, conservation and restoration practices (disaggregated by gender, recording level of Indigenous participation).

Target 3.1.2: At least 100 people per PA or ADVC trained in sustainable land management, conservation and restoration practices (at least 50% women; level of Indigenous participation proportional to Indigenous percentage of local population).

Output 3.1.3: IP&LCs and local organizations implement gender-responsive and inclusive conservation, restoration and sustainable management actions defined in POAs.

Legally constituted local organizations (OLLCs) with the capacity to receive, manage and apply resources will serve as liaisons between the project and PAs to administer the annual plans (POAs) described in Output 3.1.1. The Technical Committee of the Fund for Protected Areas (CTFANP for its Spanish acronym) will select local organizations through a call for proposals process. The call for proposals and selection process will be designed to encourage participation of women, Indigenous Peoples, Afro-descendant populations and other vulnerable groups’ organizations. The local organizations will work with CONANP to define weekly plans based on the POAs, program and disburse funds accordingly, prepare administrative reports and support CONANP with technical reports. Examples of potential activities to include in POA by CONANP staff are:

- Forest cover restoration

- Community reforestation/restoration of riverbanks

- Soil conservation and restoration practices (living fences, stubble, cover crops, organic fertilizing, productive diversification)

- Acquiring equipment for fire prevention, control, and management

- Building capacities in communities for extraction and sustainable use of plants of interest (seed banks, nurseries, cover crops, organic fertilizing, productive diversification)

- Developing sustainable and diversified practices including agroforestry and agrosilvopastoral systems

- Establishing community-led brigades and engaging local communities in monitoring programs

These activities complement other subsidies and incentives managed by CONANP, which will be aligned and co-financed in each intervention area. Each POA typically defines an average of five principal Outputs to be achieved through the types of activities listed above, with indicators and corresponding targets. Examples of indicators used in POAs include:

- Number of people (disaggregated by gender) who adopt better sustainable practices; number of people (disaggregated by gender) who participate in training;

- Number of citizen participation forums strengthened; number of partnerships between key stakeholders for the conservation of natural resources;

- Number of hectares implementing restoration processes; number of hectares under sustainable management activities such as agroforestry or sustainable livestock farming; number of hectares protected and/or maintained as biological corridors;

- Number of monitoring or management actions implemented for protected and endangered species.

Indicator 3.1.3: % of targets reached in POAs, which include gender-responsive and inclusive management actions implemented by IP&LCs and local organizations in PAs and ADVCs.

Target 3.1.3: At least 80% of targets reached in POAs.

Output 3.1.4: Emergency fund expanded to support emergency-response brigades.

One of the most cited successes of the Fund for Protected Areas (FANP) is the Emergency Fund. The project will expand this Emergency Fund to cover the 5 supported PAs and ADVC complex. This is a specific financial mechanism that provides immediate and flexible financial resources in crisis or emergency situations. Much quicker than public resources, but of lesser amount, quickly deployed funds directed to events that threaten protected areas and buffer zones can be instrumental. For example, there have been instances where community brigades are available to fight fires in protected areas, but the necessary equipment is lacking. FANP emergency fund has successfully channeled financial resources to respond to forest fire events, hurricanes and sinking boats damaging coral reefs. During the first half of 2023, this resulted in 21 forest fire events successfully addressed by community brigades in collaboration with CONANP and the National Forestry Commission (CONAFOR). The existing mechanism in FANP will serve this role for the targeted PAs in case of emergencies including fires, floods and other emergencies.

Indicator 3.1.3: % of valid emergency funding requests that result in financial support within 72 hours.

Target 3.1.3: At least 90% of funding requests resulting in delivery of financial support within 72 hours.

Component 4: Knowledge management, monitoring and evaluation for scaling impact.

Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project. Given the central role of the PFP model in closing CONANP’s funding gap, lessons learned from other PFPs that have achieved conservation at scale, such as ARPA in Brazil, will be gathered. This will include FMCN and CONANP engaging groups with PFP experience such as Enduring Earth to seek input on how best to structure the project’s transition fund and secure the necessary financial resources, as well as environmental funds in Brazil, Colombia, Costa Rica, and Peru, which have successfully launched PFPs. Given FMCN and CONANP’s current and prior shared experience with project monitoring and evaluation and knowledge sharing (including with GEF-funded FANP, CONECTA and C6), lessons learned from these experiences will inform the development of MEx30x30 M&E and knowledge management systems, including explicit mechanisms to enable adaptive management and to account for gender and cultural differences at the institutional and PA or ADVC level, and development of culturally appropriate information dissemination mechanisms and communication strategies.

Outcome 4.1: MEx30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up.

The PFP approach has been used successfully in a number of countries to implement long-term financing solutions for conservation outcomes at scale, including for Brazil’s ARPA, the world’s largest protected areas program. Lessons learned from these prior PFP experiences, mainly in Latin America, will help shape MEx30x30; at the same time, MEx30x30’s innovative application of the PFP approach will offer an important contribution to the growing global knowledge base for conservation and long-term financing at scale. MEx30x30 will also generate learning and knowledge relating to community co-management as an effective PA management tool, and cost-effective means for expanding PA networks to achieve the GBF 30x30 target; MEx30x30’s lessons on this theme will be especially valuable given the central role of Indigenous Peoples in the Project. Thus, learning and knowledge exchange under Outcome 4.1 offers a rich contribution to global conservation practice, and will provide the basis for further definition of concrete steps towards Mexico’s own 30x30 target to be capture in a scale-up strategy document. The incorporation of gender and inclusion considerations will be especially important to the outputs and activities under this Outcome, in processes for production and dissemination of materials but also as a thematic focus for the products themselves.

Indicator 4.1: # of scale-up strategy documents based on MEx30x30 experience.

Target 4.1: 1 scale-up strategy document based on MEx30x30 experience.

Output 4.1.1: Ongoing lessons learned from MEx30x30 and other long-term sustainable finance mechanisms and PA scaling experiences documented and disseminated.

The PMU will lead documentation of lessons learned and preparation of knowledge products, and dissemination of these materials. Learning topics of interest include nationally-led long-term sustainable finance mechanisms (such as those led by national protected area authorities and national protected area funds), and the relationship between such mechanisms and local or regional financing efforts. The publication plan will include dedicated products focused on the importance of gender integration and social inclusion in scale-up strategies and financing solutions, and knowledge products relating to management arrangements that facilitate IPLC-led conservation and sustainable resource use. Dissemination channels will include the CAAP as well as FMCN’s participation in networks such as RedLAC.

Indicator 4.1.1: Number of lessons-learned knowledge products prepared and shared (including products with a focus on gender and inclusion).

Target 4.1.1: At least 4 lessons-learned knowledge products prepared and shared (including at least one with a focus on gender and one with a focus on IP&LCs).

Output 4.1.2: National workshop and dissemination event held to finalize scale-up strategy document based on MEx30x30 experience.

A concluding activity of MEx30x30 will be to organize a national event to formally launch the scale-up strategy to achieve Mexico’s 30x30 goal, based on the Project’s learning and experience. To draft this document the PMU will facilitate a collaborative and consultative process led by CONANP and involving input from other government agencies, civil society, academia and the private sector. The lessons learned will be disseminated in a special event in FMCN`s Exchange of knowledge Conservation Week, held every two years with over 400 key stakeholders. The event itself also will solicit representation from the full range of stakeholders implicated in national PA creation and management, with emphasis on ensuring the participation of women and IP&LCs (stakeholder identification and engagement provisions will be detailed further in the Stakeholder Engagement Plan to be elaborated during the initial part of the project implementation phase). Thus, Output 4.1.2 will achieve broad-based recognition and buy-in for Mexico’s 30x30 ambitions, and visibility for the concrete steps to achieve those ambitions. This includes engagement with CBD and in support of Mexico completion of GBF targets as per the country's NBSAP.

Indicator 4.1.2a: # of national workshop and dissemination events held.

Target 4.1.2a: 1 national workshop and dissemination event held.

Indicator 4.1.2b: # of people participating in national workshop and dissemination event (disaggregated by gender, recording level of Indigenous participation).

Target 4.1.2b: 400 people participating in national workshop and dissemination event (at least 50% women, disaggregated by indigenous).

In relation to monitoring and evaluation and given FMCN and CONANP’s current and prior shared experience with project monitoring and evaluation (including with GEF-funded FANP, CONECTA and C6), lessons learned from these experiences will inform the development of MEx30x30 M&E framework, including explicit mechanisms to enable adaptive management and to account for gender and cultural differences at the institutional and PA or ADVC level.

Outcome 4.2: Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management.

Outcome 4.2 entails the preparation and deployment of a robust, gender-responsive and inclusive M&E system for the MEx30x30 project. Timely, high-quality project reporting is critical for adaptive management, and given the scope of MEx30x30, adaptive management will likely be required during implementation. This highlights the importance of both designing appropriate systems and processes and staffing project management with appropriate M&E skills and capacity. Both FMCN and CONANP have considerable experience with successfully developing and implementing rigorous and adaptive monitoring and evaluations systems, including national-level projects such as FANP (which includes monitoring of over 52 million ha of PAs), as well sub-national projects such as CONECTA and C6.  The reporting framework will be designed to meet the M&E needs under the GEF and CI GEF Agency with respect to impact measurement, as well as FMCN’s own institutional monitoring requirements. Moreover, data and assessments from CONANP’s “i-effectiveness” platform will be incorporated into the project’s M&E system. This effectiveness evaluation platform incorporates information under five different themes (context and planning; administrative and financial; governance and participation; stewardship; and benefits provided) to calculate an index of management effectiveness, identifying both areas of strength as well as where improvements can be made (Bezaury-Creel 2024). As the i-effectiveness tool was designed for PAs, a valuable contribution of the Project will be to refine adaptation of the tool to ADVCs under Component 1. Finally, the reporting system also will reflect the need to facilitate sharing of data and information between stakeholders to promote knowledge exchange under Component 4. Key indicators to track progress under the MEx30x30 system include performance ratings in Project Implementation Reports (PIR), the Mid-term Review (MTR) and Terminal Evaluation (TE).

Indicator 4.2: PIR, MTR and TE ratings.

Target 4.2:  PIR, MTR and TE ratings scored as “Satisfactory” to “Highly Satisfactory”.

Output 4.2.1: Clear and robust gender-responsive and inclusive Monitoring and Evaluation framework created and implemented.

The Results Framework (Annex C) is aligned with requirements and institutional metrics prescribed in the FMCN Operational Manual and will be tracked using its Project Tracking System (SISEP). The M&E system will be vital for both project governance and for substantive project delivery and reporting. The system will also serve as an accessible depository for data and information, as well as the products developed using that data and information, while reliably tracking and documenting the evolution and execution of product development processes. These functions combine the needs of project delivery and project oversight and will also generate the material that will inform knowledge-sharing among stakeholders and with other GEF-funded projects. The M&E system will incorporate (among other considerations) specific gender-related indicators, as per the project’s Gender Mainstreaming Plan. FMCN will be the lead party responsible for Output 4.2.1, with dedicated capacity in the project PMU.

Indicator 4.2.1: Number of M&E frameworks in operation.

Target 4.2.1: One M&E framework in operation.

Output 4.2.2: Project Implementation Reports, Mid-term Review, and Terminal Evaluation completed.

A core responsibility of MEx30x30 M&E capacity will be to ensure timely preparation and submission of PIRs. As part of M&E, the GEF Core Indicators will be updated in mid-term and final review and will be made available to the GEF Secretariat along with the project PIR report; the Mid-term Review (MTR) and Terminal Evaluation (TE) will verify the information in these tracking tools. Per GEF Monitoring and Evaluation Policy the project will be subject to an MTR to be commissioned and launched by the Project Lead before the project reaches its mid-point, and to a TE at the end of the project. The MTR and TE will include all parameters recommended by the GEF Evaluation Office and will verify information gathered through the GEF tracking tools, as relevant. Both will be carried out using a participatory approach including consultations with parties that may benefit or be affected by the project, identified in the stakeholder analysis. The Project Steering Committee is the CT-FANP, and will participate in the MTR and oversee a management response to the evaluation recommendations along with an implementation plan. The TE will provide an independent assessment of project performance (in terms of relevance, effectiveness and efficiency), and determine the likelihood of impact and sustainability. Project performance will be assessed against standard evaluation criteria using a six-point rating scheme. It will have two primary purposes: (i) to provide evidence of results to meet accountability requirements, and (ii) to promote learning, feedback, and knowledge sharing. The draft TE report will be sent to project stakeholders for comment. The final TE report will be publicly disclosed.

Indicator 4.2.2: % of required reports submitted to CI GEF Agency on time and determined to be satisfactory.

Target 4.2.2: 100% of required reports.

With these Outcomes and Outputs, the additionality offered by MEx30x30 with respect to Global Environmental Benefits (GEBs) will be to advance the GEBs captured as Objective level indicators:

- Core Indicator 1: Improve management of 3,665,666 ha of terrestrial PAs

- Core Indicator 2: Improve management of 22,241,504 ha of marine PAs

- Core Indicator 6: Absorb and sequester an estimated 5.7 million MtCO2e through improved PA management

- Core Indicator 11: Benefit at least 163,293 people (of which 50% will be women) through training for and implementation of sustainable management activities

A summary of incremental benefits of MEx30x30 that will make these advances on GEBs possible are tabulated below in Table 1.

Table 1: Summary of incremental benefits from the project’s interventions

| Business as Usual (without project) | Incremental Benefits (with project – contributions to baseline) |
| --- | --- |
| CONANP budget shortfall | In the long term, the project will help close the financing gap by providing technical assistance to CONANP to develop new revenue streams (Output 1.1.1, 1.1.2). Identification of the revenue streams to prioritize will take place early in the implementation phase, but examples of likely options for consideration include Payment for Ecosystem Services (PES), user fees, increased federal government budget appropriations, and environmental fees, fines and compensation. By developing these types of additional CONANP revenue, MEx30x30 will help the Government of Mexico discharge its public financing responsibility for the national protected area system. In the short to medium term, while public PA financing expands, MEx30x30 will address the annual financing gap by applying a long-term financial mechanism following a Project Finance for Permanence (PFP) approach, which will include the mobilization of domestic and international funding sources to capitalize a Transition Fund to help cover CONANP’s annual budget shortfall (Output 2.1.1, 2.1.2). |
| Insufficient CONANP capacity to pursue and use a diversity of revenue streams | To ensure that CONANP houses the requisite capacity to develop and utilize new revenue streams, MEx30x30 will include training and capacity-building on conservation finance, administrative and financial requirements for different revenue sources, and optimization of use of available financial resources, not only for CONANP but also for its partners involved in on-the-ground management through the PA Learning Community (Output 1.1.3). This will address not only the needed technical capacities but also the institutional absorptive capacity to make efficient, cost-effective, and impactful use of additional funding. |
| Recently established PAs and ADVCs exist as paper parks | MEx30x30 will generate a direct incremental benefit by making available the funding needed to ensure effective management of 5 PAs and 1 complex of ADVCs (Output 3.1.1). Without the project these areas will be paper parks that remain vulnerable to various forms of pressure on their ecosystems: deforestation and degradation, encroachment, overharvesting of resources, and other unsustainable land use. Combined with training (see below), the GEF funds represent critical additionality that contributes directly to the Global Environmental Benefits sought by the project. |
| IP&LCs in recently established PAs and ADVCs have insufficient capacity for sustainable management | Sustainable management and effective participation by IP&LCs as co-managers of PAs and managers of AVDCs requires a specific knowledge base and skill sets. MEx30x30 will deliver incremental benefits by building capacity through training (Output 3.1.2) and then solidifying training and socioeconomic benefits through IPLC sustainable management projects in each of the focal PAs/ADVCs (Output 3.1.3). |
| Gender inequality in natural resource use and management | MEx30x30 will mainstream gender considerations throughout its activities, with explicit targets for reduced gender inequality. A portion of communications, knowledge management, technical assistance, and capacity-building activities explicitly will be devoted to gender and social inclusion considerations, with specific attention to roles in natural resource management. |

MEx30x30 will have a transformative impact by helping Mexico close the financing gap for the entirety of its protected area system. This not only will make it possible for Mexico to reach its 30x30 goal in terms of the number of hectares designated for conservation, but also will ensure that this area is under effective conservation management. Moreover, effective conservation management is understood to encompass appropriate involvement of IP&LCs in PAs as well as ADVCs, which is critical as the only way that Mexico can achieve its 30x30 target will be to catalyze enormous scale-up in ADVC designation.

A significant innovation of the project will be to deploy a long-term financial mechanism following a PFP approach for the first time led by a national institution (FMCN) rather than international NGOs. The evaluation of PFP initiatives to date commissioned by the Enduring Earth partnership found that the rate at which use of PFPs can expand appears constrained by the technical and human resource bandwidth of champions of the approach such as TNC and WWF. The important precedent that MEx30x30 will set is that the PFP approach does not need to rely heavily on international environmental NGOs, but that domestic conservation actors (notably existing Conservation Trust Funds of sufficient scale and capacity) can lead the implementation of ambitious financing strategies. Global progress toward sustainable financing for PA systems and achieving the GBF 30x30 target may be significantly accelerated as domestic actors in other countries follow this precedent.

Domestically, MEx30x30 will contribute to innovation through enhanced integration of ADVCs into CONANP’s protected area management frameworks and processes, as a key community-lead strategy that directly contributes to 30x30 goals. One example in this regard will be the adaptation of CONANP’s i-effectiveness tool for measuring effectiveness of PA management to make it suitable for measuring effectiveness of ADVC management. The project will facilitate this adaptation effort and pilot the use of the adapted tool in its Chimalapas cluster site. This innovation will address a significant current gap, as provisions for monitoring of management effectiveness in ADVCs remains underdeveloped.

### Institutional Arrangement and Coordination with Ongoing Initiatives and Project.

Implementing and Executing Agencies

Conservation International (CI-GEF) is the GEF Implementing Agency for this project. Overall, the CI-GEF Implementing Agency will be responsible for technical and financial oversight of the project, being accountable to GEF. CI-GEF, ensures the project complies with the GEF’s policies and procedures, including M&E, Gender, stakeholder engagement, and safeguards. CI-GEF Agency will also make recommendations to optimize project performance, support strategic decisions and adaptive management as needed and ensure the resolution of any execution conflicts. Specifically, CI-GEF will undertake the following tasks:

- Facilitate interactions with the GEF Secretariat.

- Provide technical and financial oversight to the Executing Agency.

- Oversee and monitor implementation of the project including reviewing technical and financial project reports, undertaking annual project site visits/desk reviews, and monitoring the implementation of and compliance with safeguards.

- Ensure that project management practices (technical, financial, and administration) comply with GEF requirements.

- Monitor the project’s implementation and achievement of the project outputs.

- Ensure proper use of GEF funds.

- Review and approve any changes in budgets or work plans.

- Quality assurance includes ensuring that audits are undertaken by external auditors.

- Oversee the preparation of the annual project implementation report (PIR) for submission to the GEF Secretariat (GEFSEC).

- Commission the project’s Mid-Term Review and Terminal evaluation.

The Executing Agency (EA) will be the Mexican Fund for the Conservation of Nature (FMCN), which has implemented three successful projects (FANP 1, FANP 2 and Conservation of Coastal Watersheds in the Context of Climate Change Project), has one project under implementation (CONECTA) and has one project in the pipeline corresponding to the GEF-8 allocation (ORIGEN). In total FMCN has received more than US$70 million from the GEF. The EA will guide and lead the day-to-day execution, administration, and monitoring of the project; be responsible for financial management of the project; and facilitate knowledge sharing and information flow. FMCN will host the PMU and ensure coordination with key stakeholders including CONANP as the government counterpart and partner of this project.

The EA (through the PMU) will report technically and financially to CI-GEF by preparing and submitting the annual budget and work plan, quarterly financial and technical progress reports, the annual Project Implementation Report (PIR), an annual project and program-level progress report and the Final project and program Project Report. Specific tasks of the EA include:

- With guidance from CI-GEF, the EA will be responsible for the day-to-day project management and overall coordination of the MEx30x30 project.

- The EA will be responsible for ensuring that key entities such as executing teams, delivery partners, external-sub-grantees, and service providers deliver efficiently and effectively in line with project outputs/outcomes and in contribution to the targets.

- The EA will be responsible for Monitoring & Evaluation, including verification that gender, stakeholder engagement, and safeguards requirements are met.

- The EA will support the mobilization of co-financing and report its materialization to CI-GEF.

- The EA will ensure timely financial and technical progress reporting to CI-GEF.

- The EA will participate in the MTR and TE processes leading the coordination at a national level with the external consultants.

- The EA will lead the organization and participate in the supervision visits conducted annually by CI-GEF.

- Host the PMU including the provision of technical input across components and guidance on operations.

- Guide preparation of Terms of Reference and manage consultants' contracts to ensure delivery of outputs.

- Maintain records of all project-related documentation

- Guide the preparation and dissemination of knowledge management products.

- Ensure financial auditing of the project.

- The Project Management Unit (PMU)

The EA will recruit and host a team of specialists that will comprise the PMU; this team will be distributed among FMCN functional units (see PMU composition below, and distribution of positions among Components in Figure 5). With guidance from the EA, the PMU will be responsible for overall project management, supervising consultants, ensuring project success, and EA reporting to the CI-GEF Agency. The PMU Lead will report to the EA.

Overall, the PMU will be responsible of day-to-day project activities and monitor progress, and coordinate and support external sub-grantees and service providers as needed to ensure efficient and effective delivery of the project’s target results. As needed, consultants will be hired to provide technical assistance for specific tasks requiring expertise that cannot be undertaken by the PMU and executing partners. The composition of the Project Management Unit (PMU) is listed below, by position title and FMCN unit housing the position:

- Project Lead (FMCN Conservation Unit, part-time)

- Conservation Technical Officer (FMCN Conservation Unit, full-time)

- Follow-up Officer (FMCN Finance Unit, full-time)

- Institutional Strengthening Coordinator (FMCN Conservation Unit, supporting CONANP full-time)

- Funding Mobilization Coordinator (FMCN Research and Development unit, part-time)

- Safeguards and Monitoring and Evaluation (M&E) Coordinator (FMCN Research and Development unit, part-time)

- Communications Specialist (FMCN Research and Development unit, part-time)

Generally, the PMU will be responsible for:

- Financial management, including procurement and record-keeping

- Reporting and disbursements (financial)

- Project and program monitoring and reporting (technical)

- Preparation and submission of all technical and financial reports to the CI-GEF Agency

- Monitoring and reporting materialization of co-financing to CI-GEF

- Actively coordinate the flow of inputs, procurement, outputs, and work streams to ensure the project runs smoothly and delivers the specified outputs and overall objectives, including those of CIGEF when needed.

- Organizing and facilitating workshops and travel, including supervision visits and evaluations.

- Identification of potential risks to project activities and implementation of mitigation measures to overcome them.

- Knowledge Management.

- Setting up, monitoring, and reporting implementation progress of environmental and social safeguards.

- Ensure the smooth running of the project through continuous monitoring, coordination, and communication among partners, consultants, stakeholders, etc.

Project Steering Committee

MEx30x30 will build on FANP institutional arrangements, which have been recognized as best practice by GEF project completion reports. The Project Steering Committee (PSC) will be the FANP Technical Committee (CTFANP) that was established in 1997 and will have its 92nd meeting in April 2024. According to its by-laws, CTFANP is composed of nine members selected by the National Council of Protected Areas (CONAP) and ratified by the FMCN Board, representing the social, private, public and academic sectors. CTFANP is part of FMCN´s legal structure, reporting to both the FMCN Board and CONAP.

- By law CONAP is an advisory body on PAs to the Environmental Ministry. It has 30 members that come from the public, private, social and academic sectors and has held 62 meetings since it was first established in 1996. CONAP is currently renewing its membership to achieve gender balance.

- The FMCN Board is composed of seven members (four women and three men) that report to a 25-member Assembly composed of private, public and social sectors (11 women and 14 men).

CTFANP responsibilities include the allocation of funds per PA; the review of annual operating plans and their reports; and the selection of organizations that administer annual operating plans for PAs, as well as consultants. It also addresses challenges and opportunities that arise in the supported PAs, and it authorizes requests for emergency funds in response to fires, hurricanes, as well as damages to coral reefs. The connection of CTFANP to CONAP allows for coordination with other initiatives that take place in PAs throughout Mexico. Through FMCN, CTFANP interacts with initiatives overseen by FMCN´s four additional technical Committees, which include projects in marine conservation, regenerative ranching, development of community enterprises, watershed management and sustainable cities. During the first meeting after MEx30x30 approval, FMCN will propose the CTFANP to include the Ministry of Finance (SHCP) and the Ministry of Environment’s International Affairs Coordinating Unit (SEMARNAT- UCAI) as observers.  Also, during the next phase FMCN will discuss with CONAP and FMCN board the potential to integrate CI-GEF as an observer in specific sections of CTFANP that address MEX30x30. Specifically, CTFANP will review and approve the Annual Work Plans and Budget as well as the M&E plan for the project. Additionally, the CTFANP is required to authorize any substantive deviation from the agreed Annual Work Plan (AWP) and budget lines to be included in budget revisions submitted to CI-GEF. Specific roles and responsibilities of the CTFANP include:

- Foster adaptive management.

- Ensure that project objectives are fulfilled in an effective and efficient manner.

- Ensure institutional coordination and facilitate an effective communication and decision-making process between the EA, CONANP and CI-GEF.

- Monitor project implementation to ensure consistency with the approved work plans and results framework of the project.

Detailed Institutional Arrangements

In 1997 the first GEF project in Mexico created the Fund for Protected Areas (FANP) in FMCN. FANP is the result of a public-private partnership between CONANP and FMCN established through collaboration agreements that have been renewed through five federal administrations in 26 years. FANP started channeling the annual interest of US$16.48 million in 1998 to ten protected areas (PAs). Today its capital has reached US$165 million, which supports 55 PAs. Non-endowment funds support an additional 15 PAs. In total, in 2024 FMCN will be channeling a projected US$10 million to these 70 PAs under the management of CONANP. In this way, FANP acts as an umbrella mechanism inside FMCN, with several different accounts for different projects.

By statute, CONANP cannot receive funds directly; therefore, after signing a grant agreement with CI-GEF, FMCN will manage GEF funding for execution of project activities led by CONANP. FMCN is recognized for its administrative capacities and conducts all procurement for FANP. The FMCN Operational Manual, which reflects lessons learned in 26 years, describes its procurement procedures, project cycle, reporting and oversight. In MEx30x30 CTFANP will review and approve the annual operating plans for components 1 and 2, which will focus on increasing the fiscal budget for CONANP and raising funds from additional public, philanthropic and private sources while the financial gap is closed by CONANP. For component 1 a project coordinator hired with project funds within FMCN´s Conservation Area will develop annual plans and ensure that the required consultancies and workshops taking place according to procedures. For component 2 FMCN will strengthen its Research and Institutional Development (R&D) Area with one coordinator and one communication specialist (both part-time, FMCN will provide funds to cover these positions fully) to raise a transition fund that covers the financial gap while public funds increase and the PFP process is ready. The coordinator will provide reports on advances to CTFANP. Annual interest from the endowment will be channeled to each PA or ADVC according to the distribution agreed by CTFANP. FMCN will hire a technical analyst in its Conservation Area and an administrative analyst in its Finance Area to support CONANP in the development of Annual Operating Plans (POAs), and a safeguards and monitoring and evaluation specialist (part-time) will support overall project monitoring and implementation of safeguards tools and plans. POAs will be derived from five-year plans developed by CONANP with the support from project staff. CTFANP will select local organizations to administer the POAs per PA. Local organizations work with CONANP to break POAs into weekly plans, proceed to spend funds accordingly, prepare administrative reports and support CONANP with technical reports. MEx30x30 reports will be coordinated by FMCN´s Conservation Area.

In terms of the endowment funds in component 3, FMCN will be responsible for the financial management building on its 30-year experience. FMCN has an Investment Committee composed of seven finance specialists who oversee asset investment according to the Investment and Spending Policy included in FMCN´s Risk Control Manual. They rely on an independent financial advisor who presents investment options according to the requirements of each project and a long-term vision. The Finance Area at FMCN ensures that the decisions made by the Investment Committee are executed. The independent financial advisor provides the instructions to the custodian for the purchase and sale of instruments. The selection of both the custodian and independent financial advisor is reviewed every five years. FMCN closed 2023 with a 17.63% annual return and an endowment of US$192.5 million. In the last twenty years FMCN´s endowment has had an average annual return of 5.63% in US$ and is invested almost fully in financial instruments with an overall A rating grade for ESG standards (MSCI classification).

FMCN undergoes internal and external audits. The Institutional Accompaniment Committee (CAI) oversees risks and internal audit reports. The internal auditor reports to this Committee and also has direct access to FMCN´s Board as she is the contact for any disputes or serious complaints that require analysis and response. External auditors report to the President of the CAI, the Commissioner and the General Director. The Commissioner, as the Oversight Body of FMCN, attends all Board meetings and informs the Assembly at its meeting every June on its opinion based on the review of the report of the external auditors. FMCN held its 120th Board meeting in March 2024.

Figure 4: Flows of Funds

Figure 5: Institutional Arrangements

Note: FMCN will propose the CTFANP to include the Ministry of Finance (SHCP) and the Ministry of Environment’s International Affairs Coordinating Unit (SEMARNAT- UCAI) as observers.  Also, during the next phase FMCN will discuss with CONAP and FMCN board the potential to integrate CI-GEF as an observer in specific sections of CTFANP that address MEX30x30.

Figure 6: FMCN organizational structures involved in MEx30x30.

Will the GEF Agency play an execution role on this project?

Yes           No

If so, please describe that role here and the justification.

### Core Indicators

| Project Core Indicators |  | Expected at CEO Endorsement |
| --- | --- | --- |
| 1 | Terrestrial protected areas created or under improved management (hectare) | 3,665,666 |
| 2 | Marine protected areas created or under improved management (hectare) | 22,241,504 |
| 3 | Area of land and ecosystems under restoration (hectare) |  |
| 4 | Area of landscapes under improved practices (hectare) |  |
| 5 | Area of marine habitat under improved practices (hectare) |  |
| 6 | Greenhouse Gas Emissions Mitigated (metric ton of CO2e) | 5.7M |
| 7 | Shared water ecosystems under new or improved cooperative management (count) |  |
| 8 | Globally over-exploited marine fisheries moved to more sustainable levels (metric ton) |  |
| 9 | Chemicals of global concern and their waste reduced (metric ton of toxic chemicals reduced) |  |
| 10 | Persistent organic pollutants to air reduced (gram of toxic equivalent gTEQ) |  |
| 11 | People benefiting from GEF-financed investments disaggregated by sex (count) | 163,293 |

Core Indicator 1: The target for terrestrial protected areas under improved management effectiveness is the total area (per official government geospatial data) of the 4 terrestrial PAs (Balam-Kú, Riego043, Papigochic, Tecuani) and and the ADVC complex (Chimalapas) in which the project will work to apply funding solutions, enhance management capacity, and implement sustainable management initiatives with IP&LCs.

Core Indicator 2: The target for protected areas under improved management effectiveness is the total area (per official government geospatial data) of the marine protected area (Bajos del Norte) in which the project will work to apply funding solutions, enhance management capacity, and implement sustainable management initiatives with IP&LCs, and three other marine protected areas (Caribe Mexicano, Revillagigedo, Islas del Golfo) that will participate in the project’s capacity-building processes.

Core Indicator 6: Mitigated emissions.  We used the following assumptions:

- Data from Hansen (2013) was obtained, which provides information on forest change patterns worldwide. Using this tool, deforestation was estimated for the period 2012 to 2022 in each of the selected ANP and ADVC for this analysis.

- Land use and vegetation were estimated for each polygon based on the Comprehensive Monitoring System for Biodiversity and Degradation in Protected Natural Areas PNUD (2018).

- The scenario for land use and vegetation was calculated for 20 years was estimated for each of the ANP. To make this estimate, the set of models from the Integrated Valuation of Ecosystem Services and Tradeoffs (InVEST) software was used, based on the average observed deforestation rate.

- On the other hand, using the ex-ante carbon balance tool (EX-ACT) from the Food and Agriculture Organization of the United Nations (FAO), an estimate of the carbon reservoirs generated by each of the ecosystems present in the selected ANP was obtained.

- In the case of conservation:

  - It was assumed that the expected deforestation would convert forests and rainforest to agriculture in the absence of the project.

  - It was assumed that support for protected areas in Mexico can protect up to 23% of the trend deforestation, derived from the GEF impact evaluation study for protected areas in Mexico (Hansen et al., 2015).

Core Indicator 11: The target number of beneficiaries is the number of people resident within the PAs and ADVCs where MEx30x30 will be supported under Component 3, as documented by CONANP and the national population census.

### Explanation of Financial Structure (Only for blended finance projects under GBFF Action Area 4)

Not Applicable.

### Risks to Project Implementation

| RISK CATEGORIES | RATINGS | ASSESSMENT AND MITIGATION MEASURES |
| --- | --- | --- |
| CONTEXT |  |  |
| Climate | Low | Assessment: Mexico is vulnerable to the impacts from climate change. Climate change-related risks include failure to adequately determine the extent to which and to what degree priority areas for conservation, protected area boundaries and sustainable livelihoods will be impacted by climate change over various timeframes, thereby undermining the ability to fully achieve environmental and socioeconomic objectives over the long term. Climate change impacts and their variability can manifest in many different forms and could occur more quickly or slowly than currently projected. Impacts from climate change could alter priority areas for conservation, make existing protected area boundaries less effective, and increase threats to the country’s most important ecosystems and biodiversity. Adaptive measures implemented by the project, particularly with regards to the capacity to accurately foresee likely impacts on priority areas for conservation, could also be inadequate. Mitigation Measures: The Government of Mexico and CONANP have taken a number of measures and developed specific strategies to ensure projections from the likely impacts of climate change are understood and incorporated into planning, decision-making and management components of the country’s protected natural area system. For example, from 2013-2021, CONANP, CONAFOR and CONABIO implemented the GEF-UNDP funded “RESILENCIA” project, which allowed for the country’s protected area system to be spatially configured and managed to improve resilience of the system given the likely projected impacts from climate change on key ecosystems and biodiversity. The RESILENCIA project was implemented in 17 terrestrial, coastal and marine protected natural areas covering 7.8 million ha in 12 eco-regions. Lessons learned from the project have enabled for increased institutional capacity and more effective management system for protected natural areas facing impacts from climate change. |
| Environment and Social | Moderate | Assessment: It is not expected that the project could bring adverse environmental and/or social impacts. There may be some unintended outcomes from project activities that do not fully account for the environmental and socioeconomic contexts involved with protected natural area and ADVC management and restoration, notably when IP&LCs and other vulnerable communities are involved. Effective planning and management of protected natural areas and restoration of degraded areas includes outreach, engagement and collaboration with local communities, many of which are heavily dependent on natural resources and often rely on complex and/or unresolved land tenure arrangements. This is particularly true with IP&LCs, notably ones with ancestral territorial claims. Inappropriate restoration strategies, such as the use of non-native species that could displace biologically and/or economically important flora and fauna, could also create both environmental and social risks. Failure to adequately address these risks could lead to conflicts among and within communities over a wide spectrum of land use issues, undermining both the environmental and socioeconomic objectives of the program. Mitigation Measures: To mitigate environmental and social risks from the project’s protected natural area and restoration activities, the project will draw heavily on the considerable prior and current experience within both CONANP and FMCN to successfully design and implement projects that comprehensively address environmental issues while simultaneously safeguarding and enhancing socioeconomic wellbeing of project participants. Specific environmental and social risks associated with IP&LCs will be addressed and mitigated through both FMCN and CONANP’s previously used and successful model of partnerships with these stakeholders. Both CONANP and FMCN have robust policies and procedures to assess and mitigate environmental and social risks. Safeguard screening for the project has also considered principal environmental and social risks and will be used to inform development of relevant safeguard plans for all identified issues, notably those focused on gender, stakeholder consultation processes and indigenous peoples. CONANP capacities on gender, social and environmental safeguards will be further strengthened under component 1. |
| Political and Governance | Moderate | Assessment: The project faces political and governance risks that could undermine fully achieving its proposed outcomes. Many of Mexico’s protected areas, ADVCs and IP&LC territories are in rural, high poverty areas, heavily dependent on natural resource use and often under unsustainable practices that maximize shorter-term gains. Protected natural area management and restoration priorities run the risk of colliding with shorter-term priorities, both with communities as well as municipal and/or state leaders. The issue of territorial claims from IP&LCs can also create political and governance risks, particularly if there are unresolved legal aspects to the claims. Several of the project areas are also characterized by security concerns, posing a risk to both communities and any personnel involved in the project development and management process. The reason why the risk is moderate is because National elections will also take place in 2024, creating the potential risk of changes in key personnel with government agencies supporting Mexico’s protected natural areas system project and/or changing policies and priorities of a new government, notably with regards to fulfilling funding commitments for conservation and restoration-related initiatives. Mitigation Measures: To mitigate these risks, the project has aligned its outcomes and governance structure with government policies and priorities, notably those of CONANP and its strategies and frameworks for managing the country’s protected area’s system as well as the larger MEx30x30 national commitment to achieve effective management of 30% of Mexico’s important areas for biodiversity by 2030. This commitment is enshrined in Mexico’s National Biodiversity Strategies and Action Plan, ENBioMex, thereby creating a strong mechanism to help guarantee continuity with future administrations. Furthermore, CONANP and FMCN have worked together successfully for well over two decades with five federal administrations, regions, and IP&LCs, building close, collaborative links to advance Mexico’s biodiversity-and sustainable development-related goals. The project will use this long collaboration, its joint partnership in the Protected Areas Fund (FANP) and project governance structure to mitigate political risks and ensure continuity and successful completion of its objectives. |
| INNOVATION |  |  |
| Institutional and Policy | Low | Assessment: Mexico is an OECD country with strong political and economic institutions, and ambitious international commitments to safeguard its globally important biodiversity. However, the country continues to face significant socio-economic challenges with high levels of poverty, socioeconomic marginalization and heavy dependence on natural resources to sustain livelihoods, particularly in rural areas and IP&LCs. These challenges create considerable risks to Mexico’s policies related to conservation and restoration, and by extension, to the goals of the project. Specifically, strategies and policies could change to focus more on socio-economic development over conservation, notably through measures that maximize short-term growth and unsustainably use natural resources. Mitigation Measures: To mitigate institutional and policy risks, the project will align outcomes and activities closely with Mexico’s national-level strategies, priorities and policies, notably Mexico’s National Biodiversity Strategies and Action Plan, ENBioMex, and its MEx30x30 commitment. At the project design and implementation level, FMCN will coordinate all activities with CONANP and relevant government agencies, using its 26-year successful track record with FANP and multiple projects to ensure outcomes align with and strengthen national policies. In particular, CONAP’s role as the leading federal agency in the project will ensure continued alignment and complementarity with Mexico’s environmental and socio-economic strategies and politics. |
| Technological | < Select rating > | Does not apply |
| Financial and Business Model | Moderate | Assessment: The MEx30x30’s model focuses launching a long-term financial mechanism following a Project Finance for Permanence (PFP) approach that includes a transition fund to cover CONANP’s funding gap with other donor revenues until public revenues increase to cover costs needed to reach Mexico’s 30x30 goals. Primary risks include: 1) Financial assumptions and projections that form the basis of the PFP and CONANP’s funding gap are incorrect, resulting in larger than anticipated gaps and operational shortfalls in protected area management; 2) FMCN is unable to secure the necessary funds from other donors to cover CONANP’s funding gap, thereby undermining CONANP’s ability to increase the necessary capacity to reach project and 30x30 goals, and/or; 3) anticipated federal funds to support CONANP’s expanded protected areas network and requisite capacity for effective management are not allocated as planned. Mitigation Measures: To mitigate the project's financial model risks, both FMCN and CONANP will draw on their long, successful history of securing funding sources and developing effective finance mechanisms for Mexico’s natural protected area system. Specifically, the CONANP-FMCN partnership with the FANP has been in place for over a quarter of a century, raising over $165 million from 25 donors from various sectors and supporting effective management for 70 protected areas. Individually, FMCN has nearly three decades of fundraising and financial mechanisms development experience, securing funding and creating effective mechanisms for over $200 million in endowment and sinking funds, including the establishment of regional funds. FMCN has demonstrated a continued ability to secure funding from a broad range of sectors, helping to mitigate any potential financial shortfall risks with the project. As a member of the Latin American Environmental Funds network (RedLAC), FMCN is recognized for its best practices and efficient fundraising and sound financial mechanism development. RedLAC provides a network platform for Conservation Trust Funds (CTFs), who many have successfully mobilized financing for PFPs. FMCN also holds membership in Mexico Conservation Founders (MCF) and Ensamble -the two networks of philanthropies in Mexico, thereby deepening its ability to secure diverse funding sources. To mitigate financial risks from its end, CONANP will draw on its experiences and expertise in maintaining strong support from multiple successive administrations to conserve Mexico’s most important biodiversity and achieve international conservation commitment goals like 30x30. Moreover, CONANP will access its deep expertise in developing a diverse range of successful funding streams for Mexico’s protected area system including federal-level appropriations, entrance and use fees, payments for ecosystem services and other related compensatory measures. |
| EXECUTION |  |  |
| Capacity for Implementation | Low | Assessment: While Mexico has strong project management and institutional capacity, given the project’s objectives of closing the funding gap, increasing CONANP’s institutional capacity and improving management of natural protected areas and ADCVs, there are a number of risks for this project. Key risks include: 1) not securing adequate funding to fill the funding gap and successfully launch the PFP, leading to lower than needed levels of capacity and failure to achieve the expansion of CONAP’s ability to meet MEx30x30 goals; 2) failure to effectively use secured funding to adequately and sustainably improve protected area and ADVC management, and; 3) project restoration efforts lack the capacity and resources necessary to ensure effective implementation and long-term sustainability of restored areas. Mitigation Measures: Both CONANP and FMCN have individually and through their 26-year partnership with FANP demonstrated high levels of institutional capacity and over multiple projects, the ability to successfully build additional capacity and ensure sustainability of project outcomes. CONANP oversees a system of 226 protected areas, consistently demonstrating its ability to increase protected area coverage while simultaneously increasing both institutional and site-level management capacity. Likewise, FMCN has built considerable institutional capacity and is a recognized leader in securing resources and developing financial mechanisms (trust, sinking funds) to help secure sustainable outcomes. Jointly, they both have successfully administered the FANP since 1997, supporting 70 federal protected areas 36.6 million ha, which corresponds to 39% of the protected territory (13% terrestrial and 26% marine). To mitigate institutional capacity risks for this project, the following measures will take place during implementation: 1) Close coordination between CONANP and FMCN to identify current and potential capacity gaps at the institutional and site-level and ensure project design includes capacity-building measures, with adequate resources allocated in the budget; 2) Through the project monitoring and evaluation system, identifying capacity gaps that arise during implementation and making adaptive management corrections as needed, and; 3) Working closely with key stakeholders, including the Government of Mexico and the donor community, to both secure the funding needed to launch the PFP and fill the funding gap, as well as ensure federal appropriations are sufficient to reach the long-term budget goals. |
| Fiduciary | Low | Assessment: Failure to conduct adequate financial management and procurement presents several risks to the project, including misuse or misallocation of funds. As securing additional funds to launch a PFP, fill a funding gap and build additional CONANP capacity are key project objectives, there are multiple levels at which improper financial management can create risks to effective implementation. Mitigation Measures: To mitigate fiduciary risks, both CONANP and FMCN will use the financial management system, which includes policies and procedures that they have developed and successfully used in other GEF-funded projects, including CONECTA and C6, as well as in its effective management of FANP since 1997. These system include detailed operational manuals with policies and procedures for all aspects of project financial management, including procurement, oversight and reporting. Regular reporting to GEF will include detailed financial reports in line with agency reporting requirements, thereby allowing for any discrepancies to be identified and remedied. Internal and external audits are conducted as part of all FMCN projects. |
| Stakeholder | Low | Assessment: Project success depends on effective stakeholder engagement and commitment to achieving institutional- and site-level objectives. Ineffective or incomplete engagement processes could result in a full or partial failure to implement project activities. Specific stakeholder engagement risks for the project include: unintended exclusion of key stakeholders at the federal level, protected area stakeholders and/or IPLC level; failure to develop an inclusive and culturally appropriate engagement strategies, notably with IP&LCs, women and other vulnerable populations in project areas; and inadequate and/or inappropriate knowledge-sharing and communication of project objectives and progress to key stakeholders. Mitigation Measures: Both CONANP and FMCN have extensive, recognized experience and expertise with stakeholder engagement and facilitating multi-stakeholder processes, so their collective experience and guidelines will be utilized to mitigate stakeholder engagement risk. Specifically, to mitigate stakeholder engagement risk, the project will: 1) Apply lessons learned from prior CONANP, FMCN and similar projects for effective stakeholder engagement, including those supported by GEF; 2) Ensure all project activities comply with GEF environmental and social safeguards, including gender mainstreaming, stakeholder engagement, indigenous peoples and development of grievance accountability and redress mechanisms; 3) Fully utilize the project’s governance structure to conduct outreach with key stakeholders from the national to local level, and; 4) Develop culturally appropriate communication and knowledge sharing strategies and mechanisms to ensure key stakeholder groups understand project objectives and progress, can access necessary information, and can effectively address grievances. |
| Other | < Select rating > | < Insert text > |
| Overall Risk Rating | Low | Mexico has strong project management and institutional capacity, given the project’s objectives of closing the funding gap, increasing CONANP’s institutional capacity and improving management of natural protected areas and ADCVs. CONANP and FMCN have individually and through their 26-year partnership with FANP demonstrated high levels of institutional capacity and over multiple projects, the ability to successfully build additional capacity and ensure sustainability of project outcomes and stakeholder engagement. FMCN has robust fiduciary and monitoring systems |

## Alignment with Programming strategies and country/regional priorities

MEx30x30 will directly contribute to the Kunming-Montreal Global Biodiversity Framework (GBF) by advancing Goals A, B and D (relating to conservation, sustainable use and adequate implementation, respectively), and several GBF targets, as summarized in the table below.

| GBFF Action Areas | KMGBF Targets | MEx30x30 Components |
| --- | --- | --- |
| Action Area One: Biodiversity conservation, restoration, land/sea-use and spatial planning | Targets 1 (spatial planning), 2 (restoration), and 3 (biodiversity conservation, including 30x30 for PAs-OECMs) | Component 3 will support conservation and restoration actions in PAs and ADVCs, defined in Annual Operating Plans and implemented jointly with IP&LCs. |
| Action Area Two: Support to IP&LC stewardship and governance of lands, territories, and waters | Targets 1 (spatial planning), 2 (restoration), 3 (biodiversity conservation, including 30x30 for PAs-OECMs), and 22 (IP&LCs) | Component 3 will focus on enabling IP&LCs to undertake sustainable management in PAs and AVDCs, with training and support for implementation of sustainable management activities. Component 1 will strengthen governance capacity of IP&LCs through training provided through learning exchanges. |
| Action Area Four: Resource mobilization | Targets 18 (incentives) and 19 (financing) | In Component 1 CONANP will develop and deploy new revenue streams to address the PA system budget shortfall. Component 2 will design and launch a Project Finance for Permanence initiative to address the PA financing gap while CONANP develops revenue streams. |
|  | Target 23 (gender) | Gender-responsiveness and social inclusion are integrated throughout the design of MEx30x30. |

Mexico's National Biodiversity Strategy (ENBioMex) and 2016-2030 Action Plan seek to increase efforts that positively impact biodiversity and reduce the direct causes of its loss. ENBioMex is a public policy instrument that aims to achieve, by 2030: the continuous provision of ecosystem services for the development of life and well-being; the fair and equitable distribution of benefits derived from biodiversity; a joint commitment of government and society to the conservation and sustainable use of biodiversity; and the maintenance of biodiversity and ecosystem functionality. The design of MEx30x30 is closely aligned with these instruments, particularly the strategic axes pertaining to Knowledge, Conservation and restoration, Attention to pressure factors, and Mainstreaming and governance, and the action areas relating to conservation and sustainable use of biodiversity, and the action areas: 1.1 Generation, documentation and systematization of knowledge, 1.2 Traditional knowledge, 1.4 Development of tools for access to information, 2.1 In situ conservation, 2.3 Restoration of degraded ecosystems, 4.2 Prevention, regulation and control to avoid over-exploitation of species, 4.3 Prevention, control and eradication of invasive species, 4.6 Reduction of biodiversity vulnerability to climate change, 4.7 Land use planning and sustainable urban development, 6.1 Harmonization and integration of the legal framework, 6.2 Consolidation of the institutional framework and public policies for integration and mainstreaming, and 6.3 Social participation for biodiversity governance. See Annex K for a mapping of MEx30x30 components to key elements of ENBIOMEX.

The MEx30x30 components build on over two decades of investment and lessons learned from prior and current GEF investments, including the FNAP, CONECTA and C6 projects. MEx30x30 also aligns closely with GEF’s Mesoamerica IP through its reinforcement of Mexico’s protected area network, mobilization of new financial resources, and knowledge sharing and capacity building.

- Policy requirements

### Gender Equality and Women’s Empowerment:

We confirm that gender dimensions relevant to the project have been addressed during Project Preparation as per GEF Policy and are clearly articulated in the Project Description (Section B).

Yes        No (If –and only if— NO is selected, a pop-up field should open for the Agency to provide an explanation)

1)Does the project expect to include any gender-responsive-measures to address gender gaps or promote gender equality and women’s empowerment?

Yes        No

If the project expects to include any gender-responsive measures to address gender gaps or promote gender equality and women empowerment, please indicate in which results area(s) the project is expected to contribute to gender equality:

closing gender gaps in access to and control over natural resources;

improving women’s participation and decision-making; and/or

generating socio-economic benefits or services for women.

2)Does the project’s results framework or logical framework include gender-sensitive indicators?

Yes        No  tbd

### Stakeholder Engagement

We confirm that key stakeholders were consulted during Project Preparation as required per GEF policy, their relevant roles to project outcomes have been clearly articulated in the Project Description (Section B), and a Stakeholder Engagement Plan has been developed before CEO endorsement.

Yes   No

(If –and only if— NO is selected, a pop-up field should open for the Agency to provide an explanation)

Select what role civil society will play in the project:

Consulted only;  Yes   No

Member of Advisory Body; Contractor;  Yes   No

Co-financier;  Yes   No

Member of project steering committee or equivalent decision-making body;  Yes   No

Executor or co-executor;  Yes   No

Other (Please explain)  Yes   No

IP&LCs

| Amount ($) of GBFF project financing to support actions by IP&LCs* | PPG request stage | CEO endorsement stage |
| --- | --- | --- |
|  | 12,051,639 | 12,146,999 |

The success of MEx30x30’s goal of creating or improving the management of over 28 million ha of protected areas and ADVCs (22.2 million ha of marine and 3.6 million ha of terrestrial) will depend in large part on IP&LCs having the requisite skills and knowledge to not only successfully manage these areas, but to also receive tangible, sustainable socioeconomic benefits. To ensure effective management that delivers sustainable benefits for IP&LCs, MEx30x30 will allocate over US$12 million for Component 3 (Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories), matched with an additional US$14.1 million in co-financing. Component 3’s allocation will: 1) engage IP&LCs and other stakeholders in an inclusive participatory process to develop Annual Operating Plans for the project’s focal PAs and ADVCs; 2) provide training and capacity-building to IP&LCs in sustainable land management, conservation and restoration practices; and 3) support IP&LCs and local organizations to implement the Annual Operating Plans . To ensure the sustainability of PA and ADVC management and restoration, a funding mechanism will also be established to provide long-term support to emergency-response brigades with IPLC team members in and around the focal PAs and ADVCs. These brigades will allow for rapid responses to natural disasters such as forest fires, landslides and floods, which if unchecked, could undermine the long-term sustainability of PA/ADVC management and restoration efforts.  From this US$12.05M, over $5.8 M will support directly GBFF Action Area 2.

Development of Annual Operating Plans, training and implementation will all be undertaken through a robust gender-responsive and inclusive approach, carefully considering the needs of women and marginalized members of IP&LCs. Given the large-scale nature of the focal PAs and ADVCs (over 28 million combined hectares in six different regions across Mexico, including Indigenous areas) and target beneficiaries (over 163,000, half of which will be women), Component 3 will require a substantial investment by GEF and CONANP in community engagement, capacity-building, knowledge sharing and oversight.

Are IP&LCs to receive and manage resources for the execution of project components/activities?

Yes   No

Are IP&LCs leading the design and management of some project activities but do not manage financial resources?

Yes   No

Does the project provide in-kind support to actions by IP&LCs for biodiversity?

Yes   No

Are IP&LCs part of the project steering committee or equivalent decision-making body?

Yes   No

### Private Sector

Will there be private sector engagement in the project?

Yes           No

And if so, has its role been described and justified in section C “project description”?

Yes           No

### Environmental and Social Safeguards

We confirm that we have provided information regarding Environmental and Social risks associated with the proposed project or program, including risk screenings/ assessments and, if applicable, management plans or other measures to address identified risks and impacts (this information should be presented in Annex E).

Yes    No (If –and only if— NO is selected, a pop-up field should open for the Agency to provide an explanation)

Overall Project/Program Risk Classification:

## Other requirements

### Knowledge management*

We confirm that an approach to Knowledge Management and Learning has been clearly described during Project Preparation in the Project Description and that these activities have been budgeted and an anticipated timeline for delivery of relevant outputs has been provided.

Yes

### Socio-economic Benefits

We confirm that the project design has considered socio-economic benefits to be delivered by the project, these have been clearly described in the Project Description, and they will be monitored and reported on during project implementation (at MTR and TER).

Yes

# Annex a: FINANCING TABLES

### Total GEF Financing Table

Resources Requested by Agency(ies), Country(ies), Focal Area and the Programming of Funds. All GEF sources of funds should be included here.

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Grant | Agency Fee | Total GEF Financing |
| CI | GBFF | Mexico | Biodiversity | Action Area 1 (Conservation) | 9,169,862 | 825,288 | 9,995,150 |
| CI | GBFF | Mexico | Biodiversity | Action Area 2 (IP&LCs) | 5,835,367 | 525,183 | 6,360,550 |
| CI | GBFF | Mexico | Biodiversity | Action Area 4 (Resource mobilization) | 1,667,248 | 150,052 | 1,817,300 |
| Total GEF Resources |  |  |  |  | 16,672,477 | 1,500,523 | 18,173,000 |

### Project Preparation Grant (PPG)

Was a Project Preparation Grant requested?      Yes           No

If yes: fill in PPG table (incl. PPG fee)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | PPG | Agency Fee | Total PPG Funding |
| CI |  | GBFF | Mexico | Biodiversity | Action Area 1 (Conservation) | 135,000 | 12,150 | 147,150 |
| CI |  | GBFF | Mexico | Biodiversity | Action Area 2 (IP&LCs) | 105,000 | 9,450 | 114,450 |
| CI |  | GBFF | Mexico | Biodiversity | Action Area 4 (Resource mobilization) | 60,000 | 5,400 | 65,400 |
| Total PPG Amount |  |  |  |  |  | 300,000 | 27,000 | 327,000 |

### Action Area Elements

| Programming Directions | Trust Fund | (in $) |  |
| --- | --- | --- | --- |
|  |  | GEF Project Financing | Co-financing |
| Action Area 1 (Conservation) | GBFF | 9,169,862 | 63,724,380 |
| Action Area 2 (IP&LCs) | GBFF | 5,835,367 | 40,308,450 |
| Action Area 4 (Resource mobilization) | GBFF | 1,667,248 | 11,516,702 |
| Total |  | 16,672,477 | 115,549,532 |

### Confirmed Co-financing for the project, by name and type*

Please include evidence for each co-financing source for this project in the tab of the portal

Please describe the investment mobilized portion of the co-financing.

From FMCN, USD $12,000,000, which are endowment funds for marine PAs provided by KfW Development Bank resources to complement Mex30x30 for Component 3 (already deposited). In addition, USD $1,067,000, which will cover recurrent expenditures for Component 2, 4 and PMC.

From CONANP, $100,000 in-kind co-financing, to represent CONANP's complete annual budget upon the successful completion of the project in 2030.

From Conservation International, $2,482,532 in-kind co-financing to cover organizations costs during project implementation.

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Investment Mobilized | Amount ($) |
| --- | --- | --- | --- | --- |
| Recipient Country Government | CONANP | In kind | Recurrent Expenditures | 100,000,000 |
| GEF Agency | Conservation International | In-kind | Recurrent Expenditures | 2,482,532 |
| CSO | FMCN | Grant | Investment Mobilized | 12,000,000 |
| CSO | FMCN | In kind | Recurrent Expenditures | 1,067,000 |
| Total Co-financing |  |  |  | 115,549,532 |

# ANNEX b: EndorsementS

| Name of GEF Agency Coordinator | GEF Agency Coordinator Contact Information |
| --- | --- |
| Name of Agency Project Coordinator | Agency Project Coordinator Contact Information |

### Letter of Endorsement

Please attach the Operational Focal Point endorsement letter(s) in this Annex. For projects involving more than one country: please include a compilation of the signed LOEs in one PDF file in this annex.

# ANNEX C: Project results framework

| Objective: | To help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). |
| --- | --- |
| Indicator(s): | a. Terrestrial protected areas under improved management effectiveness (Target: 3,665,666 ha) b. Marine protected areas under improved management effectiveness (Target: 22,241,504 ha) c. Greenhouse gas emissions mitigated (Target: 5.7 million tons) d. Number of people experiencing socioeconomic benefits (male/female) (Target: 163,293 people; 50% female) |

| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |
| --- | --- | --- | --- |
| Outcome 1.1: CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. Indicator 1.1: % decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams. | Baseline 1.1: 0% decrease in annual CONANP budget shortfall as a result of new revenue streams. | Target 1.1: 10% decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams. | Output 1.1.1: New revenue streams to increase CONANP's budget are identified. Indicator 1.1.1: # of feasibility reports and action plans for accessing new revenue streams completed. Target 1.1.1: 1 feasibility report and action plan for accessing new revenue streams completed. Output 1.1.2: New revenue streams to increase CONANP's budget are accessed. Indicator 1.1.2: # of new revenue streams accessed and contributing to CONANP budget. Target 1.1.2: At least one new revenue streams accessed and contributing to CONANP budget. Output 1.1.3: The institutional capacity of CONANP is enhanced through expanding the Protected Areas Learning Community (community of practice). Indicator 1.1.3a: % improvement in CONANP institutional capacity assessment score. Target 1.1.3a: 15% improvement in CONANP institutional capacity assessment score. Indicator 1.1.3b: Increase in Protected Areas Learning Community membership (disaggregated by gender and IPLC membership). Target 1.1.3b: At least 100 new members are part the Protected Areas Learning Community, of whom at least 50% are women. |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |
| Outcome 2.1: Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years. Indicator 2.1: Percentage of required funding for a Transition Fund to cover PA financing gaps for 15 years. | Baseline 2.1: 1 M funding secured for a Transition Fund through MEx30x30. | Target 2.1: 100% required Funding pledged for phase one of a Transition Fund. | Output 2.1.1: Funding pledged to address identified financial gaps. Indicator 2.1.1: Amount of donor funding pledged to address financing gap for phase one during transition period. Target 2.1.1 100% of required funding for phase one pledged to address financing gap during transition period (amount to be confirmed in step 5 and 6 of long-term sustainable finance mechanism design process;). Output 2.1.2: Long-term sustainable finance mechanism/PFP is designed. Indicator 2.1.2: Number of long-term sustainable finance mechanism, designed and ready for closing. Target 2.1.2: One long-term sustainable finance mechanism designed and ready for closing. |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. |  |  |  |
| Outcome 3.1: PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. Indicator 3.1a: % improvement in PA management effectiveness score, as measured by i-effectiveness evaluation. Indicator 3.1b: # people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (disaggregated by gender and IP&LCs). | Baseline 3.1: 0 improvement in PA management i-effectiveness score. Baseline 3.1b: people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (disaggregated by gender and IP&LCs). | Target 3.1a: - For PAs with a rating of “Highly Effective” or “Outstanding”: Maintained or increased management effectiveness score. - For PAs with a rating of “Ineffective” or “Partially Effective”: i-effectiveness score increased by at least 15 points. Target 3.1b: 163,200 people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (at least 50% female, desegregated by gender and IP&LCs). | Output 3.1.1: Five-year plans, and associated Annual Operating Plans (POAs), developed for PAs and ADVCs through an inclusive participatory process coordinated by CONANP. Indicator 3.1.1: # of gender-responsive and inclusive Annual Operating Plans prepared and implemented. Target 3.1.1: 1 gender-responsive and inclusive Annual Operating Plan prepared and implemented per PA or ADVC per year of the project (6 total). Output 3.1.2: Gender-responsive and inclusive training provided to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation and restoration practices. Indicator 3.1.2: # of people trained in sustainable land management, conservation and restoration practices (disaggregated by gender, recording level of Indigenous participation). Target 3.1.2: At least 100 people per PA or ADVC trained in sustainable land management, conservation and restoration practices (at least 50% women; level of Indigenous participation proportional to Indigenous percentage of local population). Output 3.1.3: IP&LCs and local organizations implement gender-responsive and inclusive conservation, restoration and sustainable management actions defined in POAs. Indicator 3.1.3: % of targets reached in POAs, which include gender-responsive and inclusive management actions implemented by IP&LCs and local organizations in PAs and ADVCs. Target 3.1.3: At least 80% of targets reached in POAs. Output 3.1.4: Emergency fund expanded to support emergency-response brigades. Indicator 3.1.4: % of valid emergency funding requests that result in financial support within 72 hours. Target 3.1.4: at least 90% of funding requests resulting in delivery of financial support within 72 hours. |
| Component 4: Knowledge management, monitoring and evaluation for scaling impact. |  |  |  |
| Outcome 4.1: MEx30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. Indicator 4.1: # of scale-up strategy documents based on MEx30x30 experience. | Baseline 4.1: No scale-up strategy documents based on MEx30x30 experience. | Target 4.1: 1 scale-up strategy document based on MEx30x30 experience. | Output 4.1.1: Ongoing lessons learned from MEx30x30 and other long-term sustainable finance mechanisms and PA scaling experiences documented and disseminated, with a focus on nationally led long-term sustainable finance mechanisms. Indicator 4.1.1: Number of lessons-learned knowledge products prepared and shared (including products with a focus on gender and inclusion). Target 4.1.1: At least 4 lessons-learned knowledge products prepared and shared (including at least one with a focus on gender and inclusion). Output 4.1.2: National workshop and dissemination event held to finalize scale-up strategy document based on MEx30x30 experience. Indicator 4.1.2a: # of national workshop and dissemination events held. Target 4.1.2a: 1 national workshop and dissemination event held. Indicator 4.1.2b: # of people participating in national workshop and dissemination event (disaggregated by gender, recording level of Indigenous participation). Target 4.1.2b: 400 people participating in national workshop and dissemination event (at least 50% women, dessagregated by indigenous). |
| Outcome 4.2: Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. Indicator 4.2: PIR, MTR and TE ratings. | No ratings. | Target 4.2: PIR, MTR and TE ratings scored as “Satisfactory” to “Highly Satisfactory”. | Output 4.2.1: Clear and robust gender-responsive and inclusive Monitoring and Evaluation framework created and implemented. Indicator 5.1: Number of M&E frameworks in operation. Target 4.2.1: One M&E framework in operation. Output 4.2.2: Project Implementation Reports, Mid-term Review, and Terminal Evaluation completed. Indicator 4.2.2: % of required reports submitted to CI GEF Agency on time and determined to be satisfactory. Target 4.2.2: 100% of required reports. |

# ANNEX D: status of utilization of Project Preparation Grant (PPG)

Provide detailed funding amount of the PPG activities financing status in the table below*:

| Project Preparation Activities Implemented | GETF/LDCF/SCCF/GBFF Amount ($) 300,000 |  |  |
| --- | --- | --- | --- |
|  | Budgeted Amount | Amount Spent To date | Amount Committed |
| Personnel-Project Design and Coordination | 171,000 | 0 | 171,000 |
| International Consultant- ProDoc Development | 75,000 | 0 | 75,000 |
| International Consultants- Safeguards, Permanence Financing Project (PFP), Carbon Mitigation. | 54,000 | 0 | 54,000 |
| Total | 300,000 | 0 | 300,000 |

# annex E: project map and coordinates*

Please provide geo-referenced information and map where the project interventions will take place.

| Geo Name ID Required field if the location is not an exact site | Location Name Required field | Latitude Required field | Longitude Required field | Location Description Optional text field | Activity Description Optional text field |
| --- | --- | --- | --- | --- | --- |
|  | Balam-Kú | 18°29'13.2"N | 90°03'36.0"W | Centroids of polygon |  |
|  | Bajos del Norte | 23°03'43.2"N | 88°57'25.2"W | Centroids of polygon |  |
|  | Chimalapas cluster | 16°51'50.4"N | 94°24'32.4"W | Centroids of polygon |  |
|  | Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit | 22°15'10.8"N | 104°14'52.8"W | Centroids of polygon |  |
|  | Papigochic | 28°13'55.2"N | 107°44'27.6"W | Centroids of polygon |  |
|  | Tecuani | 17°42'39.6"N | 100°30'10.8"W | Centroids of polygon |  |

Please provide any further geo-referenced information and map where project interventions are taking place as appropriate.

# ANNEX F: Environmental and Social Safeguards documents including Rating

CI-GEF AGENCY

ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS) SCREENING REPORT

Preliminary Screening (PIF Phase or one-step) 			 Second Screening (PPG Phase)

I. PROJECT INFORMATION

- Basic Project Profile

| Countries: Mexico | GEF Project ID: |
| --- | --- |
| Project Title: Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |
| Executing Agency: Fondo Mexicano para la Conservación de la Naturaleza (FMCN) |  |
| GEF Focal Area: Global Biodiversity Framework Fund (GBFF) |  |
| GEF Project Amount: USD$ |  |
| CI-GEF Project Manager: Daniela Carrion |  |
| ESS Analysis Performed by: Ian Kissoon, Senior Director of ESMF, CI-GCF/GEF Agencies |  |
| Date of Analysis: March 22, 2024 |  |

- Summary of Project Risk Categorization, ESS Standards Triggered and Mitigation Plans Required

| Project Category: | Category A |  | Category B | Category C |
| --- | --- | --- | --- | --- |
|  |  |  | X |  |
| The proposed project activities have the potential to cause adverse environmental and social impacts. However, the impacts are anticipated to be less adverse than those of Category A projects, site-specific, and mitigation measures can be designed more readily than for Category A projects. |  |  |  |  |
| Safeguards Triggered: |  |  |  |  |
| Environmental & Social Impact Assessment |  | Cultural Heritage |  |  |
| Protection of Natural Habitats and Biodiversity Conservation Resett. & Physical/Economic Displacement Indigenous Peoples Resource Efficiency & Pollution Prevention |  | Labour and Working Conditions Community Health, Safety and Security Private Sector Direct Investments and Financial Intermediaries Climate Risk and Related Disasters |  |  |
| Mitigation Measures Required: |  |  |  |  |
| Limited or Full ESIA Environmental & Social Management Plan Plan for Natural Habitat Protection and Biodiversity Conservation Voluntary Resettlement Action Plan Process Framework Indigenous Peoples Plan |  | Resource Efficiency & Poll. Prevention Plan Cultural Heritage Management Plan Labour Management Procedures Community Health, Safety and Security Plan Environmental and Social Management Framework Climate and Disaster Risk Management Plan |  |  |

- Project Objectives:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs) effectively.

- To attract and mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen PAs and ADVCs with Indigenous Peoples and local communities (IP&LCs) to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

- Project Description:

The project has as objective to advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas. This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex). Mexico safeguards near to 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life.

The project will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community brigades, fire management, productive projects, ecotourism, and capacity building.

The project will be delivered under the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

- Project location and biological/socio-economic characteristics relevant to the ESS analysis:

The project will be implemented in Mexico. Mexico is one of the world's 15 megadiverse nations, holding an extraordinary 10-12% global biodiversity and has also earned recognition for its pivotal role in global biodiversity, being encompassed within three of Conservation International's "Biodiversity Hotspots" (Mesoamerica, California Floristic Province, and Madrean Pine-Oak Woodlands), featuring in 122 of WWF's Global 200, and boasting 275 Key Biodiversity Areas (KBAs).

Map showing the protected areas and voluntary conservation areas included in Mex30x30.

Over 12 million Mexicans rely on forests for their livelihoods, with five million indigenous people inhabiting forested areas. More than 3,000 medicinal plant species are actively utilized for traditional purposes, offering a unique avenue for promoting socioeconomic development and sustainable resource management. These areas, often in municipalities with high poverty and economic marginalization rates, represent 40% of Mexico's forested lands. Additionally, 61% of these areas fall under collective land tenure systems, such as ejidos and comunidades, making Mexico a global leader in community-managed forestland.

Mexico has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Approximately 3.9% (4,689,557 people) of the Mexican population lives in PAs, of which 5.7% are indigenous (270,476 people). Therefore, about 46% of PAs are home to indigenous people. Of the total land surface that makes up the country's PAs, more than 60% is social property, including more than 30% of indigenous territory. CONANP is the governmental institution responsible for administrating and managing protected areas in Mexico under two federal conservation strategies: top-down, represented by PAs by decree, and bottom-up, represented by certified ADVCs. Mexico supports 557 ADVCs in 28 states, totaling 1,248,438.1719 hectares. ADVC certification is a mechanism to promote voluntary social participation in conservation under an integrated landscape management approach.

Map showing the Indigenous groups in the protected areas and voluntary conservation areas included in Mex30x30

In Mexico, gender roles have historically influenced how men and women access, use, and manage natural resources in protected areas. These roles can influence decision-making processes, resource access, and governance structure participation. It is common for traditional gender norms to dictate that men often engage in activities like agriculture, forestry, or hunting. At the same time, women may be responsible for tasks related to gathering non-timber forest products, water, and food preparation, besides traditional roles of caring for the home and raising children. Moreover, gender-based violence and sexual exploitation, sexual abuse, and sexual harassment are high and regular. Around 70% of women and girls aged over 15 have experienced gender violence in Mexico. On average, ten women are killed every day, and tens of thousands go missing. In recent years, there has been a growing recognition of the importance of integrating gender perspectives into conservation and sustainable development efforts to ensure equitable access to resources, participation in decision-making processes, and addressing gender-based inequalities. In these subsidy programs, the beneficiaries of projects in which women participate may have access to up to 17% of the total amount CONANP provides to finance affirmative actions with a gender perspective.

- Executing Agency (EA)’s Institutional Capacity for Implementing ESMF:

Since 1998, FMCN has applied environmental and social standards to its projects. These have evolved alongside the policies and procedures of the World Bank, which has been the implementing agency for the four GEF-funded projects continuously coordinated by FMCN for 26 years. With the accreditation by GCF in 2019, FMCN integrated the World Bank Environmental and Social Standards published in 2018. They were incorporated into every project starting in 2019. FMCN also has a Gender Policy, which is part of its Organizational Manual, to incorporate the gender perspective in a cross-cutting manner in the operation of FMCN and all its initiatives. FMCN has staff dedicated to safeguards, gender, and stakeholder engagement, and are environmental, social, and gender specialists who have received training in safeguards, gender, and stakeholder engagement.

II. ESS STANDARDS TRIGGERED BY THE PROJECT

Based on the information provided in the ESS Screening Form, the following Environmental and Social Safeguard (ESS) Standards have been triggered:

| ESS Standard | Yes | No | TBD | Justification |  |
| --- | --- | --- | --- | --- | --- |
| 1. Environmental & Social Impact Assessment (ESIA) |  | X |  | No significant adverse environmental and social impacts that are sensitive, diverse, or unprecedented is anticipated. |  |
| 2. Protection of Natural Habitats and Biodiversity Conservation | X |  |  | The project will operate in five Protected Areas and one complex of Voluntary Conservation Areas supporting activities related to biological monitoring, restoration of degraded areas, community brigades, fire management, productive projects, ecotourism, and capacity building. |  |
| 3. Resettlement and Physical and Economic Displacement |  | X |  | The project is not proposing resettlement or physical displacement and will operate in five PAs and the Chimalapas ADVCs, where agreements on restrictions are already in place. |  |
| 4. Indigenous Peoples | X |  |  | The project will operate in lands or territories traditionally owned, customarily used, or occupied by indigenous peoples. |  |
| 5. Resource Efficiency and Pollution Prevention |  | X |  | There are no proposed activities related to the use of banned, restricted or prohibited substances, chemicals or hazardous materials. |  |
| 6. Cultural Heritage |  | X |  | The project will respect and preserve traditional knowledge and practices (e.g., the use of medicinal plants by indigenous peoples), complying with local, national, and international regulations related to cultural heritage protection. |  |
| 7. Labor and Working Conditions |  | X |  | The EA indicated compliance with the necessary policies, procedures, systems and capabilities that meets the requirements set out in the GEF Minimum Standard 8. |
| 8. Community Health, Safety and Security | X |  |  | Mexico has been assessed as Medium to High for security risks. Some of these risks include exposure to illegal actors in the project areas and the escalation of security issues across the country. |
| 9. Private Sector Direct Investments and Financial Intermediaries |  | X |  | Under Component 3, an endowment will be established to ensure permanent funding for the five decreed PAs and one ADVC complex. MEx30x30 will build on Fund for Protected Areas (FANP) institutional arrangements whose operation is overseen by the FANP Technical Committee (CTFANP). Each participating PA prepares an Annual Operating Program (POA), which goes through an Environmental and Social Safeguards Screening, and the FANP’s Technical Committee (CTFANP) reviews, approves, and oversees its operation. |
| 10. Climate Risk and Related Disasters |  | X |  | The main climate hazards that can affect project implementation include floodwaters, coastal floods, landslides, hurricanes wildfires, extreme heat, and water scarcity. These climate hazards may impose operational risks. For example, floodwaters, coastal floods, landslides, and hurricanes can damage roads, hindering access to the protected areas and delaying project activities. Wildfires may also lead to the displacement of nearby communities, impacting project stakeholders and potentially halting work needs until conditions improve. Nevertheless, as the project will work in different areas, by means that activities are not concentrated in just one location, operations could be sustained in the other PAs and ADVCs until conditions improve in the affected zone. Further, high temperature increases, wildfires, and droughts may undermine conservation efforts and restoration actions. The project will enhance efficient water management strategies and prioritize using drought-resistant crop varieties and climate-resilient native species to reduce the Project's vulnerability to these climate hazards. Further, the Emergency Fund will enhance preparedness and emergency response planning to minimize the impacts of climate-related disasters. Despite climate hazards, the project has different adaptive capacities to achieve its objectives. Mexico has developed national and local policies that support climate adaptation and mitigation efforts. CONANP has a Strategy towards 2040 (S-2040), a Climate Change Strategy for Protected Areas (ECCAP, for its acronym in Spanish), and a Special Climate Change Program. These institutional guides incorporate the concepts of adaptation, mitigation, resilience, vulnerability, risk, and landscape connectivity to increase PAs' adaptive capacity and mitigate climate change through coordinated multisector participation, gender mainstreaming, ecosystem-based adaptation, and disaster risk reduction. The project "Strengthening the effectiveness of the management and resilience of Protected Areas to protect biodiversity threatened by Climate Change" (Resiliencia) , implemented in 17 PAs, also left valuable lessons learned. For example, the inclusion of climate change as a cross-sectional issue in PA management results in substantial improvements in communicating the importance of PAs to the public, encouraging effective inter-institutional collaboration, involvement of local stakeholders, and facilitating funding for PA protection. Promoting participation mechanisms such as the Advisory Councils in the PAs also made climate change a significant issue for implementing adaptation measures. All these strategies pave the way for institutional adaptation and climate change mitigation that will be used and scaled up during the project's lifetime. |

Note: Other ESS Standards may be triggered at any time during the project cycle and the project must inform the CI-GEF Agency of any changes to the project that could affect the ESS Standards.

III. PROJECT CATEGORIZATION

Based on the ESS Standards triggered, the project is categorized as follows:

| PROJECT CATEGORY | Category A | Category B | Category C |
| --- | --- | --- | --- |
|  |  | X |  |
| Justification: The proposed project activities have the potential to cause adverse environmental and social impacts. However, the impacts are anticipated to be less adverse than those of Category A projects, site-specific, and mitigation measures can be designed more readily than for Category A projects. |  |  |  |

IV. MANAGEMENT OF ESS TRIGGERED

ESS2. Protection of Natural Habitats and Biodiversity Conservation

The project is required to develop an Environmental and Social Management Plan (ESMP) to ensure that the project activities such as restoration of degraded areas, ecotourism, and productive interventions do not cause harm to PAs and conservation areas including people, and where negative impacts are unavoidable that mitigation measures are designed, implemented and monitored in consultation with key stakeholders. In addition, restoration activities will need to demonstrate that they are viable i.e. they will restore or improve biodiversity and ecosystem composition, structure and functions, and will not involve invasive alien species.

ESS4. Indigenous Peoples

The project is required to develop an Indigenous Peoples Plan (IPP) (please use CI-GEF template) and outline how Free Prior and Informed Consent (FPIC) would be sought as well as how the project will avoid negative impacts on indigenous peoples, ensure their full and effective participation in decision making related to the project, and to provide indigenous peoples with culturally appropriate social and economic benefits that have been negotiated with them. Where the project may affect indigenous peoples in voluntary isolation, appropriate measures shall be taken to recognize, respect, and protect their lands and territories, environment, health, and culture, as well as to avoid all undesired contact. Aspects of the project that would result in such undesired contact shall not be processed further. The IPP must also take into consideration the Indigenous People’s cultural heritage that is material to the identity and/or cultural, ceremonial, or spiritual aspects, and provide measures to mitigate any adverse impact on the affected Indigenous People's lives or cultural heritage.

ESS8. Community Health, Safety and Security

The project is required to develop and implement a Community Health, Safety and Security Plan to ensure that risks or potential impacts to the health, safety and security of project staff and project-affected communities are identified, avoided and mitigated.

ESS9. Private Sector Direct Investments and Financial Intermediaries

While FANP has an environmental and social management system in place, FANP was created in 1997 and therefore a gap analysis will need to be conducted to ensure that the FANP’s ESMS is up to date with the GEF’s Minimum Standards.

Other Plans

Apart from the ESS Policy, the project will be required to comply with the CI-GEF’s Accountability and Grievance Policy, Gender Policy, and Stakeholder Engagement Policy by preparing and submitting for review and approval to the CI-GEF during the project development stage, the following plans:

- Accountability and Grievance Mechanism (AGM)

To ensure that the project meets CI-GEF Project Agency’s Accountability and Grievance Mechanism Policy, the EA is required to develop an Accountability and Grievance Mechanism (template provided) that will ensure people affected by the project are able to bring their grievances to the EA for consideration and redress. The mechanism must be in place before the start of project activities, and disclosed to all stakeholders in a language, manner and means that best suits the local context.

In addition, the EA is required to monitor and report on the following minimum accountability and grievance indicators:

1.	Number of times/events the AGM is communicated/disseminated to stakeholders; and

2.	Percentage of conflict and complaint cases reported to the project’s AGM that have been resolved.

- Gender Mainstreaming Plan (GMP)

The GMP (template provided) should include a gender analysis including the role of men and women in decision-making, and appropriate interventions with gender-related outcomes to ensure that men and women have equal opportunities to participate and benefit from the project.

Further, the project should examine the extent of Gender Based Violence (GBV), the likelihood of project activities contributing/exacerbating GBV, and proposed mitigation measures as needed.

In addition, the EA is required to monitor and report on the following minimum gender indicators:

1.	Number of persons (disaggregated by gender) who received benefits during the implementation phase; and if relevant

2.	Number of documents (disaggregated by types) derived from the project that included gender considerations or address gender gaps.

- Stakeholder Engagement Plan (SEP)

To ensure that the project complies with the CI-GEF’s Stakeholders’ Engagement Policy, the EA is required to develop a Stakeholder Engagement Plan (template provided).

In addition, the EA is required to monitor and report on the following minimum stakeholder engagement indicators:

1.	Number of stakeholder entities (disaggregated by type) involved during the project implementation phase;

2.	Number of persons (disaggregated by gender) who participated in activities during the project implementation phase; and

3.	Number of engagements (disaggregated by type of engagement) with stakeholders in during the project implementation phase.

All plans must be submitted to the CI-GEF Agency for review and approval during the project proposal development phase. Since the timeframe for the proposal development phase has been relatively short, the completed plans at CEO ER must be updated and validated with stakeholders during the first six months of implementation. For the plans (e.g. CHSS Plan) not developed at the time of CEO ER, those plans will also need to be developed and submitted to the CI-GEF Agency during the first six months of the implementation phase.

V. DISCLOSURE

Following approval of the plans, the EA must disclose the plans no later than 30 days from date of approval.

CI-GCF/GEF AGENCIES

ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS) SCREENING FORM

| Preliminary Screening (check if performed at the project/program conceptual stage) | Secondary Screening (check if performed at proposal development stage i.e. PPG/PPF) |
| --- | --- |

Guidance Notes

- This ESS Screening Form is guided by the CI-GEF/GCF Agencies’ Policy on Environmental and Social Safeguard Standards, which forms part of the CI-GCF/GEF Agencies Environmental and Social Management Framework (ESMF).

- The CI-GCF/GEF Agencies undertake environmental and social safeguard screening for every project or program to determine the risk categorization for the project, the ESS Standards triggered by the project, and the mitigation measures to be implemented by the project.

- ESS screenings are performed at (i) conceptual stage (Preliminary Screening) using the finalized versions of the PIF/PFD/CN; and (ii) proposal development stage i.e. PPG/PPF (Secondary Screening) using the project document when details of activities, project intervention areas and executing arrangements, among others, have been finalized. Additional screenings may be performed at any time when significant changes have emerged including but not limited to new proposed activities, changes in local/national context of project intervention areas, and where environmental and social risks have increased.

- The CI-GCF/GEF Agencies classify the project into one of three categories, depending on the type, location, sensitivity and scale of the project and the nature and magnitude of its potential environmental and social impacts. The descriptions of the categories and lists of types of projects identified in Appendix II of the CI-GCF/GEF’s ESMF. These descriptions are meant to serve as guidance and are not exhaustive.

- The CI-GCF/GEF Agencies do not fund projects that involve the construction or rehabilitation of large or complex dams, and resettlement of people. The CI-GCF/GEF Agencies cannot support projects that contradict CI’s mission and policies.

- The Executing Agency/Entity is responsible for fully completing and providing accurate responses to each question in this Screening Form, and to submit the completed Form to the CI-GCF/GEF Agencies in a timely manner.

- The CI-GCF/GEF Agencies is responsible for ensuring that the project complies with the CI-GCF/GEF Policy on Environmental and Social Safeguards, and will use the completed Screening Form to determine the mitigation measures for the Executing Agency/Entity to implement.

- In addition to preparing and implementing mitigation measures for the environmental and social safeguard standards triggered, the Executing Agency/Entity will also need to comply with CI-GEF/GCF’s policies on gender, stakeholder engagement and accountability and grievance mechanism. As such the Executing Agency/Entity will be required to prepare a Gender Assessment and Action Plan, a Stakeholder Engagement Plan, and an Accountability and Grievance Mechanism (see to ESMF for details).

- The Executing Agency/Entity is responsible for informing the CI-GCF/GEF Agencies in a timely manner, if at any time during the preparation and implementation of the project, the information provided in this Screening Form changes in a way that results in the risks of the project being increased.

- For additional information/clarification, please contact Ian Kissoon, Senior Director of ESMF, CI-GEF/GCF Agencies at ikissoon@conservation.org or your GEF/GCF Project Manager.

| I. PROJECT INFORMATION |  |  |  |
| --- | --- | --- | --- |
| GCF/GEF Project ID: | Country: Mexico |  |  |
| Project Title: Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| Name of the Executing Agency/Entity: Fondo Mexicano para la Conservación de la Naturaleza |  |  |  |
| Length of Project: 60 months | Anticipated Start date: |  | Anticipated End date: |
| GCF Results Area(s) / GEF Focal Area(s): Global Biodiversity Framework Fund (GBFF) |  |  |  |
| GCF/GEF Project Amount: USD |  | Co-Financing Amount: USD |  |
| Project Objectives: The Project "MEx30x30: Conserving Mexican biodiversity through communities and their protected areas" has as objective to help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas. This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex). MEx30x30 has three main objectives to reach this goal: - To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively; - To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance. - To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and local communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system. |  |  |  |
| Project Components and Main Activities Proposed: Mexico safeguards near to 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life. The Project MEx30x30 will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community brigades, fire management, productive projects, ecotourism, and capacity building. Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP has been the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). However, high levels of socioeconomic marginalization in many rural communities and heavy livelihood dependence on natural resources can result in resistance to prioritizing conservation or restoration activities that do not adequately consider local needs. CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. As a result, The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives. The Project MEx30x30 will focus on the following components: - Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget. - Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding. - Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established. - Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project. MEx30x30 is an opportunity to make possible the 30x30 goal, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes. |  |  |  |
| ESS Screening Form Completed by: FMCN - Environmental and Social Coordinator |  |  |  |
| Date of Submission/Resubmission of Completed Form to CI-GEF/GCF: 10/03/2024 |  |  |  |
| CI-GEF/GCF Comments: |  |  |  |

II. PROJECT CONTEXT

Project Location - Indicate where the project will take place AND provide a legible map highlighting the project intervention areas, towns/communities/indigenous territories, protected areas, and main rivers/watersheds): Mexico’s protected areas are vital to address directly the primary drivers of extinction and habitat loss, becoming sanctuaries for preserving significant biodiversity of national and global importance, from iconic species to unique ecosystems. PAs have been effective at slowing the rate of biodiversity loss. Analyses show that PAs supported by the Global Environmental FacilityFund (GEF) in Mexico avoided up to 23% forest loss from 2001 to 2012 compared to PAs that did not directly receive GEF support during the same period. Safeguarding protected areas ensures the survival of threatened and endangered species and the provision of vital ecosystem services, such as clean water, air purification, pollination, and climate resilience against natural disasters and extreme weather events. PAs also offer recreational opportunities and support physical and mental health, fostering an appreciation for nature. They also serve as living classrooms for environmental education and invaluable sites for scientific research, which can yield critical insights into climate change, ecological dynamics, and more. They, too, preserve cultural heritage and traditions, providing educational and cultural value. Moreover, they can boost long-term economic benefits for local economies through tourism, creating jobs, and stimulating sustainable local businesses. Providing these crucial benefits is not free; costs are associated with PA management in terms of direct expenditures and opportunity costs (alternative uses). These costs require the Government of Mexico to set aside funding for PAs every year and, in effect, to “give up” potential revenues from allowing the land to be developed for other uses. CONANP is the governmental institution responsible for administrating and managing protected areas in Mexico under two federal conservation strategies: top-down, represented by PAs by decree, and bottom-up, represented by certified ADVCs. Mexico has 226 terrestrial and marine PAs protecting 93,807,804 hectares of high socioecological value (Figure 1 and 2). It also supports 557 ADVCs in 28 states, totaling 1,248,438.1719 hectares. ADVC certification is a mechanism to promote voluntary social participation in conservation under an integrated landscape management approach. An ADVC certifies any person, legal entity, social organization, indigenous people, and community willingness to manage their land sustainably. Figure 1. Protected areas in Mexico. Figure 2. Protected areas in Mexico according to their category, number and extent (hectares). Mexico has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Approximately 3.9% (4,689,557 people) of the Mexican population lives in PAs, of which 5.7% are indigenous (270,476 people). Therefore, about 46% of PAs are home to indigenous people (Figure 3). Of the total land surface that makes up the country's PAs, more than 60% is social property, including more than 30% of indigenous territory. Figure 3. Protected areas and indigenous groups in Mexico. In ADVCs territories live around 92,756 persons, including sixteen indigenous groups: Amuzgo, Chinanteco, Chol, Chontal, Maya, Mazateco, Mixe, Mixteco, Nahuatl, Tlapaneco, Tojolabal, Totonaca, Tzeltal, Tzotzil, Zapoteco and Zoque. By its nature, conservation in ADVCs is an inclusive and participatory strategy and an adaptive model, particularly in common properties where their performance is permanently monitored in community assemblies and analyzed to ensure those decisions lead to the desired results. The assemblies and committees' actions include imposing hunting bans, regulations on fire use, restrictions on land uses, and regulating the harvest of wild products. Landowners express varied motives for seeking ADVCs certification: cultural values (including the legacy for future generations); wildlife or forest cover recovery; obtaining professional advice; implementing ecotourism; having eco-brands for local products (like coffee, honey, cacao, among others); looking for governmental protection for their natural resources (sanctions for illegal hunting and narcotraffiking); protecting lands from infrastructure development (highways, hydroelectric dams); protecting lands for extractive activities (mainly oil, fracking or mineral extraction); and, the expectation for incentives and institutional advice. In Mexico, it is also essential to acknowledge that gender roles have historically influenced how men and women access, use, and manage natural resources in protected areas. These roles can influence decision-making processes, resource access, and governance structure participation. It is common for traditional gender norms to dictate that men often engage in activities like agriculture, forestry, or hunting. At the same time, women may be responsible for tasks related to gathering non-timber forest products, water, and food preparation, besides traditional roles of caring for the home and raising children. Moreover, gender-based violence and sexual exploitation, sexual abuse, and sexual harassment are high and regular. Around 70% of women and girls aged over 15 have experienced gender violence in Mexico. On average, ten women are killed every day, and tens of thousands are missing. Collaborative approaches with local stakeholders and indigenous communities help ensure the sustainable use of natural resources and promote the well-being of people and the environment. Thus, most PAs in Mexico have an Advisory Council, which has become the primary body for the participation of local society and marks the difference in PA management. Through the Advisory Councils, government institutions, civil society, academic and research entities, and representatives of the people who inhabit, work, and use the ecosystems (e.g., ejidos, communities, indigenous groups, and women) can be aware, participate, advise, and support decision-making of the pertinent strategies to address the priority needs of the PAs. Additionally, CONANP has two budgetary programs to support local conservation activities: (a) the S046 Conservation Program for Sustainable Development (PROCODES) and (b) the U040 Program for the Protection and Restoration of Ecosystems and Priority Species (PROREST). Both constitute a public policy instrument to promote PA's conservation, protection, and restoration and provide economic support to the local population and continuous dialogue with the different local stakeholders. In recent years, there has been a growing recognition of the importance of integrating gender perspectives into conservation and sustainable development efforts to ensure equitable access to resources, participation in decision-making processes, and addressing gender-based inequalities. In these subsidy programs, the beneficiaries of projects in which women participate may have access to up to 17% of the total amount CONANP provides to finance affirmative actions with a gender perspective. The beneficiaries will determine the work role for the affirmative actions, for which they may form commissions with a minimum of two people and a maximum of four to carry out the affirmative actions required by the women, or if necessary, they may rely on people from outside the group for their execution. The progress and goals report for the second quarter of 2022 establishes that the investment with a gender perspective amounts to $251,499. Nevertheless, PAs face challenges, including decreasing funding. In 2021, CONANP's budget represented only 31% of the total needed to manage Mexico's PAs properly, making it difficult for CONANP to fulfill its mandate of protecting the natural capital. The 2023 results indicate the same pattern; the annual budget required from federally protected areas is US$160 million. Considering the yearly budget of US$70 million for 2023, there is an annual financial gap of US$90 million. However, the Mexican government has made commendable efforts to recognize biodiversity's importance by decreeing more PAs than any previous administration. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). The MEx30x30 Project represents a significant advancement, leveraging the knowledge accumulated over 26 years of a successful collaboration between CONANP and FMCN. This initiative aims to amplify the impact of past successes by enhancing the management and efficiency of protected areas. A cornerstone of this endeavor is the incorporation of key learnings from the proven Public-Private Collaboration Scheme, known as FANP, established in 1997 with invaluable support from the Global Environment Facility (GEF). FANP has been instrumental in directing strategic financial resources to 70 PAs to strengthen the operational capacities of these PAs through a multifaceted approach. The MEx30x30 Project will build upon this solid foundation to support six protected areas: two existing PA, three newly decreed PAs, and one complex of recently designated ADVCs (with eight certificates) (Figure 4 and 5). Through a comprehensive and integrated strategy, this initiative seeks to elevate the effectiveness of protected areas further, reinforcing their role as vital guardians of biodiversity and sustainable development engines for the benefit of nature and people. Additional information of each protected area can be found in Table 1. Figure 4. Protected areas and voluntary conservation areas included in Mex30x30. Figure 5. Indigenous groups in the protected areas and voluntary conservation areas included in Mex30x30.

Biological Context of Project Area - Indicate global significance (e.g. biodiversity hotspot, Ramsar site, Key Biodiversity Area) of the project area. - Identify endemic and IUCN Red Listed species. - Describe the environmental conditions of the area including pollution, threats to biodiversity, and natural disasters. Mexico is one of the world's 15 megadiverse nations, holding an extraordinary 10-12% global biodiversity, ranking third in mammal diversity with over 564 species and 30% endemic. Additionally, it secures the second spot for reptiles, boasting over 860 species, 45% exclusive to its diverse landscapes. Its rich tapestry of flora, comprising over 5,000 species, is a testament to its ecological wealth and plays a vital role in the lives of indigenous and local communities. Over 12 million Mexicans rely on forests for their livelihoods, with five million indigenous people inhabiting forested areas. More than 3,000 medicinal plant species are actively utilized for traditional purposes, offering a unique avenue for promoting socioeconomic development and sustainable resource management (CITE-BIOFIN, 2023). These areas, often in municipalities with high poverty and economic marginalization rates, represent 40% of Mexico's forested lands. Additionally, 61% of these areas fall under collective land tenure systems, such as ejidos and comunidades, making Mexico a global leader in community-managed forestland. Internationally, Mexico has also earned recognition for its pivotal role in global biodiversity, being encompassed within three of Conservation International's "Hotspots" (Mesoamerica, California Floristic Province, and Madrean Pine-Oak Woodlands), featuring in 122 of WWF's Global 200, and boasting 275 Key Biodiversity Areas (KBAs) (CEPF, 2023; Olson et al., 2000; CBD, 2021). However, nearly 50% of Mexico's territory grapples with environmental degradation from biophysical, social, and economic factors. This degradation threatens ecosystems, affecting 63 million people residing in degraded lands. The financial toll of environmental degradation reached 4.6% of Mexico's GDP in 2021, emphasizing the urgent need for collaborative efforts to address and mitigate these challenges. The MEx30x30 Project will build upon this solid foundation to support six protected areas: two existing PA, three newly decreed PAs, and one complex of recently designated ADVCs (with eight certificates). These areas were selected by CONANP as focal areas for MEx30x30 for their biological importance, the presence of IP&LCs, and diversity of regions and thus ecosystems. See below for summary descriptions of each area and additional information in Annex 1. Through a comprehensive and integrated strategy, this initiative seeks to elevate the effectiveness of protected areas further, reinforcing their role as vital guardians of biodiversity and sustainable development engines for the benefit of nature and people. Balam-Kú Balam Kú is a 463,441.76 hectare Biosphere Reserve in the state of Campeche on the border with Guatemala. The word balam kú is composed of the Maya words: balam, 'jaguar'; and kú, 'temple'. It alludes to the three jaguars that are represented in the archaeological zone located within the BR. Balam Kú is a contiguous neighbor of the Selva Maya Biosphere Reserve decreed in 1990, which has almost half a million hectares. The Selva Maya, shared by Belize, Guatemala and Mexico, represents one of the most important ecological systems at a global level, because it is considered the largest continuous massif of humid and sub-humid tropical forest in Mesoamerica and the second largest tropical forest in America, after the Amazon Rainforest. Balam Kú is linked by bioclimatic corridors with Balam Kin and Calakmul Biosphere Reserve. Balam Kú is home to 889 people and two agrarian nuclei with indigenous households in Kilometer 120 and Hecelchakán. The vegetation in this area consists mainly of low deciduous and sub-deciduous forests, as well as wetlands. In the most arid zones, the vegetation can be xerophytic and be formed by thorny scrub and cacti. The conditions of the area allow the development of other types of vegetation characteristic of this zone such as the "bajos", which are generally low flooded areas that present distinctive plant associations. A number of species are endemic to the region, including 8 reptile species, 4 species of mammals, and 76 species of vascular plants. There are also a number of species that are priorities for conservation in Mexico, including the colorless juil (Rhamdia guatemalensis), the striped spiny iguana (Ctenosaura similis), the Yucatan spiny-tailed iguana (C. defensor), the swamp crocodile (Crocodylus moreletii), the masked duck (Nomonyx dominicus), sad pigeon (Patagioenas nigrirostris), blue-crowned parrot (Amazona farinosa) and dusky-headed parrot (Pyrilia haematotis). There are 19 species of amphibians, which represents 83 % of the state's amphibian diversity, and the area contains 21 % of the bat species distributed in Mexico. Main threats to the area include deforestation and illegal logging, forest fires, introduction of invasive exotic species, and climate change. Bajos del Norte Bajos del Norte is a national marine park in the Gulf of Mexico, covering 1,304,115 hectares. The reef areas of the northeastern end of the Yucatan Peninsula are transition zones between the Gulf of Mexico and the Caribbean Sea, therefore, this is considered a region of ecological connection and, therefore, of high biodiversity. The Bajos del Norte reefs are the second most relevant site as a larval source for areas in the northern, western and central Gulf of Mexico for several key fishery species for the region's economy. The area is characterized by its upwelling system and the so-called "loop current", both of which are responsible for the balance of nutrients in the Gulf of Mexico shelf and for the genetic connectivity and biological exchange of reef species, especially those of fishery value. It is one of the main grouper fish (Epinephelinae) reproduction sites in the Gulf of Mexico. Species richness represents 6 % and 25 % of the species recorded for the Gulf of Mexico and the Mexican Caribbean, respectively. Five species of sea turtles are present: loggerhead (Caretta caretta), white (Chelonia mydas), hawksbill (Eretmochelys imbricata), olive ridley (Lepidochelys kempii) and leatherback (Dermochelys coriacea), which are listed as Endangered, as well as being priority species for conservation in Mexico. The area also hosts the threatened rocky star coral (Orbicella annularis). The area is important to the 68,944 people (6% of whom are indigenous) that belong to fishing communities on the Yucatán coast. Two coastal fishing municipalities are relevant to Bajos del Norte: Progreso and Dzilam de Bravo. Main threats include pressure on fish stocks due to overfishing capture of the reproductive stock of larger and more fecund females in deep areas, and climate change. Chimalapas Los Chimalapas is a set of 8 Areas Voluntarily Destined for Conservation (ADVCs) in the State of Oaxaca, totaling 438,662.66 hectare. It is an ancestral indigenous territory of the Zoque people, and is home to 16,286 people, 38% of which are indigenous. The protection of biocultural resources in the Los Chimalapas Region is important for generating important biological corridors with other nearby Protected Areas, in addition to protecting the area from mining and fossil fuel extraction. Important species include Puma (Puma concolor), Ocelot (Leopardus pardalis), Tigrillo (Leopardus wiedii) and Jaguar (Panthera onca), quetzal, various species of parrots, macaws, and eagles, toucans (Rampasthus sulfurathos) and pajuil (Penelopina nigra), endemic plant species, endemic amphibians including Eleutherodactylus Lineatus macdougalli, Hyla sumichrasti, and Pseudoeurycea parva, and endemic reptiles such as Abronia bogerti, Abronia ornelasi, Adelphicos latifasciatus, Ctenosaura pectinata, Sceloporus internasalis, Anolis breedlovei, Anolis compressicaudua, Scincella gemmingeri, and Heloderma horridum. Main threats to the area include deforestation and land use change, forest fires caused by agricultural burning, and poaching. Additionally, there are historical land tenure disputes in the border strip with the state of Chiapas. Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit The 2,192,656.37 hectare Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit is a natural protected area in the states of Nayarit, Jalisco, Durango and Sinaloa. More than 50% of the area is covered by oak-pine and pine-oak forests, providing important hydrological environmental services. The forests are essential for water catchment and the recharge of aquifers for supplying population centers such as Puerto Vallarta and Bahía de Banderas. This watershed is also important for maintaining Marismas Nacional in Nayarit, which includes extensive mangrove areas. The water from this protected area makes agricultural and livestock farming possible and provides drinking and industrial water to 38 municipalities in Jalisco and Nayarit. Home to 52,498 people, nearly 50% of the population is indigenous, belonging to the Huicot or Gran Nayar region. Two of the four polygons that make up this protected area coincide with CONABIO's priority terrestrial regions, RTP-62 Sierra Vallejo-Río Ameca and RTP-60 Sierra Los Huicholes, as well as with the priority hydrological region: Río Baluarte - Marismas Nacionales. There are six areas of importance for bird conservation (AICAS): Quebradas de Sinaloa Nayarit and Durango, Guacamayita, La Michilia, Sierra de Valparaíso, El Carricito and Sierra Fría. The area hosts at least 15 endemic birds; around 80 species of mammals, of which more than 15 are endemic to Mexico and eight are protected by NOM 059; more than 60 species of reptiles and 16 species of amphibians, and of these, more than half are endemic to Mexico and at least ten are threatened. Main threats to the area include deforestation, land use change, forest fires, presence of forest pests and diseases (e.g., defoliator, bark stripper, and parasitic plants), expansion of unsustainable extensive cattle ranching activities, illegal extraction of flora and fauna, soil degradation, presence of invasive exotic species, and climate change. Papigochic Papigochic is a 222,763.85 ha protected area in the state of Chihuahua. The type of vegetation that characterizes Papigochic is mixed conifer and oak forests. It has some of the last relics of old-growth forests in the world. The area coincides with CONABIO's priority terrestrial regions, Alta Tarahumara-Barrancas and Bassaseachic, and the priority hydrological region, Río Yaqui - Bassaseachic Waterfall. In addition, there is an area of importance for bird conservation (AICAS): Papigochic. Although only 10% of its population of 6,907 people is indigenous, this protected area is the only one decreed on Rarámuri (Tarahumara) lands. The area is important for tourism and recreation and provides natural resources for the local population, mainly related to the use of timber forest species for the construction of houses, and fences, and for commercial purposes, as well as for fuel. Additionally, non-timber resources such as mushrooms and wild plants are used for food and medicine, and grasses, shoots and foliage are used for fodder. Main threats include deforestation, habitat modification or loss (reduction, fragmentation), natural phenomena (snowfall, north winds, hailstorms, cold fronts, rainfall, drought), forest fires, land cover conversion for the development of productive activities (forest exploitation, mining exploration and exploitation, agriculture, livestock), presence of forest pests, and population growth near forested lands. Sierra Tecuani The 348,140.97 hectare Sierra de Tecuani Biosphere Reserve, in the state of Guerrero, is a biological corridor for the jaguar in Mexico. The term tecuani is of Nahuatl origin and refers to the "man-eater", in allusion to the various species of felines identified in the area. The Sierra Madre del Sur is in the transition zone of the Nearctic and Neotropical regions, which favors the presence of a great diversity of species, including several microendemic vertebrates such as the tree frog (Charadrahyla tecuani), the Guerrero rattlesnake (Crotalus ericsmithi), the short-crested coquette (Lophornis brachylophus) and the tropical shrew of the Sierra Madre del Sur (Cryptotis goldmani), among others. It is considered a zone of high endemism that harbors viable populations of different species with some degree of threat. Twenty-five species of fungi, 338 plant species, 16 invertebrate species, and 120 vertebrate species are endemic. 28% of the species at risk in the entire Sierra Madre del Sur are present in Tecuani. The 18 ejidos and communities (population: 17,768) that are part of the protected area have diverse populations, including indigenous peoples. There is a high level of marginalization in some of the communities. Land-use change is one of the most significant threats to the area. The expansion of avocado plantations and cattle ranching exert considerable pressure on the forests, as they involve the clearing of large areas, from the lowlands to the mountain forests. Forest fires are another cause of the alteration Example of endangered species according to IUCN Red List of threatened species: Balam Kú; Bajos del Norte; CADRN 043 Nayarit; Chimalapas; Papigochic; Sierra Tecuani. Amazona albifrons, Ateles geoffroyi, Cairina moschata, Lithobates brownorum, Micrurus diastema, Panthera onca (Jaguar), Pionus senilis, Spizaetus melanoleucus, Tapirella bairdii, Tayassu pecari.; Caretta caretta, Chelonia mydas, Eretmochelys imbricata, Lepidochelys kempii, Dermochelys coriacea, Mobula birostris, Rhincodon typus.; Colinus virginianus, Falco peregrinus, Tilmatura dupontii, Amazona finschi, Euptilotis neoxenus, Crotalus pricei, Micrurus distans.; Amazona farinosa, Crax rubra, Electron carinatum, Harpyhaliaetus solitarius, Mycteria americana, Penelopina nigra, Pharomachrus mocinno, Psarocolius wagleri, Alouatta palliata, Ateles geoffroyi, Leopardus pardalis (ocelote) Panthera onca (jaguar), Puma concolor (puma) and Tapirus bairdii.; Rhynchopsitta pachyrhyncha, Nucifraga columbiana, Accipiter cooperii, Accipiter striatus, Buteo albonotatus, Buteo gallusanthracinus, Meleagris gallipavo, Cyrtonyx montezumae, Picoides arizonae, Cinclus mexicanus, Myadestes townsendi, Myadestes occidentalis, Falco peregrinus, Ridgwayia pinicola, Accipiter gentiles, Strix occidentalis, Euptilotis neoxenus, Aquila chrysaetos, aND Bubo virginianus.; Brachypelma albiceps, Brachypelma smithi, Craugastor omiltemanus, Bolitoglossa hermosa, Heloderma horridum, Crotalus culminatus, Accipiter atricapillus, Buteo platypterus, Sarcoramphus papa, Panthera onca, Choeronycteris mexicana..

Socio-economic Context of Project Area - Describe the broad economic, social and cultural context of, and local communities living in, the area of the proposed project and identify disadvantaged groups present in the area. Include statistical information on number of men, women, indigenous people, disadvantaged/vulnerable/disabled groups, economic/livelihood activity, household income - Describe how men and women access, use, manage and govern the natural resources that the project seeks to focus on. How could project activities affect or benefit women and men, and people with diverse gender identities where relevant? - Describe the extent of gender-based violence (GBV) and Sexual Exploitation, Sexual Abuse and Sexual Harassment (SEAH). Are GBV and SEAH relatively high at the national and project level? Is the project planning to introduce activities that may perpetuate or exacerbate GBV and SEAH? The MEx30x30 Project will support six protected areas: two existing PAs, three recently decreed PAs, and one recently designated ADVC complex (with eight certificates), all located in indigenous territories. Together, the six areas have a population of approximately 162,392 people: 49.80% women and 50.20% men. Of these, an estimated 24% of the population are indigenous. The PAs with the highest percentages of indigenous population three years of age and older who speak an indigenous language are C.A.D.N.R. 043 Nayarit, Balam-Kú, and Chimalapas complex, all with more than 30%. In contrast, those with the least indigenous presence are Bajos del Norte and Sierra de Tecuani, with 6% and 4.7%, respectively (INEGI, 2020). There are five indigenous regions where the Project's PAs are located. A general description of each follows, based on information provided by the National Institute of Indigenous Peoples (2020) and the National Commission for the Development of Indigenous Peoples (2006). Maya: Located in the extreme southeast of the country, in the Yucatan peninsula, combined by the states of Campeche, Quintana Roo, and Yucatan. The Maya maintain a social organization consisting of residential units composed of domestic groups, a nuclear family, or several other units distributed in different houses. In some cases, extended families may share expenses, as well as the work of the milpa. The vision of the world in this territory is closely related to the cultivation of corn in such a way that several representations and rituals are linked to this activity. The main subsistence activity is agriculture, which is practiced following, in some places, the slash-and-burn technique in rainfed crops and using axes, machetes, and planting sticks. They plant corn, beans, and squash. In some regions, they grow citrus, henequen, flowers, legumes, chili peppers, and vegetables, mainly for commercialization. Other activities include beekeeping, raising pigs and poultry, and fishing. Huicot or Gran Nayar: The name of the region derives from Huichol, Cora, and Tepehuano and designates the mountainous territory that encompasses the south of the state of Durango, the north of Jalisco, Nayarit, and part of Zacatecas, which is also known as the Gran Nayar region. Among the indigenous peoples that inhabit the Gran Nayar region, settlement patterns of enormous dispersion predominate, linked to their particular cosmological and belief systems, together with the prevailing geographic conditions, which is why the majority of its population lives in localities of less than 100 inhabitants. It is also one of the regions with the greatest backwardness at the national level, and the most significant proportion of the indigenous population is located in the primary sector, with 52.2%. Chimalapas: It is an ancestral indigenous territory of the Zoque people. The region's social structure responds to historical uses and customs, so it is identified in hierarchical order to the Communal Assembly as the highest instance, followed by the congregations - the local regulatory bodies for access to resources. The municipalities that make up the region have a high/very high marginalization index. More than 70% of the population is employed in the primary sector; therefore, agricultural activities are the most prevalent in the region. Montaña de Guerrero: As in the Huicot or Gran Nayar region, the Montaña region presents a balanced distribution among the indigenous groups that inhabit its territory, with the population of Nahua origin being the predominant with 33.7%, followed by Mixtec and Tlapanec languages with 29.8% and 25.9%, respectively. The minority group in the region, the Amuzgo, represents 86% of the total population. All of the region's municipalities are in a situation of high or very high marginalization, the latter being close to 80%. In this territorial delimitation, most of the employed indigenous population, around 60%, continues to work in primary sector activities. Consequently, the activities related to the secondary or tertiary sector are not very important since they do not exceed 20% of those employed by indigenous people (21.3% and 17.6%, respectively). Tarahumara: Its inhabitants call themselves Rarámuri, which means runners on foot. It is located in the part of the Sierra Madre Occidental that crosses the state of Chihuahua and the southwest of Durango and Sonora. The Sierra Tarahumara is formed by high mountains that reach 2,000 to 3,000 meters above sea level and deep ravines. It has been divided geographically into Alta and Baja Tarahumara. For the Tarahumara people, the primary subsistence activity is corn cultivation. Most of their daily and ceremonial life is organized around corn. The cultivated lands are scattered on small plateaus and hillsides, which influences the dispersion of the settlements, which are organized in rancherías. The fragility of the soil only allows agricultural work with hand tools and animal traction. It also represents a portion of the oldest forest management area in Chihuahua, with more than 50 years of timber harvesting, making this forestry activity the mainstay of the region's economy. Mex30x30 PAs have a rich biodiversity and an emblematic cultural fabric, which have profoundly shaped historical norms, traditional roles, and power dynamics on how natural resources are accessed and managed within households and communities, resulting in multifaceted disparities for women. In this context, gender roles allocate specific responsibilities to men and women. Therefore, men have often been assigned agriculture, fishing, and logging, which grant them primary access to land and natural resources. This access contributes to economic power and establishes their dominance in decision-making regarding resource utilization and management strategies. Meanwhile, women have been predominantly confined to domestic roles, restricting their access to educational opportunities and public spheres where crucial decisions are made, limiting their direct involvement in resource management decisions. In terms of the states that comprise the PAs, Oaxaca, Guerrero, and Campeche are the entities with the most significant gender gaps in education, i.e., Chimalapas Complex, Sierra de Tecuani, and Balam-Ku are the territories in which this situation may affect women's participation in the Project. Patriarchal structures also tend to prioritize the voices and contributions of men and reinforce male dominance in leadership positions, marginalizing women's representation and participation in community decision-making forums and hindering their ability to influence resource management policies and practices related to land use, water management, and conservation efforts. Consequently, the invaluable knowledge and perspectives that women bring remain largely untapped. Access to land and resources is fundamental for livelihoods in these areas, but there is also an unequal distribution based on gender, which perpetuates socio-economic disparities. Women often lack ownership or control over land, facing barriers to accessing resources critical for their economic well-being. Although the Agrarian Law recognizes that men and women can be ejidatarios, only three out of every ten people with ejido or communal land titles are women. In the states associated with the Project, Yucatan and Campeche have the widest inequality gaps since nearly 80% of the subjects of agrarian rights are men. Guerrero has the highest percentage of women landowners (34%), which offers slight opportunities to encourage the participation of this sector of the population in activities related to the Project. The percentage of the working-age population (15 years or older) working or actively seeking employment, women have significantly lower percentages than men. Even so, inequalities are most evident in Campeche (Balam-Ku), and Zacatecas and Durango (C.A.D.N.R. 043 Nayarit). Gender gaps significantly influence access and decision-making power related to natural resource management. Addressing these disparities requires challenging ingrained cultural norms, promoting gender equality, and creating tailored opportunities for women and youth to participate actively in decision-making processes. By leveraging women’s unique perspectives, communities can forge more resilient and equitable approaches to conservation, ensuring the preservation of Mexico’s natural heritage for generations to come. In terms of gender violence, although the national legal framework has been strengthened and resources allocated to address this problem have increased, Mexico remains one of the most violent countries for women, with percentages well above the world average and in seventh place among the 32 nations of Latin America and the Caribbean (UN Mexico, 2021 and ECLAC, 2022). 86% of the Mexican territory is under alert for femicide violence and the disappearance of women and girls. Likewise, according to the National Survey on the Dynamics of Household Relationships (INEGI, 2021). 70.1% of women aged 15 years and older have experienced violence in their lifetime (psychological, physical, sexual, economic or marital), and 42.8% in the last 12 months. Aguascalientes, Jalisco, Chihuahua, and Yucatán are the states where women report having experienced the most episodes of violence in their lives, with percentages above 70%. The set of existing gender gaps (e.g., land tenure, participation in governance bodies, unequal payments, unpaid employment and domestic care activities) keep women in culturally reinforced cycles of poverty that discourage self-organization and individual efforts to overcome. Project activities will be designed around understanding these constraints, providing meaningful opportunities that benefit women while minimizing the costs of accessing these opportunities. By increasing the participation of women in land-use planning, targeting women as beneficiaries and developers of conservation activities, providing technical assistance and capacity building, strengthening women’s engagement in project actions, reducing administrative requirements, avoiding land ownership requests, and ensuring equal distribution of benefits and opportunities, the Project will contribute challenging traditional norms on how women and men utilize natural resources. Other strategies will include identifying appropriate meeting locations and times to adapt activities around women’s schedules, developing tailor-made materials, and guaranteeing that women are not burdened with additional responsibilities (doubled or tripled workloads). Particular attention will be paid to the intersection of gender and other vulnerable sub-groups, for example, women who are Indigenous, LGBTQI, elderly, and have disabilities, among others.

Institutional Capacity - Describe the institutional experience in implementing environmental and social safeguards, gender and stakeholder engagement. - Indicate the number of staff dedicated (part/full-time) to safeguards, gender and stakeholder engagement. - Describe the capacity of the above staff (are they subject experts such as gender specialist or have they been trained in safeguards, gender and stakeholder engagement). (The EA/EE will be required to complete an ESMF capacity self-assessment during the PPG/PPF stage). Since 1998, FMCN has applied environmental and social standards to its projects. These have evolved alongside the policies and procedures of the World Bank, which has been the implementing agency for the four GEF-funded projects continuously coordinated by FMCN for 26 years. With the accreditation by GCF in 2019, FMCN integrated the World Bank Environmental and Social Standards published in 2018. They were incorporated into every project starting in 2019. In 2022, thanks to GCF Readiness support and with the accompaniment of KfW Development Bank, FMCN developed its Environmental and Social Policy and its Environmental and Social Management System (ESMS or SGAS, for its acronym in Spanish), which are being fully implemented in 2023. The Environmental and Social Policy is part of its Operations Manual and establishes FMCN's commitment to sustainable development, human rights, gender equality, and addressing climate change. It also sets the guiding principles that govern FMCN's environmental and social risk management and promotes meaningful, inclusive, gender-sensitive, and culturally appropriate participation in the projects FMCN supports. As part of these guiding principles, the E&S Policy considers: - compliance with applicable ES laws (including national laws and relevant international treaties and commitments) - respect for human rights - ES sustainability - work and decent working conditions (respecting federal laws and ILO standards) - biodiversity conservation - respect for indigenous peoples (considering active and effective participation during the life cycle of the projects) - protection of cultural heritage - gender equality - integration of activities to reduce the effects of climate change - stakeholder engagement, and - continuous improvement and best practices integration The E&S Policy also states FMCN’s exclusion list, establishing that the following activities will not be supported or financed: - Manufacture, purchase, or trade of any product or activity considered illegal according to Mexican laws or regulations and international conventions and agreements ratified by the country. - Manufacture, purchase, or trade-in ozone-depleting substances, polychlorinated biphenyl (PCB) compounds, hazardous chemicals, fertilizers, herbicides, pesticides, persistent organic pollutants (POPs) listed in the Stockholm Convention, substances classified by the World Health Organization as extremely hazardous and very hazardous, unbound asbestos fibers, and wildlife and wildlife products regulated by the Convention on International Trade in Endangered Species of Wild Fauna and Flora. - Manufacture, purchase, or trade-in arms, ammunition, explosives, or other military goods or technologies. - Manufacture, purchase, or trade of narcotics and tobacco. - Land acquisition. - Activities within protected areas (PAs) that are not included in their management programs and, for those PAs that do not have a management program, all activities considered within this exclusion list. - Activities that promote the change of land use, deforestation, or degradation in critical habitats or that put ecosystem services at risk. - Infrastructure that may promote conversion, deforestation, degradation, or any other alteration of critical habitats. - Mining and oil or gas exploration and development projects. - The use of Genetically Modified Organisms (GMOs) and invasive alien species without technical studies and corresponding authorizations. - The use of living organisms generated by artificial cloning. - Manufacture or trade in timber or other forest products that do not come from sustainably managed forests. - Marine fishing activities with nets over 2.5 km in length and activities that contravene the provisions on priority marine species subject to protection and conservation following the current National Fisheries Charter. - Activities that may violate human rights. - Activities involving forced labor and/or harmful child labor. - Activities that generate involuntary resettlement, especially of indigenous or Afro-Mexican groups. - Activities that affect the rights of indigenous peoples or local communities, especially land ownership, without the proper Free, Prior, and Informed Consultation (FPIC) process. - Activities affecting cultural heritage. - Activities that affect people's assets or generate restrictions on access to natural resources. - Activities carried out on land under litigation, dispute, or on ejido and/or communal lands that do not have the written approval of the assembly. - Activities affecting international waters or shared waters. - The use of resources to support proselytizing or electoral campaigns, as well as betting, gambling, casinos, and equivalent companies. The E&S Policy likewise details the constituent elements, including FMCN's applicable regulation, and environmental and social safeguards aligned with IFC's performance standards and other multilateral organizations. The E&S Policy also states the staff's roles and responsibilities. The Conservation and Sustainable Management Areas, which are in charge of the operation of the projects, are responsible for environmental and social management in the different stages of project implementation. The Research and Development Area is responsible for E&S functions at the institutional level. The Finance Area ensures that FMCN's investments comply with ESG standards. General Management (under the General Director) is accountable for fulfilling E&S responsibilities in each area. Internal Audit reviews the implementation of the processes and reports its findings to General Management and the Institutional Accompaniment Committee (CAI). Internal Audit Unit is also responsible for addressing complaints received formally through the Grievance Redress Mechanism established by the institution. FMCN's ESMS identifies the environmental and social risks for projects, sub-projects, and annual operating plans of protected areas, as appropriate. FMCN channels field support through sub-projects and Annual Operating Plans. The sub-projects are grants that FMCN allocates to local organizations legally constituted in response to the demand of stakeholders and according to a selection process based on calls for proposals and the quality of the proposals received. The Annual Operating Plans are donations that FMCN channels to protected areas through local organizations to support five-year plans elaborated by the personnel of the National Commission of Protected Areas with the support of FMCN. FMCN ESMS has an Environmental and Social Safeguards Assessment Sheet through which projects are categorized according to their environmental and social risk, an "automatic" recommendation for each aspect considered, and the evaluator includes additional comments or suggestions. The ESMS also describes the procedures to manage E&S risks at the level of sub-projects (grants) and Annual Operating Plans for protected areas. The activities identified to mitigate risks in the project are included in the yearly project plans and monitored during implementation. During monitoring, additional risks to those identified in the evaluation phase may be identified and must be managed through the design of complementary mitigation measures. These are included in the annual plans at the project or sub-project level. FMCN's E&S Policy and ESMS establish the objectives, guiding principles, and scope of meaningful stakeholder engagement. It states that FMCN seeks to ensure the meaningful, effective, and informed participation of key stakeholders at different territorial scales in the preparation and operation of projects. The involvement of these stakeholders is a regular and constant process throughout the life cycle of the initiatives, which must be carried out in an inclusive, gender-sensitive, and culturally appropriate manner, without discrimination and always ensuring that opportunities for participation are open to vulnerable groups (e.g., women, youth, senior citizens, indigenous peoples, Afro-Mexican population, and people with disabilities, among others). One of FMCN's guiding principles is respect for indigenous peoples, including avoiding adverse impacts by the supported projects, promoting benefits and opportunities, respecting and preserving their culture, and engaging indigenous peoples through active and effective participation through the lifecycle of the projects. FMCN E&S safeguard on Indigenous peoples (SAS7) establishes that FMCN and the implementing organizations will identify, through a social and environmental risk and impact assessment process (Environmental and Social Safeguards Assessment Sheet), all potentially affected Indigenous Peoples' communities within the area of influence of a project, subproject, or Annual Operating Plan, as well as the nature and severity of the expected direct and indirect economic, social, cultural, and environmental impacts on these peoples. The proposed mitigation actions are developed in consultation and with the informed participation of the affected Indigenous Peoples communities. These actions are part of the sub-projects to be financed planning. FMCN also has a Gender Policy, which is part of its Organizational Manual, to incorporate the gender perspective in a cross-cutting manner in the operation of FMCN and all its initiatives. This policy promotes women's empowerment and fosters equality between men and women in natural resource conservation, management, and restoration in a culturally appropriate way. Additionally, FMCN has a Policy on Protection against Sexual Exploitation, Abuse, and Harassment, which declares zero tolerance for these practices and places human dignity and women's right to a life free of violence at the center of FMCN's work. Both policies apply to the Assembly, the Board of Directors, the Committees, FMCN contracted staff, entities staff with contractual relationships with FMCN, project beneficiaries, suppliers, and consultants. To date, FMCN's staff dedicated to safeguards, gender, and stakeholder engagement include the following positions: Part-time - General Coordinator - Director of Research and Institutional Development - Director of the Sustainable Management Area - Internal Audit Full-time - Socio-Environmental Research Coordinator - Socio-Environmental Research Officer - Gender and Social Vulnerability Officer (Climate Change and Sustainable Production Projects) - Environmental and Social Management Officer - Environmental and Social Officer The above staff are environmental, social, and gender specialists and have received training in safeguards, gender, and stakeholder engagement, such as Grievance Redress Mechanism Online Course (GCF); Community Mediation Training (GCF); Meaningful Stakeholder Engagement - 13th Edition (IDB); Environmental and Social Framework - ESF Fundamentals (WB); E-learning Master Class on EIB Environmental & Social Sustainability Management (Frankfurt School Development Finance); Gender Mainstreaming (GGGI); Induction to gender equality (INMUJERES), among others.

Additional Information - Describe any risks or factors that may affect or contribute to the project implementing safeguard measures/plans. Insecurity: Over the last two decades, criminal violence and insecurity levels have increased considerably in different parts of Mexico. One of the key drivers of this trend is the illicit drug trade. Criminal organizations have diversified their revenue-generating portfolios towards the natural resources sector, such as mining and agricultural goods, given their abundance, economic importance, and ease of access. Criminal organizations are key for forming local political orders and economic development in rural settings. Criminal rule in such cases is facilitated by controlling natural resources, including fertile agricultural lands, illegal mining, protected areas, and illegal logging. In this context, access to natural resources is both a source of revenue for criminal groups and an essential strategy for establishing their hegemony at the local level. In communities’ dependent on these commodities, their capture bolsters the ability of criminal organizations to control other economic sectors as well as the local population. Security threats can be dynamic and multifaceted, involving a combination of criminal organizations, social issues, and historical grievances. It is crucial to consult recent and reliable sources for the latest information on specific conflicts, security issues, and threats in these regions to secure the safety of the people related to the Project, especially in Chiapas, Oaxaca, and Guerrero.

III. ESMF EXCLUSIONS

This section will help the CI-GEF/GCF Agencies to determine whether they can support a project. Please provide accurate answers and details including supporting documents, where requested. If you answered “Yes” to any of the questions (i-xiii) then the CI-GEF/GCF Agencies cannot support the project.

| Will the project: | Yes | No |
| --- | --- | --- |
| - Contravene major international and regional conventions on environmental issues? |  |  |
| - Propose to create or facilitate significant degradation and/or conversion of natural habitats of any type (forests, wetlands, grasslands, coastal/marine ecosystems, etc.) including those that are legally protected, officially proposed for protection, identified by authoritative sources for their high conservation value, recognized as protected by traditional local communities, or have significant negative socioeconomic and cultural impacts that cannot be cost-effectively avoided, minimized, mitigated and/or offset? |  |  |
| - Involve adverse impacts on critical natural habitats, including forests that are critical natural habitats, including from the procurement of natural resource commodities, except for adverse impacts on a limited scale that result from conservation actions that achieve a net gain of the biodiversity values associated with the critical natural habitat? |  |  |
| - Propose to carry out unsustainable harvesting of natural resources -animals, plants, timber and/or non-timber forest products (NTFPs)- or the establishment of forest plantations in critical natural habitats? |  |  |
| - Propose the introduction of alien species that can potentially become invasive and harmful to the environment, unless there is a mitigation plan to avoid this from happening? |  |  |
| - Involve involuntary resettlement, land acquisition, and/or the taking of shelter and other assets belonging to local communities, individuals or Indigenous Peoples? |  |  |
| - Contravene major international and regional conventions on human rights, including rights specific to indigenous peoples? |  |  |
| - Propose activities that result in the exploitation of and access to outsiders to the lands and territories of indigenous peoples in voluntary isolation and in initial contact? |  |  |
| - Propose the use and/or procurement of materials deemed illegal under host country laws or regulations or international conventions and agreements, or subject to international phase-outs or bans, such as: a. ozone depleting substances, polychlorinated biphenyls (PCBs) and other specific, hazardous pharmaceuticals, pesticides/herbicides or chemicals; and b. wildlife or products regulated under the Convention on International Trade in Endangered Species or Wild Fauna and Flora (CITES)? |  |  |
| - Propose the use and/or procurement of pesticides and hazardous materials that are unlawful under national or international laws, the generation of wastes and effluents, and emissions of short- and long-lived climate pollutants? |  |  |
| - Involves the removal, alteration or disturbance of any non-replicable or critical cultural heritage, or the use of any intangible cultural heritage without the Free, Prior and Informed Consent of the communities who it belongs to? |  |  |

IV. SIMPLIFIED APPROVAL PROCESS (GCF Projects ONLY)

Questions XIV through XXII are ONLY for GCF Projects pursuing the Simplified Approval Process (SAP). If you answer “Yes” to any of the questions below, your project will undergo further review to determine eligibility for the Simplified Approval Process.

| Will the project: | Yes | No |
| --- | --- | --- |
| - Involve associated facilities and require further due diligence of such associated facilities? |  |  |
| - Involve trans-boundary impacts including those that would require further due diligence and notification to downstream riparian states? |  |  |
| - Adversely affect working conditions and health and safety of workers or potentially employ vulnerable categories of workers including women or child labor? |  |  |
| - Generate hazardous waste and pollutants including pesticides and contaminate lands that would require further studies on management, minimization and control and compliance to the country and applicable international quality standards? |  |  |
| - Involve the construction, maintenance, and rehabilitation of critical infrastructure (i.e. dams, water impoundments, coastal and river bank infrastructure) that would require further technical assessment and safety studies? |  |  |
| - Involve the resettlement and dispossession, land acquisition, and economic displacement of persons and communities? |  |  |
| - Be located in protected areas and areas of ecological significance including critical habitats, key biodiversity areas and internationally recognized conservation sites? |  |  |
| - Affect Indigenous Peoples that would require further due diligence, free, prior and informed consent (FPIC) and documentation of development plans? |  |  |
| - Be located in areas that considered to have archeological (prehistoric), paleontological, historical, cultural, artistic, and religious values or contains features considered as critical cultural heritage? |  |  |

V. ENVIRONMENTAL AND SOCIAL SAFEGUARDS (ESS) SCREENING

This section will help the CI-GEF/GCF Agencies to determine the category of the project and the ESS Standards triggered by the project. Please provide accurate answers and details including supporting documents, where requested.

| ESS1: Environmental and Social Impact Assessment |  |  |
| --- | --- | --- |
| Will the project potentially: - cause significant adverse environmental and social impacts (which may affect an area broader than the project area) that are sensitive, diverse, or unprecedented? - cause adverse environmental and social impacts (which are site-specific and few if any of them are irreversible) on human populations or environmentally or socially important areas? NO (to all of the above) TO BE DETERMINED YES (to any of the above) If TBD or Yes, please provide details here. - Has a full or limited ESIA that covers the proposed project already been completed? NO YES (If Yes, answer the following) |  |  |
| - Is the assessment a: A FULL ESIA A LIMITED ESIA | Yes | No |
| - Does the assessment meet its terms of reference, both procedurally and substantively? |  |  |
| - 3. Does the assessment provide a satisfactory assessment of the proposed project? |  |  |
| - 5. Does the assessment describe specific environmental and social management measures (e.g., avoidance, minimization, mitigation, compensation, monitoring, and capacity development measures)? |  |  |
| - 6. Does the assessment identify capacity needs of the institutions responsible for implementing environmental and social management issues? |  |  |
| - 7. Was the assessment developed through a consultative process with key stakeholder & rightsholder engagement, including issues related to gender mainstreaming and Indigenous Peoples? |  |  |
| - 8. Does the assessment assess the adequacy of the cost of and financing arrangements for environmental and social management issues? |  |  |
| For any “no” answers, describe below how the issue has been or will be resolved or addressed. |  |  |
| ESS 2: Protection of Natural Habitats and Biodiversity Conservation |  |  |  |
| Will the project: (a) involve adverse impacts on Critical Habitats, including forests that are Critical Habitats, including from the procurement of natural resource commodities, except for adverse impacts on a limited scale that result from conservation actions that achieve a Net Gain of the Biodiversity values associated with the Critical Habitat? (b) contravene applicable international environmental treaties or agreements? (c) involved the utilization of genetic resources? (d) introduce or use potentially invasive alien species? (e) affect species identified as threatened at the local and/or global levels? (f) implement habitat restoration activities? NO (to all of the above) TO BE DETERMINED (TBD) YES (to any of the above) If TBD or Yes, please provide details here. In the case of Protected Areas, provide name, location, area size, management category, governance arrangement, and current management activities of protected areas being affected by the project. MEx30x30 will operate in five Protected Areas and one complex of Voluntary Conservation Areas (with eight certificates) supporting activities related to biological monitoring, restoration of degraded areas, community brigades, fire management, productive projects, ecotourism, and capacity building. |  |  |  |

ESS 3: Resettlement, Physical and Economic Displacement

Will the project (a) involve the voluntary or involuntary resettlement of people? Resettlement including relocation or loss of shelter. (b) restrict land use and access? (c) cause economic displacement of people? Economic displacement, including the loss of access to natural resources that lead directly or indirectly to the loss of traditional/subsistence livelihoods, including assets, social capital, cultural identity, among other impacts. NO (to all of the above) TO BE DETERMINED (TBD) YES (to any of the above) If TBD or Yes, please provide details here. PAs are established to safeguard natural ecosystems, biodiversity, and cultural heritage. While these areas play a crucial role in environmental conservation, they often impose restrictions on land use and access, resulting in the economic displacement of local communities that depend on these resources for their livelihoods. This displacement disrupts traditional lifestyles and can result in cultural practices and knowledge loss. MEx30x30 will not create new PAs or ADVCs. On the contrary, the Project will operate in five established PAs and the Chimalapas ADVCs, where agreements on constraints are already in place. Hence, the Project will not involve additional land use and access limitations. Instead, it will facilitate community-based conservation initiatives to ensure sustainable resource use and strengthen protected areas management. The Project will also build capacity and develop initiatives that provide economic opportunities for sustainable and equitable outcomes. ADVCs are voluntary strategies. In the case of ejidos and communities, the decision-making process is typically collective and democratic, involving the participation of all community members with land rights. Decisions are usually taken in the General Assembly, the highest decision-making body, composed of all adult members of the community. These assemblies are typically held regularly, often monthly or quarterly, and serve as forums for discussing and deciding essential matters. In many ejidos and communities, decisions are reached through consensus rather than a majority vote. This means that all members are encouraged to express their opinions and concerns, and efforts are made to find acceptable solutions. Before making decisions, members of the ejido or community engage in thorough discussions and debates to ensure that all viewpoints are considered. This process can be time-consuming but is essential for reaching agreements that reflect the interests of the entire community. While all members have the right to participate in decision-making, ejidos and communities may also elect representatives or delegates to negotiate on behalf of the community in certain situations, such as dealing with external entities or government agencies. Given that ejidos and communities typically manage collectively owned land and natural resources, decisions often revolve around their sustainable use and conservation. This may involve agreements on farming practices, forestry management, water allocation, or other resource-related issues.

ESS 4 : Indigenous Peoples

Will the project: - work in lands or territories traditionally owned, customarily used, or occupied by indigenous peoples? - cause impacts on land and natural resources, including restrictions on land use or loss of access to natural resources, subject to traditional ownership or under customary use or occupation, or the location of a project or program on such land or the commercial development of such natural resources? - cause relocation of Indigenous Peoples from land and natural resources subject to traditional ownership, or under customary use or occupation? - cause significant impacts on an Indigenous People’s cultural heritage that is material to the identity and/or cultural, ceremonial, or spiritual aspects of the affected Indigenous People's lives, or the use of such cultural heritage for commercial purposes? - include the commercial development of lands and natural resources central to Indigenous Peoples’ identity and livelihood, or commercial use of Indigenous Peoples’ Cultural Heritage? - restrict the access of Indigenous Peoples to parks and protected areas? - Work in territories where there is Indigenous Peoples in voluntary isolation or could result in undesired contact with IPs? NO (to all of the above) TO BE DETERMINED (TBD) YES (to any of the above) If TBD or Yes, please provide details here. MEx30x30 will operate in territories traditionally owned, customarily used, or occupied by indigenous peoples (Figure 5).

ESS 5: Resource Efficiency and Pollution Prevention

Will the project: - promote the trade in or use of any substances listed under the Stockholm Convention on Persistent Organic Pollutants, or other chemicals or hazardous materials subject to international bans, restrictions or phaseouts due to high toxicity to living organisms, environmental persistence, potential for bioaccumulation, or potential depletion of the ozone layer, consistent with relevant international treaties and agreements? - generate wastes and effluents, and emissions of short- and long-lived climate pollutants? - involve pest management measures, Integrated Pest Management or Integrated Management of Vectors and Intermediate Hosts? - procure pesticides? - use energy, water and other resources and material inputs, where significant water consumption is involved and would cause adverse impacts on communities, other water users, and the environment? NO (to all of the above) TO BE DETERMINED (TBD) YES (to any of the above) If TBD or Yes, please provide details here. FMCN’s exclusion list states that it will not support or finance the “Manufacture, purchase, or trade-in ozone-depleting substances, polychlorinated biphenyl (PCB) compounds, hazardous chemicals, fertilizers, herbicides, pesticides, persistent organic pollutants (POPs) listed in the Stockholm Convention, substances classified by the World Health Organization as extremely hazardous and very hazardous, unbound asbestos fibers, and wildlife and wildlife products regulated by the Convention on International Trade in Endangered Species of Wild Fauna and Flora.” Project initiatives may involve capacity-building regarding integrated pest management measures, such as using native and diverse plant species, promoting biodiversity, maintaining healthy soil, and controlling invasive species.

ESS 6: Cultural Heritage

Will the project implement activities that affect cultural heritage (both tangible and/or intangible), including archaeological, paleontological, historical, architectural, and sacred sites including graveyards, burial sites, and sites with unique natural values? NO TO BE DETERMINED (TBD) YES If TBD or Yes, please provide details here. Mexico has strict laws and regulations to protect its cultural heritage, including archaeological sites. The Federal Law on Monuments and Archaeological, Artistic, and Historical Zones grants the government authority to designate and preserve archaeological sites. The National Institute of Anthropology and History (INAH) is the primary governmental organization responsible for the conservation, protection, and management of archaeological sites throughout Mexico, and for conducting research, conservation, and restoration activities. They also regulate site access and implement measures to protect them from damage or looting. INAH often collaborates with local communities living near archaeological sites, including consulting with indigenous communities on matters related to site management, involving residents in conservation efforts, and promoting sustainable tourism that benefits local economies. That is the case of the Balam Kú Archaeological Zone in the Balam-Kú Protected Area. The Project will not affect any cultural heritage (tangible or intangible). On the contrary, it will respect and preserve traditional knowledge and practices (e.g., the use of medicinal plants by indigenous peoples), complying with local, national, and international regulations related to cultural heritage protection. Additionally, the Project will monitor and supervise the project activities continually to identify and promptly address any foreseen impacts. If any cultural heritage is identified, measures to protect it will be implemented to prevent adverse effects and facilitate rapid response.

ESS 7: Labor and Working Conditions

Does the EA/EE have in place the necessary policies, procedures, systems and capabilities to ensure that: - the fundamental rights of workers, consistent with the International Labour Organization’s (ILO) Declaration on the Fundamental Principles and Rights at Work are respected and protected? - written labor management procedures are established in accordance with applicable national laws? - workers are provided with clear and understandable documentation of employment terms and conditions, including their rights under national law to hours of work, wages, overtime, compensation and benefits? - workers are provided regular and timely payment of wages; adequate periods of rest, holiday, sick, maternity, paternity, and family leave; and written notice of termination and severance payments, as required under national laws and the labor management procedures? - decisions relating to any aspect of the employment relationship, including recruitment, hiring and treatment of workers, are made based on the principles of non-discrimination, equal opportunity and fair treatment, and not on the basis of personal characteristics unrelated to inherent job requirements? - appropriate measures are in place to prevent harassment, intimidation, and exploitation, and to protect vulnerable workers, including but not limited to women, children of working age, migrants and persons with disabilities? - workers who participate, or seek to participate, in workers’ organizations and collective bargaining, do so without interference, are not discriminated or retaliated against, and are provided with information needed for meaningful negotiation in a timely manner? - forced labor and child labor are not used in connection with the project or program? - occupational health and safety (OHS) measures are applied to establish and maintain a safe and healthy working environment, including supply chain workers? - workers are informed of applicable grievance and conflict resolution systems provided at the workplace level? - workers may use these mechanisms without retribution, and the grievance and conflict resolution systems does not impede access to other judicial or administrative remedies available under the law or through existing arbitration procedures, or substitute for grievance systems provided through collective agreements? NO (to any of the above) TO BE DETERMINED (TBD) YES (to all of the above) If TBD or Yes, please provide details here. FMCN is the Executing Agency for the Project. It has policies, procedures, systems, and capabilities to ensure compliance with all the terms above, reflected in its Organizational Manual, Operations Manual, and Risk Control Manual, available at https://fmcn.org/es/quienes-somos/transparencia. In this regard, FMCN has proven experience concerning labor and working conditions to: - Promote fair treatment, non-discrimination, and equal opportunity for workers. - Establish, maintain, and improve the worker-management relationship. - Promote compliance with national employment and labor laws. - Protect workers, including vulnerable categories of workers such as children of working age, migrant workers, workers engaged by third parties, and workers in the supply chain. - Promote safe and healthy working conditions and the health of workers. - Avoid the use of forced labor and child labor. - Advocate for organizations implementing grants to comply with Mexican Labor Law and best hiring practices. The Mexican Labor Law is recognized internationally as one of the most complete ones in the subject. FMCN has a strong track record of adhering to it and helping associates and recipients to understand and follow its requirements. FMCN has an E&S standard related to labor and working conditions based on the lessons learned in applying the Mexican Labor Law.

ESS 8: Community Health, Safety and Security

Please complete the following Risk Assessment Tool to determine community health, safety and security risks and their mitigation measures. Guidance on how to complete the Tool can be found in Appendix IX of the ESMF (Version 7). Try to identify risks in a way that recognizes diversity, disadvantaged groups that might be disproportionally affected or affected in different ways to others. For example, elderly and people with disabilities will be more impacted by natural hazards, or women having more exposure to accidents from having less access to Personal Protective Equipment (PPE). Some of the CHSS risks may include but are not limited to: - Natural hazards/disasters such as flooding, drought, wildfires, volcanic eruptions, earthquakes, typhoons and hurricanes; - Climate change and ecosystem service stress such as increased temperatures; - Exposure to Hazardous Materials such pesticides and banned chemicals; - Exposure to communicable/vector-borne disease such as Ebola, COVID-19, and Malaria; - Security related risk such as working in areas of conflict or post-conflict or with illegal activities (e.g. poaching, growing illicit crops), context with ongoing human rights violations, human-wildlife conflict, frequent and violent protests/demonstrations, working with armed rangers; - Safety related risks such as failure of structural elements or infrastructure built by the project, lack of PPE; and - Gender-Based Violence (GBV) and Sexual Exploitation, Abuse and Harassment (SEAH). Community Health, Safety and Security Threat; Likelihood; Impact; Risk; Risk Rating; Mitigation Measures. - Natural hazards/disasters such as flooding, drought, wildfires, and hurricanes; Possible (3); Moderate (3); 9; Medium; Monitoring and disaster preparedness.. - Exposure to communicable/vector-borne disease such as COVID-19, and Malaria; Possible (3); Moderate (3); 9; Medium; Regular monitoring of guidance from national and local public health authorities, World Health Organization (WHO), and Centers for Disease Control and Prevention (CDC). Use of online engagement platforms, use of disease prevention protocols including testing, monitoring of status.. - Security related risk such as working in areas with illegal activities (e.g. poaching, growing illicit crops); Likely (4); Moderate (3); 12; High; Monitoring of risk at national and local level and coordination with relevant authorities. Development and training on safety protocols, including planning for evacuation contingencies. Adapt activities to situations involving risk, e.g., cancellation of field visits in areas experiencing increased conflict.. - Threats to human security through the risk of escalation of personal or communal conflict and violence that could be caused or exacerbated by the project; Possible (3); Moderate (3); 9; Low; Stakeholder consultation to develop programming that is sensitive to community dynamics. Coordination with appropriate authorities. Ongoing monitoring of risk and adaptation of activities as necessary.. - Project-level Gender-Based Violence (GBV) and Sexual Exploitation, Abuse and Harassment (SEAH); Possible (3); Moderate (3); 9; Medium; Provide basic training to project teams on how to respond if incidents are reported/disclosed. Ensure that the project’s GRM is designed to respond to project related incidents.. - Exposure to safety hazards related to community brigades; Possible (3); Moderate (3); 9; Low; The project will promote proper training for incidents, accidents, and emergency response. The communities will be guided to adhere to the regulations and protocols established to respond effectively to emergencies and safeguard the safety of people and the communities.. Total; 57. Average; 9.5. Overall risk rating to project-affected communities; Medium.

ESS 9: Private Sector Direct Investments and Financial Intermediaries

Will the project make either direct investments in private sector firms or Endowment Funds, or channels funds through Financial Intermediaries (FIs)? NO TO BE DETERMINED (TBD) YES (to any of the above) If TBD or Yes, the proposed fund/FI/firm would be required use this Screening Form to conduct a screening on the portfolio of the proposed investment. Under Component 3, endowment funds will ensure permanent funding for five decreed PAs (Balam-Kú, CADRN 043 Nayarit, Papigochic, Bajos del Norte, and Sierra Tecuani), and one ADVC complex (ADVC Chimalapas) as models for improved livelihoods based on biodiversity conservation. MEx30x30 will build on Fund for Protected Areas (FANP) institutional arrangements, recognized as best practice by GEF project completion reports and GEF innovation policy notes. In 1997 the first GEF project in Mexico created the FANP in FMCN. FANP is an endowment placed at FMCN, whose interests are allocated to priority protected areas in the country. It is the result of a public-private partnership between CONANP and FMCN established through collaboration agreements that have been renewed through five federal administrations in 26 years. FANP started channeling the annual interest of US$16.48 million in 1998 to ten PAs. Today, its capital has reached US$165 million, which supports 55 PAs. Non-endowment funds support an additional 15 PAs. In 2024, FMCN will be channeling a projected US$10 million to these 70 PAs, under the management of CONANP, for strategic activities such as biological monitoring, restoration of degraded areas, community brigades, fire management, productive projects, ecotourism, and capacity building. FANP operation is overseen by the FANP Technical Committee (CTFANP), established in 1997 and will have its 92nd meeting in April 2024. According to its by-laws, CTFANP comprises of nine members selected by the National Council of Protected Areas (CONAP) and ratified by the FMCN Board, representing the social, private, public, and academic sectors. CTFANP is part of FMCN´s legal structure, reporting to the FMCN Board and CONAP. - By law, CONAP is an advisory body on PAs to the Environmental Ministry. It has 30 members from the public, private, social, and academic sectors and has held 62 meetings since it was first established in 1996. CONAP is currently renewing its membership to achieve gender balance. - The FMCN Board comprises of seven members (four women and three men) that report to a 25-member Assembly composed of private, public, and social sectors (11 women and 14 men). By statute, CONANP cannot receive funds directly. Therefore, FMCN will manage funding for project activities implementation led by CONANP. FMCN is recognized for its administrative capacities and conducts all FANP procurements. FMCN Operations Manual reflects lessons learned in 26 years FANP and describes its procurement procedures, project cycle, reporting, and oversight following the environmental, social and gender safeguards regulations; the Operations Manual states the procedures for expenses for projects and sub-projects. In MEx30x30, FMCN will execute all Project components. Components 1 & 2 primarily involve capacity building for CONANP and fundraising to close the financial gap. Component 3 focuses on implementing restoration, conservation, and sustainable management activities in PAs and ADVCs through the FANP. For Component 3, FMCN will manage the economic resources and supervise their use. At the same time, CONANP will ensure that the resources are used for strategic conservation activities in the field. Each participating PA prepares an Annual Operating Program (POA), which goes through an Environmental and Social Safeguards Screening, and the FANP’s Technical Committee (CTFANP) reviews, approves, and oversees its operation (Figure 6). FMCN launches open and public calls for proposals for Legally Constituted Local Organizations (OLLC) to administer POA resources, providing advice, training, and oversee the optimal use of resources of each PA. FMCN will hire a technical analyst in its Conservation Area and an administrative analyst in its Finance Area to support CONANP in the development of Annual Operating Plans (POAs). POAs will be derived from five-year plans developed by CONANP with the support from project staff. CTFANP will select local organizations to administer the POAs per PA. Local organizations work with CONANP to break POAs into weekly plans, proceed to spend funds accordingly, prepare administrative reports and support CONANP with technical reports (Figures 7 and 8). FMCN´s Conservation Area will coordinate MEx30x30 reports. FMCN has an Investment Committee composed of seven finance specialists who oversee asset investment according to the Investment and Spending Policy included in Control Risk Manual. They rely on an independent financial advisor who presents investment options according to the requirements of each project and a long-term vision. The Finance Area at FMCN ensures that the decisions made by the Investment Committee are executed. The independent financial advisor provides instructions to the custodian for the purchase and sale of instruments. The custodian and independent financial advisor selection is reviewed every five years. FMCN closed 2023 with a 17.63% annual return and an endowment of US$192.5 million. In the last twenty years, FMCN´s endowment has had an average yearly return of 5.63% in US$ and is invested almost fully in financial instruments with an overall A rating grade for ESG standards (MSCI classification). Figure 6. Environmental and Social Safeguards System applied during POA design, implementation, and monitoring. Figure 7. Project flow of funds. Figure 8. Government bodies involved in MEx30x30.

ESS 10: Climate Risk and Related Disasters

Please refer to guiding questions in Appendix A to help answer the questions below: Describe the climate projections for the country or region, or if possible, for the specific location of the project for the next 30 years from the start date of the project. Mexico is highly vulnerable to climate change: rising temperatures, reduction in rainfall levels, intense storms, increased severity of hurricanes, floods, and fires, and rising sea levels. In the past 20 years alone, the number of extreme weather events in Mexico grew from 3.5 to 5.8 events per year, on average, impacting over 557,000 people nationwide, with storms and floods being the most common disasters. Climate change's social and economic impacts are high, and projections are not encouraging. When the average temperature increases by only 1.0°C, Mexico's per capita GDP growth would decrease between 0.77% and 1.76%. Describe the relevant potential hazards (e.g. heavy rainfall leading to flood, low rainfall leading to drought, temperature changes which could lead to heat waves, sea-level rise, or changes in other extreme events such as hurricanes and cyclone) that could prevent the project from achieving its objectives and/or outputs. Climate change is undoubtedly one of the greatest threats to biodiversity and ecosystem services (Table 2). The predicted increases in temperature and changes in both total precipitation and precipitation seasonality will likely affect species’ ranges, interactions, and even survival. In Mexico, temperature is predicted to become warmer across PAs by 2050, with more significant increases expected in arid regions that already experience high temperatures. Although the species within these types of PAs are adapted to high temperatures, further increases might represent additional stress, particularly those near their upper thermal limits. Rising temperatures in PAs located in mountainous regions and close to mountaintops are expected to exhibit severe impacts as geographic areas and, therefore, suitable habitats decrease at higher altitudes, impeding the migration of species. Other related climate risks that affect PAs involve water stress due to increasing temperatures, flooding due to more intense and frequent storms, alterations in the distribution and behavior of pests, and wildfires due to varying temperature and precipitation patterns. Specific mitigation measures include incorporating climate-resilient species and practices to adapt to changing conditions. Reducing fuel loads and implementing other fire management actions in priority sites vulnerable to wildfires will also be necessary. Table 2. Main climate hazards for MEx30x30 protected areas. Source: https://thinkhazard.org Protected Area; Climate hazards. River Flood; Coastal Flood; Landslide; Cyclone; Extreme heat; Wildfire; Water scarcity. Papigochic; Very low; nd; Low; High; Medium; High; Medium. C.A.D.N.R. 043 Nayarit; Very low; nd; High; High; Medium; High; Medium. Balam-Kú; High; High; Very low; High; High; High; Low. Bajos del Norte; -; -; -; -; -; -; -. Sierra Tecuani; Very Low; nd; High; High; Medium; High; Low. Chimalapas complex; Low; Medium; High; High; High; High; Low. Describe the current and projected exposures, vulnerabilities, and adaptive capacities (e.g. technical, institutional, financial) and how these could prevent the project from achieving its objectives and/or outputs. The main climate hazards that can affect project implementation include floodwaters, coastal floods, landslides, hurricanes wildfires, extreme heat, and water scarcity. These climate hazards may impose operational risks. For example, floodwaters, coastal floods, landslides, and hurricanes can damage roads, hindering access to the protected areas and delaying Project activities. Wildfires may also lead to the displacement of nearby communities, impacting project stakeholders and potentially halting work needs until conditions improve. Nevertheless, as the Project will work in different areas, by means that activities are not concentrated in just one location, operations could be sustained in the other PAs and ADVCs till conditions improve in the affected zone. Further, high temperature increases, wildfires, and droughts may undermine conservation efforts and restoration actions. The Project will enhance efficient water management strategies and prioritize using drought-resistant crop varieties and climate-resilient native species to reduce the Project's vulnerability to these climate hazards. Further, the Emergency Fund will enhance preparedness and emergency response planning to minimize the impacts of climate-related disasters. Despite climate hazards, the Project has different adaptive capacities to achieve its objectives. Mexico has developed national and local policies that support climate adaptation and mitigation efforts. CONANP has a Strategy towards 2040 (S-2040), a Climate Change Strategy for Protected Areas (ECCAP, for its acronym in Spanish), and a Special Climate Change Program. These institutional guides incorporate the concepts of adaptation, mitigation, resilience, vulnerability, risk, and landscape connectivity to increase PAs' adaptive capacity and mitigate climate change through coordinated multisector participation, gender mainstreaming, ecosystem-based adaptation, and disaster risk reduction. The Project "Strengthening the effectiveness of the management and resilience of Protected Areas to protect biodiversity threatened by Climate Change" (Resiliencia), implemented in 17 PAs, also left valuable lessons learned. For example, the inclusion of climate change as a cross-sectional issue in PA management results in substantial improvements in communicating the importance of PAs to the public, encouraging effective inter-institutional collaboration, involvement of local stakeholders, and facilitating funding for PA protection. Promoting participation mechanisms such as the Advisory Councils in the PAs also made climate change a significant issue for implementing adaptation measures. All these strategies pave the way for institutional adaptation and climate change mitigation that will be used and scaled up during the Project's lifetime. What mitigation measures have been identified and incorporated into the design of the project/planned for the implementation phase to reduce the likelihood and/or consequences of risks or to respond to consequences so as to ensure that the project achieves its objectives and/or outputs? PAs are a natural solution that contributes to reducing vulnerability to climate change and mitigating carbon dioxide emissions. Through their management, priority ecosystems (e.g., mangroves, coral reefs, forests) are protected and maintained, shielding populations against hurricanes, floods, landslides, and other hydrometeorological events (adaptation). Coastal wetlands contain large carbon deposits, and oceans have an immense capacity to capture and store carbon (mitigation). PAs also promote habitat connectivity (ecological flows and biological corridors) within areas and increase the ability of species to shift their distributions as climate changes. MEx30x30 will integrate climate-resilient design principles into the project, considering the potential impacts of extreme weather events, rising temperatures, and changing precipitation patterns. For example, the Project will: - Strengthen the capacities for CONANP to face adverse climate phenomena and increase its ability to effectively manage natural resources and flora and fauna to offer significant opportunities for climate change adaptation and mitigation. - Implement sustainable natural resource management practices to conserve and protect ecosystems and maintain their resilience to climate change, which is crucial in mitigating climate change and reducing vulnerabilities, considering nature-based solutions to enhance resilience, such as the use of climate-resistant native species. - Involve local communities in project planning and implementation to gain insights into their vulnerabilities and needs. - Build local capacity to respond to and recover from climate-related events, empowering stakeholders to become more resilient, such as emergency and fire management brigades. - Create early response mechanisms enabling stakeholders to timely response, such as the establishment of an emergency fund. - Stay informed about relevant climate change regulations and standards, ensuring the project incorporates latest best practices. Additionally, for Components 1 and 2, the Project will: - Develop a long-term sustainability plan for the Project beyond the funding period. It includes identifying sustainable financing mechanisms, securing ongoing support from stakeholders and donors, and integrating climate change adaptation into protected area management policies and plans. - Implement an adaptive management approach that allows for flexible decision-making and adjustment of Project activities in response to changing environmental conditions. It ensures that the Project remains effective and relevant in the face of climate change impacts. - Implement a robust monitoring and evaluation framework to track the effectiveness of project interventions within protected areas. Regularly assess project progress, adapt strategies as needed, and communicate results transparently to stakeholders and donors. - Exchange lessons learned, best practices, and scientific findings to enhance the effectiveness of climate change adaptation efforts in protected areas. For Component 3, the Project will: - Implement ecosystem restoration activities within the protected areas to enhance their resilience to climate change. It may include reforestation, habitat restoration, soil conservation, and the establishment of climate-resilient species. - Empower local communities to actively participate in conservation efforts and sustainable livelihood activities within protected areas. It fosters a sense of ownership and stewardship, ensuring the Project's long-term viability. - Build local communities, stakeholders, and relevant authorities' capacities throughout the Project's lifecycle to understand and address climate change impacts on protected areas. If one or more risks are accepted, please provide a justification.

Appendix A. Climate risk and related disaster assessment tool (adapted from FAO).

The checklist below presents some guiding questions on hazards, exposure, vulnerability and adaptive capacity (see definitions in Appendix XI of the ESMF Version 7) for completing the climate screening section of the Safeguard Screening Form:

| Existing Hazards Guiding Questions: | Yes | No | TBD |
| --- | --- | --- | --- |
| Observed climate and weather hazards in the project area: |  |  |  |
| Extreme temperature (heat/cold) | ☐ | ☐ | ☐ |
| Extreme precipitation and flooding | ☐ | ☐ | ☐ |
| Agricultural Droughts and/or dry spells | ☐ | ☐ | ☐ |
| Storms (Tropical storms, snowstorms, hailstorms, dust storms, etc.) | ☐ | ☐ | ☐ |
| Winds (Typhoons, Cyclones, Hurricanes, Tornadoes, Harmattan) | ☐ | ☐ | ☐ |
| Sea level rise (from global warming and storm surges) | ☐ | ☐ | ☐ |
| Other natural hazards observed in the project area: |  |  |  |
| Earthquakes | ☐ | ☐ | ☐ |
| Tsunamis | ☐ | ☐ | ☐ |
| Volcanic eruptions | ☐ | ☐ | ☐ |
| Landslides or avalanches | ☐ | ☐ | ☐ |
| Wildfires | ☐ | ☐ | ☐ |
| Salinization | ☐ | ☐ | ☐ |
| Ocean acidification | ☐ | ☐ | ☐ |
| Projected Hazards Guiding Questions | Yes | No | N/A |
| Do future climate scenarios foresee an incremental increase of potential hazards and climate change compared to the baseline that may affect the project over its lifetime? |  |  |  |
| Extreme temperature | ☐ | ☐ | ☐ |
| Extreme precipitation and flooding | ☐ | ☐ | ☐ |
| Agricultural Droughts and/or dry spells | ☐ | ☐ | ☐ |
| Change in temperature | ☐ | ☐ | ☐ |
| Change in rainfall | ☐ | ☐ | ☐ |
| Exposure Guiding Questions | Yes | No | N/A |
| Is the project located in high exposure areas? |  |  |  |
| Low-lying areas (valleys or coastal zones) | ☐ | ☐ | ☐ |
| Arid and semi-arid zones | ☐ | ☐ | ☐ |
| Mountains zones and permafrost areas | ☐ | ☐ | ☐ |
| Are the agricultural systems (crops, livestock, fisheries, forests) targeted by the project affected by climate related hazards? |  |  |  |
| Is crop productivity affected by rainfall variability, changes in temperature or pests and diseases? | ☐ | ☐ | ☐ |
| Is livestock productivity affected by rainfall variability, changes in temperature or parasites and diseases? | ☐ | ☐ | ☐ |
| Is fisheries productivity affected by ocean acidification, changes in sea temperature or variation of water salinity? | ☐ | ☐ | ☐ |
| Is forest productivity affected by wildfires, diseases, rainfall variability or changes in temperature? | ☐ | ☐ | ☐ |
| Is any stage of the agricultural value chain (production, storage, processing and marketing) affected by climate related hazards? | ☐ | ☐ | ☐ |
| Vulnerability Guiding Questions | Yes | No | TBD |
| Is the target population in the project area living below poverty line? | ☐ | ☐ | ☐ |
| Are the livelihoods of the target population sensitive to climate change? | ☐ | ☐ | ☐ |
| Is the target population income exclusively from agriculture? | ☐ | ☐ | ☐ |
| Is the population migrating due to food insecurity as a consequence of climate change? | ☐ | ☐ | ☐ |
| Is the project targeting sensitive groups (indigenous people or other marginalized groups) that are likely to be affected by climate change? | ☐ | ☐ | ☐ |
| Is climate change affecting certain groups more than others in the project area? | ☐ | ☐ | ☐ |
| Adaptive Capacity Guiding Questions: | Yes | No | TBD |
| Does the target population have access to climate information? | ☐ | ☐ | ☐ |
| Are there any early warning systems in the project area to anticipate and respond to climate-related events and disasters or climate-driven pest and diseases? | ☐ | ☐ | ☐ |
| Does the government or other institutions support the target population/communities with the necessary social and economic resources to prepare for or respond to climate-related events? | ☐ | ☐ | ☐ |
| Is the target population carrying out self-adaptation? | ☐ | ☐ | ☐ |
| Do policies exist that make financial credit, loans and agricultural insurance available? | ☐ | ☐ | ☐ |
| Project Modulation of Risks Guiding Questions: | Yes | No | TBD |
| - Policies and planning |  |  |  |
| Does the project support the integration of climate into national policies and planning? | ☐ | ☐ | ☐ |
| Does the project support the increased use of climate data and information in national long term and strategic planning? | ☐ | ☐ | ☐ |
| - Capacity building, training and outreach |  |  |  |
| Would the project invest in institutional development and capacity-building for national institutions involved in climate related activities? | ☐ | ☐ | ☐ |
| Would the project invest in increased information and dissemination of climate-related information to target groups? | ☐ | ☐ | ☐ |
| Does the project have opportunities to strengthen rural and indigenous climate risk management capabilities? | ☐ | ☐ | ☐ |
| Does the project support capacity of target groups to utilize and apply climate services at the farm level? | ☐ | ☐ | ☐ |
| - Data gathering, monitoring and information management |  |  |  |
| Will the project support the infrastructure and technology necessary to monitor climate variables and collect data required from climate impact assessment and modelling? | ☐ | ☐ | ☐ |
| Will the project support the national institutions to develop the skills required to monitoring and collect climate related information? | ☐ | ☐ | ☐ |
| Will the project support development of databases and repositories of climate information? | ☐ | ☐ | ☐ |
| - Mitigation |  |  |  |
| Will the project invest in measures that will reduce or mitigate emissions of GHGs from the energy sector? | ☐ | ☐ | ☐ |
| Will the project invest in measures to reduce or mitigate emissions of GHGs from livestock or agricultural production (e.g. rice production) | ☐ | ☐ | ☐ |
| Will the project invest in measures to reduce or mitigation emissions of GHGs through reforestation or land use change? | ☐ | ☐ | ☐ |
| Will the project invest in renewable energy and green technologies? | ☐ | ☐ | ☐ |
| Will the project invest in other measures to reduce or mitigate GHG emissions? | ☐ | ☐ | ☐ |
| - Adaptation |  |  |  |
| Will the project invest in climate smart agriculture activities? | ☐ | ☐ | ☐ |
| Will the project promote climate resilient practices for crops, livestock and fisheries? | ☐ | ☐ | ☐ |
| Will the project promote sustainable natural resources management? | ☐ | ☐ | ☐ |
| Does the project support Nature-based Solutions for climate change and disaster risk reduction? | ☐ | ☐ | ☐ |
| Will the project invest in agricultural insurance? | ☐ | ☐ | ☐ |

CI-GEF GENDER MAINSTREAMING PLAN (GMP)

The Gender Mainstreaming Plan provides information, analysis, and specific actions to ensure that gender dimensions are fully integrated into the project. It consists of two parts: (1) a Gender Analysis/Assessment, and (2) a Gender Action Plan. The Gender Analysis/Assessment identifies and describes relevant gender differences, gender differentiated impacts and risks, and opportunities to address gender gaps and promote the empowerment of men and women within the project context. The Gender Action Plan details any corresponding gender-responsive measures to address those differences, impacts and risks, and opportunities. Completion of a Gender Analysis/Assessment and Gender Action Plan is a requirement for all GEF and GCF funded projects as described under the CI-GEF/GCF Project Agencies’ Policy on Gender Mainstreaming.

The CI-GEF/GCF Agencies recognize the wide range of projects and this GMP is designed to be flexible and adaptable to the project size, scope, and context. For additional guidance on gender requirements within GEF + GCF projects, please also refer to:

Guidance to Advance Gender Equality in GEF Projects + Programs: https://www.thegef.org/sites/default/files/publications/GEF%20Guidance%20on%20Gender.pdf

Mainstreaming Gender in GCF Projects:

https://www.greenclimate.fund/sites/default/files/document/guidelines-gcf-toolkit-mainstreaming-gender_0.pdf

SECTION I: Project Information

A. Basic Project Profile

| PROJECT TITLE: | Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |
| --- | --- | --- | --- |
| GEF/GCF PROJECT ID: |  | PROJECT DURATION: | 60 months |
| EXECUTING AGENCY/ENTITY: | Fondo Mexicano para la Conservación de la Naturaleza (FMCN) |  |  |
| PROJECT ANTICIPATED START DATE: | 2025 | PROJECT END DATE: | 2030 |
| GMP PREPARED BY: | FMCN – Socioenvironmental Research Coordinator |  |  |
| DATE OF (RE)SUBMISSION TO CI-GEF/GCF: | 13/03/2024; 21/03/2024 |  |  |
| GMP APPROVED (CONDITIONALLY) BY: | Ian Kissoon, Senior Director, ESMF, CI-GEF Agency |  |  |
| CONDITIONS: | GMP to be validated with stakeholders during the next phase, and the indicator targets are to be finalized. |  |  |
| DATE OF CI-GEF APPROVAL: | March 22, 2024 |  |  |
| PERSON RESPONSIBLE FOR IMPLEMENTING AND MONITORING THE GMP: | Safeguards and Monitoring and Evaluation Coordinator at FMCN |  |  |
| HOW/WHERE WILL THE APPROVED GMP BE DISCLOSED: | The approved GMP will be disclosed via the project’s website and at the inception meeting with stakeholders. |  |  |
| WHEN WILL THE APPROVED GMP BE DISCLOSED: | The GMP will be disclosed in the first quarter of the implementation phase. |  |  |

- Project Objective

The Project "MEx30x30: Conserving Mexican biodiversity through communities and their protected areas" has as its objective to help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex).

MEx30x30 has three main objectives to reach this goal:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively;

- To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and local communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

- Project Description

Mexico safeguards nearly to 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life.

The Project MEx30x30 will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community vigilance, fire management, productive projects, ecotourism, and capacity building.

Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP has been the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). However, high levels of socioeconomic marginalization in many rural communities and heavy livelihood dependence on natural resources can result in resistance to prioritizing conservation or restoration activities that do not adequately consider local needs. CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. As a result, The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives.

The Project MEx30x30 will focus on the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

MEx30x30 is an opportunity to make the 30x30 goal possible, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes.

The Gender Mainstreaming Plan (GMP) is a comprehensive strategy designed to integrate a gender-responsive approach throughout the project. The primary goal of the GMP is to ensure that both women and men experience culturally compatible economic and social benefits, free from discriminatory effects during development and implementation while upholding their dignity and human rights. Beyond mere inclusion, it fosters sustainable equality of responsibilities, opportunities, and benefits, recognizing women and indigenous peoples' pivotal role in natural resource utilization and family health for rural women. The Project's GMP addresses the root causes of inequalities, encompassing limited access to and control over natural resources, inadequate employment opportunities, and capacity-building opportunities. Gender-disaggregated information will be systematically collected to monitor and track participation and engagement, fostering accountability and transparency.

SECTION II: Gender Analysis/Assessment

- National context

Mexico still faces persistent gender inequalities, which are most evident in the rural sector. In the Gender Inequality Index, Mexico ranks 86th out of 162, reflecting significant differences in reproductive health, empowerment, and labour (PNUD 2022).

Although significant progress has been made in the area of education, practically reaching gender parity, economic inequality between women and men continues to be a challenge, with notable differences in terms of labour participation and salaries. In Mexico, only 38.5% of senior positions are held by women, and women's estimated income is only 52.3% of men's. According to the Global Gender Gap Index 2023 of the World Economic Forum (WEF), Mexico ranked 33rd out of 146 countries evaluated, marking a drop of two positions from the previous year.

Gender inequalities in land access can significantly impact food security, resource management, and sustainable development. In Mexico, 1,045,892 women have recognized rights as ejidatarias, comuneras, posesionarias, or avecindadas, representing only 34% of the total number of subjects of agrarian rights (RAN, 2023). Nevertheless, it represents a significant increase since 1971 when the Federal Agrarian Reform Law recognized equal legal capacity for men and women to obtain endowment units, allowing to go from only 31,459 ejidatarias to 1,045,892 women with recognized rights in 46 years.

In terms of gender violence, although the national legal framework has been strengthened and resources allocated to address this problem have increased, Mexico remains one of the most violent countries for women, with percentages well above the world average and in seventh place among the 32 nations of Latin America and the Caribbean (UN Mexico, 2021 and ECLAC, 2022).

86% of the Mexican territory is under alert for femicide violence and the disappearance of women and girls. Likewise, according to the National Survey on the Dynamics of Household Relationships (INEGI, 2021), 70.1% of women aged 15 years and older have experienced violence in their lifetime (psychological, physical, sexual, economic or marital), and 42.8% in the last 12 months.

Likewise, at the national level, the crime with the highest incidence is family violence, since according to information from the National Citizen Observatory (2023), during 2021 and 2022, 12% (more than half a million) of the total number of investigation files initiated in Mexico corresponded to this crime.

There have been some positive developments in the protection of the rights of LGBT and other gender-non-conforming persons in Mexico. For example, discrimination explicitly based on sexual orientation has been prohibited since 2003 in a broad range of fields (employment, education, the provision of and access to goods and services, including housing), and since 2011 by the Constitution of Mexico (OECD 2020). Hate crime and hate speech motivated by bias against a person’s sexual orientation have been explicitly criminalized since 2014 (OECD 2020). The Mexican National Equality Body (CONAPRED), is explicitly responsible for assisting victims of discrimination based on sexual orientation, gender identity and sex characteristics/intersex status. On the other hand, significant gaps in protection remain. For example, the progress made by Mexico has been more modest regarding legal provisions addressing barriers to the inclusion of same-sex couples and transgender individuals (OECD 2020). Legal LGBTI inclusivity is defined as the share of laws in force among those critical to ensuring equal treatment of LGBTI people. Mexico is one of 14 countries in the OECD and this share is still moderate (OECD 2020). These countries are characterized by a below-average performance regarding their level of legal LGBTI-inclusivity as of 2019 and their progress in legal LGBTI-inclusivity between 1999 and 2019. Mexico has been below the OECD average throughout the period but is improving at a sustained pace. The Project will ensure that LGBTI status as part of a disadvantaged group will be protected through project safeguards.

The following relevant international legal frameworks on the rights of women signed by Mexico are:

- Universal Declaration of Human Rights

- American Convention on Human Rights

- Convention on the Elimination of all Forms of Discrimination against Women

- Convention on the Political Rights of Women

- Inter-American Convention to Prevent, Punish, and Eradicate Violence against Women

- Optional Protocol to the Convention on the Elimination of all Forms of Discrimination against Women

National legal frameworks on women's rights applicable to the project include:

- Political Constitution of the United Mexican States

- General Law for Equality between Men and Women

- Law of the National Institute of Women

- Law of the National Commission of Human Rights

- Law of the National Institute of Indigenous Peoples

- General Law of Electoral Institutions and Procedures

- Federal Law to Prevent and Eliminate Discrimination

- General Law of Access of Women to a Life Free of Violence

- General Law to Prevent, Punish and Eradicate crimes in the Matter of Human Trafficking and for the Protection and Assistance to the Victims of these Crimes

- Agrarian Law

- Law on Agricultural Chambers that hereinafter will be called Agricultural Associations

- General Law of Cooperative Societies

- General Law of Ecological Balance and Protection of the Environment

- General Law of Climate Change

- General Law of Sustainable Forest Development

- Law of Rural Sustainable Development

- Federal Labor Law

- General Law of Education

- Health Law

- General Law of Human Settlements, Territorial Planning and Urban Development

- General Law for the Inclusion of People with Disabilities

- NOM-035-STPS-2018 Psychosocial risk factors at work, identification, analysis and prevention

- NOM-046-SSA2-2005 Family and sexual violence against women

- NOM-007-SSA2-2016 For the care of women during pregnancy, childbirth and puerperium, and of the newborn

- NMX-R-025-SCFI-2005 Labor equality and non-discrimination

- Local context and Project-level gender considerations

- How do women and men currently utilize the natural resources that this project impacts? How might that change during and after the project?

In the five PAs and the ADVC complex, the utilization of natural resources often reflects traditional gender roles and responsibilities. A generalized view of how women and men utilize natural resources in these areas is presented in the following table:

| Activities | PA/ADVC | Men | Women |
| --- | --- | --- | --- |
| Agriculture | Balam-Kú CADRN 043 Nayarit Chimalapas complex Papigochi Sierra Tecuani | - Ownership of land and crops. - Decision-making over land cultivation and crop production, management, transportation, and marketing. - Income administration of production revenues. | - Decision-making over small-scale agriculture (kitchen gardens or small plots), focusing on crops for household consumption or local markets (vegetables, farm animals). - Temporal participation, in family plots as an unpaid activity, in the clearing of land for sowing and during harvesting. - Agriculture income is traditionally received by the head of household (males) instead of each family member (women and youth). |
| Cattle ranching | Balam-Kú CADRN 043 Nayarit Chimalapas complex Papigochi Sierra Tecuani | - Ownership of farm animals and pastures. - Decision-making over animal production, management, transportation, and marketing. - Active participation in livestock associations and exhibition events. - Income administration of production revenues from animal or sub products sales (milk, cheese, meat, eggs). | - Responsible for the care and herding of the animals as an unpaid activity. - Participation in cattle ranching administrative activities. - Participation in cheese production. - Women-headed households with farm animals have access to subsidies and usually rent their pastures. |
| Forest harvesting (timber) | Balam-Kú CADRN 043 Nayarit Chimalapas complex Papigochi Sierra Tecuani | - Decision-making over the sustainable harvesting of forest resources. - Participation in felling trees, delimbing, and bucking. - Engagement in transporting harvested timber from the forest to processing facilities or collection points, including driving trucks, operating heavy machinery like skidders or forwarders, or overseeing transportation logistics. - Decision-making over the creation of companies at the ejido level for processing, manufacturing, and adding value to timber products, such as operating sawmills, processing lumber, and manufacturing wood products such as furniture, flooring, and paper. | - Not identified at this stage. |
| Forest harvesting (non-timber) | Balam-Kú Chimalapas complex Papigochi Sierra Tecuani | - Participation in the harvesting of non-timber forest products. | - Gathering firewood and water for household subsistence activities. - Participation in wax or gum production. - Participation in honey production, carrying frames, smoking, checking boxes, cleaning and weeding the apiaries, feeding the bees and putting wax in the apiary. - Decision-making over mushroom gathering for consumption, sale, and medicinal use - Decision-making over plant harvesting for medicinal purposes and consumption - Engagement in artisanal activities using natural materials, such as weaving baskets, making handicrafts, or processing agricultural products like fruits into jams or preserves. |
| Tourism | Balam-Kú CADRN 043 Nayarit Sierra Tecuani | - Engagement in ecotourism-related activities, such as guiding nature hikes, birdwatching, or providing homestay accommodations for visitors. | - Engagement in ecotourism-related activities, such as guiding tours or providing food for visitors. |
| Fishing | Bajo del Norte | - At-sea capture activities. | - Responsible for processing and preservation of fish once it's brought ashore, including cleaning, filleting, smoking, salting, drying, and packaging fish for sale or consumption. |

- To what extent do women and men participate in decision-making processes about those natural resources and is that likely to carry over into project decision-making? What are the constraints (social, cultural, economic, political) that restrict women’s active participation in household, community and project-level decision-making processes?

Mex30x30 PAs have a rich biodiversity and an emblematic cultural fabric, which have profoundly shaped historical norms, traditional roles, and power dynamics on how natural resources are accessed and managed within households and communities, resulting in multifaceted disparities for women.

In this context, gender roles allocate specific responsibilities to men and women. Therefore, men have often been assigned agriculture, fishing, and logging, which grant them primary access to land and natural resources. This access contributes to economic power and establishes their dominance in decision-making regarding resource utilization and management strategies. Meanwhile, women have been predominantly confined to domestic roles, restricting their access to educational opportunities and public spheres where crucial decisions are made, limiting their direct involvement in resource management decisions. By attending to these gender issues, for example, by increasing participation of women in land-use planning and targeting women as beneficiaries and developers of restoration activities, the Project may impact how women and men utilize natural resources. The Project must consider the impacts, both positive and negative, of increasing women’s access to traditionally male-dominated natural resources. Similarly, project activities that increase the value of what are traditionally women’s resources could lead to attempts by men to capture those value chains. These issues will be assessed during the development of conservation, restoration and sustainable management initiatives in Component 3.

Patriarchal structures also tend to prioritize the voices and contributions of men and reinforce male dominance in leadership positions, marginalizing women's representation and participation in community decision-making forums and hindering their ability to influence resource management policies and practices related to land use, water management, and conservation efforts. Consequently, the invaluable knowledge and perspectives that women bring remain largely untapped.

Similarly, youth are often overlooked in decision-making processes and face barriers rooted in age-related biases and limited opportunities for meaningful engagement. Traditional hierarchies prioritize the wisdom of elders, side-lining the innovative perspectives and aspirations of younger generations. Consequently, youth are excluded from pivotal discussions on resource allocation and conservation strategies despite inheriting these natural assets. The lack of platforms for their involvement stifles their potential contributions and perpetuates a cycle of marginalization, inhibiting the infusion of fresh ideas crucial for adapting to evolving environmental challenges.

Access to land and resources is fundamental for livelihoods in these areas, but there is also an unequal distribution based on age and gender, which perpetuates socio-economic disparities. Women and youth often lack ownership or control over land, facing barriers to accessing resources critical for their economic well-being.

Gender roles and intergenerational gaps significantly influence access and decision-making power related to natural resource management. Addressing these disparities requires challenging ingrained cultural norms, promoting gender equality, and creating tailored opportunities for women and youth to participate actively in decision-making processes. By harnessing youth’s innovative potential and leveraging women’s unique perspectives, communities can forge more resilient and equitable approaches to conservation, ensuring the preservation of Mexico’s natural heritage for generations to come.

The set of existing gender gaps (e.g., land tenure, participation in governance bodies, unequal payments, unpaid employment and domestic care activities) keep women in culturally reinforced cycles of poverty that discourage self-organization and individual efforts to overcome. Project activities will be designed around understanding these constraints, providing meaningful opportunities that benefit women while minimizing the costs of accessing these opportunities, , such as building on activities women are already undertaking, considering childcare needs, and scheduling around women’s time constraints. By increasing the participation of women in land-use planning, targeting women as beneficiaries and developers of conservation activities, providing technical assistance and capacity building, strengthening women’s engagement in project actions, reducing administrative requirements, avoiding land ownership requests, and ensuring equal distribution of benefits and opportunities, the Project will contribute challenging traditional norms on how women and men utilize natural resources. Other strategies will include identifying appropriate meeting locations and times to adapt activities around women’s schedules, developing tailor-made materials, and guaranteeing that women are not burdened with additional responsibilities (doubled or tripled workloads). Particular attention will be paid to the intersection of gender and other vulnerable sub-groups, for example, women who are Indigenous, LGBTQI, elderly, and have disabilities, among others.

- Do women and men have equal access to information and opportunities necessary to participate and benefit fully from the activities of the project? How do gender-related barriers/challenges potentially limit women’s ability to fully participate, make decisions and benefit from the project? How will the project overcome them?

The MEx30x30 Project will support six protected areas: two existing PAs, three newly decreed PAs, and one complex of recently designated ADVCs (with eight certificates). The six regions have a population of approximately 162,392 people: 49.80% women and 50.20% men.

Figure 1. Population in the Project's PAs disaggregated by sex (INEGI, 2020).

These territories are located within ten states, which present gender differences concerning average level of schooling, economic participation rate, head of household, violence against women, and land ownership.

Knowing these differences is essential for understanding and recognizing that Project actions will have opportunities or resistance linked to the gender structures in the territories, which, being associated with power, have a direct impact on the dispositions that men and women have for accessing, using, owning and managing resources (Rocheleau et al., 2004).

In some territorial contexts in Mexico,  prejudices are rooted in cultural practices that, combined with other socioeconomic factors, have historically conditioned access to education, accentuating exclusion and inequality.

In terms of the states that comprise the PAs, Oaxaca, Guerrero, and Campeche are the entities with the most significant gender gaps in education, i.e., Chimalapas Complex, Sierra de Tecuani, and Balam-Ku are the territories in which this situation may affect women's participation in the Project.

Figure 2. The average years of schooling between men and women (INEGI, 2020).

Another aspect to consider is the difference in economic participation rates, or the percentage of the working-age population (15 years or older) working or actively seeking employment, as in all states, women have significantly lower percentages than men. Even so, inequalities are most evident in Campeche (Balam-Ku), and Zacatecas and Durango (C.A.D.N.R. 043 State of Nayarit).

Figure 3. Economic participation rates (INEGI, 2020).

The National Survey on the Dynamics of Household Relationships 2021 reported that women are more likely to be abused in the community and intimate partner spheres (ENDIREH 2021). Aguascalientes, Jalisco, Chihuahua, and Yucatán are the states where women report having experienced the most episodes of violence in their lives, with percentages above 70%.

Figure 4. Percentage of women that had experience violence (INEGI, 2022).

In 33 of every 100 Mexican households, women are recognized as heads of household (INEGI, 2020). The head of household is generally associated with the person who is the main economic responsible for the family. In the states linked to the project, Durango and Jalisco are the states with the highest number of women responsible for the family's sustenance.

Figure 5. Heads of household disaggregated by sex (INEGI, 2020).

In Mexico, ejidos and communal properties represent 50.8% of the national territory, distributed in 29,813 ejidos and 2,416 communities that occupy around 100 million hectares, over which 5.5 million people have rights (RAN, 2022). Although the Agrarian Law recognizes that men and women can be ejidatarios, only three out of every ten people with ejido or communal land titles are women. This situation reflects a male hegemony in access to land, which transcends from the family to the community level. In the states associated with the project, Yucatan and Campeche have the widest inequality gaps since nearly 80% of the subjects of agrarian rights are men. Guerrero has the highest percentage of women landowners (34%), which offers slight opportunities to encourage the participation of this sector of the population in activities related to the project.

In the case of ejidos and communities, the decision-making process is typically collective and democratic, involving the participation of all community members. Decisions are usually taken in the General Assembly, the highest decision-making body, composed of all adult members of the community. These assemblies are typically held regularly, often monthly or quarterly, and serve as forums for discussing and deciding essential matters. In many ejidos and communities, decisions are reached through consensus rather than a majority vote. This means that all community members, with or without land rights, are encouraged to express their opinions and concerns, and efforts are made to find acceptable solutions. Before making decisions, members of the ejido or community engage in thorough discussions and debates to ensure that all viewpoints are considered. This process can be time-consuming but is essential for reaching agreements that reflect the interests of the entire community.   While all members have the right to participate in decision-making, ejidos and communities may also elect representatives or delegates to negotiate on behalf of the community in certain situations, such as dealing with external entities or government agencies. Given that ejidos and communities typically manage collectively owned land and natural resources, decisions often revolve around their sustainable use and conservation. This may involve agreements on farming practices, forestry management, water allocation, or other resource-related issues.

Figure 6. Ejidatarias, posesionarias, comuneras, or avecindadas with land ownership and rights (RAN, 2023).

As explained above, historically, women have faced systemic barriers that limit their access to education, financial resources, land ownership, and decision-making spaces, restricting their ability to participate fully in projects and benefit from them compared to men. These barriers can be attributed to societal norms, cultural beliefs, economic disparities, and institutional biases, leading to their needs and perspectives being overlooked. Women also bear a disproportionate burden of unpaid care work, such as childcare and household chores, which can limit their time and energy to participate actively in project activities.

To address these challenges, the Project will incorporate a gender perspective into all planning stages to address specific barriers women face, creating an enabling environment where women and men have equal access to information and opportunities and facilitating their full participation and benefit from the project activities. For example, Project activities, training, and skills development will be flexible to accommodate women's time constraints, such as providing childcare facilities or scheduling meetings at times convenient for women to participate in project activities actively. Involving women in decision-making processes at all levels of the Project will ensure their voices are heard and their needs are addressed in POAs design and the priorization of activities that will be supported by the Project. For example, as four of the five PAs need to establish their Advisory Councils (only Papigochic has an operating Advisory Council), the Project has a significant opportunity to foster women’s engagement in these decision-making mechanisms. Additionally, awareness activities to challenge harmful gender norms and stereotypes will encourage community support for women's participation in the Project.

- How will women and men be impacted (positively or negatively) by project activities including on their livelihoods, workload, control over resources, etc.?

The project activities will provide women and men with opportunities for income generation. In this case, training programs tailored to women's needs can enhance their skills, livelihoods, or participation in community decision-making processes towards natural recources management. By involving women in decision-making processes related to resource management, the Project can help challenge traditional gender norms and promote more equitable distribution of resources within households and communities. Awareness raising activities and gender-sensitive approaches can also allow men to participate more actively in household responsibilities and caregiving duties.

- What are the different interests, needs and priorities of men and women within the project context? How will the project be able to address their respective needs and priorities?

- Women may have limited access to resources such as land and education compared to men. Addressing this disparity could involve providing equal access to resources, ensuring women are included in decision-making processes, and implementing programs that empower women economically and socially.

- Gender roles often dictate different responsibilities within households and communities. Women may be primarily responsible for collecting water and fuelwood, while men may be involved in activities like farming and fishing. Understanding these roles and responsibilities is crucial for designing conservation activities sensitive to gender dynamics.

- Women and men may possess different traditional knowledge and skills related to conservation practices. Incorporating both sets of knowledge can enhance the effectiveness of conservation initiatives. Providing training and capacity-building programs that are accessible to both genders can help bridge knowledge gaps and foster collaboration.

- Women often face more significant challenges in accessing markets and generating income. The Project can create inclusive alternative livelihood options that provide equal opportunities for both genders, such as promoting sustainable agriculture, ecotourism, or artisanal crafts that benefit local communities.

To address the respective needs and priorities, the Project will include the following strategies:

- Integrating gender considerations into Project planning, implementation, monitoring, and evaluation processes.

- Promoting gender equality and women's empowerment through targeted interventions such as training, capacity building, and leadership development.

- Reinforcing the Advisory Councils for inclusive decision-making and participation that ensure women have a voice in conservation initiatives.

- Collaborating with local women's groups, community leaders, and relevant stakeholders to leverage existing networks and resources.

- Monitoring and addressing gender-based disparities in project outcomes ensures that benefits are equally distributed among men and women.

- How might project activities create new opportunities (economic, leadership, etc.) for women?

Participation in project activities will not be linked to land ownership and will foster women's engagement and empowerment during its lifespan. For example, gender-sensitive criteria should guide POA design and development, communication materials specially designed for women should be developed, and capacity-building should be provided to raise awareness of gender equality and its benefits.

The Project will promote mechanisms for making women's economic and social roles visible for contributing to female empowerment and well-being. For example, foster community-driven projects that empower women, engage women in non-traditional roles, promote positive gender portrayals, highlight their achievements and contributions through regular updates and success stories, and support initiatives to challenge stereotypes, celebrate diversity, and encourage more participation.

The Project will guarantee equal salaries between women and men for similar work and avoid double or triple shifts for women due to project activities.

Through restoration, conservation, and sustainable practices and activities proposed by the Project, women will benefit from enhanced environmental services.

- Is there a possibility that project activities may perpetuate/increase inequalities, including gender-based violence? (why or why not)

If gender considerations are not explicitly addressed in the Project, there is a risk of perpetuating gender inequality. Therefore, the Project has been specifically crafted to enhance women's involvement and active participation in consultations and capacity-building efforts, augment female representation in decision-making positions, and ensure a more significant proportion of female beneficiaries.

In terms of preventing and responding to gender-based violence (GBV), the Project will offer fundamental training to staff and OLLCs on GBV awareness and response, including:

- Acknowledging that the Project's intervention could exacerbate the situation.

- Compiling a referral directory of organizations trained to provide necessary support.

- Requesting additional support and capacity-building from CI-GEF on GBV.

- Enforcing the GRM to address GBV incidents related to the Project.

- Adhering to national laws and regulations on GBV, including victims' rights.

Moreover, special attention will be devoted to understanding the intersectionality of gender with other vulnerable demographics, such as Indigenous women, LGBTQI individuals, older adults, and persons with disabilities, among others.

- What is the level of gender awareness and capacity to address gender issues amongst local authorities, project partners and project staff?

FMCN has the experience and capacity to address gender issues. Since 1998, FMCN has applied environmental and social standards to its projects. These have evolved alongside the policies and procedures of the World Bank, which has been the implementing agency for the four GEF-funded projects continuously coordinated by FMCN for 26 years. With the accreditation by GCF in 2019, FMCN integrated the World Bank Environmental and Social Standards published in 2018. They were incorporated into every project starting in 2019. In 2022, thanks to GCF Readiness support and with the accompaniment of KfW Development Bank, FMCN developed its Environmental and Social Policy and its Environmental and Social Management System (ESMS or SGAS, for its acronym in Spanish), which are being fully implemented in 2023.

FMCN’s Organizational Manual has a Gender Policy, which incorporates the gender perspective in a cross-cutting manner in the operation of FMCN and all its initiatives. This policy promotes women’s empowerment and fosters equality between men and women in natural resource conservation, management, and restoration in a culturally appropriate way. Additionally, FMCN has a Policy on Protection against Sexual Exploitation, Abuse, and Harassment, which declares zero tolerance for these practices and places human dignity and women’s right to a life free of violence at the center of FMCN’s work. Both policies apply to the Assembly, the Board of Directors, the Committees, FMCN contracted staff, entities staff with contractual relationships with FMCN, project beneficiaries, suppliers, and consultants. FMCN has staff dedicated to safeguards, gender, and stakeholder engagement.

CONANP has made efforts to mainstream gender considerations into its policies, programs, and projects and has demonstrated varying levels of gender awareness and capacity to address gender issues across its operations.

It recognizes the different needs, priorities, and roles of women and men in natural resource management and conservation and has developed specific programs to empower women in local communities that interact with protected areas. Efforts have also been made to engage both women and men in Advisory Councils or decision-making processes related to conservation and management, recognizing the different perspectives and contributions they bring.

CONANP also has made efforts to ensure gender representation within its organizational structure by promoting the participation of women in decision-making processes, including leadership positions within the commission. Additionally, it has enhanced the capacity of its staff to understand and address gender issues effectively through training sessions, workshops, or educational programs focused on gender equality and women's empowerment.

There may still be challenges and areas for improvement within CONANP's gender awareness and capacity. These include ensuring women's meaningful participation in all decision-making levels, addressing gender-based barriers to access and control over natural resources, and continuously evaluating and improving gender-sensitive policies and practices.

- Describe the methods (interviews, desktop research, focus groups, surveys, etc.) were used to collect information for the Gender Analysis/Assessment.

The information for the Gender Analysis/Assessment was obtained through desktop research, and experience of FMCN with previous projects. FMCN’s experience working with CONANP in similar projects and locations helped design women’s engagement strategies and coordinate on-the-ground activities for the Project. CONANP’s prior process for decreeing the Project’s PA and ADVC was also advantageous. For example, previous experience informed the dissemination strategies, including when and where to hold workshops, which types of materials to disseminate, and through which channels (e.g., radio, posters, workshops, meetings, attendance at local committees). Prior experience also revealed the importance of disseminating information in languages and media that women use most and the value of other means of communication among the rural and indigenous population.

- Describe lessons learnt during the development of the GMP. e.g. Did you have to hold meetings separately for women? Did the location/time of meetings affect women’s participation?

FMCN’s previous experience working with CONANP in similar projects and locations was beneficial to understanding and having on-the-ground experience with gender dynamics in communities living in PAs. However, gathering comprehensive data on gender gaps at the local level faces several limitations:

- Scale - Official information is mainly available at national or municipal levels and, in many cases, is not disaggregated by sex.

- Underreporting and Misrepresentation: Many marginalized groups, such as indigenous women or transgender individuals, might be underrepresented or misclassified in official data due to social stigma, discrimination, or lack of recognition of their identities.

- Data Collection Methods: Traditional data collection methods might not adequately capture the diversity of these groups. For instance, surveys or census forms might lack specific options or categories to identify diverse gender identities or cultural backgrounds accurately.

- Geographic Disparities: Rural-urban variations can influence data collection. Remote or rural areas might have less access to technology and resources, leading to the underrepresentation of data. Additionally, different needs or challenges faced by urban versus rural populations might not be adequately captured in aggregated statistics.

- Cultural Sensitivities and Trust: In specific communities, there might be distrust towards authorities or institutions conducting surveys or collecting data. This lack of trust can lead to lower participation rates and affect the accuracy and comprehensiveness of collected data.

- Intersectionality Challenges: Data often fails to capture the intersections among various identities, such as being both indigenous and female or transgender. This intersectionality is crucial in understanding the unique challenges of individuals with multiple marginalized identities.

- Lack of Longitudinal Data: Continuous tracking of changes over time within these diverse groups is often missing. Longitudinal data could provide insights into trends, improvements, or deteriorations in the living conditions and opportunities available to these populations.

- Inability to capture the full range of the activities carried out by women, in many cases, within their homes: Much of the work in rural areas and agricultural-related chores carried out by women, whether for their consumption or the market, are not recorded at a local level, meaning they are often classified as engaged in domestic chores. Additionally, the availability of information, for example, on time use, is of crucial relevance. Most of the problems and limitations women face are related to the lack of time to devote to activities that promote their development, participation, and autonomy in areas other than work. The information that can be obtained through this type of survey is not limited to evaluating people's time and participation in daily activities since one of its objectives is to advance toward a methodological proposal that will make it possible to measure the monetary value of the production of unpaid domestic and care services at the local level, to reflect their contribution in the national accounts later.

Addressing these limitations requires innovative data collection methods, increased inclusivity in survey design, culturally sensitive approaches, and a concerted effort to build trust within marginalized communities. Collaboration between CONANP, FMCN, OLLCs, and communities is essential to create more accurate and inclusive data sets reflecting the diversity and challenges different population groups face.

SECTION III: Gender Action Plan

| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Outputs | Activities to Mainstream Gender into Output | Target | Resources Required | Budget |
| Outcome 1.1. CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. | - Training and technical support will include a focus on gender mainstreaming (gender-based violence, sexual harassment, stalking and abuse, masculinities) - Incorporate increased gender-responsive and inclusive learning and knowledge sharing approaches into CAAP, thereby allowing for greater participation and access to resources to a wider spectrum of stakeholders. - Promote women’s participation and leadership (gatherings, sessions, events) | Target 1.1.3b: At least 100 new members from the Protected Areas Learning Community from IP&LCs, of whom at least 50% are women. | • Safeguards and Monitoring and Evaluation Coordinator - Training materials - Communication materials | USD$5,500 |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |  |
| Outcome 2.1. Donor support is secured to cover the financing gap for the effective management of existing PAs over the next 15 years. | - Design of long-term financing mechanism incorporates gender and inclusion considerations (e.g., conservation plan including gender consideration for conservation, restoration and sustainable development in PAs and ADVCs) - Conservation plan includes specific budget for gender and inclusion activities | Target 2.1: The Transition Fund includes gender considerations for enclosing specific budget to support gender and inclusion activities in POA. | - Environmental and Social Safeguards Officer - Advocacy and outreach materials | USD$2,000 |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. |  |  |  |  |
| Outcome 3.1. PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. | - Guarantee gender-responsive and inclusive Annual Operating Plans (POA) for conservation, restoration and sustainable development of PAs and ADVCs - Identify knowledge gaps and needs relevant to women and provide gender-responsive and inclusive training to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation, and restoration practices - Use communication channels and spaces that are relevant to women, translating to Indigenous languages, using inclusive language, choosing locations and times that are convenient for women, conducting women-only training sessions - Promote women’s participation in decision-making processes, including community groups, through the Advisory Councils - Use inclusive language in all communications and include a gender lens in all project communication - Ensure that the Emergency Fund incorporates gender and inclusion considerations to address the needs of women and marginalized people Promote the dissemination and operation of the grievance redress mechanism and gender policies | Target 3.1b: 163,200 people experiencing socioeconomic and/or environmental benefits through effective PA or ADVC management (at least 50% female, desegregated by gender and IP&LCs). Target 3.1.2: At least 100 people per PA or ADVC trained in sustainable land management, conservation and restoration practices (at least 50% women; level of Indigenous participation proportional to Indigenous percentage of local population). Target 3.1.3: At least x gender-responsive and inclusive sustainable management initiatives implemented per in PAs and ADVC. | - Environmental and Social Safeguards Officer - Communication materials - Training materials | USD$7,500 |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |  |
| Output 4.1 Mex30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. | - Inform on gender-responsive and inclusive learning and knowledge exchanges. - Dissemination mechanisms and communication strategies consider production and consumption of knowledge products and communications material by diverse groups (i.e. women, youth, elderly, and Indigenous and other vulnerable and/or marginalized groups). - Include topics related to gender and social inclusion issues in knowledge products and communication materials. - Feature knowledge and experience from communities, women-led organizations and those led by other disadvantaged groups. - Finance the participation of women in meetings of the PAs Learning Community to promote the exchange of experiences. - Gender-sensitive communication & publication principles such as: - Emphasize the importance of women participation - Ensure that women and men are equally represented (parity). - Reflect the diversity and heterogeneity of people in relation to age, ethnicity, culture, physical type, complexion, gender identity, etc. - Avoid reproducing exclusionary gender stereotypes in audiovisual messages, especially with regard to gender assignment in activities. - Use inclusive and non-sexist language. | Target 4.2.1: At least 4 lessons-learned knowledge products prepared and shared (including at least one with a focus on gender and inclusion). Target 4.2.2b: 400 people participating in national workshop and dissemination event (at least 50% women, at least x% indigenous). | - Environmental and Social Safeguards Officer - Communication materials - Training materials | USD$6,000 |
| Output 4.2. Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | - Include gender-specific indicators and gender-disaggregated targets. - Develop and implement a clear and robust gender-responsive and inclusive Monitoring and Evaluation framework. | Target 4.1.1: One gender-responsive M&E framework in operation. | - Environmental and Social Safeguards Officer - Communication materials | USD$1,000 |

SECTION IV: Monitoring and Reporting

| - Number of project events/trainings dedicated to gender | 0 |  |  | At least 11 |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| - Number of documents (disaggregated by type) derived from the project that included gender considerations or address gender gaps. | 0 |  |  | 4 knowledge products, 1 gender-responsive and inclusive Annual Operating Plan prepared and implemented per PA or ADVC per year of the project (6 total) |  |  |
| - Number of new members (disaggregated by gender) from IP&LCs participating in the Protected Areas Learning Community. | 0 | 0 | 0 | 50 | 50 | 0 |
| - Number of people per PA or ADVC trained in sustainable land management, conservation, and restoration practices. | 0 | 0 | 0 | 300 | 300 | 0 |
| - Number of persons (disaggregated by gender) who received benefits in the project implementation phase. | 0 | 0 | 0 | 81,646 | 81,647 | 0 |
| - Number of people participating in national workshop and dissemination event (disaggregated by gender, recording level of Indigenous participation). | 0 | 0 | 0 | 200 | 200 | 0 |

Note 1: In addition to the minimum indicators above, projects are strongly encouraged to provide additional gender indicators specific to their projects.

Note 2: Provide justification or explain the rationale for the gender disaggregated targets set for the project. Targets should be ambitious yet realistic.

SECTION V: Considerations for the Implementation of the GMP

- Alignment + integration

The activities, budget and staffing outlined in this action plan must be integrated into the project’s overall Project Document + Results Framework. Please confirm that:

- The activities identified in this Action Plan have been integrated into the project’s proposal document including the results framework. (Y/N)

- The necessary budget for activities identified in this Action Plan have been integrated into the project’s overall budget. (Y/N)

- Staffing capacities

FMCN has a Gender Policy, which is part of its Organizational Manual, to incorporate the gender perspective in a cross-cutting manner in the operation of FMCN and all its initiatives. This policy promotes women’s empowerment and fosters equality between men and women in natural resource conservation, management, and restoration in a culturally appropriate way. Additionally, FMCN has a Policy on Protection against Sexual Exploitation, Abuse, and Harassment, which declares zero tolerance for these practices and places human dignity and women’s right to a life free of violence at the center of FMCN’s work. Both policies apply to the Assembly, the Board of Directors, the Committees, FMCN contracted staff, entities staff with contractual relationships with FMCN, project beneficiaries, suppliers, and consultants.

To date, FMCN's staff dedicated to safeguards, gender, and stakeholder engagement include the following positions:

Part-time

- General Coordinator

- Director of Research and Institutional Development

- Director of the Sustainable Management Area

- Internal Audit

Full-time

- Socio-Environmental Research Coordinator

- Socio-Environmental Research Officer

- Gender and Social Vulnerability Officer (Climate Change and Sustainable Production Projects)

- Environmental and Social Management Officer

- Environmental and Social Safeguards Officer

The above staff are environmental, social, and gender specialists and have received training in safeguards, gender, and stakeholder engagement, such as Grievance Redress Mechanism Online Course (GCF); Community Mediation Training (GCF); Meaningful Stakeholder Engagement - 13th Edition (IDB); Environmental and Social Framework - ESF Fundamentals (WB); E-learning Master Class on EIB Environmental & Social Sustainability Management (Frankfurt School Development Finance); Gender Mainstreaming (GGGI); Induction to gender equality (INMUJERES), among others.

The Environmental and Social Safeguards Officer, an existing FMCN staff, will oversee Mex30x30 GMP, devoting 100 % of his time to implementing this GMP.

| - Number of gender-responsive and inclusive sustainable management initiatives implemented in PAs and ADVCs. | 0 | TBD* |
| --- | --- | --- |

*To be determined during the first six months of project implementation.

References

ECLAC, 2021. CEPAL. 2021. Implicancias de los roles de género en la gobernanza de los recursos naturales en América Latina y el Caribe. Disponible en: https://www.cepal.org/es/enfoques/implicancias-roles-genero-la-gobernanza-recursos-naturales-america-latina-caribe

INEGI. 2022. Encuesta Nacional sobre la Dinámica de las Relaciones en los Hogares (ENDIREH) 2021. Disponible en https://en.www.inegi.org.mx/programas/endireh/2021/

INEGI e INMUJERES. 2020. Mujeres y Hombres en México 2020. Instituto Nacional de Estadística y Geografía. Instituto Nacional de las Mujeres. México. Disponible en: http://cedoc.inmujeres.gob.mx/documentos_download/mujeresyhombresenmexico2020_101353.pdf

Instituto Nacional de Ecología y Cambio Climático (INECC) y Fondo Mexicano para la Conservación de la Naturaleza (FMCN). 2020. Análisis y Plan de Acción de Género, Proyecto "Conectando la salud de cuencas con la producción ganadera y agroforestal sustentable" (CONECTA).

Marisela Zamora-Martínez (2014). El manejo de los recursos forestales desde una perspectiva de género. Revista mexicana de ciencias forestales. Disponible en: https://www.scielo.org.mx/scielo.php?script=sci_arttext&pid=S2007-11322014000500001

Observatorio Nacional Ciudadano. 2023. Observatorio Interactivo de incidencia delictiva. México. Disponible en: https://delitosmexico.onc.org.mx/

PNUD 2021. Conjunto de datos del Índice de Desigualdad de Género del Informe sobre Desarrollo Humano. Disponible en https://hdr.undp.org/data-center/thematic-composite-indices/gender-inequality-index#/indicies/GII

RAN. 2022. Estadística agraria. Registro Agrario Nacional. México.

Rocheleau, D., Thomas-Slayter, B., & Wangari, E. (2004). Género y ambiente: una perspectiva de la Ecologia Política Feminista. En V. Vázquez García & M. Velázquez Gutiérrez (Eds.), Miradas al futuro. Hacia la construcción de sociedades sustentables con equidad de género (pp. 333–371). CRIM, PUEG, COLPOS, IDRC.

UC, Martha (2024). Diagnóstico de Género del Proyecto ACCIÓN. Fondo Mexicano para la Conservación de la Naturaleza.

IUCN (2015). Toma de decisiones y participación de las mujeres en Áreas Naturales Protegidas (ANP) Evaluación de Género y Desarrollo Sostenible en la Península de Yucatán (EGEDS-PY). Disponible en: chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.biodiversidad.gob.mx/media/1/region/files/cbmm/9-1-fact-sheet-anp.pdf

STAKEHOLDER ENGAGEMENT PLAN (SEP)

The Stakeholder Engagement Plan (SEP) outlines the differentiated measures that the Executing Agency/Entity will implement to ensure the effective participation of key project stakeholders, including both men and women and those identified as disadvantaged or vulnerable stakeholders. The level of detail in the SEP will vary; it must be scaled to the scope of the project, numbers of stakeholders involved, and potential risks and impacts present.

The SEP includes a Stakeholder Analysis (Section III) to identify all actors who directly or indirectly may affect or be affected by a project and their varying interests. The SEP also outlines stakeholder engagement throughout the project lifecycle, including: Stakeholder Engagement in PPG/PPF Phase (Section IV), Stakeholder Engagement in Implementation Phase (Section V), and Monitoring and Reporting (Section VI). These sections outline the appropriate methods for engagement, including through neutral/third party facilitators, when necessary. They also detail required public disclosure of information on project scope and impacts, a grievance redress mechanism, the budget to complete stakeholder engagement, indicators, and learning throughout the project cycle.

Each revision of the plan requires further disclosure to stakeholders.

SECTION I: Project Information

| PROJECT TITLE: | MEx30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| --- | --- | --- | --- | --- |
| GEF/GCF PROJECT ID: |  |  | PROJECT DURATION: | 60 months |
| EXECUTING AGENCY/ENTITY: | Fondo Mexicano para la Conservación de la Naturaleza, A.C. (FMCN) |  |  |  |
| PROJECT START DATE: | (mm/year) |  | PROJECT END DATE: | (mm/year) |
| SEP PREPARED BY: |  | FMCN - Socioenvironmental Research Coordinator |  |  |
| DATE OF (RE)SUBMISSION TO CI-GEF/GCF: |  | 10/03/2024; 21/03/2024 |  |  |
| SEP APPROVED (CONDITIONALLY) BY: |  | Ian Kissoon, Senior Director, ESMF, CI-GEF Agency |  |  |
| CONDITIONS: |  | SEP to be validated with stakeholders during the next phase, and targets for the Indicators are to be established. |  |  |
| DATE OF CI-GEF APPROVAL: |  | March 22, 2024 |  |  |

SECTION II: Introduction

The Project "Mexico: Conserving Mexican biodiversity through communities and their protected areas" has as objective to help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex).

MEx30x30 has three main objectives to reach this goal:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively;

- To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen PAs and ADVCs managed by Indigenous Peoples and local communities (IP&LCs) to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

The Project will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community vigilance, fire management, productive projects, ecotourism, and capacity building.

Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP has been the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). However, high levels of socioeconomic marginalization in many rural communities and heavy livelihood dependence on natural resources can result in resistance to prioritizing conservation or restoration activities that do not adequately consider local needs. CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. As a result, The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives.

The Project will focus on the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

MEx30x30 is an opportunity to make possible the 30x30 goal, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes.

Protected areas often pose unique challenges and sensitivities, and engaging with stakeholders thoughtfully and inclusively is essential. The Stakeholder Engagement Plan (SEP) was prepared to build, strengthen, and sustain effective and inclusive stakeholder engagement at all levels and across sectors. The goal is to provide a structured participation roadmap for building trust and collaboration with local communities, indigenous peoples, governmental institutions, and other stakeholders by fostering open communication, addressing concerns, and demonstrating a commitment to shared benefits through the Project design and implementation. This collaborative approach increases the likelihood of the Project meeting its objectives and creating positive outcomes for both the environment and the communities involved. Among the purposes and goals of the SEP are:

- Identify stakeholders who are indirectly or directly affected by and/or interested in the Project.

- Add value to project activities, fostering well-coordinated and planned implementation.

- Involve different types of stakeholder groups in participation processes and benefit distribution, including but not limited to engagement, capacity building, employment, skills transfer, sharing of knowledge, and the increase of cultural awareness.

- Ensure local ownership and accessibility of information by all stakeholders, including communities, indigenous communities, and other vulnerable groups.

- Encourage adherence to values of transparency, trust, equity, and fairness when seeking participation in any decision-making activities.

- Develop mechanisms to manage conflicts, adapt to changing circumstances, and generate and respond to feedback.

SECTION III: Stakeholder Analysis

| Stakeholder Name and Function Name of the key stakeholder, and their main purpose/function | Stakeholder’s Interest What are the stakeholder’s main interests in and concerns about the project? | Impact of Project on Stakeholder How will the stakeholder be affected (both positively and negatively) by the project? | Influence of Stakeholder How can the stakeholder affect the project? Can they hinder or contribute to the success of the project? | Risk Management (Is this a low, medium or high-risk stakeholder? And how would you manage medium/high risk stakeholders) |
| --- | --- | --- | --- | --- |
| Governmental Institutions |  |  |  |  |
| National Commission for Protected Areas/Comisión Nacional de Áreas Naturales Protegidas (CONANP) Deconcentrated organization of the Ministry of the Environment (SEMARNAT) Role: Develop and implement public policy for the management of Federal Protected Areas and ADVCs. Will be on the Project’s Technical Committee. | Overall leadership and policy guidance, planning, and coordination. Improved performance through training and effective management tools. Integrity of protected areas and ADVCs. | Built technical and institutional capacity for effective and efficient protected areas and ADVCs management and governance. Project can support conservation, restoration, and sustainably management practices/activities in PAs and ADVCs. | Project promoters at the national level. Key decision-makers on the environment and natural resource management in PAs and ADVCs. Technical expertise, inform best practices, align sectors towards protected areas conservation and their effective management. | High Involve CONANP in the Technical Committee and contribute to implementation of project activities, ensures country ownership, alignment with national policies and existing federal investments in biodiversity conservation, and sustainability of project results. |
| CONANP-PAs Advisory Councils | Social participation mechanism with a consultative and deliberative nature, allowing representatives of the different sectors to advise and acknowledge PA's management priorities. Strengthen Advisory Councils creation and effectiveness. | Orient project activities to increase benefits. | Play a governance and conciliation role, ensuring social participation regarding PAs management process, including vulnerable. | Low Constant engagement through CONANP. |
| CSOs/NGOs |  |  |  |  |
| Legally Constituted Local Organizations (OLLCs) | Regional cooperation, collaboration, and guidance in project activities. Service delivery. Improvements in the quality of the environment in the region and community development. | Opportunities to implement POA activities, access to training and capacity building. | Support for implementing POA for Component 3 outcomes. Transparency in activities reporting. | High Constant engagement through POAs. |
| Local communities |  |  |  |  |
| Communities and ejidos in the protected areas | Ecosystem services, biodiversity, capacity building | Opportunities for participating in project activities and learning exchanges through POA implementation | Engagement and support of POA activities is critical for maximizing project benefits | High Constant engagement through POA. |
| Indigenous Peoples and Afro-Mexican populations |  |  |  |  |
| Indigenous Peoples in the protected areas | Ecosystem services, biodiversity, community development, capacity building. | Opportunities for participating in project activities and learning exchanges through POA implementation. | Engagement and support of POA activities is critical for maximizing project benefits. | High Constant engagement through (POA. |
| Private Sector |  |  |  |  |
| Donors and private sector | Consider investment opportunities that align with interests to cover the financial gap in PAs. Long-term financial mechanisms. | Access to investment opportunities linked to long-term financial mechanisms for covering the financial gap in PAs and to conservation, restoration, and sustainable management practices to maintain ecosystem services that benefit operations. | Expand awareness of PAs financial gap, design innovative financing mechanisms for PA long-term sustainable management Potential source of investments in PAs conservation and restoration. | Medium Specific engagement regarding financing opportunities to cover the financial gap in PAs. |
| Disadvantaged/Vulnerable Groups |  |  |  |  |
| Youth, elderly, women, people with disabilities in the protected areas | Ecosystem services, biodiversity, community development, capacity building. | Opportunities for participating in project activities and learning exchanges through POA implementation. | Engagement and support of POA activities is critical for maximizing project benefits. | High Constant engagement through POA. |

SECTION IV: Stakeholder Engagement

MEx30x30 will work with six protected areas: five PA and a ADVC complex (with eight certificates).

| Protected Area | Management category | States | Terrestrial area (ha) | Marine area (ha) | Decreed in (year) | Last decree (year) |
| --- | --- | --- | --- | --- | --- | --- |
| Papigochic | Flora and Fauna Protection Area (APFF) | Chihuahua | 222,763.85 | 0 | 1939 | 2003 |
| Balam-Kú | Biosphere Reserve (RB) | Campeche | 463,441.76 | 0 | 2023 | 2023 |
| Sierra Tecuani | Biosphere Reserve (RB) | Guerrero | 348,140.97 | 0 | 2024 | 2024 |
| Bajos del Norte | National Park (PN) | Yucatán | 0 | 1,304,114.89 | 2024 | 2024 |
| C.A.D.N.R. 043 Nayarit | Natural Resources Protection Area (APRN) | Aguascalientes, Jalisco, Durango, Nayarit, Zacatecas | 2,329,026.76 | 0 | 1949 | 2002 |
| Chimalapas complex | Voluntary Conservation Areas (ADVC) | Oaxaca | 438,662.66 | 0 | 2023 | 2023 |

In the last year (2023-2024), prior governmental consultation processes were implemented for decreeing RB Balam-Kú, PN Bajos del Norte, and RB Sierra Tecuani protected areas. The legal framework governing the establishment of protected areas in Mexico requires thorough consultations during the planning and designation process. These consultations involve multiple stakeholders, from local communities and indigenous peoples to experts, ensuring that a diverse range of perspectives are considered before making the final decision. The consultations led to the development of adaptive management plans, allowing for adjustments based on changing circumstances or new information from different stakeholders. Once this process is complete, a broad consensus among stakeholders is reached. Additionally, establishing protected areas requires scientific research and environmental and social assessments through a Technical Justification Study. This document presents sufficient technical evidence from duly recognized academic and research sources, on-the-field activities, and consultation processes to confirm that the PA authorization is viable. Public consultations conducted by the government align closely with the anticipated activities outlined in the Project Component 3, as evident in PA’s Justification Studies. Public consultations involved engaging with various stakeholders, including local communities, indigenous communities, environmental organizations, and government agencies, to identify valuable insights, knowledge, and perspectives on the decreed protected areas and the activities to be supported on them. With the consultation process, the government ensured feedback on the proposed activities to adjust and align them with these stakeholders' needs, priorities, and concerns, demonstrating its commitment to openness and responsiveness. It promoted transparency and accountability in the decision-making process, enhanced its effectiveness and sustainability, addressed potential conflicts, minimized negative impacts, and maximized positive outcomes for conservation and local communities. When stakeholder's voices have been heard, and their input has been considered, they are more likely to support the PA and actively participate in its protection. This support is crucial for conservation efforts' long-term success and sustainability in the protected areas. For further reference, please find the links to the consultation page on the CONANP website: https://www.conanp.gob.mx/acciones/consulta/..

In addition, in October 2023, the Ministry of the Environment and Natural Resources (SEMARNAT) and CONANP awarded eight certificates for ADVC in Los Chimalapas, Oaxaca, favouring the active participation of communities in environmental management, the protection of biocultural resources, and the conservation of biological corridors in the region. In Mexico, the General Law of Ecological Balance and Environmental Protection (LGEEPA) incorporates the ADVC as protected areas established by a certificate that recognizes the willingness of the owners to sustainably manage their properties under any property regime (e.g., person, legal entity, social organization, indigenous peoples, ejidos and communities). Since it is voluntary, the owners assume the commitment and responsibility to protect and manage their properties sustainably without imposing modalities or restrictions on their property rights. As the establishment of the ADVC in Los Chimalapas is voluntary and recently certified, additional consultations in the PPG phase would not significantly improve management, protection or participation in these areas. Nevertheless, stakeholder engagament will be promoted through the Stakeholder Enagaement Plan during the implementation phase and all the Project’s lifetime.

Although new face-to-face consultations will not be needed in five of the six regions considered in the Project (4 ANP and ADVC Chimalapas complex), a virtual workshop will be implemented to socialize the project and the environmental and social plans in those regions. Similarly, an in-person workshop will be implemented in the APFF Papigochic. Additionally, community involvement and stakeholder engagement will be reinforced and maintained through the Project’s Stakeholder Engagement Plan and throughout the Project's lifetime to ensure sustainable conservation efforts and ongoing collaboration .

a)

| Stakeholder Names | Dates, Locations and Methods of Engagement | Outcomes |
| --- | --- | --- |
| Name the key stakeholder contacted during PPG in this column. Add rows as necessary | When and where did you meet? Was it a meeting, consultation, workshop, etc? | What was the aim/rationale? What was discussed? What decisions were made, if any? How did this contribute to the design of the project? If/how do they want to be engaged during the implementation phase? |
| Previous consultations during PAs decreeing |  |  |
| Ejido Xbonil (87 people – 31 women – 27 indigenous peoples: Chol, Maya Zoque) Ejido Kilómetro 20 (22 people – 9 women – 16 indigenous peoples: Chol) Ejido Concepción (29 people – 6 women – 15 indigenous peoples: Chol) Ejido Constitución (27 people –7 women – 3 indigenous peoples: Chol, Maya) Ejido Conhuas (47 people – 13 women – 26 indigenous peoples: Maya) Ejido N.C.P.E. Pablo García (70 people – 19 women – 21 indigenous peoples: Maya, Chol, Zoque) Ejido Emiliano Zapata (26 people – 11 women – 3 indigenous peoples_Maya, Chol) Ejido Puebla de Morelia (20 people – 7 women – 1 indigenous people: Tzeltal) | Informative meeting Balam-Kú 26-07-2023 Calakmul municipality, Campeche | In these public consultations, the technical justification studies carried out by CONANP were presented to the stakeholders to explain the issuance of the Decree to declare the sites as protected areas. The consultation discussed the ecological significance of the proposed location. It included biodiversity, unique habitats, the presence of endangered species, and the area's environmental value, which helped justify its protection. Discussions also focused on how the designation of the protected area will affect local communities, including their livelihoods, access to natural resources, and traditional practices such as agriculture or fishing. Balancing conservation goals with the needs of local people is crucial. Participants may ask about the legal and administrative mechanisms needed to establish and manage the protected area, including the regulatory frameworks, enforcement mechanisms, and governance structures. Decisions made during these consultations include: - Establishing the boundaries of the protected area. - Identifying permitted and prohibited activities within the area. - Developing management plans for conservation and sustainable use. - Allocating resources for enforcement, monitoring, and community engagement. - These public consultations contributed to the Project design as they were the departure point for defining the needs and priorities of different stakeholders. This information was essential to developing the corresponding project activities to involve local communities in conservation efforts. They also informed the design of conservation strategies tailored to the specific challenges and priorities of the protected areas. During the implementation phase, stakeholders will continue to be engaged through regular communication, collaboration, and participation in Project activities. It may involve establishing or strengthening the Advisory Councils to reinforce local involvement in decision-making, providing training and capacity-building opportunities for local communities, and facilitating dialogue and conflict resolution mechanisms to address emerging issues or concerns. |
| Ejido Justicia Social (85 people - 15 women – 14 indigenous peoples: Maya, Chol, Tzeltal, Totonaco, Zoque) | Informative meeting Balam-Kú 26-07-2023 Escárcega municipality, Campeche |  |
| Ejido Silvituc (44 people - 12 women – 5 indigenous peoples: Chol, Maya, Tzeltal) Ejido Centenario (30 people – 5 women – 3 indigenous peoples. Chol) Ejido La Libertad (63 people – 24 women – 11 indigenous peoples: Maya, Chol) Ejido Haro (74 people – 15 women – 65 indigenous peoples: Maya, Chol) Ejido N.C.P.E. Altamira de Zinaparo (42 people – 11 women – 1 indigenous peoples: Maya) Ejido La Luna (37 people – 11 women – 11 indigenous peoples: Maya, Chol) | Informative meeting Balam-Kú 27-07-2023 Escárcega municipality, Campeche |  |
| Ejido Maravilla (22 peoples – 8 women – 2 indigenous peoples: Maya) | Informative meeting Balam-Kú 28-07-2023 Escárcega municipality, Campeche |  |
| Consejo de Pesca Productores pesqueros del sector privado Productores pesqueros del sector social (21 people – 8 women) | Informative meeting Bajos del Norte 15/11/2023 Mérida, Yucatán |  |
| Observatorio de la Biodiversidad en Yucatán (12 people – 6 women) | Informative meeting Bajos del Norte 16/11/2023 Mérida, Yucatán |  |
| Ejido Pie de la Cuesta de Santo (26 people – 1 woman) | Informative meeting Sierra Tecuani 02/12/2023 Atoyac de Álvarez, Guerrero |  |
| Comunidad Coronilla (28 people – 1 woman) Ejido Los Laureles (40 people – 1 woman) | Informative meeting Sierra Tecuani 03/12/2023 San Miguel Totolapan, Guerrero |  |
| Ejido Cuatro Cruces (36 people – 8 women) Ejido El Balcón (27 people – 4 women) | Informative meeting Sierra Tecuani 04/12/2023 Ajuchitlán del Progreso, Guerrero |  |
| Ejidos Pito, Pitales y Letrados (5 men) | Informative meeting Sierra Tecuani 04/12/2023 Tecpan Galeana, Guerrero |  |
| Ejido del Platanillo (28 people – 2 women) | Informative meeting Sierra Tecuani 05/12/2023 Tecpan Galeana, Guerrero |  |
| Ejido Los Fresnos de Puerto Rico (11 men) | Informative meeting Sierra Tecuani 05/12/2023 Ajuchitlán del Progreso, Guerrero |  |
| Ejido Piedras Grandes (36 people – 10 women) | Informative meeting Sierra Tecuani 05/12/2023 Atoyac de Álvarez, Guerrero |  |
| Ejido Bajos de Balsamar (73 people – 13 women) Ejido Los Bajitos (29 people – 1 woman) | Informative meeting Sierra Tecuani 06/12/2023 Tecpan Galeana, Guerrero |  |
| Ejidos Ciénegas de Puerto Alegre (12 men) | Informative meeting Sierra Tecuani 06/12/2023 San Miguel Totolapan, Guerrero |  |
| Ejido La Trinidad (10 people – 1 woman) | Informative meeting Sierra Tecuani 06/12/2023 Ajuchitlán del Progreso, Guerrero |  |
| Ejido de Cordón Grande (43 people – 13 women) Ejido El Moreno (39 people – 1 woman) Ejido Los Humedales (38 men) | Informative meeting Sierra Tecuani 07/12/2023 Tecpan Galeana, Guerrero |  |
| Ejido Santa María (32 people – 11 women) | Informative meeting Sierra Vallejo-Río Ameca 23/11/2023 Guachinango, Jalisco |  |
| Ejido N.C.P.E. Emiliano Zapata (37 people – 10 women) | Informative meeting Sierra Vallejo-Río Ameca 23/11/2023 Mixtlán, Jalisco |  |
| Ejido Zacatongo (23 people – 8 women – 1 indigenous people) | Informative meeting Sierra Vallejo-Río Ameca 23/11/2023 Mascota, Jalisco |  |
| Ejido La Tortuga (26 people – 13 women) Ejido San Felipe de Hijar (27 people – 6 women) Ejido Estanzuelas o El Carrizo (no data) | Informative meeting Sierra Vallejo-Río Ameca 23/11/2023 San Sebastián del Oeste, Jalisco |  |
| Ejido de Zapotán (35 people - 6 women) Ejido Cándido Salazar o La Higuerita (no data) Ejido Cumbres de Huicicila (15 men) Ejido Bella Unión (24 people – 19 women) Ejido Altavista (20 people – 3 women) Ejido Carrillo Puerto (11 people – 1 woman) | Informative meeting Sierra Vallejo-Río Ameca 23/11/2023 Compostela, Jalisco |  |
| Ejido San Antonio (11 people – 1 woman) Ejido Copalitos (30 people – 7 women) Ejido Santa Ana (27 people – 11 women) Ejido Los Reyes (24 people – 4 women) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 San Sebastián del Oeste, Jalisco |  |
| Ejido Los Cerritos (16 people – 5 women) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 Amatlán de Las Cañas, Jalisco |  |
| Ejido Santa Cruz (no data) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 Ahuacatlán, Jalisco |  |
| Ejido Tebelchía (13 people – 5 women) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 Puerto Vallarta, Jalisco |  |
| Ejido La Peñita de Jaltemba (49 people – 9 women) Ejido Ixtlán del Río (10 people - 1 woman) Ejido Úrsulo (17 people – 1 woman) Ejido Puerta de la Lima (17 people – 1 woman) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 Compostela, Jalisco |  |
| Ejido Aguamilpa (23 people – 8 women) | Informative meeting Sierra Vallejo-Río Ameca 24/11/2023 Bahía de Banderas, Jalisco |  |
| Ejido Pueblito de San Pablo (33 people – 8 women) Ejido Amatanejo (35 people – 4 women - 3 indigenous peoples) Ejido Las Juntas (19 people – 3 women) Ejido San Isidro (14 people – 3 women) Ejido Soyotán (13 people – 5 women) Ejido Las Estancias de Landero (no data) | Informative meeting Sierra Vallejo-Río Ameca 25/11/2023 San Sebastián del Oeste, Jalisco |  |
| Ejido El Colomo y Anexos (31 people – 10 women) Ejido Valle de Banderas (49 people - 19 women) Ejido Higuera Blanca (23 people – 11 women) Ejido Bucerías (20 people – 6 women) | Informative meeting Sierra Vallejo-Río Ameca 25/11/2023 Bahía de Banderas, Jalisco |  |
| Asamblea General de Comuneros (638 comuneros of 2,854) | Informative meeting Chimalapas 16/01/2023 Comunidad Agraria San Miguel Chimalapa, San Miguel Chimalapa, Juchitán, Oaxaca | The President of the Comisariado de Bienes Comunales stated the need to expand the polygonal area of the ADVC El Cordón del Retén, which has the CERTIFICATION CONANP-219/2010 dated November 26, 2009, as well as the certifications of two new community reserves located in the polygons known as Cristalina and Cieneguilla within the communal property, under the modality of ADVC. The President submitted the expansion of the ADCV El Cordón del Retén for consideration by the assembly, as well as the certification of the Cristalina and Cieneguilla reserves under the denomination of ADVC Cerro Atravesado and ADVC Cerro Prieto, respectively. These areas will be protected for 30 years and certified by SEMARNAT through CONANP. After an extensive analysis by the assembly members, the proposal was put to a vote. It was approved with 638 votes, representing 100% of the community members present. |
| Asamblea General de Comuneros (250 comuneros of 1,333) | Informative meeting Chimalapas 04/03/2023 Comunidad Agraria Santa María Chimalapa, San Miguel Chimalapa, Juchitán, Oaxaca | The renewal of the Cerro Azul ADVC certificate is submitted for analysis and approval by the assembly, as well as the certification of two new communal reserves in the Tres Picos San Isidro La Gringa - Zona Oriente polygons. CONANP, through the Director of the ISTMO Oaxacan Operational Office, explained in detail the procedure for integrating the dossier to request the certification of ADVC, informing that the ADVC is the Competence of the Federation and is established using a certificate issued by CONANP at the landowners' request. The ADVC management strategy and duties were also informed. The President of the Communal Commissariat explained that they managed to certify with CONANP, under the modality of ADVC, the communal area CERRO AZUL with CERTIFICATE NUMBER 11/2004, which expired in November 2014, but internally, by agreement of the assembly, it continues to be protected and managed. There is interest in requesting CONANP to re-certify this communal reserve and the polygons of the community reserves under the modality of ADCV, known as Tres Picos San Isidro La Gringa - Zona Oriente. The proposal was submitted to a vote and was approved with 250 votes in favor. |
| Project’s consultation processes |  |  |
| - CECADHI - Centro de Capacitación en Derechos Humanos Indígenas (Rarámuri) - Asociación Civil Awe Tibuame - Rarámuri - Awe Tibuame, Consultora - Comisariado de Pichachic - Comisariado Ejidal del Ejido El Retiro y Gumeachi - Presidente del Ejido Choguita. - Presidenta de la Unidad de Manejo Forestal San Juanito - Ecosistemas y Medio Ambiente, consultoría ambiental - Unidad de Manejo Forestal San Juanito (OSC) - Profauna, AC - Prestador de Servicios Técnicos Forestales - Prestador de Servicios Técnicos Forestales El Ciruelo - Dirección de Vida Silvestre de la Dirección de Ecología del Gobierno del Estado - Instituto Nacional de Investigaciones Forestales, Agrícolas y Pecuarias - Comisión Nacional Forestal - Dirección de Desarrollo Forestal del municipio de Bocoima - Secretaria de Desarrollo Urbano y Ecología del gobierno del estado - Distrito de Desarrollo Rural San Juanito de Sader - Comisión Nacional de Áreas Naturales Protegidas (21 people – 9 women – 2 indigenous peoples) | Informative meeting Papigochic 19/03/2024 San Juanito, Chihuahua | The MEx30x30 Project was presented, addressing the general and specific objectives, the institutions involved, the components, and the PAs and ADVCs considered. FMCN's environmental and social safeguards were also presented, as well as the project's environmental and social plans: Environmental and Social Management Plan, Stakeholder Engagement Plan, Gender Mainstreaming Plan, Indigenous Peoples Plan, Community Health, Security and Safety Plan, and the Grievance Redress Mechanism. The attendees were invited to comment on the project, the possible risks or associated impacts, and mitigation measures proposed in each plan presented. Stakeholders identified various problems affecting forest management and the well-being of communities in the region, including species germplasm and relict areas loss, forest fires, illegal timber extraction, inadequate water and waste management, deficient community organization, insufficient training, restricted access to certain areas for security reasons, and lag in the application of government resources. They proposed specific mitigation measures to address these problems. Participants also identified other stakeholders for the project, such as municipal authorities, universities, NGOs, and timber and tourist enterprises. Regarding gender gaps, stakeholders proposed organizing workshops and training for people of all ages to raise awareness of the social benefits of reducing gender gaps and promoting equal opportunities between men and women. They suggested including gender mainstreaming in ejidos' internal regulations under Article 4 provisions from the Mexican Constitution to ensure greater diversity and representativeness in ejidos' decision-making structures and other spheres of community life. Additionally, they suggest fostering jobs that women can perform to promote their empowerment and contribute to gender equity in the labor and social spheres. About Indigenous Peoples, stakeholders acknowledged the importance of implementing conservation actions in close coordination with the Rarámuri community, recognizing their profound knowledge of the natural environment and their culture rooted in the land. Spaces for dialogue, meaningful consulting, and representation in decision-making processes were proposed, respecting their cultural relevance, valuing their ancestral wisdom, and addressing their needs and interests. In this sense, it is fundamental to invite indigenous governors and community leaders to participate in these processes and provide guidance and support related to their rights, procedures, support, and benefits. Regarding community health, and safety issues, stakeholders proposed including essential equipment, such as first aid kits and personal protection equipment. It was also suggested that social security be considered for firefighting projects. All these pertinent comments, proposals, and suggestions will be incorporated into the activities to be financed. |
| Balam-Kú Comisión Nacional de Áreas Naturales Protegidas Bajos del Norte Fundación Bepensa. Ecologistas subacuáticos de Yucatán A.C. Instituto Mexicano de Investigación en Pesca y Acuacultura Sustentable. Comunidad y Biodiversidad (COBI). Pronatura Península de Yucatán. Sociedad Cooperativa de Pescadores del Golfo de México. Comisión Nacional de Áreas Naturales Protegidas CARDRN 043 Nayarit Unidad Especializada en Biodiversidad y Agrobiología del Centro Nayarita de Innovación y Transferencia de Tecnología de la Universidad Autónoma de Nayarit. Comisión Nacional de Áreas Naturales Protegidas Junta Intermunicipal de Medio Ambiente de Sierra Occidental y Costa Programa de las Naciones Unidas Fundación Biosfera de Álica, A.C. Alianza Jaguar A.C. Instituto Politécnico Nacional (UPIIZ) Propietarios Particulares del Municipio de Mezquital, Durango Presidencia Municipal de Jiménez del Teul, Zacatecas Propietarios Particulares el Municipio de Jiménez del Teul, Zacatecas Comunidad Indígena de Santa María de Ocotan y Xoconoxtle Universidad Autónoma de Aguascalientes, Conservación de la Biodiversidad del Centro de México A. C. Presidente de bienes comunales de la comunidad San Bernardino de Milpillas Chico Dirección Técnica de la Comunidad San Bernardino de Milpillas Chico Chimalapas ADVC El Cordón del Reten ADVC Reserva Comunal Cerro Atravesado ADVC Reserva Comunal Cerro Prieto ADVC Reserva Comunal Cerro Azul ADVC Reserva Comunal La gringa-Zona Oriente ADVC Reserva Comunal Tres Pico CONANP - Dirección Regional de la Frontera Sur, Istmo y Pacifico Sur. CONANP - Dirección Regional Istmo Oaxaqueño Sierra Tecuani Encargado de la RB Sierra Tecuani Universidad Autónoma de Guerrero CONANP - Dirección Regional Centro y Eje Neovolcánico SEMAREN Procuraduría de Protección Ambiental Estado de Guerrero Ejido Cordón Grande Unión de Ejidos Forestales y Agropecuarios Hermenegildo Galeana (58 people – 14 women – 1 indigenous people) | Virtual meeting Balam-Kú, Bajos del Norte, CADRN 043 Nayarit, Sierra Tecuani, Chimalapas 20/03/2024 ZOOM | The MEx30x30 Project was presented, addressing the general and specific objectives, the institutions involved, the components, and the PAs and ADVCs considered. FMCN's environmental and social safeguards were also presented, as well as the project's environmental and social plans: Environmental and Social Management Plan, Stakeholder Engagement Plan, Gender Mainstreaming Plan, Indigenous Peoples Plan, Community Hygiene, Health and Safety Plan, and the Grievance Redress Mechanism. The attendees were invited to comment on the project, the possible risks or associated impacts, and mitigation measures proposed in each plan presented. Multiple problems were identified in the different PAs and ADVCs participating, including the sale of agrarian common-use rights to third parties, irregular human settlements, land-use change due to agriculture and cattle ranching expansion, solid waste management, forest fires, poaching, illegal logging, climate change, pests and invasive alien species, security issues, and pressure from unsustainable activities (e.g., mining, forest harvesting, tourism). Mitigation measures were also proposed to encourage natural resource conservation and economic benefits for the communities, including subsidies and environmental services programs (e.g., carbon credits), land tenure regularization, community participation in decision-making regarding natural resource management through consultation and consensus mechanisms, educational and awareness-raising programs for responsible consumption practices, waste separation, and recycling, strengthening waste management infrastructures and systems, training brigades for fire prevention, management, and combat, innovative technologies and strategies to monitor fires, early warning systems and adaptation plans to climate change and natural disasters, community-based brigades, monitoring, control and eradication of invasive species, adoption of good agricultural practices and promote the application of agroforestry and silvopastoral models, and strengthening of community forestry enterprises. Participants proposed incorporating additional stakeholders into the Project, such as the National Agrarian Registry, the Agrarian Attorney's Office, municipal governments, indigenous peoples, ejidatarios and comuneros, the National Institute of Indigenous Peoples (INPI), the Health and Public Education Ministries, academia, tourism operators, PROFEPA, technical forestry service providers, livestock and agricultural associations, fishing cooperatives, and NGOs. Regarding gender, stakeholders proposed training programs to strengthen women's skills and knowledge in areas relevant to community management and local development. Implement specific projects to promote women's economic and social empowerment and provide childcare services to facilitate women's participation in conservation initiatives. Facilitating women's participation, especially indigenous women, in the ejido's decision-making bodies and guaranteeing their representation and voice in the planning and project execution processes were also mentioned. Collaborating with civil society organizations, educational institutions, government agencies, and other relevant actors may facilitate gender equality and women's empowerment in rural areas. Likewise, pertinent information on human rights, gender, and citizen participation should be disseminated, and mechanisms for attention and follow-up on complaints should be established. On Indigenous Peoples, participants recognized that it is critical to have leaders who can serve as intermediaries and cultural translators between the indigenous communities and the authorities. They also emphasized the importance of valuing indigenous peoples' uses, customs, traditions, cultural wealth, and ancestral knowledge of natural resources. Thus, the proposal includes training CONANP staff in intercultural issues and community participation to raise awareness of indigenous people's rights and promote intercultural dialogue and mutual respect between authorities and local communities. Training and empowering indigenous peoples in legal issues is another crucial aspect to ensure their effective participation and representation in decision-making processes. Developing differentiated calls for proposals and opportunities for IP considering indigenous languages and specific barriers, such as lack of internet access and limited understanding of program operating rules, was also important. Collaboration and coordination between the INPI and other government institutions and promoting indigenous people's involvement in advisory councils were also advised to ensure inclusion and equity. In health, and safety, security and safety measures for immediate action to guarantee the protection of those who work in environmental conservation were proposed, such as implementing life insurance to provide additional protection to these workers and their families and first aid training. It also commented on the need for sustainable agricultural practices, organic fertilizers, and avoiding insecticides and herbicides. All these pertinent comments, proposals, and suggestions will be incorporated into the activities to be financed. |

b. Project Disclosure

Disclosing project information is essential for meaningful consultation on project design and for stakeholders to understand the potential opportunities of the project, and the risks and impacts of the project.

Confirm that the following information was shared with stakeholders in a timely manner and in an appropriate form and language during the PPG/PPF Phase:

| Information | When, How and Where this was shared? |
| --- | --- |
| The purpose, nature and scale of the project | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |
| The duration of proposed project activities | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |
| Information from the environmental and social safeguard screening process, regarding potential risks and impacts of the project on stakeholders, including: - Proposals for mitigating risks and impacts - Potential risks and impacts that might disproportionately affect vulnerable and disadvantaged groups - Description of differentiated measures to be taken to avoid and minimize disproportionate risks and impacts | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |
| The proposed stakeholder engagement process, highlighting ways in which stakeholders can participate and contribute during project design and/or implementation | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |
| The time and venue of proposed public consultation meetings, and the process by which meetings will be notified, summarized and reported | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |
| The process and means by which grievances can be raised and addressed | Consultations during PAs decree Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in 2023. Consultations during Project Preparation Information was shared in stakeholder meetings described in table in Section IVa. Information was shared with stakeholders during workshops in March 2024. |

c. Reporting of Indicators

| Number of stakeholder entities (disaggregated by type) involved in the project | Consultations during PAs decree Government authorities: 4 OLLCs: 0 Local communities and ejidos: 68 Donors and private sector: 0 Consultations during Project Preparation Government authorities: 9 OLLCs: 13 Local communities and ejidos: 18 Donors and private sector: 1 Academia: 6 |
| --- | --- |
| Number of persons (disaggregated by gender) who participated in the project | Consultations during PAs decree TOTAL: 2,851 Female: 473 Male: 1490 Unknown: 888 Consultations during Project Preparation Total: 79 Female: 23 Male: 56 |

d. Lessons Learned:

FMCN’s experience working with CONANP in similar projects and locations was useful for designing stakeholder engagement strategies and coordinating on the ground activities for the Project. CONANP prior process for decreeing the Project’s PA and ADVC was also advantageous. For example, prior experience informed the dissemination strategies, including when and where to hold workshops, which types of materials to disseminate and through which channels (e.g., radio, posters, workshops, meetings, attendance at local committees). Prior experience also revealed the importance of disseminating information in indigenous languages using the media they use most, as well as the value of other means of communication used among the rural and indigenous population. Similarly, verifying that workshops avoid coinciding with holidays and considering electoral bans or other processes that may affect dissemination activities was also critical.

SECTION V: Stakeholder Engagement in the Implementation Phase

| Stakeholder Name | Method of Engagement | Location and Frequency | Resources Required | Budget |
| --- | --- | --- | --- | --- |
| Name the key stakeholder and group type to be engaged. Add columns as necessary. | How will you involve and engage this stakeholder? (meeting, consultation, workshop, discussion, etc) | Where and When will you engage with this stakeholder? | What materials (presentations, websites, brochures, surveys, translation) are needed? What personnel are needed to lead and monitor these engagements? | How much will this engagement cost? Consider resources required, staff, transportation, etc. |
| Comisión Nacional de Áreas Naturales Protegidas (CONANP) | - Face-to-face and virtual meetings - Emails - Project Inception workshop - Capacity building workshops | Project inception workshop will be held during the first three months of project implementation. Constant coordination through the Technical Committee. Regular formal communication (emails, meetings, telephone) will ensure timely information is shared. | Presentation materials, policy briefs, reports and other materials. Staff time; travel support; meeting venue, and catering for meetings. | Project inception workshop USD$2,000 Capacity building workshops USD$3,000 Steering Committee Meetings (CTFANP) USD$1,500 TOTAL USD$6,500 |
| CONANP-PAs Advisory Councils | - Project Inception workshop - Informative meetings - Emails - Webinars - Training workshops | Regular formal communication (emails, meetings, telephone) will ensure timely information is shared. | Presentation materials, policy briefs, reports and other materials. Staff time; travel support; meeting venue, and catering for meetings. |  |
| Legally Constituted Local Organizations (OLLCs) | - Emails - Face-to-face and virtual meetings - Project Inception workshop - Training workshops - Feld visits | Project inception workshop will be held during the first three months of project implementation. Constant engagement by POA activities. | Presentation materials, project updates, brochures, leaflets and other materials. Staff time; travel support; meeting venue and catering for meetings. | POA implementation USD$500,000 |
| Communities and ejidos in PAs and ADVCs | - Consultation meeting - Project Inception workshop - Face-to-face and virtual meetings - WhatsApp and social media - Training workshops - Field visits | Project inception workshop will be held during the first three months of project implementation. Constant engagement through OLLCs and POA activities. | Presentation materials, outreach materials, brochures, leaflets and other materials that are culturally appropriate and gender-sensitive, written in Spanish and indigenous languages where needed. Staff time; travel support; meeting venue and catering for meetings. | Included in POA |
| Indigenous Peoples in PAs and ADVCs | - Consultation meeting - Project Inception workshop - Face-to-face and virtual meetings - WhatsApp and social media - Training workshops - Field visits - Dedicated support mechanisms to address vulnerable groups’ specific needs and concerns, providing necessary accommodations. | Project inception workshop will be held during the first three months of project implementation. Constant engagement through OLLCs and POA activities In-person meetings and field visits. | Accessible meeting materials, adapted documents, and translated to local languages resources that are culturally appropriate and gender-sensitive where needed. Staff time; travel support; meeting venue and catering for meetings. | Included in POA |
| Donors and private sector | - Project Inception workshop - Emails - Face-to-face and virtual meetings - Workshops - Focus group meetings | Project inception workshop will be held during the first three months of project implementation. Specific engagements regarding technical assistance and financing opportunities. | Presentation materials, policy briefs, reports and other materials. Staff time; meeting venue and catering for meetings. |  |
| Disadvantaged/ Vulnerable Groups (Youth, elderly, women, people with disabilities) | - Project Inception workshop - Face-to-face and virtual meetings - WhatsApp and social media - Training workshops - Field visits - Dedicated support mechanisms to address vulnerable groups’ specific needs and concerns, providing necessary accommodations. | Project inception workshop will be held during the first three months of project implementation. Constant engagement through OLLCs and POA activities In-person meetings and field visits. | Accessible meeting materials, adapted documents, and translated to local languages resources that are culturally appropriate and gender-sensitive where needed. Staff time; travel support; meeting venue and catering for meetings. |  |
| Project Steering Committee (CTFANP) | - Regular meetings and reports - Emails - Website updates - Presentations - Brochures and leaflets - Minutes | Project inception workshop will be held during the first three months of project implementation. Specific engagements regarding project progress. | Presentation materials, policy briefs, reports and other materials. Staff time; meeting venue and catering for meetings. |  |

The Project will endeavour to make information available to the public to allow stakeholders to get to know and understand both the environmental and social risks and impacts associated with the project, as well as opportunities provided by the project.

On an ongoing basis, the project will have a routine disclosure on the Project’s environmental and socio-economic performance. The disclosures will be done to all stakeholders through project briefs, FMCN’s webpage, social media, annual reporting, community of practice, learning exchanges, among other mechanisms.

SECTION VI: Monitoring and Reporting

The project will report on a quarterly basis (using the CI-GEF Quarterly Reporting template), progress made towards the implementation of the SEP.

On an annual basis and using the CI-GEF Project Implementation Report (PIR) template, the following CI-GEF’s minimum indicators are to be reported. The project can include other appropriate stakeholder engagement indicators in addition to the CI-GEF’s indicators.

*The following table will be completed after the workshops.

| Indicator | Baseline | Target |
| --- | --- | --- |
| - Number of stakeholder entities (disaggregated by type) involved in the project implementation phase. | 0 | TBD* Government POA # Local communities and ejidos # Indigenous Peoples # Donors and Private sector # Other vulnerable/disadvantaged people's groups |
| - Number of persons (disaggregated by gender) who participated in the project implementation phase. | 0 men 0 women | 300 men 300 women |
| - Number of engagements (disaggregated by type of engagement) with stakeholders in the project implementation phase. | 0 | TBD* |

* Targets will be reviewed during project implementation.

| Person responsible for implementing and monitoring the SEP: | Safeguards and Monitoring and Evaluation Coordinator |
| --- | --- |
| How/Where will the approved SEP be disclosed: | The approved SEP will be disclosed via the project’s website and at the inception meeting with stakeholders. |
| When will the approved SEP be disclosed: | The approved SEP will be disclosed in the first quarter of the implementation phase. |

Accountability & Grievance Mechanism (AGM)

The CI-GEF/GCF Project Agencies require all Project to have an Accountability and Grievance Mechanism in place so that Project-affected communities and other stakeholders may raise a grievance at all times to the Executing Agency/Entity, CI, the GEF or GCF on non-compliance with the ESMF. Affected communities should be informed about this possibility and contact information of the respective organizations at relevant levels should be made available publicly. Affected communities should also be assured that their grievances will be addressed in a timely manner, they will not face retaliation for submitting a grievance, and they have the option to request confidentiality.

SECTION I: Project Information

| PROJECT TITLE: | MEx30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| --- | --- | --- | --- | --- |
| GEF/GCF PROJECT ID: |  |  | PROJECT DURATION: | 60 months |
| EXECUTING AGENCY/ENTITY: | Fondo Mexicano para la Conservación de la Naturaleza, A.C. (FMCN) |  |  |  |
| PROJECT START DATE: | TBD2025 |  | PROJECT END DATE: | TBD2030 |
| AGM PREPARED BY: |  | FMCN – Socioenvironmental Research Coordinator |  |  |
| DATE OF (RE)SUBMISSION TO CI-GEF/GCF: |  | 10/03/2024 |  |  |
| AGM APPROVED (CONDITIONALLY) BY: |  | Ian Kissoon, Senior Director, ESMF, CI-GEF Agency |  |  |
| CONDITIONS: |  | AGM to be validated with stakeholders during the next phase |  |  |
| DATE OF CI-GEF APPROVAL: |  | March 22, 2024 |  |  |
| Provide a short summary of the Project and its main activities to provide a context for the AGM. The Project "Mexico: Conserving Mexican biodiversity through communities and their protected areas" has as objective to help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex). MEx30x30 has three main objectives to reach this goal: - To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively; - To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance. - To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and local communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system. The Project will focus on the following components: - Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget. - Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding. - Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established. - Component 4. Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project. MEx30x30 is an opportunity to scale up all the lessons learned in 26 years of a successful partnership between FMCN and CONANP. It will also make possible the 30x30 goal, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes. |  |  |  |  |

SECTION II: Scope

- What kinds of grievances (e.g. lack of engagement, non-adherence to agreements, on-going conflicts over natural resources, disadvantage groups being excluded) are anticipated? List all potential grievances even if they fall outside of the scope of the ESMF. In the next question, identify those that would be considered eligible by the Project’s AGM. Various grievances may arise when implementing a project within a protected area due to different stakeholders' interests, environmental concerns, and socio-economic factors. Anticipating potential grievances is crucial for effective project management and conflict resolution. Here are some common types of grievances that may occur: - Stakeholders, including local communities, NGOs, or indigenous groups, may feel that they are not being adequately engaged in the decision-making process regarding the Project. - Competing interests over natural resources within the protected area, such as water or land, can lead to conflicts. Different groups may have divergent views on resource use, allocation, and management. - There may be grievances regarding the exclusion or marginalization of particular social or ethnic groups from the Project's benefits. It could be due to unequal distribution of resources, employment opportunities, or other socio-economic advantages. - Grievances may arise if the Project's environmental and social impact mitigation measures are perceived as insufficient or ineffective. It can be particularly true if unforeseen consequences need to be adequately addressed. The Project must communicate transparently and inclusively and collaborate with relevant stakeholders throughout the Project lifecycle. Thus, developing effective Stakeholder Engagement Plan (SEP) and grievance redress mechanism can mitigate tensions and promptly address concerns. - What grievances are eligible and would be received? The Project-level GRM entertains all complaints, comments, and suggestions to improve the Project’s efficacy and efficiency, and operates throughout the Project’s life cycle, but it is neither a court of appeals nor a legal mechanism. The GRM at the Project-level receives complaints from: - Individuals or groups of two or more individuals, communities, or organizations that believe they have been or may be affected by the adverse impacts of the Project. - The legitimately allowed representative(s), provided that they submit written proof that they are authorized to represent the persons or groups of persons, communities, or organizations on whose behalf they are acting. - Persons or entities executing activities financed by the Project. - Workers linked to the Project, regardless of their position or seniority. According to the Whistleblower Protection Policy (see Section 4.7 Whistleblower Protection Policy of the Organizational Manual), whistleblowers will not receive any retaliation for their complaints. - Individuals who are members of the committees related to the Project. - Persons providing consulting services or goods and services related to the Project. The GRM receives complaints or allegations related to fraud, acts of corruption, non-compliance with FMCN's Code of Ethics, institutional procurement disputes, nonconformities regarding FMCN personnel, and environmental and social issues and breaches to the environmental and social management framework related to the Project. The GRM at the Project-level does not process complaints when: - FMCN is not responsible for the financing of the Project to which the complaint is appealing; - the specific issues or matters have already been reviewed and concluded by the GRM in another proceeding (e.g., the grievant has agreed to the solution and measures has been adopted for resolution), unless the request presents new information, material, or evidence that was not available at the time the GRM previously considered the complaint; - they are unfounded; - they seek to gain a competitive advantage; - they are submitted 24 months after the closing of the Project; - they are anonymous. Complaints should be addressed to FMCN's GRM and can be submitted in writing via postal mail (Francisco Sosa # 102, Santa Catarina, C.P. 04010, Coyoacán, Mexico City), by e-mail (denuncia@fmcn.org) or by telephone (55 5611 9779 and 55 3701 3801). FMCN also receives complaints due to supervisory procedures, such as field visits, interviews, or personal and direct observation. Complaints may be submitted in writing in Spanish or the applicant’s(s) language, accompanied by a Spanish translation. Complaints may be received by any Project's operational or administrative team member, who must immediately forward them to the Project's Area Director. No specific format is required to file a complaint. However, to be considered by GRM at the Project-level, it must contain the following: - The name, address, telephone number, e-mail address, or other contact information of the person or persons filing the complaint. - If the complaint is issued through a representative, the representative must include written proof that they are empowered to represent the persons or group of persons, communities, or organizations on whose behalf they are acting, as well as provide the identification of the person(s) on whose behalf they are submitting the request. - Indication if the applicant(s) wishes additional measures to preserve the confidentiality of their identity and the corresponding justification, if applicable. - The name, location, and nature of the Project or Annual Operating Plan (POA) that has caused or may cause adverse impacts. - A brief explanation of the situation presented in the Project or POA. - A proposal of how the complaint could be resolved (if any, but this is an optional requirement). - Any other information they deem relevant, including documents, media reports, photographs, videos, and recordings, which may assist or facilitate the processing of the complaint by the GRM at the Project-level. The GRM at the Project-level is aligned, at all times, to FMCN's relevant operational policies, such as the Code of Ethics, Privacy Notice, Whistleblower Protection Policy, Procurement Conflict Resolution Policy, Prohibited Practices Policy, Fraud and Corruption Statement, Prevention of Money Laundering and Terrorist Financing Policy, Protection from Sexual Exploitation, Abuse and Harassment Policy, and Environmental and Social Policy, which aim to prevent, avoid and mitigate harmful activities or institutional misconduct. - How will the mechanism ensure transparency and fairness? To ensure transparency in handling and processing grievances, FMCN's Internal Audit is responsible for the effective and efficient functioning of the GRM (see Section A6.5.6 of FMCN’s Operations Manual). The Internal Auditor occupies an independent and objective position within FMCN’s structure, as she reports directly to the Board of Directors and the Institutional Accompaniment Committee (CAI); both governing bodies are independent and composed of persons external to the institution. In the event of serious complaints, the relevant Committee oversees the activities of the Project-level GRM, takes appropriate action, and monitors, through its representative, the implementation of agreements reached with the individuals who made the complaints. This is done through problem-solving methods and implementing decisions made in response to the recommendations of the Project-level GRM. If there is a conflict of interest with the relevant Committee, the Institutional Accompaniment Committee (CAI) handles the complaint. The different areas of FMCN cooperate with the GRM at the Project-level in the inquiries carried out to respond to the complaints admitted. During the GRM process, the complainants are kept informed of the handling process and the outcome of the redress process promptly (see Section A6.5.6 of FMCN’s Operations Manual). As confidentiality is an integral part of fairness, the identity and personal details of complainants are never revealed; instead, a folio assigned to the case is used. - Will the mechanism receive anonymous grievance? The Project-level GRM does receive anonymous grievances. However, to be considered, they must contain the person or persons filing the complaint’s name, address, telephone number, e-mail address, or other contact information. Nevertheless, the person or persons filing the complaint may indicate whether they wish to keep their identity and the grounds for their complaint confidential. In this regard, the GRM at the Project-level will not supersede the judicial remedies available to the complainant.

SECTION III: Awareness and Accessibility

This section intends to understand how the Project plans to ensure that their different methods to socialize and access the AGM is appropriate to the Project’s stakeholders. The Project should place a special effort in securing accessibility to their AGM especially for women and those from disadvantaged groups (elderly, young people, persons with disabilities, LGBTQ, indigenous/traditional peoples, those with lowest literacy levels, among others). These groups usually are in disadvantage within their own communities and may have additional or different barriers to access given channels of communication. In the next table, the Project must ensure that they identify these differentiated barriers and include methods and accessibility adaptations intended to address them, closing gaps in accessibility to Project AGM.

| Method of Socialization | Intended Audience | Accessibility adaptations | Frequency of the action/channel | Budget |
| --- | --- | --- | --- | --- |
| How will the Project disseminate the AGM to stakeholders? What channels will be used? (e.g. via the Project’s website, at the inception meeting with stakeholders, printed and posted on notice board in community centre, radio announcement, flyers, posters, SMS/text/WhatsApp messages, illustration/animated video, at the end of every presentation or community engagement) | Who are the stakeholders the Project is intending to reach using each different channel? (e.g. government officials, indigenous/traditional peoples, etc.) | What adaptations to cater diverse groups (especially disadvantaged/vulnerable groups) will be in place for every method/channel? (e.g. translated versions for local languages, infographics for those with low literacy levels, traditional communication methods, post-in of information in high traffic areas of affected stakeholders, women’s gathering spaces) | When and how often will the Project disseminate/socialize the AGM to stakeholders? (The EA is required to continuously socialize the AGM with all stakeholders involved at different stages of Project implementation) | Indicate the estimated costs to socialize the AGM and make it accessible to diverse groups and be culturally appropriate. Please work with the finance lead to ensure that the budget costs are included in the Project’s overall budget. |
| - FMCN’s website and social media - Inception meetings - Information sessions - Workshops - Webinars - Field trips Learning community | - Governmental agencies - Civil Society Organizations - Private sector | - Tailored materials by geographical location (infographic and social media posts) | From the beginning of the Project and during the whole Project lifetime | 10% salary and benefits of FMCN’s Communication Specialist |
| - FMCN’s website and social media - Inception meetings - Information sessions - Workshops - Webinars - Field trips - Learning community | - Local and indigenous communities, including vulnerable groups (women, elderly, youth, people with disabilities) | - Tailored materials by geographical location. For example, visual large-font printed materials with simple language and culturally relevant imagery, such as brochures, infographics, and posters distributed in community centers and places where women or other vulnerable groups gather; local radio broadcasts; social media posts and online articles for those with internet access; community meetings in accessible locations for direct interaction and privilege oral communication. - Translated versions for local languages - Use a mix of traditional (radio, posters) and digital channels (WhatsApp, social media) | - From the beginning of the Project and during the whole Project lifetime | - 10% salary and benefits of FMCN’s Communication Specialist |

Please reply to the questions below, which intend to address the adaptations and capacity of the AGM to be gender-responsive and has adaptations in place to address differentiated needs from disadvantaged groups: - Are the persons responsible of the GRM aware and knowledgeable of the commitment of the mechanism to be gender responsive and inclusive of those in disadvantaged groups? Explain your answer. FMCN’s Internal Auditor handles the complaints received to ensure independence from the design and implementation teams, as the position directly reports to the Board of Directors and the Institutional Accompaniment Committee (CAI). The Internal Auditor has suitable qualities to process complaints, especially severe ones, and is in continuous training to handle them. For example, a Master's Degree in Defense and Promotion of Human Rights (Honorable Mention) from the Autonomous University of Mexico City, and several training courses such as Grievance Redress Mechanism Online Course (Green Climate Fund), Community Mediation Training (Green Climate Fund), Gender Mainstreaming Course (Green Global Growth Institute), and ISO 31000: Risk Management (European School of Excellence). - Are the formats in place and channels available gender-sensitive and inclusive of those in disadvantaged groups? For example, the different formats ask the grievant to specify if they prefer mediators of a certain gender or with context-specific gender expertise so that they feel more comfortable, particularly if there are instances of SEAH involved. Explain your answer. The Project-level GRM seeks to be accessible, efficient, safe, and fair to women and other vulnerable groups (e.g., indigenous peoples), taking the barriers they are more likely to face into account concerning language, literacy levels, access to information and digital technology, mobility, and lack of time due to unpaid care responsibilities. It involves, among other things: - Ensuring grievance mechanism staff develops a gender sensitivity and prevents unconscious bias via continuous training. GRM staff should also know about the Gender Policy, the Policy to protect against sexual exploitation, abuse, and harassment, and other related policies. - Ensuring dissemination of the grievance mechanisms to all individuals, particularly women, different gender identities, and vulnerable groups, mainly during outreach events and in-person or virtual workshops, considering potential lower literacy levels (e.g., verbal communication and relevant materials). - Establishing multiple channels to maximize access and relevance (in-person, toll-free hotline, e-mail, postal address, and social media). - Providing for independent, culturally appropriate, gender-sensitive investigations of violations and committing to addressing power imbalances during dispute resolution processes. It includes giving the complainant the option to select a mediator of a particular gender so that they feel more comfortable, mainly if there are instances of Sexual Exploitation, Sexual Abuse, and Sexual Harassment involved. - Protecting all people who register complaints from retaliations by maintaining absolute confidentiality of complainants unless they have agreed otherwise. - Including women counselors within the Board of Directors and the Institutional Accompaniment Committee in the GRM process. - Monitoring the grievance mechanism to ensure access and remediation outcomes are provided on an equal basis and incorporating lessons learned for improving its effectiveness to be inclusive and gender-responsive.

SECTION IV: Channels for Receiving/Reporting/Registering Grievances

Please list all the channels that will be part of the AGM of the Project, this can include boxes or reporting points, virtual channels, or other any other applicable channels.

| FMCN |  |
| --- | --- |
| Postal address(es): | Francisco Sosa # 102, Santa Catarina, C.P. 04010, Coyoacán, Mexico City |
| Telephone/Fax Number(s): | 55 5611 9779 & 55 3701 3801 |
| Email address(es): | denuncia@fmcn.org |
| CONSERVATION INTERNATIONAL |  |
| Postal address(es): | Conservation International Director of Compliance, Conservation International 2011 Crystal Drive, Suite 600 Arlington, VA 22202, USA |
| Webpage: | CI’s EthicsPoint Hotline: https://secure.ethicspoint.com |

SECTION V: Processing and Documentation

Processing Describe how your mechanism will handle and process the grievances. - How will the grievance be screened to ensure it is related to the GEF/GCF Project? The GRM at the Project level has specific eligibility criteria to screen and process complaints related to any FMCN-funded Project, yet complaints will be excluded when: - FMCN is not responsible for the financing of the Project to which the complaint is appealing; - the specific issues or matters have already been reviewed and concluded by the GRM in another proceeding unless the request presents new information, material, or evidence that was not available at the time the GRM previously considered the complaint; - they are unfounded; - they seek to gain a competitive advantage; - they are submitted 24 months after the closing of the Project, - they are anonymous. - How will the mechanism deal with confidentiality? The GRM allows any person or persons filing a complaint to indicate whether they wish to keep their identity and the grounds for their complaint confidential. Internal Audit is responsible for maintaining the grievant’ s personally identifiable information secure. Thus, the complainer’s information is kept secret at every stage of the process. Instead, the folio (reference number) is used. Records are retrievable by folio, which are cross-referenced by individual names. Access to and use of grievance documents are limited to Internal Audit or personnel who need the records to perform their official duties (e.g., General Director). - How will the mechanism protect grievants from retaliation for submitting a grievance? FMCN has a Whistle-blower Protection Policy to provide comprehensive protection against retaliation or discrimination against those who express grievances. Additionally, the GRM specifies that confidentiality is guaranteed for people who request it and secures that the complainant’s identity is not revealed without the complainant’s authorization. - How will the mechanism handle oral/verbal grievances? FMCN’s GRM receives and acknowledges any complaint verbally or in writing through postal mail, e-mail, telephone, and in-person during supervisory procedures, such as field visits, interviews, or personal and direct observation. All complaints are handled according to the process established in FMCN’s Organizational and Operations Manuals. - How will the mechanism deal with grievances that are ineligible? If the complaint is deemed to be outside the scope of the grievance mechanism (not eligible), the complaint must be rejected, providing the petitioner with a written explanation of why the complaint is beyond the scope of the GRM and, if possible or applicable, guidance on where to address the problem. The Internal Auditor or the head of the receiving area should sign the explanation. - How will your mechanism acknowledge receipt of the grievance? How long will it take for this receipt to be given to the grievant? Once a complaint is received, the Internal Auditor or/and Area Director must acknowledge receipt of the grievance to the complainant. They have five working days to assess the complaint eligibility as part of an internal assessment process. If not eligible, the Internal Auditor or/and Area Director responds to the grievance, explaining why the complaint was not considered. If eligible, the Internal Auditor or/and Area Director explain the procedure to be followed. - How long will your mechanism take to provide a resolution to the grievant? Once a complaint is received, the Internal Audit or/and Area Director has five working days to review the complaint eligibility and inform the person or group filing the complaint of the acknowledgement, eligibility, and the procedure to be followed. When an investigation is required, or the issue must be transferred to the next level, the deadline for a resolution is 20 working days. If there are any factors that delay the process, an extension may apply, and the grievant should be informed of the reasons for the delay and the revised timeframe. - Do you plan to provide periodic updates throughout the process to the grievant? As the grievance progresses, the GRM will provide periodic updates to the grievant regarding the status and current actions to resolve the grievance so there is a clear understanding of how the grievance is being addressed. Updates may be informed through an email, a letter, or verbally (followed by written confirmation). Files for each grievance will be available for review by the claimant through the folio (reference number) used, and appropriate steps will be taken to maintain the confidentiality of the claimant if previously requested. - Will there be a tiered system where grievances get classified/escalated depending on their seriousness or ability to be resolved? A tiered system could be to first address the grievance at the field level; second level can be at the Project Management Unit; third level can be at the Project Steering Committee level; and fourth level can be CI’s EthicsPoint Hotline. FMCN’s GRM is a tiered system, which makes the following distinctions: - When the complaint is simple, does not involve the operational team, and does not require further information, the Area Director proposes the solution and, together with the person(s) filing the complaint, decides whether the option offered is acceptable to both parties. - When the complaint requires an investigation, the Area Director requests support from the Internal Audit to analyze and assess the magnitude of the adverse effect, compile the necessary documentation, and conduct the appropriate interviews. Internal Audit will keep General Management informed. After analysis, Internal Audit issues a recommendation, which may include the issuance of an administrative report; a warning; cancellation or modification of a Project or POA; dismissal of the person involved; escalation of the complaint to the Committee corresponding to the Project; or presentation of the matter to the Institutional Accompaniment Committee. Where appropriate, the proposed solution for complaints about the field execution of Project or POAs is made jointly with the corresponding Area Directorate. In contrast, those of an administrative nature, disputes over acquisitions, and managing financial resources related to Project and POAs will additionally involve the Finance Directorate. Internal Audit carries out this process independently when the complaint or allegation involves FMCN's operational or administrative team. In both cases, implementing the recommendation requires authorization from General Management to be considered an institutional resolution. - When the complaint involves FMCN's General Management or an Area Director, Internal Audit immediately refers the case to FMCN's Institutional Accompaniment Committee or the Board of Directors, depending on the nature of the complaint. - If the grievance is related to CONANP, the claim should be through CONANP’s channels established in Section IV. - If the grievant prefers, s/he may choose to file a claim through CI’s EthicsPoint Hotline at https://secure.ethicspoint.com. Alternatively, the grievant may file a claim with the Director of Compliance (DOC) who is responsible for the CI Accountability and Grievance Mechanism and who can be reached at: Director of Compliance, Conservation International 2011 Crystal Drive, Suite 600 Arlington, VA 22202, USA. - How will the grievance be verified? Will there be site visits, face-to-face meeting, etc. Internal Audit is responsible for investigating the complaint and gathering facts to understand the grievance’s circumstances clearly. Modes of verification typically include a review of documents, a meeting with the complainant (if known and willing to engage), a meeting with those who can resolve the issue (including members from the implementing agencies), and, if appropriate, site visits. - What’s the institutional/organizational structure to handle grievances? Will the grievance be assigned/directed to a specific Project staff or committee to deal with the grievance? FMCN’s GRM is a tiered system, which makes the following distinctions: - When the complaint is simple, does not involve the operational team, and does not require further information, the Area Director proposes the solution and, together with the person(s) filing the complaint, decides whether the option offered is acceptable to both parties. - When the complaint requires an investigation, the Area Director requests support from the Internal Audit to analyze and assess the magnitude of the adverse effect, compile the necessary documentation, and conduct the appropriate interviews. Internal Audit will keep General Management informed. After analysis, Internal Audit issues a recommendation, which may include the issuance of an administrative report; a warning; cancellation or modification of a Project or POA; dismissal of the person involved; escalation of the complaint to the Committee corresponding to the Project; or presentation of the matter to the Institutional Accompaniment Committee. Where appropriate, the proposed solution for complaints about the field execution of Project or POAs is made jointly with the corresponding Area Directorate. In contrast, those of an administrative nature, disputes over acquisitions, and managing financial resources related to Project and POAs will additionally involve the Finance Directorate. Internal Audit carries out this process independently when the complaint or allegation involves FMCN's operational or administrative team. In both cases, implementing the recommendation requires authorization from General Management to be considered an institutional resolution. - When the complaint involves FMCN's General Management or an Area Director, Internal Audit immediately refers the case to FMCN's Institutional Accompaniment Committee or the Board of Directors, depending on the nature of the complaint. - If the Project fails to address the grievance, what steps would be taken to achieve a resolution? Will the Project set up an arbitration process? Are there national mechanisms that the Project can use? If there are national processes, do the communities and other stakeholders have faith in them, know about them and have easy access to them, and are they likely to use them? If a joint agreement cannot be reached to resolve the complaint, Internal Audit may engage an impartial body selected in agreement with the person(s) filing the complaint. This neutral body investigates the facts and mediates between the parties until an agreement is reached. Suppose efforts to resolve the complaint or allegation are unsuccessful or inappropriate. In that case, Internal Audit may terminate the process after consulting with and providing written notice to the complainant(s) and informing General Management, the Institutional Accompaniment Committee, and, if necessary, the Board of Directors. In this regard, the GRM will not supersede the judicial remedies available to the complainant. If the process does not result in resolution of the grievance, or if the grievant prefers, s/he may choose to file a claim through CONANP or CI’s EthicsPoint Hotline at https://secure.ethicspoint.com. Alternatively, the grievant may file a claim with the Director of Compliance (DOC) who is responsible for the CI Accountability and Grievance Mechanism and who can be reached at: Director of Compliance, Conservation International 2011 Crystal Drive, Suite 600 Arlington, VA 22202, USA. Documentation - How will grievances be recorded, including verbal ones? Will there be a grievant form? Will there be a register/book of records of grievances received? Grievances are submitted verbally or in writing, and the Internal Auditor records them in the Grievance registry sheet, which contains the following information: - Folio (reference number) - Date of reception - Mode of reception (email, mail, phone, in-person, social media, other) - Complainers information (name, sex, ethnic group, email, phone number, address, other) - Nature of grievance - Project associated - Description of the complaint - Actions taken/Resolution - Comments - Date of resolution/closure - Name, position, and signature of GRM responsible person - How and where would these records be stored? And for how long will they be kept? Internal Audit maintains grievance records in hard copy stored in file folders indexed by year. The grievance registry sheet summarizes data of records, which is also held on a computer. Records are indefinitely retained after the grievance case is closed. However, when the records become unmanageable, a five-year period after closing the grievance case will be established to keep and destroy the records. - How will the personal identifiable information of the grievant be kept secure, and who within the team will have access to it? Internal Audit is responsible for keeping the grievant personal identifiable information secure. Thus, the complainer’s information is kept secret during the grievance redress procedure. Instead, the folio (reference number) is used. Records are retrievable by folio, which are cross-referenced by individual names. Access to and use of grievance records are limited to Internal Audit or personnel who need the records to perform their official duties. Computers are password-protected for individuals with access, and all databases are designed with stringent security measures to prevent unauthorized access, alteration, or disclosure.

SECTION VI: Monitoring and Reporting

Describe how will you track and ensure that the mechanism is working. It is important to recognize that lack of grievances does not mean that there are none, it may indicate that the mechanism is not working properly. Describe how you will account for this possibility.

A complete system review is carried out annually to identify difficulties in handling complaints or responding to complainants to ensure that the mechanism is operating effectively. Internal Audit prepares an annual assessment report on GRM's performance for presentation to the Institutional Accompaniment Committee. This Committee, in turn, may request an independent review of the Grievance Redress Mechanism at any time or every five years, including a detailed assessment of the GRM guidelines and procedures. Based on the evaluation, the Institutional Accompaniment Committee decides on the pertinent modifications to the GRM. Additionally, some FMCN’s Projects regularly report to donors the progress made towards implementing the grievance mechanism, including the number of grievances received and the outcome of the grievance process.

On an annual basis and using the CI-GEF Project Implementation Report (PIR) template, the following CI-GEF’s minimum indicators are to be reported. The Project can include other appropriate accountability and grievance indicators in addition to the CI-GEF/GCF’s indicators.

| Indicator | Baseline | Target |
| --- | --- | --- |
| - Number of times the Accountability and Grievance Mechanism is communicated/disseminated to stakeholders | 0 | 5 per year (25 total) |
| - Percentage of conflict and complaint cases reported to the Project’s Accountability and Grievance Mechanism that have been resolved | 100% | 100% |

| Person responsible for implementing and monitoring the AGM: | Selina Villegas Internal Auditor Fondo Mexicano para la Conservación de la Naturaleza, A.C. |
| --- | --- |
| Budget Summary | 5% salary and benefits of FMCN’s Internal Auditor (co-financed) 10% salary and benefits of FMCN’s Communication Specialist |

Indigenous Peoples Plan

SECTION I: Project Information

A. Basic Project Profile

| PROJECT TITLE: | Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| --- | --- | --- | --- | --- |
| GEF/GCF PROJECT ID: |  |  | PROJECT DURATION: | 60 months |
| EXECUTING AGENCY/ENTITY: | Fondo Mexicano para la Conservación de la Naturaleza (FMCN) |  |  |  |
| PROJECT START DATE: | 2025 |  | PROJECT END DATE: | 2030 |
| IPP PREPARED BY: |  | FMCN - Socioenvironmental Research Coordinator |  |  |
| DATE OF (RE)SUBMISSION TO CI-GEF/GCF: |  | 13/03/2024; 21/03/2024 |  |  |
| IPP APPROVED (CONDITIONALLY) BY: |  | Ian Kissoon, Senior Director, ESMF, CI-GEF Agency |  |  |
| CONDITIONS: |  | IPP to be validated with stakeholders during the next phase. |  |  |
| DATE OF CI-GEF APPROVAL: |  | March 22, 2024 |  |  |

- Project Description

Mexico safeguards nearly to 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life.

The Project "MEx30x30: Conserving Mexican biodiversity through communities and their protected areas" has as its objective to

To help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex).

MEx30x30 has three main objectives to reach this goal:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively;

- To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and local communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

The Project MEx30x30 will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community vigilance, fire management, productive projects, ecotourism, and capacity building.

Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP has been the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). However, high levels of socioeconomic marginalization in many rural communities and heavy livelihood dependence on natural resources can result in resistance to prioritizing conservation or restoration activities that do not adequately consider local needs. CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. As a result, The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives.

The Project MEx30x30 will focus on the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

MEx30x30 is an opportunity to make the 30x30 goal possible, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes.

The Indigenous Peoples Plan (IPP) is a comprehensive strategy designed to integrate an indigenous people’s responsive approach throughout the project. The primary goal of the IPP is to ensure that indigenous women and men experience culturally appropriate economic and social benefits, free from discriminatory effects during development and implementation while upholding their dignity and human rights. Beyond mere inclusion, it fosters sustainable equality of responsibilities, opportunities, and benefits, recognizing indigenous peoples' pivotal role in natural resource utilization and family health for rural women. The Project's IPP addresses the root causes of inequalities, encompassing limited access to and control over natural resources, inadequate employment opportunities, and capacity-building opportunities. Systematic information will be collected to monitor and track participation and engagement, fostering accountability and transparency.

The specific objectives of this Plan are to:

- Ensure broad access and participation of Indigenous Peoples in the project.

- Avoid, prevent and mitigate possible adverse impacts on the Indigenous population.

- Recognize and respect, through project activities, the rights based on the customs or traditions of Indigenous Peoples and local communities, with respect to lands and territories traditionally occupied and used.

- Promote sustainable development benefits and opportunities for Indigenous Peoples in ways that are accessible, culturally appropriate, and inclusive.

SECTION II: Legal and Institutional Framework

- Relevant laws and institutional frameworks

In Mexico, following the recognition of indigenous communities and peoples as subjects of public law, it is up to the indigenous communities and individuals themselves, in the exercise of their self-determination and autonomy, to self-identify themselves under the concept that best suits their history, identity, and worldview. In 2020, 23,229,089 people self-identified as indigenous, representing 19.4% of the country's total population (INPI, 2020).

Of the more than 23.2 million people who self-identify as indigenous, 51.4% (11.9 million) are women, and 48.6% (11.3 million) are men. Of the total, only 7.1 million (30.8%) spoke an indigenous language, 6.4 million (87.2%) also speak Spanish, and 866 thousand (11.8%) do not (INEGI, 2020).

In Mexico, there are several laws and constitutional provisions aimed at protecting the rights of Indigenous Peoples safeguarding their cultural heritage. Some of the key legal instruments include:

International Conventions

- United Nations Declaration on the Rights of Indigenous peoples: Approved by the General Assembly on September 13, 2007, the document recognizes the pressing need to respect and promote the rights and inherent characteristics of indigenous peoples, particularly their rights to their lands, territories, and resources, which stem from their political, economic, and social structures, as well as their cultures, spiritual traditions, history, and worldview. The document highlights the right of indigenous peoples to live with dignity, preserve and enhance their own institutions, cultures, and traditions, and pursue their own development in accordance with their self-determined needs and interests.

- International Labour Organization (ILO) Convention 169: Mexico ratified ILO Convention 169 in 1990. This convention is a legally binding international instrument that sets out the rights of Indigenous and tribal peoples, including the right to land, natural resources, and cultural integrity. Mexico's ratification of this convention obligates the government to take measures to ensure the full application of its provisions within its territory.

- Convention Concerning the Protection of the World Cultural and Natural Heritage: It is a treaty and the most important standard for the conservation of properties belonging to World Heritage, demanding their preservation as a legacy for all of humanity. The Convention aims to identify, protect, conserve, enhance, and transmit to future generations the cultural and natural heritage of Outstanding Universal Value.

- Convention for the Safeguarding of Intangible Cultural Heritage: It is the first binding multilateral instrument to protect intangible cultural heritage, which has four main purposes: (i) to safeguard intangible cultural heritage; (ii) to ensure respect for the intangible cultural heritage of the communities, groups and individuals concerned; (iii) to raise awareness at the local, national and international levels of the importance of intangible cultural heritage and the need to ensure its reciprocal recognition; and (iv) to foster international cooperation and assistance.

- Regional Agreement on Access to Information, Public Participation and Access to Justice in Environmental Matters in Latin America and the Caribbean (Escazú Agreement): Guarantees the full and effective implementation in Latin America and the Caribbean of the rights of access to environmental information, public participation in environmental decision-making processes, and access to justice in environmental matters, as well as the creation and strengthening of capacities and cooperation, contributing to the protection of the right of each person, of present and future generations, to live in a healthy environment and to sustainable development.

National Laws and Regulations

- Political Constitution of the United Mexican States (Article 2): The Mexican Constitution recognizes the rights of Indigenous Peoples and affirms Mexico as a pluricultural nation. Article 2 of the Constitution was amended in 1992 to explicitly acknowledge the right of Indigenous Peoples to self-determination, autonomy, and the preservation of their cultural identity. It also guarantees the right to maintain and develop their own social, economic, political, and cultural institutions. Section C of Article 2 (added on August 9, 2019) recognizes Afro-Mexican Peoples and communities, regardless of their self-denomination, as part of the pluricultural composition of the Nation. They will have the rights indicated in the previous sections of this article in the terms established by law, in order to guarantee their free determination, autonomy, development and social inclusion.

- National Institute of Indigenous Peoples Law (Ley del Instituto Nacional de los Pueblos Indígenas): Promulgated in 2018, instituting a federal agency responsible for promoting the development and welfare of Indigenous Peoples (National Institute for Indigenous Peoples - INPI): The INPI implements various programs and policies aimed at supporting Indigenous communities in areas such as education, health, infrastructure, and economic development.

- General Law on Linguistic Rights of Indigenous Peoples: This law, enacted in 2003, aims to protect and promote the linguistic rights of Indigenous Peoples in Mexico. It recognizes the right of Indigenous individuals and communities to use their languages in all spheres of public and private life, including in education, justice, and government services. The law also mandates the provision of bilingual education and the translation of official documents into Indigenous languages.

- General Law for the Protection of the Cultural Heritage of Indigenous and Afro-Mexican Populations and Communities (the “Cultural Heritage Law”): This new law enacted in 2022 aims to prevent unauthorized appropriation and unauthorized use, exploitation, or commercial exploitation of cultural knowledge, identity, and other expressions that are part of the material and immaterial heritage of Indigenous and Afro-Mexican Peoples and communities, and seeks to sanction the use and exploitation by third parties outside the community.

- Law on Indigenous and Tribal Peoples and Communities of Mexico (Ley de los Derechos de los Pueblos y Comunidades Indígenas y Afromexicanas): Enacted in 2020, this law recognizes the rights of Indigenous and Afro-Mexican Peoples to self-determination, autonomy, and cultural integrity. It establishes mechanisms for the protection of Indigenous lands and resources, as well as measures to combat discrimination and promote the social and economic development of Indigenous communities.

- Sustainable Rural Development Law: It promotes sustainable rural development in the country, ensuring an adequate environment and the role of the State in promoting equity. This includes the planning and organization of agricultural production, industrialization, commercialization, and the provision of goods and services, as well as all actions aimed at improving the quality of life of the rural population.

- General Law of Ecological Balance and Environmental Protection (LGEEPA): Guarantees the right of communities, including Indigenous Peoples, to the protection, preservation, use and sustainable exploitation of natural resources and the safeguarding and use of biodiversity. For the planning, execution, evaluation and monitoring of the environmental and natural resources policy, Indigenous Peoples must be consulted so that they can express their opinions and proposals.

- General Law on Sustainable Forest Development (LGDFS): It regulates and promotes the comprehensive and sustainable management of forest territories, including the conservation, protection, restoration, production, cultivation, and use of the country's forest ecosystems and their resources. It also distributes the corresponding competencies in forestry matters. Articles 2 and 3 aim to respect and protect, within the scope of the Law, the rights of indigenous peoples and similar communities, as well as their use and enjoyment of forest resources, in accordance with applicable national regulations and binding international instruments. Additionally, it contributes to the socioeconomic development of indigenous peoples, communities, ejidatarios, communal owners, cooperatives, small landowners, and other holders of forest resources.

- General Law on Climate Change: It establishes significant elements to promote the adaptation of Mexico's natural and human systems to climate change. Article 26 states that in the formulation of national policy and the adoption of measures to address climate change, full respect must be given to human rights, the right to health, the rights of indigenous peoples, local communities, migrants, children, persons with disabilities, and persons in situations of vulnerability, as well as the right to development. It also emphasizes the importance of gender equality, women's empowerment, and intergenerational equity. Article 71 highlights the importance of gender equity and the participation of populations most vulnerable to climate change, including indigenous peoples, academics, and researchers, in planning processes.

- Federal Archaeological, Artistic and Historical Monuments and Zones Law: Research, protection, conservation, restoration and recovery of archaeological, artistic and historical monuments and monument areas.

- Agrarian Law: Regulatory law of article 27 of the Constitution in agrarian matters and of general observance throughout the Republic, for the development and promotion of agriculture and livestock, for ejidos and communities (including indigenous peoples), for the expropriation of ejido and communal property, among others.

- National Program for Indigenous Peoples 2018-2024: its fundamental premises are to strengthen the processes of autonomy and their forms of organization, consolidate their effective participation in the design, implementation, and evaluation of public policies and government programs that concern them, and to promote the sustainable use of their lands, territories and natural resources, as well as the fair and equitable distribution of wealth, to combat the pressing poverty and marginalization in which they find themselves.

Indigenous communities in Mexico continue to govern themselves through customary laws and traditional governance structures. These systems are often based on collective decision-making, consensus-building, and respect for elders' wisdom. Community assemblies and traditional authorities play crucial roles in resolving disputes, managing natural resources, and maintaining social cohesion. Mexico operates under a system of legal pluralism, where Indigenous legal traditions coexist with national legal norms. This recognition of legal pluralism allows Indigenous communities to apply their customary laws in certain matters, such as resolving intra-community disputes or managing local resources, while still adhering to the overarching framework of Mexican law.

- EA internal policies and procedures, including FPIC

FMCN's E&S Policy and ESMS establish the objectives, guiding principles, and scope of meaningful stakeholder engagement. It states that FMCN seeks to ensure the meaningful, effective, and informed participation of key stakeholders at different territorial scales in the preparation and operation of projects. The involvement of these stakeholders is a regular and constant process throughout the life cycle of the initiatives, which must be carried out in an inclusive, gender-sensitive, and culturally appropriate manner, without discrimination and always ensuring that opportunities for participation are open to vulnerable groups (e.g., women, youth, senior citizens, Indigenous Peoples, Afro-Mexican population, and people with disabilities, among others).

One of FMCN's guiding principles is respect for Indigenous Peoples, including avoiding adverse impacts by the supported projects, promoting benefits and opportunities, respecting and preserving their culture, and engaging Indigenous Peoples through active and effective participation through the lifecycle of the projects. FMCN E&S safeguard on Indigenous Peoples (SAS7) establishes that FMCN and the implementing organizations will identify, through a social and environmental risk and impact assessment process (Environmental and Social Safeguards Assessment Sheet), all potentially affected Indigenous Peoples' communities within the area of influence of a project, subproject, or Annual Operating Plan, as well as the nature and severity of the expected direct and indirect economic, social, cultural, and environmental impacts on these peoples. The proposed mitigation actions are developed in consultation and with the informed participation of the affected Indigenous Peoples communities.

FMCN's stakeholder engagement processes with Indigenous Peoples align with IFC Performance Standard 7, including:

- Indigenous Peoples will have access to relevant project information before any decision-making that will affect them, including information on potential adverse environmental and social impacts affecting them at each stage of project implementation.

- The engagement process will take account of existing social structures, leadership, and decision-making processes as well as social identities such as gender and age, and be cognizant of, among other things, The existence of patriarchal traditions and social norms and values that may limit women's participation in leadership roles and decision-making processes; The need to protect and ensure the legal rights of Indigenous women; and Marginal or vulnerable groups' potentially limited realization of their economic and social rights as a consequence of poverty and restricted access to financial resources, social services, or decision-making processes.

The design and implementation of project activities will be guided by the rights and responsibilities set out in the United Nations Declaration on the Rights of Indigenous Peoples and according to Mexican Legislation, including, in particular, the right to free, prior, and informed consent. The Mexican Regulation states that Free Prior and Informed Consent (FPIC) is only required when a project involves the following situations:

- Has adverse impacts on land and natural resources subject to traditional ownership or customary use and occupancy.

- Causes the relocation of Indigenous Peoples from lands and natural resources subject to traditional ownership or customary use and occupancy.

- Have significant impacts on the cultural heritage of Indigenous Peoples that are relevant to the identity or cultural, ceremonial, or spiritual aspects of Indigenous Peoples' lives.

Mex30x30 will foster broad, meaningful, effective, and informed participation of multiple and potentially affected stakeholders throughout the project life cycle. FMCN is committed to avoiding prejudice and discrimination and providing equal access to opportunities to individuals and groups who may historically be disadvantaged or excluded from project benefits, such as Indigenous communities, women, and youth. Participation will be voluntary, transparent, inclusive, gender-sensitive, and culturally appropriate, and a grievance redress mechanism at the project level will be established throughout the project life cycle to allow stakeholders to raise concerns, worries, comments, questions, and suggestions. Additionally, as part of its commitment to Indigenous populations, FMCN has an Exclusion List, which states that any of the following activities will not be supported or financed:

- Land acquisition.

- Activities that may violate human rights.

- Activities involving forced labor and/or harmful child labor.

- Activities that generate involuntary resettlement, especially of Indigenous or Afro-Mexican groups.

- Activities that affect the rights of Indigenous peoples or local communities, especially land ownership, without the proper Free, Prior, and Informed Consultation (FPIC) process.

- Activities affecting cultural heritage.

- Activities that affect people's assets or generate restrictions on access to natural resources.

- Activities carried out on land under litigation, dispute, or on ejido and/or communal lands that do not have the written approval of the assembly.

As MEx30x30 will involve indigenous peoples and local communities, the Project will adhere to CI-GEF requirements for Free, Prior, and Informed Consent (FPIC) principles. FPIC ensures that these groups are meaningfully involved in decisions that affect their rights, territories, and resources.

The Project initiated early engagement and consultation with indigenous peoples and local communities in March 2024. It involved identifying key stakeholders and understanding previous FPIC processes developed by CONANP to decree three PAs, and certifying the Chimalapas ADVCs.

CONANP organized 39 prior FPIC processes during 2023 in Guerrero (Sierra Tecuani), Jalisco (CADRN 043 Nayarit), Campeche (Balam-kú), and Yucatán (Bajos del Norte), in which participated 66 ejidos and communities and around 1,963 people: 24% women, 76% men, and 12% indigenous peoples. The Chimalapas ADVC was approved with 638 San Miguel Chimalapa Community Assembly votes and 250 votes from the Santa Maria Chimalapa Community Assembly.

For the Project, a consultation workshop was held in Chihuahua (Papigochic) on March 19, 2024, and a virtual consultation was organized on March 20, 2024, for the five other PAs and the ADVC Chimalapas. In these workshops, the Project provided comprehensive information about the proposed activities, potential impacts, proposed mitigation measures, and benefits to indigenous peoples and local communities in order to obtain feedback, address their concerns and recommendations, and adjust the corresponding Stakeholder Engagement Plan and other related environmental and social plans as appropriate.

Through continuous engagement, the Project will facilitate a voluntary, transparent, and culturally appropriate participation process, incorporating indigenous peoples' and local communities' traditional knowledge and practices into conservation planning and implementation. MEx30x30 will also ensure that indigenous peoples and local communities benefit from conservation activities through employment and capacity-building opportunities. The process may involve community meetings, consultations, and consensus-building mechanisms. The Project will also establish and foster a grievance redress mechanism to address complaints that may arise during implementation.

SECTION III: Characteristics of IPs/TEs in project sites

Indigenous territories are rich in biodiversity, and their peoples possess ancestral knowledge and a profound relationship with flora, fauna, water, and climate, which has allowed them to develop techniques for selecting and domesticating plants and animals, adapting them to diverse climatic conditions (CONANP, 2020).

The south-southeast region of the country has the largest indigenous population. States such as Oaxaca, Chiapas, Yucatán, and Guerrero top the list of states with the highest proportion of indigenous language speakers, accounting for more than half of these speakers nationwide. This linguistic diversity includes 68 living indigenous languages, of which Nahuatl, Maya, and Tseltal are the predominant ones (SIC, 2024).

In Mexico, the population of people 15 years of age and older who speak an indigenous language has an average schooling of 6.2 grades, which corresponds to a complete primary education. Women who speak an indigenous language have a notable schooling gap, with an average of 5.8 grades, in contrast to the 9.9 average schooling grades of women who do not speak an indigenous language.

Among the Mexican population aged 15 years and older who speak an indigenous language, the illiteracy rate reaches 20.9%, significantly contrasting with the 3.6% recorded among those who do not speak indigenous languages, reflecting a notable gap of 17.3 percentage points. Due to high rates of poverty and the patriarchal structures inside indigenous families, where the will of the woman has been generationally subject to the choice of a male figure, the limited economic resources available for attending school are primarily given to boys. Girls who receive family support to attend school must also help their mothers with household chores, diminishing their school performance as overwork affects their concentration and stamina. At school, indigenous girls often encounter gender discrimination. Male classmates are the enactors in 39.3% of the incidents reported, while male teachers are involved in 14.4% of the cases (INEGI, 2017). While these statistics reflect official reports of discrimination against girls in school, anecdotal data suggests the rates may be much higher in rural indigenous communities (Osorio, 2017). In addition, the isolation of their villages from the urban centers is another safety factor that discourages indigenous parents from supporting girls to attend higher levels of education, which are only available outside of their communities. Some of the roads represent a hazard for indigenous girls walking long distances alone, sometimes before sunrise, to attend early school activities since they could be attacked, robbed, or assaulted by passers-by during their journey to school (Osorio, 2017). With higher levels of education, women improve their reproductive health, increase their economic productivity and income, and develop a greater degree of freedom and power over their lives—with the consequent possibility of making better decisions about their well-being (Inmujeres, 2016).

In 2020, 60.5% of the population over 12 who spoke an indigenous language was considered economically active. There was higher labor participation among indigenous men (79.2%) than non-indigenous men (75.6%). In contrast, only 42.8% of indigenous women were reported as economically active, a lower percentage than non-indigenous women (49.5%). Disadvantages in education for women due to a quadruple burden of poverty, indigeneity, rurality, and gender do not allow them to compete fairly in the labor market, especially for adult women, most of whom have not completed primary education. Additionally, 46.4% of the Indigenous population survives on an income below the poverty line (CONEVAL 2020). In 2020, 834 municipalities had 80% or more of their Indigenous Peoples in poverty (CONEVAL 2020).

According to the National Human Rights Commission, indigenous people in Mexico frequently face acts of racism, discrimination, and violence, both physical and emotional, and are often excluded from public services, which seriously violates their human rights (CNDH, 2022). For example, 67.4% of the Indigenous language-speaking population still suffers from a lack of basic housing services (CONEVAL, 2020).

Indigenous territories represent 14.3% of Mexico's national surface and capture 23% of the country's water. More than half of these territories receive more than 1,000 mm³ of rainfall annually, exceeding the national average. 76.2% of their territory has primary or secondary vegetation, indicating high ecosystem conservation. In addition, 71% of these territories coincide with Priority Terrestrial Regions, and 26.3% are located in Protected Areas (SEMARNAT, 2014).

In PAs, 44 indigenous peoples act as essential allies in the conservation of natural resources, contributing their lands, whether private or community lands, as Areas Voluntarily Designated for Conservation. In addition, they participate in managing these territories through Advisory Councils, where they promote actions and commitments for the conservation and protection of the environment (CONANP, 2020).

The MEx30x30 Project will support six protected areas: two existing PAs, three recently decreed PAs, and one recently designated ADVC complex (with eight certificates), all located in indigenous territories. Together, the six areas have a population of approximately 162,392 people. Of these, an estimated 24% of the population are indigenous.

The PAs with the highest percentages of indigenous population three years of age and older who speak an indigenous language are C.A.D.N.R. 043 Nayarit, Balam-Kú, and Chimalapas complex, all with more than 30%. In contrast, those with the least indigenous presence are Bajos del Norte and Sierra de Tecuani, with 6% and 4.7%, respectively (INEGI, 2020).

Figure 1. Indigenous population in the project PAs.

There are five indigenous regions where the Project's PAs are located. A general description of each follow, based on information provided by the National Institute of Indigenous Peoples (2020) and the National Commission for the Development of Indigenous Peoples (2006).

Maya: Located in the extreme southeast of the country, in the Yucatan peninsula, combined by the states of Campeche, Quintana Roo, and Yucatan. The Maya maintains a social organization consisting of residential units composed of domestic groups, a nuclear family, or several other units distributed in different houses. In some cases, extended families may share expenses, as well as the work of the milpa. The vision of the world in this territory is closely related to the cultivation of corn in such a way that several representations and rituals are linked to this activity. The main subsistence activity is agriculture, which is practiced following, in some places, the slash-and-burn technique in rainfed crops and using axes, machetes, and planting sticks. They plant corn, beans, and squash. In some regions, they grow citrus, henequen, flowers, legumes, chili peppers, and vegetables, mainly for commercialization. Other activities include beekeeping, raising pigs and poultry, and fishing.

Huicot or Gran Nayar: The name of the region derives from Huichol, Cora, and Tepehuano and designates the mountainous territory that encompasses the south of the state of Durango, the north of Jalisco, Nayarit, and part of Zacatecas, which is also known as the Gran Nayar region. Among the indigenous peoples that inhabit the Gran Nayar region, settlement patterns of enormous dispersion predominate, linked to their particular cosmological and belief systems, together with the prevailing geographic conditions, which is why the majority of its population lives in localities of less than 100 inhabitants. It is also one of the regions with the greatest social lag or social undervelopment at the national level, and the most significant proportion of the indigenous population is located in the primary sector, with 52.2%.

Chimalapas: It is an ancestral indigenous territory of the Zoque people. The region's social structure responds to historical uses and customs, so it is identified in hierarchical order to the Communal Assembly as the highest instance, followed by the congregations - the local regulatory bodies for access to resources. The municipalities that make up the region have a high/very high marginalization index. More than 70% of the population is employed in the primary sector; therefore, agricultural activities are the most prevalent in the region.

Montaña de Guerrero: As in the Huicot or Gran Nayar region, the Montaña region presents a balanced distribution among the indigenous groups that inhabit its territory, with the population of Nahua origin being the predominant with 33.7%, followed by Mixtec and Tlapanec languages with 29.8% and 25.9%, respectively. The minority group in the region, the Amuzgo, represents 86% of the total population. All of the region's municipalities are in a situation of high or very high marginalization, the latter being close to 80%. In this territorial delimitation, most of the employed indigenous population, around 60%, continues to work in primary sector activities. Consequently, the activities related to the secondary or tertiary sector are not very important since they do not exceed 20% of those employed by indigenous people (21.3% and 17.6%, respectively).

Tarahumara: Its inhabitants call themselves Rarámuri, which means runners on foot. It is located in the part of the Sierra Madre Occidental that crosses the state of Chihuahua and the southwest of Durango and Sonora. The Sierra Tarahumara is formed by high mountains that reach 2,000 to 3,000 meters above sea level and deep ravines. It has been divided geographically into Alta and Baja Tarahumara. For the Tarahumara people, the primary subsistence activity is corn cultivation. Most of their daily and ceremonial life is organized around corn. The cultivated lands are scattered on small plateaus and hillsides, which influences the dispersion of the settlements, which are organized in rancherías. The fragility of the soil only allows agricultural work with hand tools and animal traction. It also represents a portion of the oldest forest management area in Chihuahua, with more than 50 years of timber harvesting, making this forestry activity the mainstay of the region's economy.

Figure 2. Indigenous territories in MEx30x30 PAs.

MEx30x30 will foster biological and cultural diversity with no potential adverse impacts on the indigenous populations beyond those associated with their exclusion. Thus, indigenous peoples' engagement and meaningful participation must be ensured, and their cultural diversity, autonomy, and indigenous self-determination must be recognized, respected, and safeguarded at all Project stages, activities, and under equal conditions.

SECTION IV: Capacity of EAs and Indigenous/Traditional Communities

Through previous projects (C6 and CONECTA), FMCN has experience with the engagement of IPs. FMCN's E&S Policy and ESMS establish the objectives, guiding principles, and scope of meaningful stakeholder engagement. It states that FMCN seeks to ensure the meaningful, effective, and informed participation of key stakeholders at different territorial scales in the preparation and operation of projects. The involvement of these stakeholders is a regular and constant process throughout the life cycle of the initiatives, which must be carried out in an inclusive, gender-sensitive, and culturally appropriate manner, without discrimination and always ensuring that opportunities for participation are open to vulnerable groups (e.g., women, youth, senior citizens, Indigenous Peoples, Afro-Mexican population, and people with disabilities, among others).

One of FMCN's guiding principles is respect for Indigenous Peoples, including avoiding adverse impacts by the supported projects, promoting benefits and opportunities, respecting and preserving their culture, and engaging Indigenous Peoples through active and effective participation through the lifecycle of the projects. FMCN E&S safeguard on Indigenous Peoples (SAS7) establishes that FMCN and the implementing organizations will identify, through a social and environmental risk and impact assessment process (Environmental and Social Safeguards Assessment Sheet), all potentially affected Indigenous Peoples' communities within the area of influence of a project, subproject, or Annual Operating Plan, as well as the nature and severity of the expected direct and indirect economic, social, cultural, and environmental impacts on these peoples. The proposed mitigation actions are developed in consultation and with the informed participation of the affected Indigenous Peoples communities. These practices have been employed successfully in C6 and CONECTA.

One of the fundamental spaces in Indigenous communities is the community assembly since through it, the authorities are appointed, and important decisions are made about the use of the territory and resources. Assemblies can be held periodically on established days or can be called for a specific purpose, with different levels of formality (in terms of convening, verification of attendance, or registration of agreements). Attendance at the sessions is usually mandatory for families who must send a representative. The community assembly is the highest body of authority for Indigenous Peoples, so this is an essential space for decision-making. There are also moral authorities (comparable to that of the representatives of the churches present in the region). Therefore, MEx30x30 will consider them in the participatory processes to be developed in the Project. Hence, in the localities of the municipalities classified as Indigenous, the Project must establish the link and communications with the formal government institutions (community and ejidal assemblies) and, optionally, through local authorities (justices of the peace, elders council) to communicate matters related to the Project. Building on the successful experience of the C6 and CONECTA projects, MEx30x30 will engage community or Indigenous institutions  as a mediating body if any disagreements arise from the Project's actions. c

The Project will not adversely affect indigenous peoples. On the contrary, it will respect and preserve traditional knowledge and practices, complying with local, national, and international regulations. The legal recognition of Indigenous rights and land tenure in Mexico is crucial, as it has evolved with constitutional reforms and international agreements providing a framework for Indigenous autonomy and self-governance. Access to information about the Project, its impacts, mitigation measures, and benefits is essential for informed decision-making. Thus, MEx30x30 will enhance the provision of comprehensive information in languages and formats accessible to Indigenous communities to facilitate meaningful engagement. Specific means will be used to reach the Indigenous population, especially women within this population sector. For example, the presence of the community radio station or other communications channels mostly used by indigenous populations will be taken advantage of. Through the state and municipal women's institutes, we will seek to reach women in general and Indigenous women in particular. In this sector, the contacts of civil organizations will be handy due to deep knowledge and roots in the Indigenous regions of the basins. The consultation process is described in the Stakeholder Engagement Plan.

Additionally, capacity building will be conducted with Indigenous populations to increase access to project activities and benefits.

SECTION V: Potential impact of project on IPs/TCs

The assessment carried out in the selected PAs and ADVCs does not identify negative impacts of Mex30x30 on the ways of life, economic activities and identity of the Indigenous population. On the contrary, the project represents an opportunity to improve their agricultural activities and seeks to incorporate them into the economic, social (e.g. health) and environmental benefits thereof. The Project does not promote the expansion or growth of agricultural or livestock activity, but rather its productive reorientation towards sustainable schemes and towards value chains that differentiate the products coming from these types of processes. Agroforestry activities can be directly related to low-scale exploitation practices, traditionally practiced by Indigenous populations, such as the use of cornfields or forest products (e.g. floriculture, mushroom collection or craft activity). These activities could be enhanced by the project by strengthening community organization for production and access to markets, as well as disseminating traditional productive practices that maintain or increase forest cover, such as the establishment of native plant nurseries with commercial value.

According with FMCN´s exclusion list, the following activities will not be financed or supported:

- Activities that generate involuntary resettlement, especially of Indigenous or Afro-Mexican Peoples.

- Activities that affect the rights of Indigenous Peoples or local communities, especially land ownership, without due process of Free, Prior and Informed Consultation (FPIC).

- Activities that affect cultural heritage.

- Activities that affect people's assets or generate restrictions on access to natural resources.

- Activities carried out on disputed or disputed lands or on ejido and/or communal lands that do not have the written approval of the assembly.

The selected proposals for PAs and ADVCs with IP&LCs to conserve, restore and sustainably manage territories will be reviewed and adjusted to comply with the Indigenous Peoples Plan (IPP). Thus, each of these selected services/PLATs and subprojects will adopt the form of an IPP. The project Environmental and Social Safeguards Officer will ensure these proposals adhere to the guidelines of the IPP throughout its lifespan.

While Mex30x30 is expected to have positive impacts on Indigenous Peoples, it is necessary to consider the risks that would prevent the project from maximizing these positive impacts. Such risks are fundamentally associated with the possibility that the project will not be able to generate the interest of the Indigenous population or that it will not be able to disseminate information about the project in a culturally appropriate manner. The table below summarizes the potential impacts identified for the Indigenous population and the corresponding general mitigation measures proposed to be considered. The risk assessment (likelihood, scale, and duration) takes into account the proposed mitigation measures.

| Project Output or Activity | Impact (positive/negative) of the activity for IPs/TEs |  | Likelihood | Scale (in terms of magnitude) |  | Duration | Mitigation measure (negative impacts)/Measures to promote culturally appropriate benefits (positive impacts) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |  |  |  |  |
| Output 1.1. CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. | Positive - Increased funding can lead to better conservation efforts, habitat restoration, wildlife protection, ecosystem monitoring, and research, contributing to the preservation of biodiversity and improved overall ecosystem health. - Increased budget can facilitate indigenous people’s involvement, ensuring their engagement in conservation efforts and benefiting from sustainable practices. - Improved capacity allows for better management of productive activities within protected areas (e.g., tourism), minimizing negative impacts and promoting sustainable practices and economic opportunities for indigenous communities. |  | High | Large |  | Long | The Project will: - Ensure that conservation efforts respect and incorporate traditional indigenous knowledge, practices, and land management systems to achieve shared conservation goals. - Collaborate with indigenous communities to develop and implement sustainable livelihood initiatives that respect their cultural practices, minimize environmental impact, and ensure equitable economic benefits. - Strengthen existing mechanisms for regular participation that involve indigenous representatives in decision-making at various levels (e.g., Advisory Councils). - Provide training for enforcement CONANP personnel, and collaborate with local communities to act as stewards for effective conservation management. - Develop training and technical support focused on social inclusion, cultural sensitivity, inclusion, and the recognition of indigenous rights, fostering a collaborative and mutually beneficial relationship. - Use appropriate communication channels, locations, materials, and languages, and engage trusted culturally sensitive local organizations for outreach and communication with indigenous communities - Establish transparent financial and operational processes and ensure accountability through regular audits, and involve external organizations for oversight. |
|  | Negative - Ineffective allocation of funds or mismanagement, undermining trust and the effectiveness of conservation efforts. - Lack of indigenous people’s involvement may lead to conflicts between conservation initiatives and local communities. - The increased capacity may not necessarily translate into inclusive decision-making processes, leaving indigenous communities marginalized. |  | Low | Small |  | Medium |  |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |  |  |  |  |
| Output 2.1. Donor support is secured to cover the financing gap for the effective management of existing PAs over the next 15 years. | Positive - Adequate funding can lead to enhanced conservation efforts, protecting biodiversity and ecosystem services. - Donor support can facilitate community involvement in decision-making processes related to protected area management. - Increased funding may create job opportunities for indigenous people in conservation and sustainable-related activities |  | High | Large |  | Medium | The Project will: - Ensure that conservation activities financed by the transition fund are carried outin a culturally appropriate way, engageging indigenous communities, incorporating their traditional ecological knowledge and respecting their rights. - Promote the appropriation of the grievance redress mechanism and IPP policies. |
|  | Negative - External actors may exploit conservation projects for their interests, leading to negative consequences for indigenous communities. - Co-financing plans fail to consider the culture and specific needs of Indigenous Peoples. |  | Low | Small |  | Medium |  |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore, and sustainably manage territories. |  |  |  |  |  |  |  |
| Output 3.1. PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. | Positive - Indigenous stewardship may lead to sustainable resource management practices, contributing to biodiversity conservation within protected areas (e.g., better fire management and emergency response). - Indigenous communities may have sustainable resource management practices, leading to long-term environmental benefits. - Recognizing and respecting indigenous cultures contributes to the preservation of traditional knowledge and practices. - Implementing gender-equitable actions can enhance social cohesion and contribute to more sustainable development. |  | High | Large |  | Long | The Project will: - Engage with Indigenous Peoples to participate in brigades (fire management, emergency response, monitoring). - Ensure that emergency needs of Indigenous Peoples (and particularly Indigenous women) are prioritized. - Encourage traditional ecological knowledge and practices in conservation planning and collaborate with indigenous communities in monitoring and protecting biodiversity. - Develop collaborative resource management initiatives that integrate indigenous knowledge with scientific approaches, ensuring sustainable use of resources. - Establish transparent benefit-sharing mechanisms, ensuring equitable distribution of benefits and addressing power imbalances. - Identify knowledge gaps and needs relevant to Indigenous Peoples for designing and implement tailor-made trainings. - Provide equitable and accessible training conducted in Indigenous languages (if necessary) and carried out in culturally appropriate locations, timing, and methods for meaningful Indigenous participation. - Facilitate dialogue and accessible and appropriate procedures to address potential complaints, conflicts, and claims from Indigenous Peoples, through the Grievance Redress Mechanism adapted for the specific needs of Indigenous Peoples (e.g. disseminated using appropriate channels and languages, clearly explained and accessible). |
|  | Negative - Competition over resources may lead to conflicts between indigenous communities and conservation efforts. - Training is not accessible or does not meet the needs of Indigenous Peoples. - Emergency needs of Indigenous Peoples are not met |  | Low | Small |  | Medium |  |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |  |  |  |  |
| Output 4.1 Mex30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. | Positive - Views of Indigenous Peoples are used to improve the Project. Indigenous Peoples contribute to and benefit from learning communities | Medium | Medium | Long | The Project will: - Disseminate mechanisms and communication strategies considering the production and consumption of knowledge products and communications material by diverse groups (i.e. women, youth, elderly, and Indigenous and other vulnerable and/or marginalized groups). - Feature knowledge and experience from Indigenous communities and Indigenous-led organizations. - Capacity building and training on the IPP for all Project personnel. - Finance the participation of Indigenous Peoples in meetings of the Learning Community to promote the exchange of experiences. - Prepare knowledge products in formats and languages accessible to different audiences. - Use communication materials, channels and spaces that are relevant to Indigenous Peoples, translating to local languages and choosing locations and times that are convenient for them. - Indigenous Peoples-sensitive communication & publication principles such as: - Emphasize the importance of Indigenous Peoples participation - Ensure that indigenous women and men are equally represented (parity). - Reflect the diversity and heterogeneity of people in relation to age, ethnicity, culture, physical type, complexion, gender identity, etc. - Avoid reproducing discriminatory stereotypes in audiovisual messages. Use inclusive and non-discriminatory language. |  |
|  | Negative - Views of Indigenous Peoples are excluded. - Indigenous Peoples do not access learning communities. Indigenous Peoples do not engage with knowledge products. | Low | Medium | Medium |  |  |
| Output 4.2. Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | Positive - Monitoring framework incorporates information relevant to Indigenous Peoples. | Medium | Small | Short | The Project will: - Include Indigenous Peoples-specific indicators and targets. - MTR will review/evaluate compliance with IPP. - Views of Indigenous Peoples will be represented in the reports. |  |
|  | Negative - Indigenous Peoples are not considered in monitoring framework. | Low | Medium | Short |  |  |

SECTION VI: IP/TC Action Plan

| Project Outputs | Activities (agreed with IPs) to ensure mitigation of identified risks, promote culturally appropriate benefits, and ensure FPIC | Resources Required | Budget |
| --- | --- | --- | --- |
| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |
| Output 1.1. CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. | - Training and technical support will include a focus on IPs meaningful participation. - Create and strengthen PAs Advisory Councils to facilitate meaningful and inclusive participation of IPs in decision-making processes. This can empower IPs and ensure their voices are heard in the management of PAs and ADVCs. - Promote IP’s participation and leadership (gatherings, sessions, events) | - Environmental and Social Safeguards Officer - Training materials - Communication materials | - USD$3,000 |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |
| Output 2.1. Donor support is secured to cover the financing gap for the effective management of existing PAs over the next 15 years. | - Prioritize providing support to IPs in PAs and ADVCs - Secure funding for IPs leadership to promote positive examples - Capacity building and sensitization to donors about IPs | - Environmental and Social Safeguards Officer - Advocacy and outreach materials | USD$2,500 |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore, and sustainably manage territories. |  |  |  |
| Output 3.1. PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. | - Develop tailored capacity building programs in collaboration with IPs to identify gaps and enhance their knowledge of conservation, restoration, and sustainable management practices. - Use communication channels and spaces that are relevant to IPs, translating to Indigenous languages, using inclusive language, choosing locations and times that are convenient for them, conducting IP-only training sessions. - Foster employment opportunities and support for community development initiatives that align with the goals and values of IPs. - Ensure that the mechanism for addressing grievances that may arise during implementation is accessible to IPs. The GRM should prioritize dialogue, mediation, and consensus-building and should be culturally sensitive and responsive to the needs and preferences of IPs. | - Environmental and Social Safeguards Officer - Communication materials - Training materials | USD$4,000 |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |
| Output 4.1 Mex30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. | - Inform on IP learning and knowledge exchanges. - Dissemination mechanisms and communication strategies consider production and consumption of knowledge products and communications material by diverse groups (i.e. women, youth, elderly, and Indigenous and other vulnerable and/or marginalized groups). - Feature knowledge and experience from IP communities, and those led by other disadvantaged groups. - Finance the participation of IP in meetings of the PAs Learning Community to promote the exchange of experiences. - IP culturally appropriate communication & publication principles such as: - Emphasize the importance of IP participation - Ensure that women and men are equally represented (parity). - Reflect the diversity and heterogeneity of people in relation to age, ethnicity, culture, physical type, complexion, gender identity, etc. - Avoid reproducing exclusionary stereotypes in audiovisual messages. - Use inclusive language. | - Environmental and Social Safeguards Officer - Communication materials - Training materials | USD$3,000 |
| Output 4.2. Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | - Include IP specific indicators and disaggregated targets. - Develop and implement a robust monitoring framework to track conservation outcomes and the well-being of IPs. | - Environmental and Social Safeguards Officer - Communication materials | USD$1,000 |

SECTION VII: Monitoring and Reporting

Reporting of Indicators During PPG/PPF

| Percentage of Indigenous/traditional communities present in the project sites that were involved in the design of the project. | During PAs decree Total communities involved: 68 Traditional communities: 74% Indigenous communities: 26% During project preparation Total communities involved: 18 Traditional communities: 61% Indigenous communities: 38% |
| --- | --- |
| Number of engagements with Indigenous/traditional communities present in the project sites during PPG phase | During PAs decree: 68 During project preparation: 18 |

Indicators for Implementation Phase

| Indicator | Baseline | Target |
| --- | --- | --- |
| - Percentage of Indigenous/traditional communities where FPIC has been sought and documented | 0% | 100% |
| - Number of Indigenous/traditional communities present in the project sites that participated in the project | TBD | TBD |

* The Project will review the target at the start of the implementation phase.

| Person responsible for implementing and monitoring the IPP: | Safeguards and Monitoring and Evaluation Coordinator |
| --- | --- |
| Budget Summary: | Specific budget described in Section VI. |

References

CNDH, (2022). Comisión Nacional de Derechos Humanos 2022. Pueblos y comunidades indígenas. Disponible en: informe.cndh.org.mx/menu.aspx?id=82#:~:text=Con%20frecuencia%20los%20indígenas%20de,vulnera%20gravemente%20sus%20derechos%20humanos.

CNDI, 2006. Comisión Nacional para el Desarrollo de los Pueblos Indígenas. Regiones Indígenas de México. Disponible en: chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://www.gob.mx/cms/uploads/attachment/file/35735/cdi-regiones-indigenas-mexico.pdf

CONANP, (2020). Los pueblos indígenas en las Áreas Naturales Protegidas. Comisión Nacional de Áreas Naturales Protegidas. Disponible en: https://www.gob.mx/conanp/es/articulos/los-pueblos-indigenas-en-las-areas-naturales-protegidas?idiom=es#:~:text=Los%20pueblos%20ind%C3%ADgenas%20que%20sobresalen,Mazahuas%2C%20Mazatecos%2C%20entre%20otros.

INEGI, 2020. Instituto Nacional de Estadística y Geografía. Censo de Población y Vivienda 2020. México.

INPI, (2020). Instituto Nacional de Pueblos Indígenas. Indicadores Socioeconómicos de los Pueblos Indígenas. Disponible en: inpi.gob.mx/indicadores2020/

SEMARNAT, (2014). Pueblos Indígenas y Áreas Naturales Protegidas. Secretaría de Medio Ambiente y Recursos Naturales. Disponible en: chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://simec.conanp.gob.mx/Publicaciones2020/Publicaciones%20CONANP/Parte%203/Participacion%20social/2014%20Pueblos%20indigenas%20y%20ANP.pdf

SIC, (2024). Sistema de Información Cultural. Lenguas indígenas por estado: 68. Disponible en: https://sic.cultura.gob.mx/lista.php?table=inali_li&tado_id=7&municipio_id=-1

Community Health, Safety and Security Plan (CHSSP)

SECTION I: Project Information

A. Basic Project Profile

| PROJECT TITLE: | Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| --- | --- | --- | --- | --- |
| GEF/GCF PROJECT ID: |  |  | PROJECT DURATION: | 60 months |
| EXECUTING AGENCY/ENTITY: | Fondo Mexicano para la Conservación de la Naturaleza (FMCN) |  |  |  |
| PROJECT START DATE: | 2025 |  | PROJECT END DATE: | 2030) |
| PREPARED BY: |  | Socioenvironmental Research Coordinator at FMCN |  |  |
| DATE OF (RE)SUBMISSION TO CI-GEF/GCF: |  | 20/03/2024; 21/03/2024 |  |  |
| CHSSP APPROVED (CONDITIONALLY) BY: |  | Ian Kissoon, Senior Director, ESMF, CI-GEF Agency |  |  |
| CONDITIONS: |  | CHSSP to be validated with stakeholders during the next phase |  |  |
| DATE OF CI-GEF APPROVAL: |  | March 22, 2024 |  |  |

- Project Description

Mexico safeguards nearly 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life.

The Project "MEx30x30: Conserving Mexican biodiversity through communities and their protected areas" has the objective of

To help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategy and Action Plan (ENBioMex).

MEx30x30 has three main objectives to reach this goal:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively;

- To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and Local Communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

The Project MEx30x30 will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration between FMCN, the Conservation Trust Fund of Mexico, and CONANP. FANP was established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community vigilance, fire management, productive projects, ecotourism, and capacity building.

Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP is the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more federal PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives.

The Project MEx30x30 will focus on the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams,. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

MEx30x30 is an opportunity to make the 30x30 goal possible, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue expanding geographically while it increases public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes.

The Community Health, Safety, and Security Plan (CHSSP) provides information on the nature and extent of environmental and human health effects that may result from Project operations and unplanned emergencies at project intervention sites. The CHSSP protects the well-being of communities and Project staff and enhances environmental initiatives' overall success and sustainability by fostering trust, cooperation, and long-term positive impacts on human and environmental health.

The specific objectives of this plan are:

- To forge a culture of prevention in projects coordinated by CONANP and FMCN.

- To identify and minimize potential risks associated with Project activities.

- To safeguard individuals' health, safety, and security in Project areas, including preventing harm to community members and Project staff during Project implementation and ensuring their continued well-being afterward.

- To establish guidelines for rapid response and effective management to mitigate any adverse impacts on community and Project staff health, safety, and security before, during, or after emergencies or unforeseen incidents.

- To ensure local stakeholders' concerns are addressed and their input incorporated into safety and security measures.

- To build the capacity of community members and Project staff to identify, address, and respond to health, safety, and security issues effectively, thereby promoting sustainable practices and resilience.

SECTION II: National Legal Framework on Community Health, Safety, and Security

The following relevant international legal frameworks related to community safety, security, and health are signed by Mexico:

- International Health Regulations (IHR): Mexico is a signatory to the International Health Regulations, a legally binding international agreement adopted by the World Health Assembly. The IHR aims to prevent, protect against, control, and respond to the global spread of disease.

- International Labour Organization (ILO) Conventions: Mexico has ratified various ILO conventions related to occupational health and safety, including conventions on occupational safety and health, the prevention of occupational accidents, and the protection of workers' rights

The national legal frameworks on community safety applicable to the Project include:

- Political Constitution of the United Mexican States: It includes the rights of the Mexican people and promotes a federal government that actively encourages those rights. Article 27 establishes that the ownership of lands and waters within the limits of the national territory originally belongs to the Nation, which has the right to transfer the ownership of these lands and waters to individuals, thereby constituting private property. Expropriations can only be carried out for public utility and with compensation. Section VII of this article recognizes the legal personality of ejidos and communal population centers and protects their land ownership, for human settlements and productive activities. The law, while respecting and strengthening the communal life of ejidos and communities, safeguards land for human settlements, regulates the use of lands, forests, and communal waters, and provides necessary development actions to improve the standard of living for their inhabitants. It grants authority to the ejidal assembly as the supreme body of the ejidal organization.

- Federal Labor Law: Article 2nd defines it as mandatory to observe and maintain safety and hygiene conditions in the performance of any type of work, as well as to comply with the applicable regulations and Mexican Official Standards related to safety, health, and the work environment.

- General Civil Protection Law: It establishes powers and obligations of the state and individuals to safeguard the integrity of the population in the face of risks, vulnerabilities, or eventualities in the short, medium, and long term through a National Civil Protection System focused on prevention and describes the mechanisms for dealing with disasters or disruptions.

- General Health Law: The highest authority for the evaluation of public health risks corresponds to the State, for which the Federal Commission for Protection against Sanitary Risks is created, which establishes a National Policy for Protection against Sanitary Risks that develops specific instruments on pesticides, plant nutrients, toxic or hazardous substances for health; biotechnological products, raw materials and additives that intervene in the elaboration of products; as well as in the prevention and control of harmful effects of environmental factors on human health, occupational health and basic sanitation. The Ministry of Health and state agencies are responsible for establishing and operating a National Epidemiological Surveillance System, on the basis of which measures and guidelines are established to guide the control and attention to public health threats.

- National Security Law: This law establishes the guidelines and principles for national security, including measures related to defense, public security, and the protection of critical infrastructure.

- General Law on Ecological Equilibrium and Environmental Protection: Addresses environmental protection measures, including regulations to safeguard public health from environmental hazards.

- NOM-017-STPS-2008: Establishes the minimum requirements for the employer to select, acquire, and provide its workers with the personal protective equipment necessary to protect them from agents in the work environment that may harm them physically or their health.

- NOM-026-STPS-1998: Safety and hygiene colors and signs-Identification of risks due to fluids conducted in pipelines.

- NOM-113-STPS-1994: Protective footwear.

- NOM-115-STPS-1994: Protective Helmets-Specifications, test methods, and classification.

- NOM-116-STPS-1994: Safety-Air purifying respirators against harmful particles.

- NOM-047-SSA1-2011: Establishes the Biological Exposure Indexes for personnel occupationally exposed to chemicals to support detecting health risk levels based on exposure to chemicals in establishments and supporting industrial hygiene and personnel health protection measures.

- NOM-232-SSA1-2009: Establishes the requirements for packaging, packing, and labeling of technical grade products for agricultural, forestry, livestock, gardening, urban, industrial, and domestic use.

- NOM-032-SSA2-2014: Establishes specifications, criteria, and procedures to reduce the risk of infection, disease, complications, or death from vector-borne diseases.

- NOM-082-SAG-FITO/SSA1-2017: Establishes the technical guidelines and procedures for authorizing of maximum residue limits (MRLs) of chemical pesticides for agricultural use for registration and use. Importing MRLs is not the subject of this Standard.

- DN-III-E Plan: A military operating instrument that establishes general guidelines for the agencies of the Mexican Army and Air Force to carry out prevention, relief, and recovery activities for the population affected by natural or human disasters, optimizing the use of human and material resources to provide timely, effective, and efficient assistance, while also supporting the preservation of their assets and the environment.

SECTION III: Health, Safety, and Security Risks and Mitigation Measures

Over its three-decade tenure, the Mexican Fund for the Conservation of Nature (FMCN) has undertaken various initiatives to manage operational risks effectively, including all the challenges FMCN personnel, communities, and partners have encountered during project implementation. Central to this endeavor are the strategies and recommendations provided to identify, assess, mitigate, and monitor risks that have the potential to impede the realization of project objectives and are based on the collective knowledge built by the joint efforts of the National Commission for Protected Areas (CONANP) and FMCN.

A. Insecurity in Mexico

The geography of crime is dynamic and requires continuous monitoring. Therefore, it is advisable to consult recent and relevant information on the situation of insecurity in Mexico before performing any field activities. The following websites are recommended:

- http://www.informeseguridad.cns.gob.mx/. Provides information on crimes in Mexico by day, by type of crime, and by entity.

- http://www.semaforo.com.mx/. Provides a crime traffic light in Mexico monthly, according to the type of crime and entity.

- https://www.inegi.org.mx/temas/incidencia/. Provides information on the incidence of crime in Mexico annually by type and entity.

- https://www.cemda.org.mx/publicaciones-y-estudios-del-cemda/. Provides annual reports on the situation of environmental human rights defenders in Mexico.

B. Health, Safety, and Security Risks

Conservation projects can expose communities and staff to health, safety, and security risks. These risks can vary depending on the nature of the project, the location, and the specific circumstances, including:

| Risk | Description |
| --- | --- |
| - Physical hazards | Conservation projects often occur in remote or rugged environments, exposing workers and community members to falls, trips, or injuries from uneven terrain, extreme weather conditions (heatwaves, storms, cold), encounters with wildlife, or road accidents. |
| - Work-related injuries | Tasks associated with conservation projects, such as habitat restoration or field surveys, can involve physical labor and the operation of machinery or tools, increasing the risk of accidents and injuries. |
| - Vector-borne diseases | Working outdoors in natural environments can expose individuals to vector-borne diseases carried by insects such as mosquitoes, ticks, or flies. Depending on the region, these diseases can include malaria, dengue fever, Lyme disease, and others. |
| - Water-borne diseases | In areas with limited clean water sources, staff and community members may be at risk of contracting water-borne diseases such as cholera, typhoid fever, or dysentery. |
| - Chemical exposure | Exposure to pesticides, herbicides, pollutants, or other hazardous substances can pose health risks to staff and nearby communities. |
| - Security risks | In some regions, social conflicts, illegal resource extraction, political instability, and illegal activities, among others, can expose staff and communities involved in conservation activities to violence, kidnapping, confrontations, or threats. |
| - Theft and vandalism | Equipment, supplies, or infrastructure related to conservation projects may be targeted for theft or vandalism, especially in areas with high poverty levels or limited law enforcement presence. |
| - Natural disasters | Communities and project staff may be at risk of natural disasters such as earthquakes, floods, hurricanes, or wildfires, which can disrupt project activities and pose immediate threats to life and property. |
| - Mental health | Working in challenging environments or facing setbacks in conservation efforts can lead to stress, burnout, or mental health issues among staff. Communities may experience stress or anxiety due to environmental or livelihood changes. |

The estimated impact that these threats may cause and the probability of their occurrence can be visualized in the following matrix according to the specific letter assigned to each risk:

For MEx30x30 the following project specific risks were identified:

| Community Health, Safety and Security Threat | Likelihood | Impact | Risk | Risk Rating |
| --- | --- | --- | --- | --- |
| - Natural hazards/disasters such as flooding, drought, wildfires, and hurricanes | Possible (3) | Moderate (3) | 9 | Medium |
| - Exposure to communicable/vector-borne disease such as COVID-19, and malaria | Possible (3) | Moderate (3) | 9 | Medium |
| - Security related risk such as working in areas with illegal activities (e.g. poaching, growing illicit crops) | Likely (4) | Moderate (3) | 12 | High |
| - Threats to human security through the risk of escalation of personal or communal conflict and violence that could be caused or exacerbated by the project | Possible (3) | Moderate (3) | 9 | Low |
| - Project-level Gender-Based Violence (GBV) and Sexual Exploitation, Abuse and Harassment (SEAH), including disappearance of women | Possible (3) | Moderate (3) | 9 | Medium |
| - Exposure to safety hazards related to community brigades | Possible (3) | Moderate (3) | 9 | Low |
| - Work-related injuries, including road accidents, encounters with wildlife, vector and water-borne diseases, and mental health issues | Possible (3) | Moderate (3) | 9 | Low |

Mitigation measures for these health, safety, and security risks will be described in more detail in the following section.

C. Preventive Actions and Mitigation Measures

This CHSSP covers all activities related to the implementation of the Project. It outlines CONANP and FMCN’s commitment and approach to avoid and reduce community and personnel health, safety, and security risks that may arise from the Project.

CONANP typically implements rigorous hygiene, safety, and security protocols within protected areas to ensure the well-being of personnel, communities, and visitors. These protocols often involve regular sanitation of facilities, provision of safety equipment, and enforcing regulations to protect wildlife and people.

CONANP collaborates closely with the Federal Attorney for Environmental Protection (PROFEPA) and the Guardia Nacional (National Guard) to enhance security measures. This collaboration involves joint patrols, surveillance efforts, and information sharing to prevent illegal activities within protected areas, such as poaching, logging, and illegal activities.

Additionally, CONANP conducts training programs for personnel and local communities to promote awareness of safety procedures and environmental conservation practices. These efforts aim to create a safer and more sustainable environment within protected areas, benefiting both present and future generations.

MEx30x30 will train project staff and local communities to address concerns and establish appropriate safety protocols and emergency responses. Capacity-building processes will be supported by the Learning Community in Project’s Component 1. Additional training workshops and emergency response will be organized depending on POA priorities and needs. For example, community brigades may be trained in fire management, prevention, control and fighting, first aid, and emergency response. The cost will be included in the overall Learning Community and POA budget.

Any serious incident under the Project will be reported to FMCN within 48 hours. Other incidents shall be reported to FMCN in the monthly reports and to CI-GEF in the semi-annual reports, which shall also detail subsequent actions and follow-up to such incidents. In an emergency, CONANP and FMCN will seek guidance from CI’s security experts.

Collaboration with local authorities and other stakeholders will help improve security and support the successful implementation of conservation initiatives. Relevant governmental agencies and telephone numbers are in the following table:

| Governmental Agency | Purpose | Telephone number |
| --- | --- | --- |
| Emergencies | 9-1-1 is the single number for emergency calls. It standardizes all emergency medical, security, and civil protection numbers at the federal, state, and municipal levels. The single emergency call number, 9-1-1, is available 365 days a year, 24 hours a day, to request the support of: - National and State Commission of Citizen Security - National, State, and Municipal police - Attorney General's Office - Red Cross - Firefighters - Civil Protection - National Emergency Attention System | 911 |
| Anonymous complaints | If you are a victim or know of a possible crime that needs to be investigated, report it safely and anonymously, including telephone extortion, kidnapping, drug sales, human trafficking, extortion, fuel theft, and arms trafficking, among others. | 089 |
| National Guard | The purpose of the National Guard is to carry out the public security function of the Federation and, if necessary, to temporarily collaborate in the public security tasks that correspond to the states or municipalities. | 088 |
| Secretariat of Security and Citizen Protection (SSPC) | The Secretariat of Security and Citizen Protection coordinates federal security policies and strategies to ensure public safety. | 55 1103 6000 |
| National Disaster Prevention Center (CENAPRED) | The National Disaster Prevention Center conducts and coordinates research on the origin, behavior, and consequences of natural and anthropogenic phenomena that cause disasters, the results of which impact technological development, hazard identification, disaster risk reduction, and warning. CENAPRED is technically responsible for coordinating, facilitating, and supervising the formulation and implementation of the National Policy and the National Plan for Disaster Risk Management in risk estimation, prevention, reduction, and reconstruction. | 55 5424 6100 |
| Civil Protection | Civil Protection safeguards the physical integrity of people in the event of a disaster caused by natural or human agents through actions that reduce or eliminate the loss of human lives, the destruction of material goods, and damage to nature. | 55 5128 0000 55 5683 2222 |
| Forest fires | In the presence of a forest fire, neighboring communities are asked not to act on their own, stay away, and report it immediately. | 800 4623 6346 |
| Red Cross | The Red Cross serves people or communities affected by emergency or disaster situations, health problems, diseases, injuries caused by accidents, migration, and social exclusion. It emphasizes prevention and increasing individual and collective capacities so that the beneficiaries are socially organized, prepared, and resilient in the face of threats and adversities. | 55 5395 1111 |
| Ministry of Health (SSA) | The Ministry of Health oversees public health policies, healthcare services, disease prevention, and health promotion programs. | 55 5062 1600 |
| Comisión Federal para la Protección contra Riesgos Sanitarios (COFEPRIS) | The Federal Commission for the Protection against Sanitary Risks regulates and monitors health risks associated with food, medicines, healthcare products, and environmental health. A health report allows you to report facts, acts, or omissions that represent a risk or cause damage to health. | 800 033 5050 |

The main mitigation measures to avoid and minimize community and personnel health, safety, and security risks foreseen are listed below. These measures will be enforced during the project lifecycle so that project communities and staff can adhere to them and encourage compliance. For example, providing comprehensive training and encouraging peer-to-peer accountability foster a culture of compliance, awareness, and effectiveness. Random supervision visits facilitate timely interventions and corrective actions. Strengthening transparent reporting mechanisms for incidents and effective communication channels ensures that relevant information reaches the appropriate stakeholders promptly, promoting a safer and more secure environment for everyone.

CAR INCIDENTS

Preventive measures - Driver

- Prepare travel logbook

- Share logbook with supervisor and organization being visited

- Travel with original and provide copy of personal identification to employer

- Travel with institutional identification

- Travel with a personal medical policy card

Preventive measures - Automobile

- Travel with a valid driver's license

- Check to have a valid vehicle registration card

- Check to have a current insurance policy

- Confirm the existence of spare tires, tools, gas can, red flannel, or red cloth

- Check tire pressure

- Verify that the indicators on the control panel are functioning correctly

- Check fluid levels

- Check headlights and taillights

- Check the balance of the toll tag

- Fill gas tank

- Consult if there is an environmental (air quality) contingency

- Know traffic regulations

Preventive measures - Route

- Avoid driving tired or drowsy

- Do not drive at night

- Avoid being distracted by the use of cell phones or other accessories

- Do not give rides to strangers

- Avoid eating a heavy meal before the trip

- Opt for toll roads when the destination allows it

- Never travel alone

- Wear uniform - institutional t-shirt

- Be respectful in checkpoint areas

- Respect speed limits

CAR ACCIDENTS

Actions during an automobile accident

- Keep calm

- Make sure you are in good health

- Check the health state of other people

- Avoid moving a severely injured person

- Search for roadside assistance

- Avoid leaving the site

- Turn off the car to reduce the likelihood of a fire

- Avoid traffic discussions

- Place preventive triangles 30 meters away from the crashed car

- Contact the insurance company

- Take photographs of the damage, the site, and those involved

- Avoid pursuing the offender

- Avoid taking responsibility for the accident,. Wait for the claims adjuster

- Collect information: license plate number and model of the cars involved

Actions after an automobile accident

- Report to the authorities and the insurance company the details of what happened

- Avoid cash payments

- Visit the doctor

WORK-RELATED INJURIES

Preventive measures

- Recognize your health status

- Accept physical impairments and ask for help when necessary

- Use footwear suitable for the terrain

- Wear the appropriate clothes and equipment for the programmed visit

- Carry a map of the area to be visited

- Follow the instructions of local personnel

- Respect restricted areas and risk zones

- Check the weather forecast

- Define waiting and meeting points during the visit

- Keep hydrated

- Carry energy food

- Cease physical activity if any pain occurs

- Ensure that first aid kits are readily available

- Ensure staff and communities are trained in basic first aid procedures to address immediate health concerns (minor injuries)

- Promptly report any injuries, accidents, or near misses immediately to supervisors. Prompt reporting allows for swift response and investigation to prevent similar incidents in the future

Professional attention

- Ensure that all work-related injuries receive a thorough medical evaluation by qualified healthcare professionals. This evaluation helps determine the severity of the injury and appropriate treatment options

- Maintain detailed records of all work-related injuries, including incident reports, medical evaluations, and follow-up treatments. Accurate documentation is essential for compliance with regulatory requirements and insurance claims

- Support and assist injured staff throughout their recovery process, including access to rehabilitation services, counseling, and accommodations for returning to work

INCIDENTS WITH ANIMALS

Preventive measures

- Respect the habitat

- Know the species that inhabit the area

- Avoid intentionally attracting or approaching an animal

- Avoid disturbing, mistreating, or harming an animal

- Maintain a safe distance from the animal

- Minimize odors or attractants and avoid the use of perfume or similar products

- Wear attire appropriate to the area - Shake out clothes and shoes before getting dressed

- Shake out sheets, blankets, and sleeping bags every day

- Use repellents or sprays

- Walk in groups of three or more people

- Stay alert

- Avoid leaving food outdoors and cover garbage containers tightly

- Avoid excursions or swimming at night

- Avoid swimming in fishing areas

- Ensure that first aid kits are readily available at project sites (with antidotes if required)

- Ensure staff and communities are trained in basic first aid procedures to address immediate health concerns (insect bites)

During an animal attack

- Keep calm

- Avoid responding to aggression

- Avoid sudden movements

- Move away slowly and without provoking the animal further

- Avoid running

After an incident with an animal

- Seek medical attention

VECTOR-BORNE & WATER-BORNE DISEASES AND CHEMICAL EXPOSURE

Preventive measures

- Know the signs and symptoms of these diseases

- Implement proper hygiene practices, such as frequent handwashing, adequate sanitation facilities, and waste disposal

- Wear appropriate clothes and equipment

- Use insect repellents and insecticide-treated bed nets

- Ensure that first aid kits are readily available at project sites

- Ensure staff and communities are trained in basic first aid procedures to address immediate health concerns (chemical exposure)

Immediate attention

- Communicate to colleagues, friends, and family that you are feeling unwell.

- Develop and communicate an emergency response plan outlining procedures for a health-related incident, including whom to contact and where to seek medical assistance

- Establish mechanisms for rapid diagnosis and treatment of vector-borne and water-borne diseases to minimize the spread of infections and mitigate their impact on affected individuals

- Move to a health center

Professional attention

- Ensure access to healthcare services, including primary healthcare facilities and specialists for more complex health issues

- Take the recommended medication

- Monitor your health status

SECURITY RISKS

Preventive measures

- Build strong relationships with local communities to gain their trust and cooperation, as they can provide valuable insights and support in mitigating security risks

- Implement strict travel protocols, including pre-travel briefings, secure transportation, location apps, and adherence to designated safe routes

- Provide comprehensive security training to project staff, partners, and communities, including protocols for dealing with security threats and emergencies

- Establish effective communication channels for sharing security-related information, reporting suspicious activities or security incidents, and updates among project team members and stakeholders

- Collaborate with local authorities, government agencies, NGOs, and other relevant stakeholders to address security concerns and coordinate response efforts

- Avoid displaying high-value personal items

- Avoid routines and regular routes

- Avoid risky and unknown areas

- Avoid storing confidential contents in cell phones (passwords, addresses, direct access to e-mail)

- Avoid carrying large sums of cash and several credit cards

- Avoid providing personal data in hotels or restaurants

- Memorize important telephone numbers

- Identify suspicious persons or situations and report them

- Keep the staff and a family member informed of your scheduled activities for the day, duration of visit, location, contact details - Identify in the team the people who can lead in emergencies and identify support security consultants

Immediate attention

- Implement systems for quickly alerting project personnel about security incidents or threats, such as emergency communication networks or mobile apps

- Designate a dedicated emergency response team trained to promptly assess and respond to security incidents

- Maintain constant communication with project staff and stakeholders during security incidents to provide updates and instructions

- Encourage personnel to remain calm and make swift, informed decisions in case of an incident, such as activating tracking devices or following established communication protocols

- Ensure rapid deployment of resources, including trained security personnel, negotiators (if applicable), and support from law enforcement agencies to assist in resolving the situation

Professional attention

- Seek advice and assistance from security consultants or firms specializing in risk management and security planning

- Coordinate with local security forces or law enforcement agencies to enhance security measures and receive support during high-risk situations

- Engage professional crisis management teams or consultants to provide guidance and support in managing security crises effectively

- Provide comprehensive support to affected personnel, including access to counseling services, medical assistance, and legal support throughout and after the incident resolution

Conflict management

- Identify points of controversy

- Reduce discrepancies

- Establish a frank dialogue with the parties involved

- Appoint a mediator

- Strive for a constructive attitude

- Inform, create options, negotiate, etc.

- Build trust

- Clarify misunderstandings and prejudices

- Build consensus

- Accept agreements

THEFT AND VANDALISM

Preventive measures

- Avoid leaving valuables in plain view

- Avoid carrying large sums of cash and several credit cards

- Avoid using ATMs at night

- Avoid counting cash in public

- Walk/drive on illuminated avenues with high vehicular and pedestrian traffic

- Have your keys ready when you get home/office

- Have the keys ready when approaching the car

- Drive with windows closed

- Keep alert

- Keep asset invoices in a secure place

- Maintain insurance for assets

Actions during a robbery

- Keep calm

- Avoid resistance

- Avoid eye contact with the perpetrator

- Avoid responding to physical and verbal aggression

- Follow the perpetrator's instructions

- Avoid sudden movements, tell the perpetrator what action you are going to take

Actions after a robbery

- Move to a safe place

- Seek companionship and recover

- Inform the supervisor and family members

- Cancel credit cards

- File a report with the Public Prosecutor's Office

- Report the event to insurance companies

- Replace personal documents

NATURAL DISASTER

Preventive measures

- Keep an online copy of personal documents

- Maintain a briefcase with first aid kits, food, water, essential medications, a lamp, and a battery-powered radio

- Outline procedures for evacuations, medical emergencies, and communication protocols in the event of a natural disaster

- Designate a trained emergency response team responsible for coordinating immediate responses to natural disasters

- Establish clear evacuation routes, assembly points, and security zones

- Agree with staff/family members on meeting point and time to report in

- Conduct regular drills to practice evacuation procedures

- Avoid placing large objects in aisles and doorways

- Check gas and electrical installations frequently

- Memorize emergency numbers

- Identify shelters

- Encourage community members to develop emergency plans and establish communication networks - Opt for infrastructure that can withstand natural disasters (ex. storm windows and movable docks for places with hurricanes)

Actions during a natural disaster

- Keep calm

- Avoid wasting time gathering personal items

- Go to a safety zone

- Avoid running, shouting, or pushing

- Avoid using elevators and stairs

- Keep away from windows and falling objects

- Ignore alarmist rumors and avoid spreading them

Actions after a natural disaster

- Keep calm

- Call for help, in case of being trapped, by hitting with an object

- Move away from damaged properties

- Follow the instructions of the emergency brigades

- Keep gas, electricity, and water services disconnected

- Avoid stepping on or touching any loose wires

- Report gas and water leaks

- Remain alert to possible aftershocks

- Avoid using elevators and be cautious with the use of stairs

- Avoid lighting matches, candles, open flames, or electrical appliances

- Use the telephone only to report an emergency

- Conduct post-disaster assessments to evaluate the impact of natural disasters and identify areas for improvement in preparedness and response strategies

MENTAL HEALTH

Preventive measures

- Raise awareness about the potential mental health challenges, such as exposure to difficult environmental conditions

- Provide training on stress management, resilience-building, and coping strategies

- Foster a supportive work environment where team members feel comfortable discussing mental health concerns without fear of stigma or judgment

- Encourage a healthy work-life balance by implementing policies that promote adequate rest, breaks, and time off

Immediate attention

- Train designated team members in mental health first aid techniques so they can provide immediate support to individuals experiencing mental health crises or distress

- Ensure that team members have access to resources such as hotlines, counseling services, and crisis intervention support

- Conduct debriefing sessions after particularly challenging or traumatic experiences to allow team members to process their emotions and reactions in a supportive environment

Professional attention

- Ensure that personnel can access to medical assistance provided through medical insurance or social security

- Ensure medical follow-up

EXTORTION

Preventive measures

- Be wary of calls and messages from strangers

- Do not answer unknown numbers

- Hang up in case of an extortion attempt

- Maintain constant communication with team and family members

- Do not respond to telephone surveys

- Do not provide personal information

- Do not disseminate personal data (facebook location, photos, etc.)

- Do not provide banking information

- Minimize cash withdrawals

GENDER VIOLENCE

Preventive measures

- Implement and raise awareness around FMCN and CONANP policies that explicitly address gender-based violence (GBV). These policies promote gender equality, respect, and safety for all project participants

- Provide training to all project staff, communities, and partners on recognizing, preventing, and responding to gender-based violence. This training should include information on gender dynamics, power imbalances, and respectful communication

- Establish confidential and accessible reporting mechanisms for individuals who experience or witness gender-based violence

- Allocate resources specifically for addressing gender-based violence within projects. It may include funding for training, support services, and raising awareness

- Communicate risk situations to team members

Immediate attention

- Ensure staff is trained to provide immediate support to survivors, including access to medical care and emergency shelters

- Offer survivors of gender-based violence information about counseling and psychosocial support services

- Provide survivors with information about legal support services

Professional attention

- Collaborate with local authorities, NGOs, and other relevant stakeholders to coordinate professional interventions for survivors of gender-based violence. It may include referrals to healthcare providers, legal aid organizations, or shelters

- Monitor the effectiveness of interventions and adjust strategies as needed to improve outcomes for survivors

d. Monitoring and reporting

The compliance of Project activities with the CHSSP will be continually monitored throughout the Project lifespan. The Safeguards and Monitoring and Evaluation Coordinator will ensure specific ESS monitoring and assessing the effectiveness of environmental and social safeguard risk management activities. Based on monitored and unforeseen risks, the monitoring plan will be periodically reviewed and updated in conjunction with the CHSSP. Further identification of risks during the monitoring process will reduce the project's overall environmental and social impact as these risks are promptly identified and addressed accordingly. Monitoring will also be complemented by information gathered during ongoing engagement with communities and other stakeholders through the Stakeholder Engagement Plan, the Gender Mainstreaming Plan, the Grievance Redress Mechanism, therefore, contributing to the dynamism, adaptability, and, ultimately, the effectiveness of the Project.

Indicators for Implementation Phase

| Indicator | Baseline | Target | Frequency | Responsible |
| --- | --- | --- | --- | --- |
| - Number of health, safety and/or security incidents reported and addressed. | 0 | TBD | Semi-annual | PMU Safeguards and Monitoring and Evaluation Coordinator |
| - Percentage of measures implemented to ensure that risks or potential impacts to the health, safety and security of project-affected communities/project staff are avoided or mitigated. | 0% | 100% | Semi-annual | PMU Safeguards and Monitoring and Evaluation Coordinator CONANP |

| Person responsible for implementing and monitoring the ESMP | Safeguards and Monitoring and Evaluation Coordinator |
| --- | --- |
| Budget Summary: | Included in POA and Learning Community |

ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN (ESMP)

I. PROJECT INFORMATION

| I. PROJECT INFORMATION |  |  |  |
| --- | --- | --- | --- |
| GEF Project ID: | Country: Mexico |  |  |
| Project Title: Mex30x30: Conserving Mexican biodiversity through communities and their protected areas |  |  |  |
| Name of the Executing Agency/Entity: Fondo Mexicano para la Conservación de la Naturaleza |  |  |  |
| Length of Project: 60 months | Anticipated Start date: |  | Anticipated End date: |
| GCF Results Area(s) / GEF Focal Area(s): Global Biodiversity Framework Fund (GBFF) |  |  |  |
| GEF Project Amount: USD$ |  | Co-Financing Amount: USD$ |  |
| ESMP Developed by: FMCN – Socioenvironmental Research Coordinator |  |  |  |
| Date of Submission/Resubmission of Completed Form to CI-GEF/GCF: 13/03/2024 |  |  |  |
| CI-GEF Comments: The ESMP is to be revised during the next phase, particularly to address the potential environmental and social impacts on the PAs/ADVCs and local communities with regards to project activities such as restoration of degraded areas, community brigades, fire management, productive projects, and ecotourism, among others. |  |  |  |

A. Basic Project Profile

- Project Objective

The Project "MEx30x30: Conserving Mexican biodiversity through communities and their protected areas" has as objective to help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas (national parks and ADVCs). This goal is aligned with GBFF targets and responds to the National Biodiversity Strategies and Action Plan (ENBioMex).

MEx30x30 has three main objectives to reach this goal:

- To strengthen the National Commission for Protected Areas (CONANP) to increase its budget and manage protected areas (PAs) and Voluntary Conservation Areas (ADVCs, for its acronym in Spanish) effectively;

- To mobilize funding to cover the financial gap in PAs while public funding reaches its target. CONANP will work with FMCN to close the financial gap with additional donors, mainly from philanthropy, while public funds take over, thus addressing the threat to conserving biodiversity of global significance.

- To strengthen recently established PAs, and ADVCs managed by Indigenous Peoples and local communities (IP&LCs), to conserve, restore, and sustainably manage territories. The partnership model will be scaled to achieve a national impact on the entire PA system.

- Project Description

Mexico safeguards near to 12% of global biodiversity. However, around 50% of Mexico's territory faces environmental degradation due to biophysical, social, and economic factors, which can harm ecosystems and negatively impact human life.

The Project MEx30x30 will scale up the lessons learned in 26 years of a successful partnership between FMCN and CONANP to strengthen protected areas' management and efficiency, ensure the long-term conservation of critical biodiversity and representative ecosystems, and deliver concrete socioeconomic benefits to local communities. The Project will build upon the Protected Areas Fund (FANP), a public-private collaboration scheme between FMCN, the Conservation Trust Fund of Mexico, and CONANP, established in 1997 with GEF funding. FANP channels strategic financial resources to 70 PAs to strengthen their operation and management through strategic activities such as biological monitoring, restoration of degraded areas, community vigilance, fire management, productive projects, ecotourism, and capacity building.

Successful PA planning and management at the landscape level typically requires extensive coordination among multiple levels of stakeholders. Given the complexity of interests, policies, and logistics and many agencies being overworked and under-resourced, successful coordination is challenging even under the best circumstances. At the federal level, CONANP has been the governmental institution in charge of promoting the conservation and sustainable management of Mexico's biodiversity through protected areas. Recently, the Mexican government has made commendable efforts to recognize the importance of biodiversity by decreeing more PAs than any previous administration. PAs can have a federal, state, or municipal decree. They can also be ADVCs by landowners' request, most of them IP&LCs. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024). However, high levels of socioeconomic marginalization in many rural communities and heavy livelihood dependence on natural resources can result in resistance to prioritizing conservation or restoration activities that do not adequately consider local needs. CONANP has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Thus, engaging local communities, indigenous groups, and other stakeholders fosters a sense of ownership and collaboration and ensures long-term sustainable management practices. As a result, The Project will work together with different stakeholders to join efforts for conservation and social care strategies to pursue greater spatial and temporal scale objectives.

The Project MEx30x30 will focus on the following components:

- Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. MEx30x30 will enhance the capacity of CONANP to close its financial gap for the existing federal protected areas through a variety of revenue streams,. Furthermore, CONANP also will increase its institutional capacity commensurate with the increase in the budget.

- Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. MEx30x30 will design and deploy a long-term financing mechanism following the Project Finance for Permanence (PFP) approach, including a transition fund to cover the funding gap while CONANP develops its revenue streams (Component 1) to increase public funding.

- Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. Using GEF funds, the MEx30x30 project will establish a US$12 million endowment to ensure permanent funding for three recently decreed PAs currently, two PAs previously decreed, and a complex of eight ADVCs recently established.

- Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. Component 4 will entail close coordination between FMCN, CONANP, the donor community and IP&LCs to ensure that project activities and results are properly monitored and evaluated, and that knowledge management facilitates the efficient sharing of information at every level of the project.

MEx30x30 is an opportunity to make possible the 30x30 goal, building on the unprecedented commitment of this administration to decree PAs and allowing CONANP to continue decrees and increase public funding until 30% of the territory is effectively managed by 2030. The Project will directly contribute to global environmental benefits, including the conservation of globally significant biodiversity, enhanced biodiversity and ecosystem functions and services, and conservation and enhanced carbon stocks in critical landscapes.

The ESMF aims to ensure that the Project-related adverse environmental and social risks and impacts are avoided or, when unavoidable, minimized and appropriately mitigated, providing an approach that enhances gender mainstreaming, stakeholder engagement, and grievance redress mechanisms throughout the project cycle. Any identified adverse environmental and social impacts and risks will be addressed and tracked to guarantee that supported activities comply with the corresponding policies and practices under the adoption of the precautionary principle.

The objectives of MEx30x30 ESMF are:

- Strengthen the quality of programming by ensuring a principled approach.

- Avoid adverse impacts on people and the environment.

- Minimize, mitigate, and manage adverse impacts where avoidance is not possible.

- Ensure complete and adequate stakeholder engagement, including a mechanism to respond to complaints from project-affected people.

II. APPLICABLE NATIONAL AND INTERNATIONAL ENVIRONMENTAL AND SOCIAL REGULATIONS

Compliance with national and international environmental and social regulations is part of the essential requirements applicable to MEx30x30. These regulations include (Annex 1):

National regulations

- Political Constitution of the United States of Mexico

- General Ecological Equilibrium and Environmental Protection Law

- General Climate Change Law

- Sustainable Forest Development Law

- Sustainable Fishing and Aquaculture Law

- General Wildlife Law

- Sustainable Rural Development Law

- National Waters Law

- Federal Environmental Liability Law

- Agrarian Law

- Federal Law to Prevent and Eradicate Discrimination

- General Equal Opportunities Law

- Elimination of Violence Against Women Law

- General Civil Protection Law

- General Health Law

- General Human Settlements Law

- Federal Labor Law

- Social Security Law

- Rights of Girls, Boys, and Adolescents Law

- National Workers’ Housing Fund Institute Law

International regulations

- Universal Declaration of Human Rights

- Convention on Biological Diversity

- Cartagena Protocol on Biosafety

- Nagoya Protocol on the Fair and Equitable Sharing of Benefits Arising out of the Utilization of Genetic Resources

- Convention on International Trade in Endangered Species of Wild Fauna and Flora

- United Nations Framework Convention on Climate Change

- Kyoto Protocol

- Montreal Protocol on Substances that Deplete the Ozone Layer

- Paris Agreement

- Stockholm Convention on Persistent Organic Pollutants

- Regional Agreement on Access to Information, Public Participation, and Access to Justice in Environmental Matters in Latin America and the Caribbean (Escazú Agreement)

- International Labor Organization Conventions 138, 169 and 182

- United Nations Declaration on the Rights of Indigenous Peoples

- Convention concerning the Protection of the World Cultural and Natural Heritage

- Convention for the Safeguarding of the Intangible Cultural Heritage

III. BASELINE INFORMATION

Mexico is one of the world's 15 megadiverse nations, holding an extraordinary 10-12% global biodiversity, ranking third in mammal diversity with over 564 species and 30% endemic. Additionally, it secures the second spot for reptiles, boasting over 860 species, 45% exclusive to its diverse landscapes. Its rich tapestry of flora, comprising over 5,000 species, is a testament to its ecological wealth and plays a vital role in the lives of indigenous and local communities.

Over 12 million Mexicans rely on forests for their livelihoods, with five million indigenous people inhabiting forested areas. More than 3,000 medicinal plant species are actively utilized for traditional purposes, offering a unique avenue for promoting socioeconomic development and sustainable resource management (CITE-BIOFIN, 2023). These areas, often in municipalities with high poverty and economic marginalization rates, represent 40% of Mexico's forested lands. Additionally, 61% of these areas fall under collective land tenure systems, such as ejidos and comunidades, making Mexico a global leader in community-managed forestland.

Internationally, Mexico has also earned recognition for its pivotal role in global biodiversity, being encompassed within three of Conservation International's "Hotspots" (Mesoamerica, California Floristic Province, and Madrean Pine-Oak Woodlands), featuring in 122 of WWF's Global 200, and boasting 275 Key Biodiversity Areas (KBAs) (CEPF, 2023; Olson et al., 2000; CBD, 2021).

However, nearly 50% of Mexico's territory grapples with environmental degradation from biophysical, social, and economic factors. This degradation threatens ecosystems, affecting 63 million people residing in degraded lands. The financial toll of environmental degradation reached 4.6% of Mexico's GDP in 2021, emphasizing the urgent need for collaborative efforts to address and mitigate these challenges.

Mexico has been actively working to conserve its rich biodiversity and natural resources through various strategies, including creating and managing protected areas to maintain forests, deserts, mountains, and coastal regions.

Mexico’s protected areas are vital to address directly the primary drivers of extinction and habitat loss, becoming sanctuaries for preserving significant biodiversity of national and global importance, from iconic species to unique ecosystems. PAs have been effective at slowing the rate of biodiversity loss. Analyses show that PAs supported by the Global Environmental Fund (GEF) in Mexico avoided up to 23% forest loss from 2001 to 2012 compared to PAs that did not directly receive GEF support during the same period. Safeguarding protected areas ensures the survival of threatened and endangered species and the provision of vital ecosystem services, such as clean water, air purification, pollination, and climate resilience against natural disasters and extreme weather events.

PAs also offer recreational opportunities and support physical and mental health, fostering an appreciation for nature. They also serve as living classrooms for environmental education and invaluable sites for scientific research, which can yield critical insights into climate change, ecological dynamics, and more. They, too, preserve cultural heritage and traditions, providing educational and cultural value. Moreover, they can boost long-term economic benefits for local economies through tourism, creating jobs, and stimulating sustainable local businesses.

Providing these crucial benefits is not free; costs are associated with PA management in terms of direct expenditures and opportunity costs (alternative uses). These costs require the Government of Mexico to set aside funding for PAs every year and, in effect, to “give up” potential revenues from allowing the land to be developed for other uses.

CONANP is the governmental institution responsible for administrating and managing protected areas in Mexico under two federal conservation strategies: top-down, represented by PAs by decree, and bottom-up, represented by certified ADVCs. Mexico has 226 terrestrial and marine PAs protecting 93,807,804 hectares of high socioecological value. It also supports 557 ADVCs in 28 states, totaling 1,248,438.1719 hectares. ADVC certification is a mechanism to promote voluntary social participation in conservation under an integrated landscape management approach. An ADVC certifies any person, legal entity, social organization, indigenous people, and community willingness to manage their land sustainably.

Mexico has a social vision of conservation, recognizing that it is impossible to maintain biodiversity without the active participation of society. Approximately 3.9% (4,689,557 people) of the Mexican population lives in PAs, of which 5.7% are indigenous (270,476 people). Therefore, about 46% of PAs are home to indigenous people. Of the total land surface that makes up the country's PAs, more than 60% is social property, including more than 30% of indigenous territory.

In ADVCs territories live around 92,756 persons, including sixteen indigenous groups: Amuzgo, Chinanteco, Chol, Chontal, Maya, Mazateco, Mixe, Mixteco, Nahuatl, Tlapaneco, Tojolabal, Totonaca, Tzeltal, Tzotzil, Zapoteco and Zoque. By its nature, conservation in ADVCs is an inclusive and participatory strategy and an adaptive model, particularly in common properties where their performance is permanently monitored in community assemblies and analyzed to ensure those decisions lead to the desired results. The assemblies and committees' actions include imposing hunting bans, regulations on fire use, restrictions on land uses, and regulating the harvest of wild products. Landowners express varied motives for seeking ADVCs certification: cultural values (including the legacy for future generations); wildlife or forest cover recovery; obtaining professional advice; implementing ecotourism; having eco-brands for local products (like coffee, honey, cacao, among others); looking for governmental protection for their natural resources (sanctions for illegal hunting and narcotraffiking); protecting lands from infrastructure development (highways, hydroelectric dams); protecting lands for extractive activities (mainly oil, fracking or mineral extraction); and, the expectation for incentives and institutional advice.

In Mexico, it is also essential to acknowledge that gender roles have historically influenced how men and women access, use, and manage natural resources in protected areas. These roles can influence decision-making processes, resource access, and governance structure participation. It is common for traditional gender norms to dictate that men often engage in activities like agriculture, forestry, or hunting. At the same time, women may be responsible for tasks related to gathering non-timber forest products, water, and food preparation, besides traditional roles of caring for the home and raising children. Moreover, gender-based violence and sexual exploitation, sexual abuse, and sexual harassment are high and regular. Around 70% of women and girls aged over 15 have experienced gender violence in Mexico. On average, ten women are killed every day, and tens of thousands are missing.

Collaborative approaches with local stakeholders and indigenous communities help ensure the sustainable use of natural resources and promote the well-being of people and the environment. Thus, most PAs in Mexico have an Advisory Council, which has become the primary body for the participation of local society and marks the difference in PA management. Through the Advisory Councils, government institutions, civil society, academic and research entities, and representatives of the people who inhabit, work, and use the ecosystems (e.g., ejidos, communities, indigenous groups, and women) can be aware, participate, advise, and support decision-making of the pertinent strategies to address the priority needs of the PAs.

Additionally, CONANP has two budgetary programs to support local conservation activities: (a) the S046 Conservation Program for Sustainable Development (PROCODES) and (b) the U040 Program for the Protection and Restoration of Ecosystems and Priority Species (PROREST). Both constitute a public policy instrument to promote PA's conservation, protection, and restoration and provide economic support to the local population and continuous dialogue with the different local stakeholders. In recent years, there has been a growing recognition of the importance of integrating gender perspectives into conservation and sustainable development efforts to ensure equitable access to resources, participation in decision-making processes, and addressing gender-based inequalities. In these subsidy programs, the beneficiaries of projects in which women participate may have access to up to 17% of the total amount CONANP provides to finance affirmative actions with a gender perspective. The beneficiaries will determine the work role for the affirmative actions, for which they may form commissions with a minimum of two people and a maximum of four to carry out the affirmative actions required by the women, or if necessary, they may rely on people from outside the group for their execution. The progress and goals report for the second quarter of 2022 establishes that the investment with a gender perspective amounts to $251,499.

Nevertheless, PAs face challenges, including decreasing funding. In 2021, CONANP's budget represented only 31% of the total needed to manage Mexico's PAs properly, making it difficult for CONANP to fulfill its mandate of protecting the natural capital. The 2023 results indicate the same pattern; the annual budget required from federally protected areas is US$160 million. Considering the yearly budget of US$70 million for 2023, there is an annual financial gap of US$90 million. However, the Mexican government has made commendable efforts to recognize biodiversity's importance by decreeing more PAs than any previous administration. The current government aims to designate 14% of the land surface and 25% of the marine area as protected by the end of its term (2024).

The MEx30x30 Project represents a significant advancement, leveraging the knowledge accumulated over 26 years of a successful collaboration between CONANP and FMCN. This initiative aims to amplify the impact of past successes by enhancing the management and efficiency of protected areas. A cornerstone of this endeavor is the incorporation of key learnings from the proven Public-Private Collaboration Scheme, known as FANP, established in 1997 with invaluable support from the Global Environment Facility (GEF). FANP has been instrumental in directing strategic financial resources to 70 PAs to strengthen the operational capacities of these PAs through a multifaceted approach.

The MEx30x30 Project will build upon this solid foundation to support six protected areas: two existing PA, three newly decreed PAs, and one complex of recently designated ADVCs (with eight certificates). These areas were selected by CONANP as focal areas for MEx30x30 for their biological importance, the presence of IP&LCs, and diversity of regions and thus ecosystems. See below for summary descriptions of each area (Figure 1 and 2). Through a comprehensive and integrated strategy, this initiative seeks to elevate the effectiveness of protected areas further, reinforcing their role as vital guardians of biodiversity and sustainable development engines for the benefit of nature and people.

Figure 1. Protected areas and voluntary conservation areas included in Mex30x30.

Figure 2. Indigenous groups in the protected areas and voluntary conservation areas included in Mex30x30.

Balam-Kú

Balam Kú is a 463,441.76 hectare Biosphere Reserve in the state of Campeche on the border with Guatemala. The word balam kú is composed of the Maya words: balam, 'jaguar'; and kú, 'temple'. It alludes to the three jaguars that are represented in the archaeological zone located within the BR. Balam Kú is a contiguous neighbor of the Selva Maya Biosphere Reserve decreed in 1990, which has almost half a million hectares. The Selva Maya, shared by Belize, Guatemala and Mexico, represents one of the most important ecological systems at a global level, because it is considered the largest continuous massif of humid and sub-humid tropical forest in Mesoamerica and the second largest tropical forest in America, after the Amazon Rainforest. Balam Kú is linked by bioclimatic corridors with Balam Kin and Calakmul Biosphere Reserve. Balam Kú is home to 889 people and two agrarian nuclei with indigenous households in Kilometer 120 and Hecelchakán. The vegetation in this area consists mainly of low deciduous and sub-deciduous forests, as well as wetlands. In the most arid zones, the vegetation can be xerophytic and be formed by thorny scrub and cacti. The conditions of the area allow the development of other types of vegetation characteristic of this zone such as the "bajos", which are generally low flooded areas that present distinctive plant associations. A number of species are endemic to the region, including 8 reptile species, 4 species of mammals, and 76 species of vascular plants. There are also a number of species that are priorities for conservation in Mexico, including the colorless juil (Rhamdia guatemalensis), the striped spiny iguana (Ctenosaura similis), the Yucatan spiny-tailed iguana (C. defensor), the swamp crocodile (Crocodylus moreletii), the masked duck (Nomonyx dominicus), sad pigeon (Patagioenas nigrirostris), blue-crowned parrot (Amazona farinosa) and dusky-headed parrot (Pyrilia haematotis). There are 19 species of amphibians, which represents 83% of the state's amphibian diversity, and the area contains 21% of the bat species distributed in Mexico. Main threats to the area include deforestation and illegal logging, forest fires, the introduction of invasive exotic species, and climate change. Irregular human settlements in the outer limits of Balam-Kú trigger other illegal activities such as land use changes for cattle ranching and agriculture, illegal logging, and poaching.

Bajos del Norte

Bajos del Norte is a national marine park in the Gulf of Mexico, covering 1,304,115 hectares. The reef areas of the northeastern end of the Yucatan Peninsula are transition zones between the Gulf of Mexico and the Caribbean Sea, therefore, this is considered a region of ecological connection and, therefore, of high biodiversity. The Bajos del Norte reefs are the second most relevant site as a larval source for areas in the northern, western and central Gulf of Mexico for several key fishery species for the region's economy. The area is characterized by its upwelling system and the so-called "loop current", both of which are responsible for the balance of nutrients in the Gulf of Mexico shelf and for the genetic connectivity and biological exchange of reef species, especially those of fishery value. It is one of the main grouper fish (Epinephelinae) reproduction sites in the Gulf of Mexico. Species richness represents 6 % and 25 % of the species recorded for the Gulf of Mexico and the Mexican Caribbean, respectively. Five species of sea turtles are present: loggerhead (Caretta caretta), white (Chelonia mydas), hawksbill (Eretmochelys imbricata), olive ridley (Lepidochelys kempii) and leatherback (Dermochelys coriacea), which are listed as Endangered, as well as being priority species for conservation in Mexico. The area also hosts the threatened rocky star coral (Orbicella annularis). The area is important to the 68,944 people (6% of whom are indigenous) that belong to fishing communities on the Yucatán coast. Two coastal fishing municipalities are relevant to Bajos del Norte: Progreso and Dzilam de Bravo. Main threats include pressure on fish stocks due to overfishing capture of the reproductive stock of larger and more fecund females in deep areas, and climate change.

Chimalapas

Los Chimalapas is a set of 8 Areas Voluntarily Destined for Conservation (ADVCs) in the State of Oaxaca, totaling 438,662.66 hectare. It is an ancestral indigenous territory of the Zoque people, and is home to 16,286 people, 38% of which are indigenous. The protection of biocultural resources in the Los Chimalapas Region is important for generating important biological corridors with other nearby Protected Areas, in addition to protecting the area from mining and fossil fuel extraction. Important species include Puma (Puma concolor), Ocelot (Leopardus pardalis), Tigrillo (Leopardus wiedii) and Jaguar (Panthera onca), quetzal, various species of parrots, macaws, and eagles, toucans (Rampasthus sulfurathos) and pajuil (Penelopina nigra), endemic plant species, endemic amphibians including Eleutherodactylus Lineatus macdougalli, Hyla sumichrasti, and Pseudoeurycea parva, and endemic reptiles such as Abronia bogerti, Abronia ornelasi, Adelphicos latifasciatus, Ctenosaura pectinata, Sceloporus internasalis, Anolis breedlovei, Anolis compressicaudua, Scincella gemmingeri, and Heloderma horridum. Main threats to the area include deforestation and land use change, forest fires caused by agricultural burning, and poaching. Additionally, there are historical land tenure disputes in the border strip with the state of Chiapas.

Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit

The 2,192,656.37 hectare Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit is a natural protected area. More than 50% of the area is covered by oak-pine and pine-oak forests, providing important hydrological environmental services. The forests are essential for water catchment and the recharge of aquifers for supplying population centers such as Puerto Vallarta and Bahía de Banderas. This watershed is also important for maintaining Marismas Nacional in Nayarit, which includes extensive mangrove areas. The water from this protected area makes agricultural and livestock farming possible and provides drinking and industrial water to 38 municipalities in Jalisco and Nayarit. Home to 52,498 people, nearly 50% of the population is indigenous, belonging to the Huicot or Gran Nayar region. Two of the four polygons that make up this protected area coincide with CONABIO's priority terrestrial regions, RTP-62 Sierra Vallejo-Río Ameca and RTP-60 Sierra Los Huicholes, as well as with the priority hydrological region: Río Baluarte - Marismas Nacionales. There are six areas of importance for bird conservation (AICAS): Quebradas de Sinaloa Nayarit and Durango, Guacamayita, La Michilia, Sierra de Valparaíso, El Carricito and Sierra Fría. The area hosts at least 15 endemic birds; around 80 species of mammals, of which more than 15 are endemic to Mexico and eight are protected by NOM 059; more than 60 species of reptiles and 16 species of amphibians, and of these, more than half are endemic to Mexico and at least ten are threatened. Main threats to the area include deforestation, land use change, forest fires, presence of forest pests and diseases (e.g., defoliator, bark stripper, and parasitic plants), expansion of unsustainable extensive cattle ranching activities, illegal extraction of flora and fauna, soil degradation, presence of invasive exotic species, and climate change.

Papigochic

Papigochic is a 222,763.85 ha protected area in the state of Chihuahua. The type of vegetation that characterizes Papigochic is mixed conifer and oak forests. It has some of the last relics of old-growth forests in the world. The area coincides with CONABIO's priority terrestrial regions, Alta Tarahumara-Barrancas and Bassaseachic, and the priority hydrological region, Río Yaqui - Bassaseachic Waterfall. In addition, there is an area of importance for bird conservation (AICAS): Papigochic. Although only 10% of its population of 6,907 people is indigenous, this protected area is the only one decreed on Rarámuri (Tarahumara) lands. The area is important for tourism and recreation and provides natural resources for the local population, mainly related to the use of timber forest species for the construction of houses, and fences, and for commercial purposes, as well as for fuel. Additionally, non-timber resources such as mushrooms and wild plants are used for food and medicine, and grasses, shoots and foliage are used for fodder. Main threats include deforestation, habitat modification or loss (reduction, fragmentation), natural phenomena (snowfall, north winds, hailstorms, cold fronts, rainfall, drought), forest fires, land cover conversion for the development of productive activities (forest exploitation, mining exploration and exploitation, agriculture, livestock), presence of forest pests, and population growth near forested lands.

Sierra Tecuani BR

The 348,140.97 hectare Sierra de Tecuani Biosphere Reserve, in the state of Guerrero, is a biological corridor for the jaguar in Mexico. The term tecuani is of Nahuatl origin and refers to the "man-eater", in allusion to the various species of felines identified in the area. The Sierra Madre del Sur is in the transition zone of the Nearctic and Neotropical regions, which favors the presence of a great diversity of species, including several microendemic vertebrates such as the tree frog (Charadrahyla tecuani), the Guerrero rattlesnake (Crotalus ericsmithi), the short-crested coquette (Lophornis brachylophus) and the tropical shrew of the Sierra Madre del Sur (Cryptotis goldmani), among others. It is considered a zone of high endemism that harbors viable populations of different species with some degree of threat. Twenty-five species of fungi, 338 plant species, 16 invertebrate species, and 120 vertebrate species are endemic. 28% of the species at risk in the entire Sierra Madre del Sur are present in Tecuani. The 18 ejidos and communities (population: 17,768) that are part of the protected area have diverse populations, including indigenous peoples. There is a high level of marginalization in some of the communities. Land-use change is one of the most significant threats to the area. The expansion of avocado plantations and cattle ranching exert considerable pressure on the forests, as they involve the clearing of large areas, from the lowlands to the mountain forests. Forest fires are another cause of the alteration of vegetation cover, in addition to timber extraction.

IV. INSTITUTIONAL ARRANGEMENTS

Conservation International (CI-GEF) is the GEF Implementing Agency for this project. Overall, the CI-GEF Implementing Agency will oversee technical and financial project oversight and supervision, ensuring the project complies with the GEF's policies and procedures, including M&E, Gender, stakeholder engagement, and safeguards. CI-GEF Agency will also make recommendations to optimize project performance and ensure the resolution of any execution conflicts.

The Executing Agency (EA) will be the Mexican Fund for the Conservation of Nature (FMCN). In total, FMCN has received more than US$70 million from GEF. The EA will guide and lead the day-to-day execution, administration, and monitoring of the project, be responsible for financial management, environmental and social safeguards and gender mainstreaming, and facilitate knowledge sharing and information flow within the project cycle.

The EA will recruit and host a team of specialists comprising the Project Management Unit (PMU) distributed among FMCN functional units. With guidance from the EA, the PMU will be responsible for overall project management, supervising consultants, monitoring and evaluation of progress of the agreed actions that address safeguard issues during project implementation, ensuring project success, and EA reporting to the CI-GEF Agency. The PMU Lead will directly coordinate with CI-GEF and report to the EA as needed. The composition of the Project Management Unit (PMU) is listed below, by position title and FMCN unit housing the position):

a.	Technical Lead (FMCN Conservation Unit)

b.	Administrative Analyst (FMCN Finance Unit)

c.	Institutional Strengthening Coordinator (FMCN Conservation Unit)

d.	Funding Mobilization Coordinator (FMCN Research and Development unit)

e.	Conservation Technical Analyst (FMCN Conservation Unit)

f.	Safeguards and Monitoring and Evaluation (M&E) Coordinator (FMCN Conservation Unit)

g.	Communications Specialist (FMCN Research and Development unit)

A Project Steering Committee (PSC) will be established, comprised of representatives from CONANP, FMCN, and CI GEF Agency. The PSC will meet (in-person or virtually) with additional ad hoc meetings, if necessary, to discuss key project performance indicators and to provide guidance on project direction. Specifically, the PSC will review and approve the Annual Work Plans and Budget as well as the M&E plan for the project.

Figure 3. Institutional arrangements.

V. INSTITUTIONAL CAPACITIES

Since 1998, FMCN has applied environmental and social standards to its projects. These have evolved alongside the policies and procedures of the World Bank, which has been the implementing agency for the four GEF-funded projects continuously coordinated by FMCN for 26 years. With the accreditation by GCF in 2019, FMCN integrated the World Bank Environmental and Social Standards published in 2018. They were incorporated into every project starting in 2019. In 2022, thanks to GCF Readiness support and with the accompaniment of KfW Development Bank, FMCN developed its Environmental and Social Policy and its Environmental and Social Management System (ESMS or SGAS, for its acronym in Spanish), which are being fully implemented in 2023.

The Environmental and Social Policy is part of its Operations Manual and establishes FMCN's commitment to sustainable development, human rights, gender equality, and addressing climate change. It also sets the guiding principles that govern FMCN's environmental and social risk management and promotes meaningful, inclusive, gender-sensitive, and culturally appropriate participation in the projects FMCN supports. As part of these guiding principles, the E&S Policy considers:

- compliance with applicable ES laws (including national laws and relevant international treaties and commitments)

- respect for human rights

- ES sustainability

- work and decent working conditions (respecting federal laws and ILO standards)

- biodiversity conservation

- respect for indigenous peoples (considering active and effective participation during the life cycle of the projects)

- protection of cultural heritage

- gender equality

- integration of activities to reduce the effects of climate change

- stakeholder engagement, and

- continuous improvement and best practices integration

The E&S Policy likewise details the constituent elements, including FMCN's applicable regulation, and environmental and social safeguards aligned with IFC's performance standards and other multilateral organizations. The E&S Policy also states the staff's roles and responsibilities. The Conservation and Sustainable Management Areas, which are in charge of the operation of the projects, are responsible for environmental and social management in the different stages of project implementation. The Research and Development Area is responsible for E&S functions at the institutional level. The Finance Area ensures that FMCN's investments comply with ESG standards. General Management (under the General Director) is accountable for fulfilling E&S responsibilities in each area. Internal Audit reviews the implementation of the processes and reports its findings to General Management and the Institutional Accompaniment Committee (CAI). Internal Audit Unit is also responsible for addressing complaints received formally through the Grievance Redress Mechanism established by the institution.

FMCN's ESMS identifies the environmental and social risks for projects, sub-projects, and annual operating plans of protected areas, as appropriate. FMCN channels field support through sub-projects and Annual Operating Plans. The sub-projects are grants that FMCN allocates to local organizations legally constituted in response to the demand of stakeholders and according to a selection process based on calls for proposals and the quality of the proposals received. The Annual Operating Plans are donations that FMCN channels to protected areas through local organizations to support five-year plans elaborated by the personnel of the National Commission of Protected Areas with the support of FMCN. FMCN ESMS has an Environmental and Social Safeguards Assessment Sheet through which projects are categorized according to their environmental and social risk, an "automatic" recommendation for each aspect considered, and the evaluator includes additional comments or suggestions. The ESMS also describes the procedures to manage E&S risks at the level of sub-projects (grants) and Annual Operating Plans for protected areas. The activities identified to mitigate risks in the project are included in the yearly project plans and monitored during implementation. During monitoring, additional risks to those identified in the evaluation phase may be identified and must be managed through the design of complementary mitigation measures. These are included in the annual plans at the project or sub-project level.

FMCN's E&S Policy and ESMS establish the objectives, guiding principles, and scope of meaningful stakeholder engagement. It states that FMCN seeks to ensure the meaningful, effective, and informed participation of key stakeholders at different territorial scales in the preparation and operation of projects. The involvement of these stakeholders is a regular and constant process throughout the life cycle of the initiatives, which must be carried out in an inclusive, gender-sensitive, and culturally appropriate manner, without discrimination and always ensuring that opportunities for participation are open to vulnerable groups (e.g., women, youth, senior citizens, indigenous peoples, Afro-Mexican population, and people with disabilities, among others). One of FMCN's guiding principles is respect for indigenous peoples, including avoiding adverse impacts by the supported projects, promoting benefits and opportunities, respecting and preserving their culture, and engaging indigenous peoples through active and effective participation through the lifecycle of the projects. FMCN E&S safeguard on Indigenous peoples (SAS7) establishes that FMCN and the implementing organizations will identify, through a social and environmental risk and impact assessment process (Environmental and Social Safeguards Assessment Sheet), all potentially affected Indigenous Peoples' communities within the area of influence of a project, subproject, or Annual Operating Plan, as well as the nature and severity of the expected direct and indirect economic, social, cultural, and environmental impacts on these peoples. The proposed mitigation actions are developed in consultation and with the informed participation of the affected Indigenous Peoples communities. These actions are part of the sub-projects to be financed planning.

FMCN also has a Gender Policy, which is part of its Organizational Manual, to incorporate the gender perspective in a cross-cutting manner in the operation of FMCN and all its initiatives. This policy promotes women's empowerment and fosters equality between men and women in natural resource conservation, management, and restoration in a culturally appropriate way. Additionally, FMCN has a Policy on Protection against Sexual Exploitation, Abuse, and Harassment, which declares zero tolerance for these practices and places human dignity and women's right to a life free of violence at the center of FMCN's work. Both policies apply to the Assembly, the Board of Directors, the Committees, FMCN contracted staff, entities staff with contractual relationships with FMCN, project beneficiaries, suppliers, and consultants.

To date, FMCN's staff dedicated to safeguards, gender, and stakeholder engagement include the following positions:

Part-time

• General Coordinator

• Director of Research and Institutional Development

• Director of the Sustainable Management Area

• Internal Audit

Full-time

• Socio-Environmental Research Coordinator

• Socio-Environmental Research Officer

• Gender and Social Vulnerability Officer (Climate Change and Sustainable Production Projects)

• Environmental and Social Management Officer

• Environmental and Social Officer

The above staff are environmental, social, and gender specialists and have received training in safeguards, gender, and stakeholder engagement, such as Grievance Redress Mechanism Online Course (GCF); Community Mediation Training (GCF); Meaningful Stakeholder Engagement - 13th Edition (IDB); Environmental and Social Framework - ESF Fundamentals (WB); E-learning Master Class on EIB Environmental & Social Sustainability Management (Frankfurt School Development Finance); Gender Mainstreaming (GGGI); Induction to gender equality (INMUJERES), among others.

VI. ENVIRONMENTAL AND SOCIAL SAFEGUARDS

FMCN Environmental and social safeguards (ESS) constitute standards for identifying and assessing potential environmental and social risks  and impacts  associated with the projects that FMCN designs and/or finances to help prevent, reduce, and mitigate them, including the obligation to ensure the participation of stakeholders and to disclose the activities that make up such projects.

The particular objectives of the ESS are:

- Enhance the positive environmental and social effects of projects.

- According to the mitigation hierarchy, avoid negative impacts on the environment and people.

- Focus on the environmental and social risk management capabilities of FMCN personnel and their local partners.

- Promote the meaningful, free, full, informed, timely, and effective participation of stakeholders in the territories where the projects are carried out, including populations in vulnerable situations.

FMCN has the following ten Environmental and Social Safeguards:

- Assessment and management of environmental and social risks and impacts

- Labor and working conditions.

- Efficiency in the use of resources and pollution control and prevention

- Community health and safety

- Involuntary resettlement

- Conservation of biodiversity and sustainable management of natural resources

- Indigenous peoples

- Cultural heritage

- Gender

- Climate change

These ESS are aligned with the country's legal and regulatory framework, as well as with the Environmental and Social Safeguards of the Green Climate Fund (GCF); with the Performance Standards of the International Finance Corporation (IFC) and its Guidance Notes ; with the Environmental and Social Standards of the World Bank (WB) and its Environmental, Health, and Safety Guides , and with the Environmental and Social Performance Standards of the Inter-American Development Bank (IDB). For the purpose of this Project, FMCN will also align with the CI-GEF Environmental and Social Management Framework (ESMF), including ESS9 on financial intermediaries, that is not part of FMCN’s ESS but will apply to this Project.

VII. SUMMARY OF ESMF EXCLUSIONS

FMCN E&S Policy states its exclusion list, establishing that the following activities will not be supported or financed:

- Manufacture, purchase, or trade of any product or activity considered illegal according to Mexican laws or regulations and international conventions and agreements ratified by the country.

- Manufacture, purchase, or trade-in ozone-depleting substances, polychlorinated biphenyl (PCB) compounds, hazardous chemicals, fertilizers, herbicides, pesticides, persistent organic pollutants (POPs) listed in the Stockholm Convention, substances classified by the World Health Organization as extremely hazardous and very hazardous, unbound asbestos fibers, and wildlife and wildlife products regulated by the Convention on International Trade in Endangered Species of Wild Fauna and Flora.

- Manufacture, purchase, or trade-in arms, ammunition, explosives, or other military goods or technologies.

- Manufacture, purchase, or trade of narcotics and tobacco.

- Land acquisition.

- Activities within protected areas (PAs) that are not included in their management programs and, for those PAs that do not have a management program, all activities considered within this exclusion list.

- Activities that promote the change of land use, deforestation, or degradation in critical habitats or that put ecosystem services at risk.

- Infrastructure that may promote conversion, deforestation, degradation, or any other alteration of critical habitats.

- Mining and oil or gas exploration and development projects.

- The use of Genetically Modified Organisms (GMOs) and invasive alien species without technical studies and corresponding authorizations.

- The use of living organisms generated by artificial cloning.

- Manufacture or trade in timber or other forest products that do not come from sustainably managed forests.

- Marine fishing activities with nets over 2.5 km in length and activities that contravene the provisions on priority marine species subject to protection and conservation following the current National Fisheries Charter.

- Activities that may violate human rights.

- Activities involving forced labor and/or harmful child labor.

- Activities that generate involuntary resettlement, especially of indigenous or Afro-Mexican groups.

- Activities that affect the rights of indigenous peoples or local communities, especially land ownership, without the proper Free, Prior, and Informed Consultation (FPIC) process.

- Activities affecting cultural heritage.

- Activities that affect people's assets or generate restrictions on access to natural resources.

- Activities carried out on land under litigation, dispute, or on ejido and/or communal lands that do not have the written approval of the assembly.

- Activities affecting international waters or shared waters.

- The use of resources to support proselytizing or electoral campaigns, as well as betting, gambling, casinos, and equivalent companies.

For the purpose of this Project, FMCN will also adhere to CI-GEF ESMF exclusion list.

VIII. ENVIRONMENTAL AND SOCIAL MANAGEMENT PLAN

It is not expected that the project could bring environmental and/or social impacts. There may be some unintended outcomes from project activities that do not fully account for the environmental and socioeconomic contexts involved with protected natural area and ADVC management and restoration, notably when IP&LCs and other vulnerable communities are involved. Effective planning and management of protected natural areas and restoration of degraded areas includes outreach, engagement and collaboration with local communities, many of which are heavily dependent on natural resources and often rely on complex and/or unresolved land tenure arrangements. This is particularly true with IP&LCs, notably ones with ancestral territorial claims.

| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcomes | Outputs | Activities | Potential Positive/negative impacts and risks | Mitigation measures | Responsible | Schedule | Budget |
| Outcome 1.1. CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. | Output 1.1.1. New revenue streams to increase CONANP's budget are identified. Output 1.1.2. New revenue streams to increase CONANP's budget are accessed. Output 1.1.3. The institutional capacity of CONANP is enhanced through expanding the Protected Areas Learning Community (community of practice). | Increase and strengthen CONANP’s institutional capacities regarding: - Environmental and Social Safeguards - Gender mainstreaming and GBV - Youth and indigenous groups’ inclusion - Advisory Councils - Natural disaster prevention and response, including fires, droughts, and hurricanes - Measuring PAs effectiveness - Adapting the i-effectivity model to ADVCs and support for implementation Expand the Protected Areas Learning Community (community of practice). | Positive - Increased funding can lead to better conservation efforts, habitat restoration, wildlife protection, ecosystem monitoring, and research, contributing to preserving biodiversity and improving overall ecosystem health. - Increased budget can facilitate communities’ involvement, ensuring their engagement in conservation efforts and benefiting from sustainable practices. - Improved capacity allows for better management of productive activities within protected areas (e.g., tourism), minimizing negative impacts and promoting sustainable practices and economic opportunities for local communities. | - Develop a training plan to enhance the capacities, skills, and knowledge of CONANP staff on ESS, gender mainstreaming, and other relevant subjects. - Collaborate with experts to provide specialized training in environmental and social safeguards, gender mainstreaming, and vulnerable groups’ inclusion. - Reinforce Advisory Councils to foster communities‘ meaningful engagement in conservation goals, management strategies, and their role in decision-making processes. | PMU Project Lead Safeguards and Monitoring and Evaluation Coordinator CONANP | Year 1-3 | USD$15,000 |
|  |  |  | Negative - CONANP’s increased capacity may not necessarily translate into inclusive decision-making processes, leaving communities marginalized. - Lack of community involvement may lead to conflicts between conservation initiatives and local communities. |  |  |  |  |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |  |  |  |  |
| Outcome 2.1. Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years. | Output 2.1.1. Funding pledged to address identified financial gaps Output 2.1.2. Long-term sustainable finance mechanism/PFP2 is designed | Develop and execute the strategic outreach plan to secure donor commitments to the long-term sustainable financing mechanism based on the PFP approach. | Positive - Adequate funding can enhance conservation efforts, protecting biodiversity and ecosystem services. - Donor support can facilitate community involvement in Advisory Councils for decision-making processes related to protected area management. - Increased funding may create job opportunities for local communities in conservation and sustainable-related activities. | - Operationalize the Stakeholder Engagement Plan to ensure meaningful participation from different stakeholders. - Operationalize the Project Grievance Redress Mechanism to address complaints promptly and fairly. | PMU Project Lead Safeguards and Monitoring and Evaluation Coordinator | Year 1-5 | USD$5,000 |
|  |  |  | Negative - Women and indigenous peoples may face exclusion from project activities and benefits, leading to social inequities. |  |  |  |  |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore, and sustainably manage territories. |  |  |  |  |  |  |  |
| Outcome 3.1. PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. * | Output 3.1.1. Five-year plans, and associated Annual Operating Plans (POAs), developed for PAs and ADVCs through an inclusive participatory process coordinated by CONANP. Output 3.1.2. Gender-responsive and inclusive training provided to local communities in PAs and ADVCs to enhance their skills and knowledge in sustainable land management, conservation and restoration practices. Output 3.1.3. IP&LCs and local organizations implement gender-responsive and inclusive conservation, restoration and sustainable management actions defined in POAs. Output 3.1.4. Emergency fund expanded to support emergency-response brigades. | Develop Annual Operating Plans for each PA through the Advisory Councils and the engagement of stakeholders to finance sustainable development practices adoption and restoration activities, where appropriate, that can be implemented to improve biodiversity and key ecosystem services. IP&LCs’ capacity building and increase knowledge in sustainable land use practices and, where appropriate, restoration activities, tailored to each context, based on local needs and opportunity assessments conducted with the Advisory Council. POAs will finance activities such as forest cover restoration; community reforestation / restoration of riverbanks; soil conservation and restoration practices (living fences, stubble, cover crops, productive diversification); acquiring equipment for fire prevention, control, and management; community capacity-building for sustainable use of plants of interest (seed banks, nurseries, cover crops, productive diversification); developing sustainable and diversified practices including agroforestry and agrosilvopastoral systems; establishing community-led brigades and engaging local communities in monitoring programs. Expand FANP’s Emergency Fund to cover the five supported PAs and ADVC complex, including fires, floods, and other emergencies | Positive - POAs enhance conservation efforts, habitat restoration, wildlife protection, and ecosystem monitoring, contributing to preserving biodiversity and improving overall ecosystem health. - Communities’ stewardship may lead to sustainable resource management practices, contributing to biodiversity conservation within protected areas (e.g., better fire management and emergency response). - Communities may have sustainable resource management practices, leading to long-term environmental benefits. - Recognizing and respecting communities’ culture and knowledge contributes to the preservation of traditional knowledge and practices. - Implementing gender-equitable actions can enhance social cohesion and contribute to more sustainable development. | - Ensure POA activities improve biodiversity and key ecosystem services and align with local communities’ interests and needs to ensure relevance and effectiveness through the Advisory Councils. - Facilitate culturally appropriate capacity-building workshops and training sessions for community members to enhance their knowledge of sustainable practices and effective conservation strategies. Consider various learning styles and provide materials in local languages to ensure broader community participation and appropriation. - Support training and equipment for community brigades, such as first aid, fire management, and emergency response. - Use only native species in restoration efforts. Species selection will be based on site-specific matching and climate resilience, ensuring that promoted species have suitable characteristics given the environmental and bio-geophysical conditions. - Provide training and technical support for invasive species identification and report. - Support community-based monitoring activities (e.g., biodiversity) for adaptive management and improve outcomes of conservation, restoration, or best management practices. - Strengthen outreach mechanisms (e.g., Advisory Councils) to ensure the inclusion of marginalized groups in project activities, opportunities, and benefits. - Foster meaningful participation of women, indigenous peoples and another stakeholders and ensure equal access to opportunities and resources through the Gender Mainstreaming Plan, the Indigenous Peoples Plan, and the Stakeholder Engagement Plan. - Operationalize the Community Health, Safety, and Security Plan. - Operationalize the Project Grievance Redress Mechanism to address complaints promptly and fairly. - Fulfill periodic assessments for all the POAs, including progress reports and follow-up field visits. | PMU Project Lead Safeguards and Monitoring and Evaluation Coordinator CONANP | Throughout the Project’s lifetime | USD$90,000 |
|  |  |  | Negative - POAs may not consider local communities’ needs or interests. - Training is not accessible or does not meet the needs or interests of communities. - Community brigades need to be adequately trained and equipped. - Inappropriate restoration practices may disrupt local ecosystems. - Unintentional introduction of invasive species during restoration activities. - Women and indigenous peoples may face exclusion from project activities and benefits, leading to social inequities. |  |  |  |  |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |  |  |  |  |
| Outcome 4.1: MEx30x30 and related programs and initiatives in Mexico and elsewhere benefit from gender-responsive and inclusive learning and knowledge exchange to inform future scale-up. | Output 4.1.1: Ongoing lessons learned from MEx30x30 and other long-term sustainable finance mechanisms and PA scaling experiences documented and disseminated. Output 4.1.2: National workshop and dissemination event held to finalize scale-up strategy document based on MEx30x30 experience. | Document lessons learned, prepare knowledge products, and disseminate materials. Organize a national event to formally launch the scale-up strategy to achieve Mexico’s 30x30 goal, based on the Project’s learning and experience. | Positive - Views of communities are used to improve the Project. Communities contribute to and benefit from the national workshop and knowledge products. | - Establish a strategy for capturing and documenting lessons learned, success stories, and practical tips throughout the project lifecycle. - Tailor knowledge products to different target audiences. - Implement inclusive outreach strategies and ensure diverse representation in the national workshop. | PMU Project Lead Safeguards and Monitoring and Evaluation Coordinator | Throughout the Project’s lifetime | USD$20,000 |
|  |  |  | Negative - Views of communities are excluded. - Communities do not access nor benefit from the national workshop. Communities do not engage with knowledge products. |  |  |  |  |
| Outcome 4.2: Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | Output 4.2.1: Clear and robust gender-responsive and inclusive Monitoring and Evaluation framework created and implemented. Output 4.2.2: Project Implementation Reports, Mid-term Review, and Terminal Evaluation completed. | Establish a M&E system for project delivery and oversight. Generate the material to inform knowledge-sharing among stakeholders and with other GEF-funded projects. Timely preparation and submission of PIRs. | Positive - Monitoring framework incorporates information relevant to communities and for environmental conservation. | - Ensure compliance with relevant environmental and social regulations and standards. - Establish a continuous feedback loop to review the effectiveness of the M&E framework. - Present periodic reports on how ESMP, GMP, SEP, and GRM are being addressed and respected during the implementation of the Project. - Communicate Project findings, progress, and challenges to inform stakeholders of the Project results in culturally appropriate ways. | PMU Project Lead Safeguards and Monitoring and Evaluation Coordinator | Throughout the Project’s lifetime | USD$10,000 |
|  |  |  | Negative - Communities are not considered in the monitoring framework. - Inaccurate monitoring and reporting can lead to misguided environmental decisions. |  |  |  |  |
|  |  |  | Negative - Views of communities are excluded. - Communities do not access nor benefit from the national workshop. - Communities do not engage with knowledge products. |  |  |  |  |

IX. ENVIRONMENTAL AND SOCIAL PLANS

The Stakeholder Engagement Plan (SEP) is a roadmap for involving various stakeholders along the Project activities. Through stakeholder mapping, the SEP details their interests, impacts on the project, influence, and associated risks. The plan outlines stakeholders' engagement during the design phase, including dates, locations, methods, objectives, and outcomes. Emphasizing ongoing communication, the SEP also addresses disclosure, reporting of indicators, and lessons learned during the design phase. The monitoring and evaluation section outlines reporting frequency, responsible parties, and disclosure details, ensuring continuous improvement and responsiveness.

The Gender Mainstreaming Plan (GMP) and the Indigenous Peoples Plan (IPP) are a comprehensive strategy designed to integrate an indigenous peoples and gender-responsive approach throughout the project. The primary goal of the IPP and the GMP is to ensure that both women and men as well as vulnerable groups experience culturally compatible economic and social benefits, free from discriminatory effects during development and implementation, while upholding their dignity and human rights. Beyond mere inclusion, it fosters sustainable equality of responsibilities, opportunities, and benefits, recognizing women and indigenous peoples' pivotal role in natural resource utilization and family health. The project's IPP and GMP addresses root causes of inequalities, encompassing limited access to and control over natural resources, inadequate employment opportunities, and capacity building opportunities. Systematic collection of Indigenous and gender-disaggregated information will be collected to monitor and track participation and engagement, fostering accountability and transparency.

The Grievance Redress Mechanisms (GRM) addresses complaints and grievances related to the project's adherence to safeguard procedures. It provides transparent procedures for raising concerns, ensuring dialogue, and maintaining public support. The GRM details eligible and ineligible grievances, mechanisms for transparency and fairness, confidentiality, accessibility, timelines for resolution, documentation, monitoring, and reporting. The involvement of FMCN in the grievance process ensures formal tracking, investigation, and monitoring. The GRM also outlines the responsible persons, budget requirements, and resources for implementation and monitoring, reinforcing the commitment to transparency and accountability throughout the project's lifespan.

X. MONITORING AND REPORTING

The compliance of Project activities with the ESMP and other management interventions will be continually monitored throughout the Project lifespan. The  Safeguards and Monitoring and Evaluation Coordinator will ensure specific ESS monitoring and assessing the effectiveness of environmental and social safeguard risk management activities. Based on monitored and unforeseen risks, the monitoring plan will be periodically reviewed and updated in conjunction with the ESMP. Further identification of risks during the monitoring process will reduce the project's overall environmental and social impact as these risks are promptly identified and addressed accordingly. Monitoring will also be complemented by information gathered during ongoing engagement with communities and other stakeholders through the Stakeholder Engagement Plan, the Gender Mainstreaming Plan, the Grievance Redress Mechanism, therefore, contributing to the dynamism, adaptability, and, ultimately, the effectiveness of the project.

|  | Audience | Objectives | Indicators | Baseline | Target | Frequency | Data Gathering |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |  |  |  |  |  |  |  |
| Outcome 1.1. CONANP’s budget and capacity to effectively manage PAs and ADVCs has increased. | CONANP staff and relevant stakeholders | - Increase CONANP’s capacity to effectively manage PAs and ADVCs, ensuring effective implementation of environmental and social safeguards and promoting gender mainstreaming, youth, and indigenous groups inclusion. | - i-effectivity index | - i-effectivity baseline | - Improvement in i-effectivity index compared to baseline | Annually | - Training and knowledge exchange activities reports - Meeting minutes - Progress reports - ESS reports |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |  |  |  |  |
| Outcome 2.1. Donor support is secured to cover the financing gap for effective management of existing PAs over the next 15 years. | Potential donors and relevant stakeholders | - Secure long-term sustainable financing commitments. | - Funding commitments secured | - % of total funding needed | - % of funding secured | Annually | - Tracking donations and pledges |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore, and sustainably manage territories. |  |  |  |  |  |  |  |
| Outcome 3.1. PAs and ADVCs are effectively managed and directly generating inclusive, gender-equitable benefits for IP&LCs. * | CONANP, Advisory Councils, OLLCs, IP&LCs, and other stakeholders | - Support conservation, restoration, and sustainable development practices. - Biodiversity and ecosystem service improvements. | - POAs with activities satisfactorily fulfilled. progress - People trained in sustainable practices funded by the Project (disaggregated by gender and IPs) - Hectares protected or restored by the Project | - 0% of POAs with activities satisfactorily fulfilled - 0 peoples trained - 0 hectares protected or restored | - 100% of POAs with activities satisfactorily fulfilled - 400 people trained - X hectares protected or restored | Every six months | - POAs monitoring progress reports - ESS reports - Advisory Councils meeting minutes - Supervision visits |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |  |  |  |  |
| Outcome 4.2: Robust gender-responsive and inclusive Monitoring and Evaluation framework applied to the MEx30x30 project to assess the effectiveness of interventions and guide adaptive management. | Project management team, CONANP, and stakeholders | - Ensure effective project delivery and oversight. - Compliance with project objectives. - Scale-up strategy documents based on MEx30x30 experience. - Operation and compliance with ESMP, GMP, SEP, IPP, CHSSP. | - Lessons-learned knowledge products prepared and shared (including product with a focus on gender and inclusion). - Reports submitted to CI GEF Agency on time and determined to be satisfactory. - Operation and compliance with ESMP, GMP, SEP, IPP, CHSSP. | - 0 knowledge products prepared and shared - 0% reports submitted to CI GEF Agency on time and determined to be satisfactory. - 0% of ESMP, GMP, SEP, IPP, CHSSP measures implemented. | - X knowledge products prepared and shared - 100% reports submitted to CI GEF Agency on time and determined to be satisfactory. - 100% of ESMP, GMP, SEP, IPP, CHSSP measures implemented. | Annually | - Regular progress reports - ESS reports - Supervision visits |

| Person responsible for implementing and monitoring the ESMP | Safeguards and Monitoring and Evaluation Coordinator |
| --- | --- |
| Budget Summary: | Included in POA and Learning Community |

# ANNEX G: Budget Table

Please upload and paste below the budget table here*

Budget is included as a separate attachment.

Please explain any aspects of the budget as needed here.

# ANNEX H: Blended-finance relevant annexes

Annex H1 : Termsheet, following the template provided for the GEF-8 blended finance program of the GEF Trust Fund.

Annex H2 : GEF Agency Eligibility to Administer Concessional Finance, following the template provided for the GEF-8 blended finance program of the GEF Trust Fund.

Other documents to be uploaded to the GEF project portal:

- Gender Action Plan

- Gender Analysis undertaken during project preparation

- Stakeholder Engagement Plan (including or separate please include a list of people consulted during project preparation including dates and locations of consultations)

- TORs for key project staff funded by GEF grant and/or co-finance

# ANNEX I:  MONITORING AND EVALUATION PLAN

Project monitoring and evaluation will be conducted in accordance with established Conservation International and GEF procedures by the project team and the CI-GEF Project Agency. The project's M&E plan will be presented and finalized at the project inception workshop, including a review of indicators, means of verification, and the full definition of project staff M&E responsibilities.

## Section A. Monitoring and Evaluation Roles and Responsibilities

The Project Management Unit on the ground will be responsible for initiating and organizing key monitoring and evaluation tasks. This includes the project inception workshop and report, progress reporting, quarterly, semi-annual, and annual progress and implementation reporting, documentation of lessons learned and knowledge management, and support for and cooperation with the independent external evaluation exercises.

FMCN is responsible for ensuring the monitoring and evaluation activities are carried out in a timely and comprehensive manner, and for initiating key monitoring and evaluation activities, such as the independent evaluation exercises.

Regional Funds and other partners are responsible for providing any and all required information and data necessary for timely and comprehensive project reporting, including results and financial data, as necessary and appropriate.

The CTFANP plays a key oversight role for the project, with meetings according to its rules to receive updates on project implementation progress and approve annual workplans. CTFANP also provides continuous ad-hoc oversight and feedback on project activities, responding to inquiries or requests.

The CI-GEF Project Agency plays an overall assurance, backstopping, and oversight role with respect to monitoring and evaluation activities.

The CI Internal Audit function is responsible for contracting and oversight of the planned independent external evaluation exercises at the midterm and end of the project.

## Section B. Monitoring and Evaluation Components and Activities

The Project M&E Plan should include the following components (see M&E table 3 for details):

  - Project Results Monitoring Datasheets (Objective, Outcomes, and Outputs). A Project Monitoring Data Sheet will be developed by FMCN, which will include objective, outcome and output indicators, metrics to be collected for each indicator, methodology for data collection and analysis, baseline information, location of data gathering, frequency of data collection, responsible parties, and indicative resources needed to complete the plan. Annex I provides the Project Results Monitoring Plan table that will help complete this M&E component.

During implementation, FMCN will be responsible for the overall project monitoring. Progress will be measured against the Results Framework (RF). Technical reports will be prepared under the oversight of the CTFANP, presented to CI-GEF every six months. CI-GEF, in coordination with FMCN, will commission an independent mid-term and a final evaluation, including quantitative assessment of outcomes and analysis of achievements and difficulties encountered, compliance with environmental and social standards, and lessons learned. The final review will focus on the achievement of indicators, sustainability of results, and final lessons learned and recommendations.

In addition to the objective, outcome, and output indicators, the Project Results Monitoring Plan table will also include all indicators identified in the Safeguard Plans prepared for the project, thus they will be consistently and timely monitored.

Monitoring these indicators throughout the life of the project will be necessary to assess if the project has successfully achieved its expected results. The FMCN has developed strong monitoring and evaluation systems and capacity; the results information on Component 1, 2 and 3 will rely on the FMCN Information System for Project Follow-up (Sistema de Seguimiento a Proyectos, SISEP) developed for the GEF-funded Consolidation of the Protected Area System (SINAP II) project and improved under the GEF-funded C6 project, both implemented by the FMCN through the World Bank. The Regional Funds will help to collect and analyze said information in collaboration with the PMU.

Baseline Establishment: in the case that all necessary baseline data has not been collected during the PPG phase, it will be collected and documented by the relevant project partners within six months of project implementation.

  - GEF Core Indicator Worksheet
The relevant section of the GEF Core Indicator Worksheet was updated for the CEO endorsement submission. This worksheet will also be updated (i) annually, (ii) prior to mid-term review, and (iii) prior to the terminal evaluation.

  - CTFANP Meetings
CTFANP meetings will be held semi-annually or when required. Meetings shall be held to review and approve project annual budget and work plans, discuss implementation issues and identify solutions, and to increase coordination and communication between key project partners. The meetings held by FMCN will be monitored and results adequately reported.

  - CI-GEF Project Agency Field Supervision Missions
The CI-GEF PA will conduct annual visits to the project country and potentially to project field sites based on the agreed schedule in the project's inception Report/Annual Work Plan to assess firsthand project progress. Oversight visits will be after the submission of reports. A Field Visit Report will be prepared by FMCN and CI-GEF staff participating in the oversight mission and will be circulated to the project team and CTFANP members at the end of the visit.

  - Quarterly Progress Reports
FMCN will submit progress reports every three months to the CI-GEF Project Agency, including a budget follow-up and requests for disbursement to cover expected expenditures.  A summary of the reports will be shared with CTFANP.

  - Annual Progress Report
Each year the project will share an annual project implementation report (PIR) in compliance with GEF guidelines. This report will be shared with the CTFANP.

  - Final Project Report
FMCN will draft a final report at the end of the project, with inputs from the External Terminal Evaluation.

  - Independent External Mid-term Review
The project will undergo an independent Mid-term Review within 3 months of the mid-point of the grant term. The Mid-term Review will determine progress being made toward the achievement of outcomes and will identify course correction if needed. The Mid-term Review will highlight issues requiring decisions and actions, and will present initial lessons learned about project design, implementation, and management, in accordance with the FMCN Operational Manual. As part of the adaptive management and the CI-GEF Evaluation Policy, findings and recommendations of the Mid-term Review will be incorporated to secure maximum project results and sustainability during the second half of project implementation.

  - Independent External Terminal Evaluation
An independent Terminal Evaluation will take place within six months after project activities completion and will be undertaken in accordance with CI-GEF and GEF guidance, as well as the FMCN Operational Manual. The terminal evaluation will focus on the delivery of the project’s results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place). The FMCN in collaboration with the CTFANP will provide a formal management answer to the findings and recommendations of the terminal evaluation using the CI-GEF agency response matrix.

  - Financial Statements Audit
Annual Financial reports submitted by the executing Agency will be audited annually by external auditors appointed by the Executing Agency.

Section C. M&E Plan and PMC Cost Summary

Table 2. M&E Plan Summary

| Type of M&E | Reporting Frequency | Responsible Parties | Indicative Budget from GEF ($) |
| --- | --- | --- | --- |
| a. Inception workshop and Report, Closing Workshop | Within three months of signing of CI Grant Agreement for GEF Projects. Within three months prior to the end of the Grant Agreement. | · Project Team | 23,637 |
|  |  | · Executing Agency |  |
|  |  | · CI-GEF PA |  |
| b. Inception workshop Report | Within one month of inception workshop | · Project Team | 4,500 |
|  |  | · CI-GEF PA |  |
| c. Project Results Monitoring Plan (Objective, Outcomes and Outputs) | Annually (data on indicators will be gathered according to monitoring plan schedule shown on Appendix IV) | · Project Team | 10,000 |
|  |  | · CI-GEF PA |  |
| d. GEF Indicator Tracker | i) i) Annually; ii) Project development phase; iii) prior to project mid-term evaluation; and iii) project completion | · Project Team | 8,500 |
|  |  | · Executing Agency |  |
|  |  | · CI-GEF PA |  |
| e. CI-GEF Project Agency Field Supervision Missions | Approximately annual visits, after project submission One visit for Midterm Review Validation | · CI-GEF PA | 39,274 |
| f. Annual Project Implementation Report (PIR) | Annually | · Project Team | 36,500 |
|  |  | · Executing Agency |  |
|  |  | · CI-GEF PA |  |
| g. Project Completion Report | Upon project operational closure | · Project Team | 6,391 |
|  |  | · Executing Agency |  |
| h. Independent External Mid-term Review | Approximate mid-point of project implementation period | · CI Evaluation Office | 60,000 |
|  |  | · Project Team |  |
|  |  | · CI-GEF PA |  |
| i. Independent external Terminal Evaluation | Evaluation field mission within three months prior to project completion. | · CI Evaluation Office | 60,000 |
|  |  | · Project Team |  |
|  |  | · CI-GEF PA |  |
| Summary M&E total |  |  | 248,802 |

Table 3. Project Management Costs (PMC) Summary

| Type of PMC | Reporting Frequency | Responsible Parties | Indicative Budget from GEF (USD) |
| --- | --- | --- | --- |
| a. Project Steering Committee Meetings | Annually | · Project Team | 326,000 |
|  |  | · Executing Agency |  |
|  |  | · CI-GEF PA |  |
| b. Quarterly Progress Reporting | Quarterly | · Project Team | 390,568 |
|  |  | · Executing Agency |  |
|  |  | · Executing Agency |  |
|  |  | · CI-GEF PA |  |
| c. Financial Statements Audit | Annually | · Executing Agency | 77,359 |
|  |  | · CI-GEF PA |  |
| Summary PMC total |  |  | 793,927 |

# Section D. Project Results Monitoring Plan

| Indicators | Metrics | Methodology | Baseline | Location | Frequency | Responsible Parties | Indicative Resources |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: o help Mexico advance toward the Global Biodiversity Framework 30x30 target through long-term sustainable financing for the existing national protected areas. |  |  |  |  |  |  |  |
| Indicator a: Terrestrial protected areas under improved management effectiveness | Hectares | Project Tracking System (SISEP) and i-efectividad data analysis of land under improved management | 0 | Mexico City | Annually and at MTR and TE | PMU- Data from CONANP | $5,000 |
| Indicator b: Marine protected areas under improved management effectiveness | Hectares | Project Tracking System (SISEP) and i-efectividad data analysis of land under improved management | 0 | Mexico City | Annually and at MTR and TE | PMU- Data from CONANP | $5,000 |
| Indicator c: Greenhouse gas emissions mitigated | MtCO2e | Ex-Act tool applied to GIS mapping of land under restoration and landscapes under improved management | 0 | Mexico City | MTR and TE | PMU | $10,000 |
| Indicator d: Number of people experiencing socioeconomic benefits (male/female) | People (disaggregated by gender) | Official data from people living in the areas and project Tracking System (SISEP) track participants in/beneficiaries of sustainable management activities | 0 | Mexico City | Annually and at MTR and TE | PMU | $1,000 |
| Component 1: Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively |  |  |  |  |  |  |  |
| Indicator 1.1: % decrease (after third year of project implementation) in annual CONANP budget shortfall as a result of new revenue streams. | % (reduced budget shortfall as % of baseline) | Budget analysis | 0% | Mexico City | Annually | PMU- Data from CONANP | $0 |
| Indicator 1.1.1: # of feasibility reports and action plans for accessing new revenue streams completed. | Document packages | Document check | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 1.1.2: # of new revenue streams accessed and contributing to CONANP budget. | # of new funding sources | Document check | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 1.1.3a: % improvement in CONANP institutional capacity assessment score. | % (points improvement as a % of baseline) | Application of tailored capacity assessment scorecard to be developed | 0 | Mexico City | Annual | PMU- Data from CONANP | $1,000 |
| Component 2: Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |  |  |  |  |  |  |  |
| Indicator 2.1: Percentage of required funding for a Transition Fund to cover PA financing gaps for 15 years. | % (funding secured as a % of total need) | Document check (budget analysis and financial records) | 0 | Mexico City | Annual | PMU | $5,000 |
| Indicator 2.1.1: Amount of donor funding for phase one pledged to address financing gap during transition period. | US$ | Document check (notification of pledges) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 2.1.2: Number of long-term sustainable finance mechanism designed and ready for closing. | # of mechanisms | Document check (complete design packages) | 0 | Mexico City | Annual | PMU | $0 |
| Component 3: Strengthening recently established PAs, and ADVCs managed by IP&LCs, to conserve, restore and sustainably manage territories. |  |  |  |  |  |  |  |
| Indicator 3.1a: % improvement in PA management effectiveness score, as measured by i-effectiveness evaluation. | % (points improvement as % of baseline) | Document check (i-effectiveness scores) | 0 | Mexico City | Annual | PMU- Data from CONANP | $0 (included in Indicator a and b monitoring costs) |
| Indicator 3.1.1: # of gender-responsive and inclusive Annual Operating Plans prepared and implemented. | # of Plans | Document check and field visits (plans and implementation reports) | 0 | Mexico City | Annual | PMU | $15,000 |
| Indicator 3.1.2: # of people trained in sustainable land management, conservation and restoration practices (disaggregated by gender, recording level of Indigenous participation). | # of people and field visits (disaggregated by gender and Indigenous participation) | Document check (reporting on training events) | 0 | Mexico City | Annual | PMU | $15,000 |
| Indicator 3.1.3: % of targets reached in POAs, which include gender-responsive and inclusive management actions implemented by IP&LCs and local organizations in PAs and ADVCs. | % (proportion of each target achieved as % of target) | Document check and field visits (Annual reports on POA implementation) | 0 | Mexico City | Annual | PMU- Data from CONANP | $40,000 |
| Indicator 3.1.4: % of valid emergency funding requests that result in financial support within 72 hours. | Percent (# of requests with response / total number of requests) | Document check | 0 | Mexico City | Annual | PMU | $0 |
| Component 4: Knowledge management, monitoring and evaluation for scaling-up impact. |  |  |  |  |  |  |  |
| Indicator 4.1: # of scale-up strategy documents based on MEx30x30 experience. | # of documents | Document check (strategy package) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 4.1.1: Number of lessons-learned knowledge products prepared and shared (including products with a focus on gender and inclusion). | # of knowledge products | Document check (reports, cases studies, project briefs, etc.) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 4.1.2a: # of national workshop and dissemination events held. | # of events | Document check (post-event reports) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 4.1.2b: # of people participating in national workshop and dissemination event (disaggregated by gender, recording level of Indigenous participation). | # of people (disaggregated by gender and Indigenous participants) | Document check (participant lists in post-event reports) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator 4.2: PIR, MTR and TE ratings. | Rating (on a scale of: Unable to Assess; Highly Unsatisfactory; Unsatisfactory; Moderately Unsatisfactory; Moderately Satisfactory; Satisfactory; Highly Unsatisfactory) | Document check (verifying ratings) | 0 | Mexico City | Annual and at MTR and TE | PMU | $0 (No including MTR and TE cost $60,000 each one) |
| Indicator 4.2.1: Number of M&E frameworks in operation. | M&E Frameworks | Document check | 0 | Mexico City | Annual | PMU | $5,000 |
| Indicator 4.2.2: % of required reports submitted to CI GEF Agency on time and determined to be satisfactory. | Percent (# of reports submitted / total number of reports required) | Document check | 0 | Mexico City | Annual | PMU | $10,000 |
| Safeguard Plans: |  |  |  |  |  |  |  |
| Indicator AGM.1: Number of times the Accountability and Grievance Mechanism is communicated/disseminated to stakeholders | # of times | Document check | 0 | Mexico City | Annual | PMU | $0 |
| Indicator AGM.2: Percentage of grievances cases reported to the project’s Accountability and Grievance Mechanism that have been resolved | # of cases resolved as share of total cases reported | Document check (mechanism register) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator GMP.1: Number of persons (disaggregated by gender) who received benefits in the project implementation phase. | # of men and # of women | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| Indicator GMP.2: Number of documents (disaggregated by type) derived from the project that include gender considerations or address gender gaps. | # of strategies, plans, and policies | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $0 |
| Indicator SEP.1: Number of stakeholder entities (disaggregated by type) involved in the project implementation phase | # of entities | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| Indicator SEP.2: Number of persons (disaggregated by gender) who participated in the project implementation | # of men and # of women | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| Indicator SEP.3: Number of engagements (disaggregated by type of engagement) with stakeholders in the project implementation phase. | # of engagements | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $1,000 |
| ESS2.1: Number of hectares of natural and/or critical natural habitats negatively impacted by the project. | # of hectares | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| ESS4.1: Number of people from Indigenous/traditional communities present in the project sites that participated in the project. | # of people | Document check (reporting on training and sustainable management activities) | 0 | Mexico City | Annual | PMU | $5,000 |
| ESS8.1: Number of health, safety and/or security incidents reported and addressed. | # of incidents | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| ESS8.2: Percentage of measures implemented to ensure that risks or potential impacts to the health, safety and security of project-affected communities/project staff are avoided or mitigated. | % (measures implemented as % of measures identified in mitigation plans) | Document check (project reporting) | 0 | Mexico City | Annual | PMU | $5,000 |
| ESS9.1: Number of sub-projects/sub-grantees/investees screened by the EA/EE/FI to determine their ESMF risk category (POAs). | # of sub-projects | Document check (ESMF screenings of subgrantees) | 0 | Mexico City | Annual | PMU | $5,000 |

# ANNEX J: MEx30x30 site details

Mexico stands out globally for its remarkable biodiversity, hosting various plant and animal species within its borders. The pivotal role of protected areas in upholding this biodiversity and ensuring the vitality of ecosystems cannot be overstated. These areas are crucial bastions of ecosystem services, encompassing water purification, climate regulation, and pollination. Furthermore, they act as essential carbon sinks, playing a pivotal role in mitigating climate change by absorbing carbon dioxide from the atmosphere. The significance of these services extends beyond the local context, impacting both human well-being and the overall health of our planet.

Adding to their ecological importance, many of Mexico's protected areas carry cultural and historical significance, safeguarding traditional knowledge, offering recreational opportunities, and making notable contributions to tourism and local economies.

Despite these vital functions, Mexico confronts a series of challenges regarding its protected areas, including illegal logging, poaching, habitat degradation, and insufficient funding for conservation initiatives. These challenges exert considerable pressure on the biodiversity and ecosystems thriving within these protected zones.

Recognizing the urgency of the situation, the provision of substantial financial support for these protected areas is imperative. Enhanced funding can be strategically utilized for law enforcement, undertaking habitat restoration initiatives, and implementing community engagement programs. These endeavors are critical in the battle against illegal activities like logging and poaching. Furthermore, fostering the active involvement of local communities is indispensable for promoting sustainable livelihoods and instilling a sense of ownership, motivating communities to participate actively in conservation activities.

The ripple effect of increased support for these protected areas is profound. Preserving diverse plant and animal species becomes a reality, making a tangible contribution to global biodiversity conservation efforts. Additionally, the knowledge generated through these conservation efforts provides invaluable insights that contribute to a broader understanding of ecosystems, species, and effective conservation strategies.

In essence, backing protected areas in Mexico is not just a matter of local significance but a global imperative. Such support is fundamental to the preservation of biodiversity, the sustenance of critical ecosystem services, and the safeguarding of cultural values. The far-reaching impact encompasses the well-being of local communities and extends to global environmental benefits, including mitigating climate change and conserving invaluable ecosystems.

Balam-Kú

463,441.76 ha

889 people

Species Richness

It is home to 1,759 native taxa: 6 lichens, 27 bryophytes, 660 vascular plants, 592 invertebrates and 474 vertebrates, representing 64% of the species recorded in the state of Campeche. There are 23 species of fish, 19 amphibians, 44 reptiles, 314 birds and 74 mammals.

A wide diversity of invertebrates has been recorded, with a total of 592 native species belonging to 2 phyla: Arthropoda (579 species) and Mollusca (13), 5 classes, 20 orders and 124 families. Among the arthropods, there are 4 subphyla represented: Hexapoda, with 576 species and Chelicerata, Crustacea and Myriapoda with one species each. Of the total, the orders Lepidoptera (355 species), Hemiptera (69 species) and Coleoptera (52 species) stand out, which together represent about 89 % of the biodiversity of arachnid arthropods and insects recorded in the state of Campeche.

A variety of pollinating invertebrates have been recorded, including 355 species of butterflies and moths (order Lepidoptera), 69 bugs and cicadas (order Hemiptera), 52 beetles (order Coleoptera), 16 ants (family Formicidae), 2 stingless bees: jicote (Melipona beecheii) and orange-assed bee (Trigona fulviventris), and 1 wasp (Ammophila gaumeri). Among the butterflies, the most important pollinators are the striking sphinx moth (Eumorpha labruscae), striped sphinx (Protambulyx strigilis) and giant gray moth (Pseudosphinx tetrio).

There are 23 native fish species, classified in 5 orders and 5 families, which represents 38 % of the state's richness.  The families of the freshwater mojarras (Cichlidae) and the water voles (Poeciliidae) are the most diverse, with 10 and 8 species, respectively, which coincides with the diversity reported for Campeche. Among the species recorded, the most important is the colorless juil (Rhamdia guatemalensis), which is included in the NOM-059-SEMARNAT-2010 under the category of subject to special protection.

There are 19 species of amphibians, classified in 2 orders: 18 of Anura and 1 of Caudata, and in 7 families, with the tree frog family (Hylidae) being the most abundant, with 7 species. This figure represents 83 % of the state's amphibian diversity.

There are records of 44 species of native reptiles distributed in three orders: Crocodylia, with one family and one species; Squamata (squamates), with 12 families and 35 species; and Testudines, with 3 families and 8 species. In general, the Colubridae family, among the squamates, has the highest specific richness (16 species, 36 % of the total number of reptile species in the PA).

There are at least 314 native bird species, distributed in 23 orders, 60 families and 218 genera, representing 64% of the state's birds. The orders with the highest specific richness are Passeriformes with 154 and Accipitriformes with 23 species. There are 225 resident species, 64 are winter migrants, 19 are transient and 6 are summer migrants; 261 are of terrestrial habitat and 53 are aquatic.

RB Balam Kú records 74 species of native terrestrial mammals, from 11 orders and 25 families, which represent 67% of the state's wealth of terrestrial taxa. Among the orders, Quiroptera stands out with 40.5 % of the reported species, followed by Rodentia (23 %) and Carnivora (15 %). In fact, the diversity of bats in the polygon is such that they represent 55 % of the bats in the state of Campeche and 21 % of the bat species distributed in Mexico.

The vegetation in this area consists mainly of low deciduous and sub-deciduous forests, as well as wetlands.

The native species of vascular plants are distributed in 39 orders and 97 families. This diversity represents 53% of the state's flora. Among the families with the greatest diversity of species are: Fabaceae with 79, Euphorbiaceae with 37, Rubiaceae with 34, Asteraceae with 33 and Poaceae with 30. These figures coincide with the observed pattern of dominance of the Fabaceae and Euphorbiaceae families in the jungles of the Neotropics, likewise, with those of greater richness in the state of Campeche.

In the most arid zones, the vegetation can be xerophytic and be formed by thorny scrub and cacti. Some of the most representative species in this region are the sapote (Pouteria sapota), chicozapote (Manilkara zapota), ramón (Brosimum alicastrum), tinto (Haematoxylum campechianum and Haematoxylum calakmulens), machiche (Lonchocarpus castilloi), tzalam (Lysiloma latisiliquum), chechem (Metopium brownei), jabín (Piscidia piscipula), among others. Likewise, the conditions of the area allow the development of other types of vegetation characteristic of this zone such as the "bajos", which are areas of low altitude, generally flooded and that present distinctive plant associations that vary according to the dominance of the species in terms of biomass and structure, for example, the tintales, dominated by tinto (Haematoxylum calakmulense and H. campechianum), are also characterized by having a large biomass and diversity of epiphytic plants.

Endemic Species

It is home to 1,759 native taxa: 6 lichens, 27 bryophytes, 660 vascular plants, 592 invertebrates and 474 vertebrates, representing 64% of the species recorded in the state of Campeche. There are 23 species of fish, 19 amphibians, 44 reptiles, 314 birds and 74 mammals.

A wide diversity of invertebrates has been recorded, with a total of 592 native species belonging to 2 phyla: Arthropoda (579 species) and Mollusca (13), 5 classes, 20 orders and 124 families. Among the arthropods, there are 4 subphyla represented: Hexapoda, with 576 species and Chelicerata, Crustacea and Myriapoda with one species each. Of the total, the orders Lepidoptera (355 species), Hemiptera (69 species) and Coleoptera (52 species) stand out, which together represent about 89 % of the biodiversity of arachnid arthropods and insects recorded in the state of Campeche.

A variety of pollinating invertebrates have been recorded, including 355 species of butterflies and moths (order Lepidoptera), 69 bugs and cicadas (order Hemiptera), 52 beetles (order Coleoptera), 16 ants (family Formicidae), 2 stingless bees: jicote (Melipona beecheii) and orange-assed bee (Trigona fulviventris), and 1 wasp (Ammophila gaumeri). Among the butterflies, the most important pollinators are the striking sphinx moth (Eumorpha labruscae), striped sphinx (Protambulyx strigilis) and giant gray moth (Pseudosphinx tetrio).

There are 23 native fish species, classified in 5 orders and 5 families, which represents 38 % of the state's richness.  The families of the freshwater mojarras (Cichlidae) and the water voles (Poeciliidae) are the most diverse, with 10 and 8 species, respectively, which coincides with the diversity reported for Campeche. Among the species recorded, the most important is the colorless juil (Rhamdia guatemalensis), which is included in the NOM-059-SEMARNAT-2010 under the category of subject to special protection.

There are 19 species of amphibians, classified in 2 orders: 18 of Anura and 1 of Caudata, and in 7 families, with the tree frog family (Hylidae) being the most abundant, with 7 species. This figure represents 83 % of the state's amphibian diversity.

There are records of 44 species of native reptiles distributed in three orders: Crocodylia, with one family and one species; Squamata (squamates), with 12 families and 35 species; and Testudines, with 3 families and 8 species. In general, the Colubridae family, among the squamates, has the highest specific richness (16 species, 36 % of the total number of reptile species in the PA).

There are at least 314 native bird species, distributed in 23 orders, 60 families and 218 genera, representing 64% of the state's birds. The orders with the highest specific richness are Passeriformes with 154 and Accipitriformes with 23 species. There are 225 resident species, 64 are winter migrants, 19 are transient and 6 are summer migrants; 261 are of terrestrial habitat and 53 are aquatic.

RB Balam Kú records 74 species of native terrestrial mammals, from 11 orders and 25 families, which represent 67% of the state's wealth of terrestrial taxa. Among the orders, Quiroptera stands out with 40.5 % of the reported species, followed by Rodentia (23 %) and Carnivora (15 %). In fact, the diversity of bats in the polygon is such that they represent 55 % of the bats in the state of Campeche and 21 % of the bat species distributed in Mexico.

The vegetation in this area consists mainly of low deciduous and sub-deciduous forests, as well as wetlands.

The native species of vascular plants are distributed in 39 orders and 97 families. This diversity represents 53% of the state's flora. Among the families with the greatest diversity of species are: Fabaceae with 79, Euphorbiaceae with 37, Rubiaceae with 34, Asteraceae with 33 and Poaceae with 30. These figures coincide with the observed pattern of dominance of the Fabaceae and Euphorbiaceae families in the jungles of the Neotropics, likewise, with those of greater richness in the state of Campeche.

In the most arid zones, the vegetation can be xerophytic and be formed by thorny scrub and cacti. Some of the most representative species in this region are the sapote (Pouteria sapota), chicozapote (Manilkara zapota), ramón (Brosimum alicastrum), tinto (Haematoxylum campechianum and Haematoxylum calakmulens), machiche (Lonchocarpus castilloi), tzalam (Lysiloma latisiliquum), chechem (Metopium brownei), jabín (Piscidia piscipula), among others. Likewise, the conditions of the area allow the development of other types of vegetation characteristic of this zone such as the "bajos", which are areas of low altitude, generally flooded and that present distinctive plant associations that vary according to the dominance of the species in terms of biomass and structure, for example, the tintales, dominated by tinto (Haematoxylum calakmulense and H. campechianum), are also characterized by having a large biomass and diversity of epiphytic plants.

Genetic Diversity

The purpose of the PA is to promote the preservation of genetic diversity through the sustainable management of ecosystems and their elements; the protection of their natural environments; as well as to promote actions that increase habitat conditions that favor wildlife.

Ecosystem Functions and Services

Rainwater harvesting and infiltration.

Protection against evaporation of water reserves. Humidity regulation.

Provision of food from drought-resistant sources. Regulation of water flows. Temperature regulation through shade and evapotranspiration of vegetation. Maintenance of water sources for fire management. Water infiltration. Natural barriers against water currents. Natural barrier against winds. Soil retention.

Ecological Connectivity

Balam Kú is linked by bioclimatic corridors with the state-owned Balam Kin Ecological Conservation Zone and the federal Calakmul Biosphere Reserve. It is also 1.4 km from the Ejido Puebla de Morelia ADVC, 8.9 km from the N.C.P.E. Centauro del Norte ADVC, and 13.1 km from the Ejido El Chichonal ADVC. In addition, on the border with Guatemala, it is a contiguous neighbor of the Selva Maya Biosphere Reserve decreed in 1990, which in turn has almost half a million hectares. In this sense, the Selva Maya, shared by Belize, Guatemala and Mexico, represents one of the most important ecological systems at a global level, because it is considered the largest continuous massif of humid and sub-humid tropical forest in Mesoamerica and the second largest tropical forest in America, after the Amazon Rainforest, in which more than 20 ecosystems are distributed, with important functions of providing essential environmental services for the population, such as the capture and provision of water, carbon sequestration and landscape connectivity.

Cultural and Social Value

It is the natural environment of sites of biocultural importance such as the Archaeological Zone of Balam Kú where there is a unique stucco frieze in the Mayan area and Nadzca'an, which are evidence of the presence of this culture in notable cities linked to the Petén region in early times.

Two agrarian nuclei with population in indigenous households have been identified in the BR: Kilometer 120 and Hecelchakán.

The word balam kú is composed of the Maya words: balam, 'jaguar'; and kú, 'temple': "The temple of the jaguar". It alludes to the three jaguars that are represented in the archaeological zone located within the BR.

Vulnerability and Threats

Deforestation and illegal logging. Forest fires. Introduction of invasive exotic species.

The main climate or climate change-related threats that could arise or increase their impact in the Balam Kú region are the increase in average temperature, the decrease in the availability of water resources, and the impact of tropical cyclones, heavy rains, and floods.

16 plants, 1 invertebrate and 127 vertebrates are in some category of risk according to the Mexican Official Standard NOM-059-SEMARNAT-2010.

Affected by changes in the spatial and temporal availability of water.

Bajos del Norte

1,304,114.89 ha

68,944 people (3,827 indigenous, 6%)

Species Richness

It is home to 679 native taxa: 105 algae (prokaryotes and eukaryotes), 335 invertebrates and 239 chordates (37 tunicates and 202 vertebrates). This richness represents 6 % and 25 % of the species recorded for the Gulf of Mexico and the Mexican Caribbean, respectively. Some relevant invertebrate species are: Soft coral, sea fan (Plexaura homomalla), black coral (Plumapathes pennacea), staghorn (Acropora cervicornis), elkhorn (Acropora palmata), stony or massive star coral (Orbicella annularis), mountain or massive star coral (Orbicella faveolata). Vertebrates include: giant manta ray, giant manta ray, flying manta ray (Mobula birostris), whale shark (Rhincodon typus). Bony fishes (Class Actinopteri): midnight parrot, black macaw (Scarus coelestinus), blue parrot, blue macaw, jabon (Scarus coeruleus), macaw parrot, macaw, macaw (Scarus guacamaia). Reptiles: loggerhead, loggerhead turtle (Caretta caretta), green turtle, white turtle (Chelonia mydas), hawksbill, hawksbill turtle (Eretmochelys imbricata), olive ridley, olive ridley turtle (Lepidochelys kempii), leatherback, leatherback turtle (Dermochelys coriacea).

Endemic Species

There are records of 12 native species of polychaetes, such as the fire worm (Hermodice carunculata) and the polychaetes Lumbrinerides nasuta, Phalacrophorus uniformis, Nereis riisei, Bispira brunnea and Spirobranchus giganteus.  Five species of sea turtles are also registered: loggerhead (Caretta caretta), white (Chelonia mydas), hawksbill (Eretmochelys imbricata), olive ridley (Lepidochelys kempii) and leatherback (Dermochelys coriacea), which are listed as Endangered according to NOM-059-SEMARNAT-2010, as well as being priority species for conservation in Mexico.

Genetic Diversity

This area is characterized by its upwelling system and the so-called "loop current", both of which are responsible for the balance of nutrients in the Gulf of Mexico shelf and for the genetic connectivity and biological exchange of reef species, especially those of fishery value.

Ecosystem Functions and Services

This space contributes to the continuity of biodiversity and ecosystem services, fundamental aspects for maintaining the quality of life of the human communities that inhabit it. It is also an important tool for scientific research and environmental education, allowing the study and understanding of the natural processes that occur in these spaces.

Other functions and services it provides are the internal exchange of fishery resource larvae, the protection of more than one million hectares of marine area in the region, especially the reproduction and growth areas of various species, ensuring the maintenance of healthy populations and continuous development, which contributes to the food security of the families belonging to the fishing communities of the Yucatan coast.

Ecological Connectivity

The reef areas of the northeastern end of the Yucatan Peninsula are transition zones between the Gulf of Mexico and the Caribbean Sea (Tunnell et al., 2007), this means that the coral reefs of Bajos del Norte share species from the Mexican Caribbean and the Gulf of Mexico; therefore, this is considered a region of ecological connection and, therefore, of high biodiversity. The Bajos del Norte reefs are the second most relevant site as a larval source for areas in the northern, western and central Gulf of Mexico for several key fishery species for the region's economy.

Cultural and Social Value

Although the proposal for Bajos del Norte NP has no direct connection with terrestrial communities because it is located 100% in maritime territory, it can be considered to have influence over two municipalities geographically. The coastal municipalities that are in front of the proposed area and from which the medium height fleet departs are Progreso and Dzilam de Bravo.

Vulnerability and Threats

In terms of human intervention at the site, two fundamental aspects stand out: local fishing activity and the transit of ships since the viceregal period.

Decrease of the fishing resource as a result of increased fishing effort, subsidy policies that stimulated greater investment in the fishing industry, the capture of the reproductive stock of larger and more fecund females in deep areas, reducing reproductive potential, and methods of maintaining production for marketing, such as the widespread use of ice, freezing chambers and packaging, which extended the shelf life of the product, which has caused the fishery to be at unsustainable levels in the long term. In addition, the environmental effects of climate change by increasing the temperature negatively affect the reproduction process.

Chimalapas Cluster

438,662.66 ha

16,286 people (6,711 indigenous, 38%)

Species Richness

For the Chimalapa region, there are 609 records of terrestrial vertebrate species, 99 correspond to mammals, 220 to birds, 37 to reptiles and 8 to amphibians. In addition, there are 191 records of 51 fish species.

In this area you can find spider monkeys and saraguato monkeys, wild boars, various felines such as Puma (Puma concolor), Ocelot (Leopardus pardalis), Tigrillo (Leopardus wiedii) and Jaguar (Panthera onca), armadillos, tepezcuintles, mazates; river otters, Tamandua mexicana, Tayassu pecari, Ara militaris and tapir. Several bird species are reported, such as harpy eagles (Harpia harpyja) and elegant eagles (Spizaetus ornatos), solitary eagle (Harpyhaliaetus solitarius), quetzal (Pharomachrus macinno), hocofaisan (Crax rubra), Pajuil (Penelopina nigra) and king vulture (Sarcoramphus papa). The area is an important reservoir for parrots, macaws, toucans (Rampasthus sulfurathos) and pajuil (Penelopina nigra).

Flora: white cedar (Cupressus lusitanica), old man's head cactus (Mammillaria senilis), Alsophila salvini, Cyathea bicrenata, C. fulva, C. schiedeana, Ceratozamia norstogii, Chamaedorea Metallica, C. rigida, C. sartorii, C. woodsoniana.

Endemic Species

Among the most important endemic plant species of Los Chimalapas are: Begonia lyniceorum, Colubrina johnstonii, Diplopteris mexicana, Dostenia uxpanapa, Ocotea uxpanapana, Rinorea uxpanap. Some endemic species of reptiles are: Abronia bogerti, Abronia ornelasi, Adelphicos latifasciatus, Ctenosaura pectinata, Sceloporus internasalis, Anolis breedlovei, Anolis compressicaudua, Scincella gemmingeri, and Heloderma horridum. Among the endemic amphibians there are three frogs: Eleutherodactylus Lineatus macdougalli and Hyla sumichrasti and a salamander (Pseudoeurycea parva).

Genetic Diversity

The fundamental purpose of the protected area is to preserve and interconnect the natural environments representative of the different natural ecosystems, as well as to safeguard the genetic diversity of the wildlife of the ecosystems and their elements. That is, to expand habitat connectivity to facilitate the movement of individuals between the different zones that make up the landscape and ensure the exchange of genes and the genetic variability of flora and fauna populations.

Ecosystem Functions and Services

Provision of food from drought-resistant sources. Regulation of water flows. Temperature regulation through shade and evapotranspiration of vegetation. Maintenance of water sources for fire management. Water infiltration. Natural barriers against water currents. Natural barrier against winds. Soil retention.

Ecological Connectivity

With the declaration of Areas Voluntarily Destined for Conservation, the protection of biocultural resources in the Los Chimalapas Region is privileged, generating important biological corridors with other nearby Protected Areas, in addition to stopping the extraction of hydrocarbons and the installation of mining companies.

Cultural and Social Value

It is an ancestral indigenous territory of the Zoque people. The social structure of the region responds to the historical uses and customs, so it is identified in hierarchical order to the Communal Assembly as the highest instance, then to the congregations, which are the local regulatory body for access to resources.

Vulnerability and Threats

Deforestation and land use change, Forest fires caused by agricultural burning and poaching. Historical land tenure disputes in the border strip with the state of Chiapas.

Cuenca Alimentadora del Distrito Nacional de Riego 043 Nayarit

2,329,026.76 ha

52,498 people (25,768 indigenous, 49%)

Species Richness

More than 2000 species of vascular plants of Holarctic and neotropical affinity; around 300 species of birds, including terrestrial, aquatic and marine birds of Nearctic and tropical affinity, of which at least 15 are endemic to our country; more than 800 species of insects; around 80 species of mammals, of which more than 15 are endemic to Mexico and eight are protected by NOM 059; more than 60 species of reptiles and 16 species of amphibians, and of these, more than half are endemic to our country and at least ten are threatened; around ten species of ichthyofauna of which one is endemic to the region.

Fauna: Guajolote, wild turkey (Meleagris gallopavo), White-tailed deer (Odocoileus virginianus ), Collared peccary (Pecari tajacu), White-tailed deer (Odocoileus virginianus ), Puma (Puma concolor), Coyote (Canis latrans), Castilian or Serrano rabbit (Sylvilagus floridanus), Black-tailed hare (Lepus californicus), Golden eagle (Aquila chrysaetos), Montezuma quail (Cyrtonyx montezumae), Chichimoco (Tamias bulleri), Spotted owl (Strix occidentalis), Rattlesnake (Crotalus lepidus), Euptilotis neoxenus (Euptilotis neoxenus), Green Macaw (Ara militaris), Gadwall (Anas strepera), Blue-winged Teal (Anas discors), Northern Shoveler (Anas discors), Northern shoveler (Anas clypeata), Cotuí quail (Colinus virginianus), White-winged dove (Zenaida asiatica), Palomahuilota (Zenaida macroura), Long-tailed dove (Columbina inca), Coquita dove (Columbinapasserina), Pacific vole (Poecilia butleri), Blackish bat, dusky bat (Myotisnigricans), Jaguarundi, jaguar (Puma yagouaroundi), river otter (Lontra longicaudis), jaguar (Panthera onca), ocelot, ocelot (Leopardus pardalis), cat's eye night snake (Hypsiglenatorquata), Pacific centipede snake (Tantilla calamarina), royal coral snake (Lampropeltistriangulum), black iguana (Ctenosaura pectinata).

Flora: Piñon pine (Pinus cembroides), Pino triste (Pinus lumholtzii), Pino colorado, teocote (Pinus teocote), Pino blanco (Pinus durangensis), Pino de navidad (Pinus ayacahuite), San Juan cedar (Cupressus lusitanica), Holm oak, Quercus laurina (Quercus laurina), Quercus rugosa (Quercus rugosa), old man's head cactus (Mammilaria senilis), royal pine (Pinus engelmannii), Chinese ocote (Pinus leiophylla), Chihuahua pine (Pinus chihuahuana), Cedar (Juniperusdeppeana), Táscate (Juniperus durangensis), (Quercus resinosa), (Quercus potosina), (Quercuseduardii), (Quercus grisea), (Quercus sideroxyla),  (Quercus chihuahuensis), (Quercus aristata), (Quercus uxoris), (Quercus gentry), (Artostaphylos pungens), Encino chaparro (Quercusmicrophylla), Ejechí (Mastichodendron capiri), Cedar (Cedrela odorata), (Bouteloua sp.), Acacia (Acacia spp.), Pine (Pinus spp.), (Juniperus spp.), (Quercus spp.), (Tabebuia chrysantha), Pink Lapacho (Handroanthus impetiginosus), Arbutus xalapensis, (Amoreuxia palmatifida), Pinabeto (Pseudotsuga menziensii var. glauca), Montezuma Cypress (Taxodium huegelii), (Pseudotsuga menziensii var. glauca), (Pseudotsuga menziensii var. glauca), (Pseudotsuga menziensii var. glauca), (Pseudotsuga menziensii var. glauca), (Pseudotsuga menziensii var. glauca), (Pseudotsuga menziensii var. glauca).

Endemic Species

Shadbush (Abelia occidentalis), Asteracea (Acourtia rigida), Child-faced Frog (Agalychnis dacnicolor), Snake-root (Asteracea) Member (Ageratina oligocephala),Sander (Ageratina palmeri), Five-striped Zacatonero (Amphispiza quinquestriata), Chives (Alliumglandulosum), Beryl Hummingbird (Amazilia berillyna), Plateau Toad (Anaxyrus compactilis), Oaxacan Bushbat (Anolis nebuloides), Western Strawberry Tree (Arbutus occidentalis), Hairy Fruit Bat (Artibeus hirsutus), Araxi (Asclepias mcvaughii), Huico Llanero (Aspidoscelis costata), Escobilla (Baccharis multiflora), Lagarto Alicante del Popocatépetl (Barisia imbricata), Orégano (Brickellia secundiflora), Rascador cejas verdes (Arremon vrenticeps), Tepozán Cimarrón (Buddlejaparviflora), Sapo Jaspeado, Marbled Toad (Incilius marmoreus), Pinero Toad (Inciliusoccidentalis), Mexican Cassowary (Cassiculus melanicterus), Serrano Bush Chat (Campylorhynchusgularis), Red-capped Hornbill (Cardellina rubra), Marsh Grass (Carex marianensis), Mexican Thrush (Catharus occidentalis), Narigon Ground Snake (Conopsis nasus), Mexican Mule Bat (Corynorhinus mexicanus), Bise'Ebeero (Cosmos intercedens), Smith's Barking Frog (Craugastor hobartsmithi), Coastal Barking Frog (Craugastor occidentalis), Sonoran Barking Frog (Craugastor vocalis), Ahuitule (Critoniopsis uniflora), Queretaro Dusky Rattlesnake (Crotalus aquilus), Saye's Rattlesnake (Crotalus basiliscus), Mexican Spiny Iguana (Ctenosaura pectinata), Pega hormiga (Cuphea lobophora), San Blas Chara (Cyanocoraxsanblasianus), Chilillo (Delphinium pedatisectum), Crab Grass (Digitaria paniculata), Coyamol (Echeandia flavescens), Lili (Echeandia mexicana), Lili (Echeandia occidentalis), Dazzling Frog (Eleutherodactylus nitidus), Gecko (Plestiodon brevirostris), Southern Pygmy Skink (Eumeces parvulus), Crucetillo (Eupatorium leptodictyon), Lipa-Cai-Nofal (Euphorbia succedanea), Eared Quetzal (Euptilotis neoxenus), Kidneywoods (Eysenhardtiaplatycarpa), Acitron Barrel Gecko (Ferocactus histrix), Limiscui (Ficus petiolaris), PeriquitoCatarino (Forpus cyanopygius), Nanche (Gaudichaudia subverticillata), Culebra Minera deChihuahua (Geophis dugesii), Granatelo Mexicano (Granatellus venustus), Gumplant (Grindeliaoxylepis), Gutierrezia (Gutierrezia sericocarpa), Guishi (Hilaria cenchroides), Cambalacherade Allen's Rat (Hodomys alleni), Mountain Tree Frog (Hyla eximia), Western Mountain Parakeet (Rhynchopsitta pachyrhyncha), Lerma Catfish (Ictalurus dugesii), Green River Catfish (Ictalurusmexicanus), Calandria Flancos Negros (Icterus abeillei), Sinaloense Toad (Incilius mazatlanensis), Cuatolotlanenzi (Iostephane heterophylla), Quiebra Planto (Ipomoea stans), Casquito de Burro, Mexican Broken-breasted Turtle (Kinosternon integrum), Chichiltepetzacuxóchitl (Laeliaspeciosa), Potosina Royal Snake (Lampropeltis mexicana), Mexican Bush Snake (Lepidocolaptesleucogaster), Poace (Leptocoryphium villaregalis), Southwestern Cat's Eye Snake (Leptodeiramaculata), Perico Gargantilla Snake (Leptophis diplotropis), Otác (Lithobates magnaocularis), Montezuma Leopard Frog (Lithobates montezumae), Ziix Hax Ano Quiij (Lithobates pustulosus), Large-Flowered Cactus (Mammillaria longiflora), Pirul (Marina grammadenia), Zipolite Star (Matelea pilosa), Southern Desert Shrew (Megasorex gigas), Masked Woodpecker (Melanerpes chrysogenys), Blue Mulatto (Melanotis caerulescens), Cinnamon Nape Scratcher (Melozone kieneri), Dry Love (Mentzelia hispida), Starry, Wild Lily (Milla biflora), Cinnamon-crowned Momoto (Momotus mexicanus), Zacate-pasto (Muhlenbergia aguascalientensis), Liendrilla de Pinar (Muhlenbergia dubia), Cola de Ratón (Muhlenbergia emersleyi), Zacatón, Soromuta (Muhlenbergia macroura), Zacate de Escobillas (Muhlenbergia robusta), Garambullo (Myrtillocactus geometrizans), Rata Cambalachera, Rata Cambalachera Diminuta, Rata Montera, Rata-Cambalachera Diminuta (Nelsonia neotomodon), Pañuelo (Norops nebulosus), ZacatoneroSerrano (Oriturus superciliosus), Chachalaca Vientre Castaño (Ortalis wagleri), Ratón Arbustero (Peromyscus boylii subsp. glasselli), White-footed Mouse, Bare-footed Mouse (Peromyscus difficilis), Field Mouse, North American Mouse (Peromyscus maniculatus), Black-footed Wild Mouse (Peromyscus melanocarpus), Table Mouse, Black-footed Mountain Mouse (Peromyscus melanophrys), Black-footed Mountain Mouse (Peromyscus spicilegus), Chameleon, Mountain Chameleon, Mountain Horned Lizard, Tapayaxin (Phrynosoma orbiculare), Gopher (Pappogeomys bulleri), Pinyon Mouse (Peromyscus gratus), Mexican Gecko (Phyllodactylus lanei), Alicante, Cincuate, Mexican Cincuate, Mexican Deaf Snake (Pituophis deppei), Mexican Tree Frog (Plectrohyla bistincta), Encinero Lizard, Lincer de Encinos, Lagartija, Lagartija deCola Azul, Lagartija deCola Azul,Lincer de Los Pinos (Plestiodon lynxe), Nardo de Varogachic (Polianthes densiflora), Nardo de Nueva Galicia (Polianthes platyphylla), Tlaconete Pinto (Pseudoeurycea belli), Gordolobo (Pseudognaphalium inornatum), Encino Chaparro (Quercus aristata Hook. &amp; Arn.), Palo Blanco (Quercus laeta Liebm.), Encino Enano (Quercus macrophylla), Roble blanco (Quercus resinosaLiebm.), Montezuma Frog (Rana montezumae), Waterfall Frog (Rana pustulosa), Western Sierra Madre Harvest Mouse, Zacatecas Harvest Mouse, Zacatecas Wild Mouse (Reithrodontomys zacatecae), Culebra Café de Occidente (Rhadinaea hesperia), Culebra Acotera, Culebra Café Coronada, Culebra de Collar, Hojarasquera Corona (Rhadinaealaureata), Murciélago Amarillo de Orejas Largas (Rhogeesa gracilis), Murciélago Amarillo Mayor (Rhogeessa alleni), Aztec Blackbird (Ridgwayia pinicola), Hediondilla (Roldana lineolata), Baird's SnakeChata, Baird's Patched Snake, Striped Snake (Salvadora bairdi), Cuijera (Salvadoramexicana), Dugués Scaly Lizard (Sceloporus dugesii), Lagartija Espinosa Jalisciense, Lagartija-Escamosa Dorso Carinado (Sceloporus heterolepis), Chintete Común, Lagartija Escamosa, Lagartija Escamuda, Roño Espinoso, Lagartija Espinosa del Pacifico (Sceloporus horridus), Lesser Spiny Lizard (Sceloporus jarrovi minor), Nelson's Spiny Lizard (Sceloporus nelsoni), Salvin's Scaly Lizard (Sceloporus salvini), Long-tailed Mountain Striped Snake (Sceloporus scalaris), Spiny, Scaly-tailed Lizard (Sceloporusspinosus), Barred Scaly Lizard (Sceloporus torquatus), Tree Squirrel (Sciurusnayaritensis), White-eared Cotton Rat (Sigmodon leucotis), Jalisco Sissy Rat (Sigmodon mascotensis), Jalisco Coluda Shrew (Sorex emarginatus), Mountain Shrew (Sorex vagrans monticola), Worthen's Sparrow (Spizella wortheni), Mexican Brown Snake (Storeria storerioides), White-naped Swift (Streptoprocne semicollaris), Mexican Nymph (Thalurania ridgwayi), Wandering Slaty Snake (Thamnophis errans), Water Snake (Thamnophis scaliger), Wall-happy Salta (Thryothorus felix), Sinaloan Saltapared (Thryothorussinaloa), Mexican False Nauyaca (Trimorphodon tau), Teocintle (Tripsacum zopilotense), Long-tailed Saltapared (Tryomanes bewickii), Cinnamon-backed Blackbird (Turdus rufopalliatus), Yellow-rumped Vireo (Vireo hypochryseus), Larch Vireo (VireolanIus melitophrys), Serrano Sparrow (Xenospiza baileyi), River Dipper (Gobiesox fluviatilis), Highland Tree Frog (Smilisca dentata), (Mexianthus mexicanus), Palo prieto (Mimosa rosei), (Muhlenbergia depauperata), (Muhlenbergialongiglumis), (Muhlenbergia polycaulis), (Myotis fortidens), Atzatzamolli (Nymphaeagracilis), (Odontotrichum multilobum), (Oryzomys palustris), (Panicumdecolorans), (Pedicularis glabra), (Perymenium uxoris), (Pinus maximartinezii),  (Polyanthesgeminiflora ), (Psacalium amplum), (Psacalium megaphyllum), (Psacalium platylepis), (Psacaliumsinuatum), Dwarf oak (Quercus coccolobifolia), (Rana magnaocularis), (Ruellia jaliscana), (Rynchospora jaliscensis),  (Salvia keerlii), (Salvia ramamoorthyana), Scaly ground lizard (Sceloporus utiformis), (Schoenocaulon jaliscense), (Sedum minimum ), (Senecio filaris), (Senecioguadalajarensis), (Senecio stoechadiformis),  (Senecio toluccanus), Pacific cane rat (Sigmodon alleni), (Sinclairia palmeri), Michoacan ground snake (Sonora michoacanensis), (Stevia trifida), (Stipa eminens), Poppy (Tabebuia palmeri), (Tagetes pringlei), Bocourt's Hooded Snake (Tantilla bocourti), Black-bellied Water Snake (Thamnophismelanogaster), (Tigridia mexicana), Rnica (Trixis angustifolia), Pacific Tree Lizard (Urosaurus bicarinatus), (Verbesina culminicola),  (Verbesina oxylepis), (Vernonia autumnalis), (Vernonia bealliae), Ahuitule (Vernonia salicifolia), (Viguiera grahamii), (Viguiera linearis), (Viguierapringlei), (Yucca jaliscensis), Nopal arrastradillo (Opuntia spraguei)

Genetic Diversity

The fundamental purpose of the protected area is to preserve and interconnect the natural environments representative of the different natural ecosystems, as well as to safeguard the genetic diversity of the wildlife of the ecosystems and their elements. That is, to expand habitat connectivity to facilitate the movement of individuals between the different zones that make up the landscape and ensure the exchange of genes and the genetic variability of flora and fauna populations.

Ecosystem Function and Services

More than 50% of the PA's surface is occupied by oak-pine and pine-oak forests, excellent providers of hydrological environmental services. Therefore, its forests are essential for water catchment and the recharge of aquifers for supplying population centers such as Puerto Vallarta and Bahía de Banderas. This watershed is of the utmost importance for maintaining Marismas Nacional in Nayarit, which includes extensive mangrove areas. Likewise, the water from this PA makes agricultural and livestock farming possible and provides drinking and industrial water to 38 municipalities in Jalisco and Nayarit.

Ecological Connectivity

Two of the four polygons that make up this PA coincide with CONABIO's priority terrestrial regions, RTP-62 Sierra Vallejo-Río Ameca and RTP-60 Sierra Los Huicholes, as well as with the priority hydrological region: Río Baluarte - Marismas Nacionales. There are also six areas of importance for bird conservation (AICAS): Quebradas de Sinaloa Nayarit and Durango, Guacamayita, La Michilia, Sierra de Valparaíso, El Carricito and Sierra Fría.

Cultural and Social Value

More than 40% of the population in this basin is indigenous, belonging to the Huicot or Gran Nayar region.

Vulnerability and Threats

Deforestation, land use change, forest fires, presence of forest pests and diseases (e.g., defoliator, bark stripper, and parasitic plants), expansion of unsustainable extensive cattle ranching activities, illegal extraction of flora and fauna, use of stone materials in forest lands, soil degradation, presence of invasive exotic species, loss of habitat for flora and fauna species, loss of water sources, impact of extreme hydro-meteorological phenomena.

Papigochic

222,763.85

6,907 people (712 indigenous, 10%)

Species Richness

The type of vegetation that characterizes Papigochi is mixed conifer and oak forests. It has some of the last relics of old-growth forests in the world. These communities are integrated by species of Arizona pine (Pinus arizonica) with an abundant distribution and adjacent to the pinyon pine (Pinus cembroides). The Durango pine (Pinus durangensis) is found in humid areas at higher elevations; in the canyons, the ayacahuite pine (Pinus ayacahuite); in very exposed areas, the weeping pine (Pinus lumholtzii); and in areas with deep soils, the Chinese ocote (Pinus leiophylla). There are also species of Chihuahuan pine (Pinus chihuahuana) and Apache pine (Pinus engelmannii). In the primary pine forests, the lower stratum is relatively poor in shrubs, but with abundant grasses, such as banderilla (Bouteloua curtipendula), zacate (Festuca arundinacea), bromo de california (Bromus carinatus), liendrilla del pinar (Muhlenbergia dubia) and popotillo azul (Schizachyrium scoparium), among others. Some mammals that can be found in the Protected Area are: coyote (Canis latrans), puma (Puma concolor), spotted skunk (Spilogale gracilis), coati, solitary (Nasua narica), the emblematic American black bear (Ursus americanus), white-tailed deer (Odocoileus virginianus), collared peccary (Pecari tajacu), opossum (Didelphis virginiana), California hare (Lepus californicus), and gray squirrel (Sciurus aberti). An important number of birds have also been recorded in the Protected Natural Area, such as the mountain parakeet (Rhynchopsitta pachyrhyncha), the trogon (Trogon mexicanus), the owl (Tyto alba), the acorn woodpecker (Melanerpes formicivorus), the great spotted woodpecker (Colaptes auratus), the goshawk (Accipiter gentilis), the golden eagle (Aquila chrysaetos), the red-tailed eagle (Buteo jamaicensis), the creeping hawk (Circus cyaneus) and the green-winged teal (Anas crecca). Amphibians in the Papigochic Flora and Fauna Protection Area include the Great Plains toad (Anaxyrus cognatus), red-spotted toad (Anaxyrus punctatus), rock frog (Hyla arenicolor), and tiger salamander (Ambystoma verlasci).

Endemism

Western saw-tailed parakeet (Rhynchopsitta pachyrhyncha), Long-eared trogon (Euptilotis neoxenus), White-tailed deer (Odocoileus virginianus), Spiny pinyon (Picea chihuahuana), Pinabete (Pseudotsuga mensiezzi), Arizona pine (Pinus arizonica).

Genetic Diversity

Papigochic is biogeographically located in the Nearctic region within the Rocky Mountains subregion. It is within the biotic province of the Sierra Madre Occidental. It maintains a solid faunal exchange with the surrounding biotic provinces: to the west, with the Sonoran and Sinaloa provinces, with which it forms deep slopes and interdigitations and from whose plains the faunal expansion takes place, and to the east, with the Chihuahua-Zacatecas biotic province with which it maintains a more continuous altitudinal level than with the previous ones. The PA has the fundamental objective of conserving the natural environments representative of the most fragile ecosystems to ensure the balance and continuity of the evolutionary and ecological processes that occur in them.

Ecosystem Function and Services

In addition to providing timber resources, 47% of its surface is considered harvestable forest area and includes ecosystem services such as water quality and quantity, carbon sequestration, oxygen generation, buffering the impact of natural phenomena, climate modulation or regulation, and biodiversity protection, either naturally or through sustainable management.

The scenic beauty of the area's mountainous topography and pine forests, as well as the importance of its conservation to maintain the ecological balance by preserving its green wooded areas, which represent pleasant places for recreation and leisure for national and foreign tourists, are also important.

The PA also provides natural resources for the local population, mainly related to the use of timber forest species of the Pinus, Quercus, Abies, and Picea genera, among others, to obtain wood for the construction of houses, fences, and work tools and for commercial purposes, as well as non-timber resources such as mushrooms and wild plants used for food and medicine (leaves, roots, fruits, etc.), as fodder (grass, grasses, etc.), and as fodder (grasses, grasses, etc.).), as fodder (grasses, shoots, foliage), as fuel (standing and felled dead trees), as ornamentals (plants, foliage, flowers); in addition to the use of wildlife species for food and commercial purposes; the use and exploitation of water and soil, as well as the use of land for agriculture and livestock.

Ecological Connectivity

Papigochic is biogeographically located in the Nearctic region within the Rocky Mountains subregion. It is within the biotic province of the Sierra Madre Occidental. It maintains a solid faunal exchange with the biotic provinces that surround it: to the west, with the Sonoran and Sinaloa provinces, with which it forms deep slopes and interdigitations and from whose plains faunal expansion takes place, and to the east, with the Chihuahua- Zacatecas biotic province, with which it maintains a more continuous altitudinal level than with the previous ones.

Its polygon coincides with CONABIO's priority terrestrial regions, Alta Tarahumara-Barrancas and Bassaseachic, and the priority hydrological region, Río Yaqui - Bassaseachic Waterfall. In addition, there is an area of importance for bird conservation (AICAS): Papigochic.

Cultural and Social Value

Although only 10% of its population is indigenous, this PA is the only one decreed on Rarámuri (Tarahumara) lands.

Vulnerability and Threats

Deforestation, habitat modification or loss (reduction, fragmentation), incidence of natural phenomena (snowfall, north winds, hailstorms, cold fronts, rainfall, drought), forest fires, land cover conversion for the development of productive activities (forest exploitation, mining exploration and exploitation, agriculture, livestock), presence of forest pests, population growth near forested lands.

Tecuani

348,140.97 ha

17,768 people

Species Richness

There are 1,879 native species. The total number of vascular plant species (1,040) present in the PA represents 30% of the richness of the Sierra Madre del Sur in the Guerrero state portion. Likewise, 28% of the species at risk in the entire Sierra Madre del Sur according to NOM-059-SEMARNAT2010 are present.

In addition, there are 23 of the 46 species of Salvia spp. endemic to the Sierra Madre del Sur or the state of Guerrero (50%), 7 of the 19 endemic species of Stevia (37%), 10 of the 17 endemic species of Epidendrum (59%), 33% of Lobelia and 40% of Castilleja, which is of regional relevance for the safeguarding of Mexico's exclusive genetic resources. It has species with high economic and biological value, because they are timber species such as anacahuite (Cordia morelosana), thunder (Cordia elaeagnoides), palo de aro (Lonchocarpus caudatus), and guaje (Leucaena macrophylla), among others. Sierra Tecuani also has three species of the Agave genus. In this genus is recognized the relationship of coevolution with nectarivorous bats also present: Leptonycteris nivalis, Leptonycteris yerbabuenae, Choeronycteris mexicana and Glossophaga sp. with which they maintain a close mutualistic relationship.

In terms of herpetofauna, it is home to 27 species of amphibians and 64 native reptiles, which together represent 6% of the total species in Mexico and 50% of the herpetofauna present in the Sierra Madre del Sur in Guerrero. Regarding birds, the total number of birds in the proposed PA (288 species) exceeds the richness previously recorded in the Sierra Madre del Sur in Guerrero (204 species). Regarding the mastofauna, Sierra Tecuani harbors 68 species and the PA polygon is part of the 1% of the surface of the state of Guerrero with suitable habitat for species of restricted distribution such as the tropical shrew of the Sierra Madre del Sur (Cryptotis goldmani).

On the other hand, the Sierra Madre del Sur is in the transition zone of the Nearctic and Neotropical regions, which favors the presence of a great diversity of species, including several microendemic vertebrates such as the tree frog (Charadrahyla tecuani), the Guerrero rattlesnake (Crotalus ericsmithi), the short-crested coquette (Lophornis brachylophus) and the tropical shrew of the Sierra Madre del Sur (Cryptotis goldmani), among others.

Endemic Species

It is considered a zone of high endemism that harbors viable populations of different species with some degree of threat. Twenty-five species of fungi, 338 plant species, 16 invertebrate species, and 120 vertebrate species are endemic. The most important endemic species are the Mexican thrush (Catharus occidentalis), the Sinaloa wren (Thryothorus sinaloa) and happy wren (Thryothorus felix), the Neovolcanic quailtail (Dendrortyx macroura) and the unicolor chara (Aphelocoma unicolor). Of the vascular plants, 19 are endemic to the biogeographic province Sierra Madre del Sur, such as the orchid (Artorima erubescens), and 23 are endemic to the state of Guerrero, for example, the dahlia (Dahlia hintonii). Of the amphibians, seven are endemic to the SMS biogeographic province, such as the pine tree frog (Charadrahyla pinorum) and another seven species are endemic to the state of Guerrero, for example, the large small salamander (Thorius grandis). Of the reptiles, 13 are endemic to the SMS biogeographic province, such as the mountain nauyaca of Guerrero (Mixcoatlus barbouri), and five are endemic to the state of Guerrero, for example, the poppy snail (Tropidodipsas papavericola). Of the mammals, two are endemic to the SMS biogeographic province, such as the shrew (Cryptotis goldmani) and one is endemic to the state of Guerrero, such as the giant Guerrero mouse (Megadontomys thomasi).

Genetic Diversity

The purpose of the PA is to promote the preservation of genetic diversity through the sustainable management of ecosystems and their elements; the protection of their natural environments; as well as to promote actions that increase habitat conditions that favor wildlife.

Ecosystem Functions and Services

It has three core zones, which have unique conservation characteristics that make them habitat for important species and reservoirs for carbon sequestration, water supply, reproduction of endemic species, and soil conservation. Other relevant ecosystem services include aesthetic and cultural value, climate regulation, hydrological regulation, timber and fuel production, and oxygen production, among others.

Ecological Connectivity

The Sierra Madre del Sur in the state of Guerrero serves as a biological corridor for several mammal species, allowing genetic exchange between populations that disperse between the states of Guerrero, Oaxaca and Chiapas, as well as those that migrate latitudinally from the Pacific coast to the Balsas basin. In the South Pacific Region, 18 biological corridors have been identified for the jaguar in Mexico. In the south, the Sierra de Tecuani BR is part of the jaguar biological corridors 20. Michoacán-Petatlán and 21. On the Balsas side, it is part of the 23. Michoacán-Iguala corridor.

Cultural and Social Value

The Sierra de Tecuani has an important aesthetic and cultural value. The 18 ejidos and communities that are part of this PA are inserted in the socio-demographic context of the Sierra de Guerrero region. The communities express diverse beliefs, customs and traditions in their daily practices that make them a true cultural melting pot. Its inhabitants have different origins, mestizos and indigenous, with different economic activities.

The term tecuani is of Nahuatl origin and refers to the "man-eater", in allusion to the various species of felines identified in the area.

Vulnerability and Threats

Land-use change is one of the most significant problems. The expansion of avocado plantations and cattle ranching exert considerable pressure on the forests, as they involve the clearing of large areas, from the lowlands to the mesophilic mountain forests.  Both activities cause soil erosion, the elimination of native species, deforestation, contamination of water sources, and the generation of greenhouse gases. Forest fires are also another cause of the alteration of vegetation cover, in addition to timber extraction.

Another problem is the high levels of marginalization and social backwardness in some of the communities within the PA.

# ANNEX k: alignment of MEx30x30 with the enbiomex

Mexico is part of a select group of 17 countries recognized as megadiverse. It stands out for its cultural diversity, intrinsically related to its biodiversity. MEx30x30 will directly contribute to global environmental and social benefits through the conservation and sustainable use of natural resources in the country. It integrates coherently and complementarily with the guiding principles, strategic axes, and activities outlined in Mexico's National Biodiversity Strategy (ENBioMex) and the 2016-2030 Action Plan. These documents aim to increase efforts that positively impact biodiversity and reduce the direct causes of its loss.

ENBioMex is a public policy instrument that, through its implementation, aims to achieve by 2030: the continuous provision of ecosystem services for the development of life and well-being; the fair and equitable distribution of benefits derived from biodiversity; a joint commitment of government and society to the conservation and sustainable use of biodiversity; and the maintenance of biodiversity and ecosystem functionality.

The following table provides a clear and concise overview of how key elements of ENBIOMEX converge with MEx30x30 components, thus strengthening the joint commitment to advancing global efforts for the use and conservation of biodiversity. For this purpose, it was identified that the strategic axes of ENBioMex compatible with MEx30x30 are those related to Knowledge, Conservation and restoration, Attention to pressure factors, and Mainstreaming and governance. Additionally, it displays the action areas defined within ENBioMex to address challenges and objectives related to the conservation and sustainable use of biodiversity in Mexico, as well as specific activities identified within the Strategy, highlighted for their importance and relevance to achieving established goals. Finally, it indicates how MEx30x30 aligns with the strategic axes, action areas, and activities defined in ENBIOMEX, emphasizing the coherence and complementarity between both approaches to advance the conservation and sustainable use of biodiversity in Mexico.

| ENBioMex Strategic Axes | ENBioMex Action Areas | ENBioMex Activities, underlined are | MEx30x30 aligned to |
| --- | --- | --- | --- |
| Strategic axis 1. Knowledge | 1.1 Generation, documentation and systematization of knowledge | Identify areas of important biological processes | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Conduct studies for the sustainable use and management of biodiversity. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 1.2 Traditional knowledge |  |  |
|  |  | Identify indicators of disturbance, degradation levels or conservation status of ecosystems.. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Rescue, compile, systematize and protect the traditional knowledge of indigenous peoples and local communities, particularly that of women. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Expand studies on the conservation status of species and populations of ecological, economic, social and cultural importance. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Expand and strengthen capacities for the development and use of tools, projects and programs that promote inclusive participation in the generation and compilation of information on biodiversity. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 1.4 Development of tools for access to information |  |  |
|  |  | Promote and encourage participatory and inclusive monitoring to support territorial self-management and community resource management | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
| Strategic axis 2. Conservation and restoration | 2.1 In situ conservation | Strengthen and consolidate protected area networks. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 2.3 Restoration of degraded ecosystems | Develop, strengthen and implement financial and economic mechanisms and instruments for the conservation and sustainable use of ecosystems and their services. | Component 1. Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |
|  |  | Promote and adapt successful traditional knowledge and practices that contribute to biodiversity conservation. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Implement and strengthen restoration programs with species of cultural and social importance. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
| Strategic axis 4. Attention to pressure factors | 4.1 Prevention and reduction of ecosystem degradation and loss. | - Develop and implement : - Permanent long-term monitoring programs to identify dynamics, habitat loss and deterioration in terrestrial and aquatic (marine, coastal and inland) ecosystems. - Programs to respond to ecosystem degradation and loss.Strategies to avoid and reduce the processes of degradation and loss of ecosystems, habitat and connectivity. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Strengthen the capacities of communities that have species at risk in order to promote sustainable use and prevent overexploitation. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Promote that the sustainable use of biodiversity leads to fair and equitable benefits for the communities safeguarding it, acknowledging their traditional knowledge. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Implement measures for the prevention, early detection, control and eradication of invasive species. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 4.2 Prevention, regulation and control to avoid over-exploitation of species. | Emphasize the most vulnerable ecosystems to climate change and anthropogenic pressures | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 4.3 Prevention, control and eradication of invasive species | Promote schemes and actions for the conservation, protection, and restoration of terrestrial and aquatic ecosystems and their environmental services as measures for climate change mitigation and adaptation, strengthening and ensuring the participation and empowerment of women. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 4.6 Reduction of biodiversity vulnerability to climate change | Strengthen, with a gender perspective, the necessary compensation mechanisms to mitigate the effects of climate change. | Component 1. Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. |
|  | 4.7 Land use planning and sustainable urban development | Promote territorial planning with a dynamic approach at different scales and in different environments that incorporates the conservation of biodiversity and ecosystem services as a central criterion. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
| Strategic axis 6. Mainstreaming and governance | 6.1 Harmonization and integration of the legal framework | Work with the different sectors for biodiversity mainstreaming. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 6.2 Consolidation of the institutional framework and public policies for integration and mainstreaming | Identify and address existing problems in the application of the current national regulatory framework in relation to the conservation and sustainable use of biodiversity. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Apply regulations regarding access to and ownership of benefits derived from biological resources by women. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Consider as priority issues access to genetic resources and equitable distribution of benefits | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Consider community norms, gender aspects, lack of access to land rights and problems of over-regulation. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  |  | Define the destination of resources for compensation and restoration and, based on this, develop and propose binding instruments that are harmonized with existing ones. | Component 1. Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |
|  |  | Develop portfolios of local initiatives (projects) and make them available to funding sources (financing, funds). | Component 1. Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. |
|  |  | Develop capacities of communities and/or local technical agencies to generate initiatives that contribute to biodiversity conservation. | Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories. |
|  | 6.3 Social participation for biodiversity governance | Strengthen the capacities of local communities to access and adequately apply financing for the conservation, sustainable use, recovery and restoration of biodiversity | Component 1. Strengthening CONANP to increase its budget and manage PAs and ADVCs effectively. Component 2. Mobilizing funding to cover the financial gap in PAs while the public funding reaches its target. Component 3. Strengthening recently established PAs, and ADVCs managed by IP&LCs to conserve, restore and sustainably manage territories |

The target for protected areas under improved management effectiveness is the total area of the 5 terrestrial protected areas in which the project will work to apply funding solutions and enhance management capacity.

The target for protected areas under improved management effectiveness is the total area of the marine protected areas in which the project will work to apply funding solutions and enhance management capacity, including 3 co-financed marine protected areas.

The target for Greenhouse gas emissions mitigated was calculated following the assumptions:

- Data from Hansen (2013) was obtained, which provides information on forest change patterns worldwide. Using this tool, deforestation was estimated for the period 2012 to 2022 in each of the selected ANP and ADVC for this analysis.

- Land use and vegetation were estimated for each polygon based on the Comprehensive Monitoring System for Biodiversity and Degradation in Protected Natural Areas PNUD (2018).

- The scenario for land use and vegetation was calculated for 20 years was estimated for each of the PA. To make this estimate, the set of models from the Integrated Valuation of Ecosystem Services and Tradeoffs (InVEST) software was used, based on the average observed deforestation rate.

- On the other hand, using the ex-ante carbon balance tool (EX-ACT) from the Food and Agriculture Organization of the United Nations (FAO), an estimate of the carbon reservoirs generated by each of the ecosystems present in the selected ANP was obtained.

- In the case of conservation:

  - It was assumed that the expected deforestation would convert forests and rainforest to agriculture in the absence of the project.

  - It was assumed that support for protected areas in Mexico can protect up to 23% of the trend deforestation, derived from the GEF impact evaluation study for protected areas in Mexico (Hansen et al., 2015).

The expected avoided emissions from deforestation is 5.7M TCO2eq

The target number of beneficiaries is the number of people resident within the PAs where MEx30x30 will be supported under Component 3, as documented by CONANP and the national population census.

The project will prepare a capacity assessment tool and establish a baseline in the first year of implementation to capture the following areas prioritized for capacity strengthening: 1) CONANP capacities to face climate change events ; 2) Mainstreaming gender, environmental and social safeguards; 3) Monitoring and measuring efficiency of ADVCs; and 4) Governance and participation.

Required funding refers to the funding identified after the financial gap estimation and the financial model assessed for the objectives agreed by the coalition for the first phase, which includes steps 5 and 6 of Component 2 process.

Long-term sustainable finance mechanism here refers to a single initiative that secures the funding necessary to meet specific conservation goals of the program over a defined long-term timeframe, to ensure the sustainability of the program.

Steps required before closing are: 1. Formation of a coalition of institutions; 2. Hiring and designation of long-term sustainable finance mechanism design team; 3. Development of a shared conservation vision; 4. Financial gap estimation; 5. Design of a conservation plan; 6. Design of a financial model or plan; 7. Design of the institutional arrangements for the adequate implementation of the initiative; 8. Assessment and development of domestic mechanisms for sustainable financing (through Component 1); 9. Design and implementation of a communications strategy.

Management effectiveness of protected areas is measured by CONANP using the “i-effectiveness” tool, similar to METT. Management effectiveness of protected areas is measured by CONANP using the “i-effectiveness” tool, similar to METT. The tool assesses 48 indicators in 5 Components (Management; Context & Planning; Administration & Finance; Uses & Benefits; and Governance & Social Participation); 30 of these indicators are shared with the METT. PAs are then rated on a 100-point scale as Outstanding (84-100); Highly Effective (68-83); Partially Effective (52-67); Ineffective (36-51); or Insufficient Information (0-35).

Each POA typically defines five principal Outputs to be achieved through the types of activities listed above, with at least five indicators and corresponding targets. Examples of indicators used in POAs include:

- Number of people who adopt better sustainable practices; number of people who participate in training;

- Number of citizen participation forums strengthened; number of partnerships between key stakeholders for the conservation of natural resources;

- Number of hectares implementing restoration processes; number of hectares under sustainable management activities such as agroforestry or sustainable livestock farming; number of hectares protected and/or maintained as biological corridors;

- Number of monitoring or management actions implemented for protected and endangered species.

"Established or strengthened emergency fund" refers to a specific financial mechanism created or strengthened for the purpose of providing immediate and flexible financial resources in crisis or emergency situations.

“Ejidos” and “comunidades” are communal land ownership systems, legally recognized under the Agrarian Law. In Mexico, Comunidades (or ―agrarian communities) are long-standing rural population centers that have been given formal ownership of their traditional or customary lands. Ejido refers to a portion of land that has been titled to a rural population nucleus that was formed more recently or relocated from another area. Both types of community property are governed by a similar structure, with an “Asamblea” of all “ejidatarios” or “comuneros”, a “Comisariado Ejidal” or “Comisariado de Bienes Comunales” and a “Consejo de Vigilancia”.

Prior PFPs such as Costa Rica Forever have utilized a “single close” approach, where all partners agree to meet a clear set of one-time prerequisites, such as committed funding, prior to implementation of fund activities (see Cabrera et al 2021).

Long-term sustainable finance mechanism here refers to a single initiative that secures important policy changes, and all funding necessary to meet specific conservation goals of the program over a defined long-term timeframe, to ensure the sustainability of the program.

During project implementation, it will be assessed if it will continue to operate as an endowment fund or if it will be converted to sinking fund and be part of the transition fund supported under Component 2. In both cases, the activities supported under Component 3 in the selected PAs will be implemented as described in this component and according to the results framework.

The Emergency fund is part of FANP, and currently operational in 70 PAs, under this project it will be expanded for the PAs supported under Component 3. The operational details of the Emergency Fund is described in FMCN operations manual (pp. 128).

Management effectiveness of protected areas is measured by CONANP using the “i-effectiveness” tool, similar to METT. The tool assesses 48 indicators in 5 Components (Management; Context & Planning; Administration & Finance; Uses & Benefits; and Governance & Social Participation); 30 of these indicators are shared with the METT. PAs are then rated on a 100 point scale as Outstanding (84-100); Highly Effective (68-83); Partially Effective (52-67); Ineffective (36-51); or Insufficient Information (0-35).

In addition to the Monitoring and Evaluation Coordinator, the project will be supported by a co-financed Safeguards Officer hosted at FMCN Conservation Unit

Note: Make this into a “pop-up” which appears only if PPG was selected, and if amount requested is above limits, they have to justify it

This Objective is aligned with GBFF targets and responds to the National Biodiversity Strategy and Action Plan.

The target for protected areas under improved management effectiveness is the total area of the 5 terrestrial protected areas in which the project will work to apply funding solutions and enhance management capacity.

The target for protected areas under improved management effectiveness is the total area of the marine protected areas in which the project will work to apply funding solutions and enhance management capacity, including three co-financed areas.

- Data from Hansen (2013) was obtained, which provides information on forest change patterns worldwide. Using this tool, deforestation was estimated for the period 2012 to 2022 in each of the selected ANP and ADVC for this analysis.

- Land use and vegetation were estimated for each polygon based on the Comprehensive Monitoring System for Biodiversity and Degradation in Protected Natural Areas PNUD (2018).

- The scenario for land use and vegetation was calculated for 20 years was estimated for each of the ANP. To make this estimate, the set of models from the Integrated Valuation of Ecosystem Services and Tradeoffs (InVEST) software was used, based on the average observed deforestation rate.

- On the other hand, using the ex-ante carbon balance tool (EX-ACT) from the Food and Agriculture Organization of the United Nations (FAO), an estimate of the carbon reservoirs generated by each of the ecosystems present in the selected ANP was obtained.

- Once the aforementioned data was obtained, the amount of carbon that would be lost if the same patterns of forest cover loss observed between 2012 and 2022 continue was calculated using the InVEST tool, assuming the trend will continue in the absence of the project.

- In the case of conservation:

  - It was assumed that the expected deforestation would convert forests and rainforest to agriculture in the absence of the project.

  - It was assumed that support for protected areas in Mexico can protect up to 23% of the trend deforestation, derived from the GEF impact evaluation study for protected areas in Mexico (Hansen et al., 2015).

The target number of beneficiaries is the number of people resident within the PAs where MEx30x30 will be supported under Component 3, as documented by CONANP and the national population census.

Early in the first year of implementation CONANP and FMCN will develop a refined analysis of the current financing gap; this analysis will include determination of the baseline budget shortfall for this indicator.

The project will prepare a capacity assessment tool and establish a baseline in the first year of implementation to capture the following areas prioritized for capacity strengthening: 1) CONANP capacities to face climate change events ; 2) Mainstreaming gender, environmental and social safeguards; 3) Monitoring and measuring efficiency of ADVCs; and 4) Governance and participation.

Required funding refers to the funding identified after the financial gap estimation and the financial model assessed for the objectives agreed by the coalition for the first phase, which includes steps 5 and 6 of Component 2 process.

Long-term sustainable finance mechanism here refers to a single initiative that secures the funding necessary to meet specific conservation goals of the program over a defined long-term timeframe, to ensure the sustainability of the program.

Steps required before closing are: 1. Formation of a coalition of institutions; 2. Hiring and designation of long-term sustainable finance mechanism design team; 3. Development of a shared conservation vision; 4. Financial gap estimation; 5. Design of a conservation plan; 6. Design of a financial model or plan; 7. Design of the institutional arrangements for the adequate implementation of the initiative; 8. Assessment and development of domestic mechanisms for sustainable financing (through Component 1); 9. Design and implementation of a communications strategy.

Management effectiveness of protected areas is measured by CONANP using the “i-effectiveness” tool, similar to METT. Management effectiveness of protected areas is measured by CONANP using the “i-effectiveness” tool, similar to METT. The tool assesses 48 indicators in 5 Components (Management; Context & Planning; Administration & Finance; Uses & Benefits; and Governance & Social Participation); 30 of these indicators are shared with the METT. PAs are then rated on a 100-point scale as Outstanding (84-100); Highly Effective (68-83); Partially Effective (52-67); Ineffective (36-51); or Insufficient Information (0-35).

Each POA typically defines five principal Outputs to be achieved through the types of activities listed above, with at least five indicators and corresponding targets. Examples of indicators used in POAs include:

- Number of people who adopt better sustainable practices; number of people who participate in training;

- Number of citizen participation forums strengthened; number of partnerships between key stakeholders for the conservation of natural resources;

- Number of hectares implementing restoration processes; number of hectares under sustainable management activities such as agroforestry or sustainable livestock farming; number of hectares protected and/or maintained as biological corridors;

- Number of monitoring or management actions implemented for protected and endangered species.

" Emergency fund" refers to a specific financial mechanism existent under FANP that will be expanded under this project for PAs under Component 3 for the purpose of providing immediate and flexible financial resources in crisis or emergency situations.

This Results Framework will be aligned with the criteria of the FMCN manual and will be tracked using the Project Tracking System (SISEP).

Associated facilities are those that are not funded as part of the project, and that would not have been constructed or expanded if the project did not exist and without which the project would not be viable.

Critical Habitat means a Habitat with high Biodiversity value, including (i) Habitats of significant importance to Critically Endangered or Endangered species, as listed on the International Union for the Conservation of Nature (IUCN) Red List of threatened species or equivalent national approaches, (ii) Habitats of significant importance to endemic or restricted-range species, (iii) Habitats supporting globally or nationally significant concentrations of migratory or congregatory species, (iv) highly threatened or unique ecosystems, and (v) ecological functions or characteristics that are needed to maintain the viability of the Biodiversity values described in (i) to (iv).

According to CI Policy on Indigenous Peoples, “CI identifies indigenous peoples in specific geographic areas by the presence, in varying degrees, of: a) Close attachment to ancestral and traditional or customary territories and the natural resources in them; b) Customary social and political institutions; c) Economic systems oriented to subsistence production; d) An indigenous language, often different from the predominant language; and f) Self-identification and identification by others as members of a distinct cultural group”.

Cultural Heritage means both tangible and intangible cultural heritage, including movable or immovable objects, sites, structures, natural features and landscapes that have archaeological, paleontological, historical, architectural, religious, aesthetic, or other cultural significance, located in urban or rural settings, above ground, underground or under water; as well as practices, representations, expressions, knowledge, or skills – as well as the instruments, objects, artifacts and cultural spaces associated therewith – that communities, groups, and in some cases individuals, recognize as part of their heritage, as transmitted from generation to generation and constantly recreated by them in response to nature and a shared history

GEF Project implemented by PNUD.

Approved Safeguard plans are to be disclosed to stakeholders in a manner and form that they will understand and that is culturally appropriate. This may require translation of the document.

Although the proposal for Bajos del Norte has no direct connection with terrestrial communities because it is located 100% in maritime territory, it can be considered to influence two municipalities.

Disadvantaged/Vulnerable refers to those who may be more likely to be adversely affected by the project impacts and/or more limited than others in their ability to take advantage of a project’s benefits. Such an individual/group is also more likely to be excluded from/unable to participate fully in the mainstream consultation process and as such may require specific measures and/or assistance to do so. This will take into account considerations relating to age, including the elderly and minors, and including in circumstances where they may be separated from their family, the community or other individuals upon which they depend.

Method of engagement can be face-to-face meeting, telephone call, workshop, consultation, survey, etc.

Ejidos, being traditional Mexican agrarian communities with communal land tenure, often have entrenched power structures that may marginalize women and vulnerable groups. The Project will implement multifaceted strategies in a comprehensive and culturally sensitive manner to promote gender inclusion, contributing to more equitable and sustainable development outcomes for all community members. Among them are:

* Conduct sensitization sessions to raise awareness about the importance of gender equality and inclusion in the Project, using culturally appropriate communication methods, such as local media and storytelling, to convey the message effectively.

* Provide targeted capacity-building initiatives to enhance the skills and knowledge of women and vulnerable groups within the community so the Project will empower these individuals with the necessary skills and confidence to participate actively in project activities.

* Implement measures to address barriers that hinder women and vulnerable groups from participating, such as providing childcare support.

* Create economic opportunities for women and vulnerable groups through the Project activities.

* Establish robust monitoring and evaluation mechanisms to track progress towards gender inclusion objectives throughout the project lifecycle. Regularly collect sex-disaggregated data and qualitative feedback to assess the impact of project interventions on women and vulnerable groups. Use this information to make informed decisions, adjust strategies as needed, and demonstrate accountability to stakeholders.

* Foster safe spaces for women and vulnerable groups to voice their opinions, concerns, and needs, feeling comfortable expressing themselves.

Approved Safeguard plans are to be disclosed to stakeholders in a manner and form that they will understand and that is culturally appropriate. This may require translation of the document.

Stakeholders may submit a grievance in their native language without the translation, but this may result in additional processing time.

In Mexico, the justices of the peace (jueces de paz) play a significant role in ejidos and community governments. They are typically community members appointed or elected as mediators in local disputes to reach mutually acceptable resolutions without formal legal proceedings. When mediation fails or disputes require a formal decision, justices of the peace may act as judges, issuing rulings based on customary laws, local regulations, or relevant statutes. These rulings are binding within the community. Justices of the peace may also serve as community representatives in interactions with external entities, such as government agencies or neighboring communities. It's important to note that the specific roles and authority of justices of the peace can vary between different ejidos and communities, as they often operate according to local customs and traditions. Additionally, while justices of the peace handle many types of disputes, certain serious criminal matters or disputes beyond their jurisdiction may be referred to higher-level courts or authorities within the formal legal system.