REQUEST FOR PROPOSALS (RFP)

Conservation International Foundation (‘CI’), the Contracting Entity, is issuing a Request for Proposals (RFP) for the procurement described below. This Request for Proposal (RFP) contains all the necessary information for interested Offerors.

- General information

| RFP number : | 004/2026 |  |
| --- | --- | --- |
| Name of Service/Good requested: | Providing research, capacity building and stakeholder engagement support to selected countries to establish fiscal instruments that unlock finance for protected areas under the Keystone Protected Areas Finance (KPAF) project |  |
| Funded by Program name and background: | Keystone Protected Areas Finance (KPAF) project. |  |
| Type of contract/purchase order : | ☐ Cost Reimbursement ☒ Fixed Price ☐ Not Specified |  |
| Submission instructions: | All correspondence, including submission of Proposals and Clarifications should be sent by email to ProcurementkenyaKE@conservation.org. The subject line of the email must reference the RFP name of this solicitation. All submissions are due to CI by 5.00PM EAT on 12th November 2026. |  |
| Validity of bid: | 90 days from the submission deadline. |  |
| Important Dates | RFP Issue Date | 23rd October 2028 |
|  | Clarification Requests Due | 29th October 2028 |
|  | Clarification to all Known bidders | 6th November 2026 |
|  | Proposal Submission Due | 12th November 2026 |
|  | Estimated Award Decision | 23th November 2026 |

- Procurement details

Description of the project

Conservation International (CI) is leading a four-year project whose primary goal is to mobilize finance at scale to support the financial sustainability of Africa's Keystone Protected Areas (KPAs). The project commenced in the second half of 2025 and will conclude at the end of 2029. This Keystone Protected Areas Finance (KPAF) work is being delivered through seven technical assistance facilities (TAFs) that represent seven important conservation finance modalities within the organization’s sustainable nature finance framework, as set out in Table 1. In their respective areas of focus, each TAF: (i) develops conservation finance capacity, and the conducive enabling environment, at the global, national and KPA level; and (ii) originates, develops, and executes conservation finance transactions, resulting in financial flows to KPAs during the project period. Table 1: KPAF Technical Assistance Facilities (TAFs) TAF; Examples of Financing Mechanisms. Payment for Ecosystem Services; Carbon markets, biodiversity credits, water payment schemes. Fiscal and Tax Incentives; Nature-taxes and tax breaks, tourism levies and park fees, concession policies. Structured Nature Finance; Debt-for-nature swaps, green bonds, blended finance, results-based instruments. Protected Area Finance; Conservation trust funds, own-source revenue retention, public-private finance partnerships. Nature-Based Tourism; Ecotourism, hunting and fishing concessions, wildlife experience revenue. Resource Mobilization; Multilateral grants, bilateral aid, corporate donors, philanthropic finance. Finance Plan Development; Supporting all TAF instruments. Within this project delivery structure, the Fiscal Instruments and Taxes (FIT) TAF works to develop and support policies that generate increased, sustainable and more effective fiscal revenue to KPAs and that incentivizes nature-positive behavior in target countries. Examples of potential instruments or policies under consideration by the TAF include earmarking of nature-taxes, ecological fiscal transfers, and reviews of concession and park revenue-retention policies. The FIT TAF will focus its efforts, from 2027 onward, on strategic engagement with stakeholders in four selected African countries. Countries will be selected where engagement is feasible and most likely to have a decisive impact on enhanced public funding and enabling conditions for in-country KPAs. The FIT TAF has conducted rapid assessments of a pool of countries, and four countries will be selected in October 2026 from the following five: - Kenya - Tanzania - Mozambique - Zambia - Uganda The FIT TAF requires consultancy services, from early 2027, as our work moves from the desk-based assessment phase to focused engagement in the selected countries.

Definition of the goods or services required with detailed specifications

## Objectives The objective of FIT in-country engagement in each of the four countries is to: - Undertake political economy and stakeholder mapping - Engage government and other key stakeholders - Identify specific priority fiscal instruments that are feasible and have high potential impact in a national context - Draft initial policy briefs for each country, setting out prospective fiscal and policy instrument pathways for improved KPA financing - Prepare finalized policy briefs that integrate government and stakeholder perspectives - Strategically disseminate policy briefs and engage government and other stakeholders through workshops, technical consultations and other engagements so as to generate specific fiscal pathways for adoption - Identify and engage policy champions and other policy-shapers leading to some or all these fiscal pathways being adopted

- Offeror requirements: The below listed criteria represent the minimum requirements for all offerors responding to the RFP.

- Click or tap here to enter text.

- Submission requirements: Proposals will be considered complete if they include all these items:

| Technical Proposal | ☒ |
| --- | --- |
| Cost Proposal | ☒ |
| Signed Offeror Representation of Transparency, Integrity, Environmental and Social Responsibility | ☒ |
| Other: | ☒ |

This RFP does not obligate CI to execute a contract, nor does it commit CI to pay any costs incurred in the preparation or submission of the proposals. Furthermore, CI reserves the right to reject any and all offers, if such action is considered to be in the best interest of CI.

Technical Proposal

| Part 1: Technical Approach, Methodology and Detailed Work Plan. | Understanding of the assignment (1-2 pages) A concise statement demonstrating your understanding of the objectives, scope, and key challenges of this engagement Proposed approach (1-2 pages) Indicate how you will approach key deliverables, especially identifying and obtaining key documentation, the mapping of stakeholders and the political economy, workshop convening and facilitating access to key stakeholders Ability to work in multiple African jurisdictions (1-2 pages) 1) indication of where you currently have an in-country presence, the nature, scope and duration of your presence 2) indication of your ability to establish an in-country presence in countries where you do not have a country presence at the moment and the approach you will follow in such cases. |
| --- | --- |
| Part 2: Relevant experience and skills management, Key Personnel, and Staffing Plan. | 2-3 pages) Examples of comparable assignments, including: client, geography, scope, outcomes, and challenges faced. Team structure and CVs Names, roles, and short CVs for all proposed team members |
| Part 3: Financial Proposal | - Proposals should be submitted on a time-based (FTE-equivalent) remuneration basis, taking into account the deliverables set out above, and setting out the FTE cost basis for each role, broken down by seniority level. - The financial proposal should assume work in four African countries and should provide both aggregate costs, and per-country costs. - Assumptions underlying the financial proposal should be clearly set out in narrative form, including assumptions around cost-differences between countries. The financial proposal may, but does not have to, distinguish between higher and lower cost jurisdictions or a similar cost-projection device. - The financial proposal should demonstrate a sound understanding of cost-drivers and assumptions across multiple African jurisdictions given that a final country selection will be made in November 2026. - The financial proposal should be shared in a separate document from the technical proposal - The proposed payment for 1st deliverable of inception report should not exceed 10% of consultancy fees. Please note that the upper limit for the consultancy cost is USD 65,000 inclusive of time, travel costs and taxes. |

Cost Proposal

- The cost proposal is used to determine which proposals are the most advantageous and serves as a basis of negotiation for the award of a contract.

- The cost proposal must be all-inclusive of profit, fees, or taxes.

- Additional costs cannot be included after award, and revisions to proposed costs may not be made after submission unless expressly requested by CI should the offeror's proposal be accepted.

- Offerors must provide a detailed budget showing major expense line items. Offers must show unit prices, quantities, and total price. All items, services, etc. must be clearly labeled and included in the total offered price.

- All cost information must be expressed in USD.

- The cost shall also include a budget narrative that explains the basis for the estimate of every cost element or line item.

- Supporting information must be provided in sufficient detail to allow for a complete analysis of each cost element or line item.

- CI reserves the right to request additional cost information if the evaluation committee has concerns about the reasonableness or completeness of an Offeror’s cost proposal.

- If selected, the Offeror shall use its best efforts to minimize the financing of any taxes on goods and services, or the importation, manufacture, procurement, or supply thereof.   If the Offeror is eligible to apply for refunds on taxes paid, the Offeror shall do so.  Any tax savings should be reflected in the total cost.

- Scope of Work, Deliverables, and Deliverables Schedule

Scope of Work

The consultancy services the FIT TAF requires will support the attainment of the above objectives; the consultants will specifically provide support in: - Identifying and obtaining country policy, fiscal, KPA and related information that is crucial to correctly identifying priority fiscal instruments - Mapping stakeholders and the political economy of the country - Strategically connecting the TAF with key decisionmakers and stakeholders - Supporting stakeholder engagements (workshops, meetings) to identify high potential fiscal instruments - Providing inputs, additional perspectives and recommendations on the draft policy briefs, as well as strategically oriented feedback on these briefs - Supporting the strategic dissemination of the draft policy briefs - Identifying and securing meetings with key policy makers and other stakeholders to engage around the briefs and providing feedback on the final drafts which arise out of these engagements - Supporting the strategic dissemination of the policy briefs, building capacity and engaging government and other stakeholders so as to generate specific fiscal pathways for adoption - Identifying policy champions and facilitating their engagement leading to some or all these fiscal pathways being adopted

Deliverables & Deliverables Schedule

|  | Activity | Due Date | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| 1 | Compilation of work plan, following consultation with CI | Month 1 | Consultant submits draft one-year work plan to CI, submits final work plan to CI after feedback | CI feedback on draft inception workplan is integrated into final inception workplan which is approved and accepted by CI. |
| 2 | Compilation of key country (4) document list | Month 2 | Consultant submits draft key documents list per country; discussion with CI leading to final list per country | CI feedback on initial key country documents lists is integrated into final country document lists which are approved and accepted by CI. |
| 3 | Key country documents collected, collated, submitted. | Month 3 | Consultant obtains and presents key documents per country to CI | CI’s approval and acceptance of documents submitted that align with document list, in format and/or on platform requested by CI |
| 4 | Compilation of stakeholder mapping report with key stakeholders identified | Month 4 | Consultant submits stakeholder mapping report to CI, including priority stakeholders for CI to engage | CI’s approval and acceptance of stakeholder mapping report including key stakeholders identified |
| 5 | Attend workshops, facilitate selected sessions, support attendance of key stakeholders | Month 4-6 | Country workshops (2 per country) convened and conducted by CI to identify priority fiscal instruments, consultants to attend, facilitate some sessions, help ensure strategically important stakeholders attend | Workshops attended, selected sessions attended, key stakeholders attended. |
| 6 | Provide feedback on draft country policy briefs | Month 8 | Consultants provide feedback, insights into draft country policy briefs prepared by CI for the selected countries | CI’s approval and acceptance of feedback, whether through a report or verbally or by other means as agreed and set out in the inception workplan. |
| 7 | Facilitate access to strategic players for policy brief engagement | Month 8-12 | Consultants facilitate access to strategic players to engage on draft policy briefs, at least 4 per country | CI’s approval and acceptance of access actions to facilitate access to 4 or more strategic players per country for draft policy brief engagement |
| 8 | Provide final insights into policy briefs | Month 11-12 | Feeback, insights into revised country policy briefs prepared by CI for selected countries in the form of a 3–5-page report per country | CI approval and acceptance of policy brief reports for each country policy brief. |

- Evaluation: An award will be made to the Offeror whose proposal is determined to be responsive to this solicitation document, meets the eligibility criteria stated in this RFP, meets the technical capability requirements, and is determined to represent the most advantageous to CI.

| Evaluation Criteria | Total Possible Points |
| --- | --- |
| Technical Proposal |  |
| Part 1 - Technical Approach, Methodology and Detailed Work Plan |  |
| Understanding of the Assignment. Does the proposal clearly explain, understand and respond to the objectives of the project as stated in the Scope of Work? | 25 |
| Proposed Approach. Does the proposed program approach and detailed activities and timeline fulfill the requirements of executing the Scope of Work effectively and efficiently? | 25 |
| Ability to work in multiple African jurisdictions. Does the proposal demonstrate the Offeror’s knowledge related to technical sectors required by the Scope of Work? | 15 |
| Part 2- Management, Key Personnel, and Staffing Plan |  |
| Relevant Experience and Skills/Personnel Qualifications – Do the proposed team members have necessary experience and capabilities to carry out the Scope of Work? Company Background and Experience – Does the company have experience relevant to the project Scope of Work? | 20 |
| Cost Proposal |  |
| Cost: Budget narrative clearly demonstrates the basis and reasonability of proposed costs | 15 |

- Important Information

| Currency | Price must be quoted in USD. CI reserves the right to determine upon seeing the bids which components of pricing should be used as the basis of comparison between proposals. |
| --- | --- |
| Resulting Award | CI reserves the right to issue an award with no further discussion, or to modify the award type. Issuance of this RFP in no way obligates CI to award a contract, nor does it commit CI to pay any costs incurred by the bidder in preparing and submitting the proposal. CI reserves the right to enter negotiations about price and terms as required. |
| Confidentiality | All proprietary information provided by the bidder shall be treated as confidential and will not be shared with potential or actual applicants during the solicitation process. This includes but is not limited to price proposals, cost proposals and technical proposals. CI may, but is not obliged to, post procurement awards on its public website after the solicitation process has concluded, and the contract has been awarded. CI’s evaluation results are confidential and applicant scoring will not be shared among bidders. |
| Code of Conduct | The Code of Conduct reflects CI’s commitment to ethical behavior and decision-making, grounded in CI’s core values and mission to protect nature for the benefit of all. The Code of Conduct applies to CI staff, as well as grantees, contractors, suppliers, consultants and their employees (collectively, “Delivery Partners”). The full Code of Conduct is herein attached. Delivery Partners are expected to review and adhere to the principles outlined in the Code of Conduct. Delivery Partners may report potential violations of our Code, policies or applicable laws and regulations to the CI Ethics Hotline at www.ci.ethicspoint.com. Grievances related to Code of Conduct violations will be addressed in accordance with the grievance mechanism required as an integral part of the Environmental and Social Safeguards Standards (https://cdn.sanity.io/media-libraries/mlmEWUxEY7eQ/files/containers/344hUx1SD9kzYOnGM6kmadJINVx/ci-gef-gcf-esmf-version-7.pdf). |

Offeror Representation of Transparency, Integrity, Environmental and Social Responsibility

All Offerors are expected to exercise the highest standards of conduct in preparing, submitting and if selected, eventually carrying out the specified work in accordance with CI’s Code of Conduct. CI’s Code of Conduct provides guidance to CI employees, service providers, experts, interns, and volunteers in living CI’s core values, and outlines minimum standards for ethical conduct which all parties must adhere to. Any violations of the Code of Conduct should be reported to CI via its Ethics Hotline at www.ci.ethicspoint.com.

CI relies on the personal integrity, good judgment and common sense of all third parties acting on behalf, or providing services to the organization, to deal with issues not expressly addressed by the Code or as noted below.

- With respect to CI’s Code of Conduct, we certify:

  - We understand and accept that CI, its contractual partners, grantees and other parties with whom we work are expected to commit to the highest standards of Transparency, Fairness, and Integrity in procurement.

- With respect to social and environmental standards, we certify:

  - We are committed to high standards of ethics and integrity and compliance with all applicable laws across our operations, including prohibition of actions that facilitate trafficking in persons, child labor, forced labor, sexual abuse, exploitation or harassment. We respect internationally proclaimed human rights and take no action that contributes to the infringement of human rights. We protect those who are most vulnerable to infringements of their rights and the ecosystems that sustain them.

  - We fully respect and enforce the environmental and social standards recognized by the international community, including the fundamental conventions of International Labour Organization (ILO) and international conventions for the protection of the environment, in line with the laws and regulations applicable to the country where the contract is to be performed.

- With respect to our eligibility and professional conduct, we certify:

  - We are not and none of our affiliates [members, employees, contractors, subcontractors, and consultants] are in a state of bankruptcy, liquidation, legal settlement, termination of activity, or guilty of grave professional misconduct as determined by a regulatory body responsible for licensing and/or regulating the offeror’s business

  - We have not and will not engage in criminal or fraudulent acts. By a final judgment, we were not convicted in the last five years for offenses such as fraud or corruption, money laundering or professional misconduct.

  - We are/were not involved in writing or recommending the scope of work for this solicitation document.

  - We have not engaged in any collusion or price fixing with other offerors.

  - We have not made promises, offers, or grants, directly or indirectly to any CI employees involved in this procurement, or to any government official in relation to the contract to be performed, with the intention of unduly influencing a decision or receiving an improper advantage.

  - We have taken no action, nor will we take any action to limit or restrict access of other companies, organizations or individuals to participate in the competitive bidding process launched by CI.

  - We have fulfilled our obligations relating to the payment of social security contributions or taxes in accordance with the legal provisions of the country where the contract is to be performed.

  - We have not provided, and will take all reasonable steps to ensure that we do not and will not knowingly provide, material support or resources to any individual or entity that commits, attempts to commit, advocates, facilitates, or participates in terrorist acts, or has committed, attempted to commit, facilitate, or participated in terrorist acts, and we are compliant with all applicable Counter-Terrorist Financing and Anti-Money Laundering laws (including  USA Patriot Act and U.S. Executive Order 13224).

  - We certify that neither we nor our directors, officers, key employees or beneficial owners are included in any list of financial or economic sanctions, debarment or suspension adopted by the United States, United Nations, the European Union, the World Bank, or General Services Administration’s List of Parties Excluded from Federal Procurement or Non-procurement programs in accordance with E.O.s 12549 and 12689, “Debarment and Suspension”.

I CERTIFY THAT THE INFORMATION PROVIDED ABOVE IS COMPLETE AND CORRECT TO THE BEST OF MY KNOWLEDGE.

| Offeror Signature |  |
| --- | --- |
| Name & Title |  |
| Date |  |