| Project Overview & Consultation Strategy |  |
| --- | --- |
| Project | Training Product Review – Home Energy Efficiency and Sustainability |
| JSC Remit | BuildSkills Australia (BSA) |
| The Workforce Challenge | BuildSkills has consulted with key stakeholders who have confirmed that the current qualification no longer reflects emerging policy settings, the shift toward existing-home assessments, and the skills required of contemporary assessors. Their feedback has directly informed the scope of this review. This project will review CPP41126 Certificate IV in Home Energy Efficiency and Sustainability, to ensure the qualification is informed by industry needs and describes industry-relevant and future-oriented knowledge and skills that are adaptable to structural change. This qualification is primarily used to support the occupational outcome of Home Energy Assessor. BuildSkills Australia has been informed that there is an established workforce of over 800 energy assessors delivering home energy ratings for Australian homes. These (ratings) assessments are being conducted under government schemes such as the Australian Capital Territory (ACT) Energy Efficiency Rating (EER) Disclosure Scheme, and the Nationwide House Energy Rating Scheme (NatHERS). Historically and currently, the majority of home energy assessments have been provided through NatHERS. NatHERS is the preferred pathway to demonstrate compliance with the energy efficiency requirements of the national construction code, used for over 90% of new home approvals across Australia. The Australian Government is now expanding NatHERS to include assessments for existing homes. The Scheme has set additional minimum training requirements for Home Energy Rating assessors. This has expanded to include a data collector role and set minimum training requirements for this role. NatHERS has been endorsed by Australian governments as the assessment process for single dwellings and apartments for the disclosure of home energy ratings at the point of sale and/or lease under the Home Energy Ratings Disclosure Framework Version 2, published in 2024 by the Energy and Climate Change Ministerial Council. Home energy ratings are not yet mandatory nationwide, only the Australian Capital Territory currently requires disclosure. This framework sets policy parameters for jurisdictions to implement home energy rating disclosure schemes. If implemented nationally, mandatory disclosure at the point of sale and lease could result in up to 700,000 NatHERS assessments of existing homes each year, further increasing workforce need and placing pressure on the training system to deliver consistent assessor capability. Industry feedback indicates that CPP41126 Certificate IV requires a review to ensure it meets the needs of the changing assessor role and accurately reflects the necessary skills and knowledge. The outcome of this project will support training as the demand for assessors rises due to the adoption of mandatory home energy rating disclosure schemes by states and territories. |
| Deliverables | The intention of the project is to review CPP41126 Certificate IV in Home Energy Efficiency and Sustainability, to ensure it is fit for purpose and reflects the skills and knowledge requirements of the Energy Assessor occupation. The updated training products will help support training as demand for assessors increases in line with the state and territory adoption of the Home Energy Rating Disclosure Framework. The project will: - Work broadly with the Home Energy Efficiency and Sustainability stakeholder network to establish a fit for purpose Energy Assessors Skills and Knowledge Profile (SK Profile) against which the Deliverables can be assessed. - Conduct an analysis of the existing CPP41126 Certificate IV in Home Energy Efficiency and Sustainability and the SK Profile - Identify whether suitable training products are required to meet the requirements of the SK Profile, and Home Energy Efficiency and Sustainability stakeholder network - Develop suitable training products against the SK Profile. |
| Timeframes | Project commencement date:; 22 June 2026. Proposed end date:; 29 October 2027. Training Product Priority:; Complex. |
| Consultation Strategy Consultation Process Please be aware that any dates mentioned in the Consultation Process may change as the project progresses and this document may be updated on the website to reflect those changes. Contacts | Stakeholders BuildSkills will engage the following stakeholders through the training product development process: Organisation; Stakeholder type; Footprint. Department of Climate Change, Energy the Environment and Water; The Commonwealth, state and territory governments (including licensing and regulatory bodies); National. Energy Assessors; Learners and other interested stakeholders as appropriate; National. Real Estate Institute of Australia; Employers and their representatives/peak bodies; National. Building Designers Association of Australia; Employers and their representatives/peak bodies; National. Design Matters; Employers and their representatives/peak bodies; National. Housing Energy Raters Association; Employers and their representatives/peak bodies; National. Australian Property Institute; Employers and their representatives/peak bodies; National. Australian Sustainable Built Environment Council; Employers and their representatives/peak bodies; National. United Workers Union; Employees and their representatives/unions; National. State Training Authorities (STAs); The Commonwealth, State and Territory Governments; Per state. Skills Insight; Other Jobs and Skills Councils; National. Northern Victoria Institute of TAFE (3097); Registered Training Organisation; Victoria. Education In Building Pty Ltd (32418); Registered Training Organisation; Queensland. Transformed Pty Ltd (88152); Registered Training Organisation; ACT / NSW. Chisholm Institute (0260); Registered Training Organisation; Victoria. Academia of Trade (45739); Registered Training Organisation; National. Consultation Approach BuildSkills will conduct consultations which are: - Purposeful: Set a clear understanding of what is to be achieved - Inclusive: Identify relevant stakeholders and make it easy for them to engage - Timely: Involve stakeholders early in the process and agree on when and how to engage - Transparent: Be open, honest and set clear expectations - Respectful: Acknowledge the expertise, perspectives and needs of stakeholders. If one or more stakeholders disagree about a proposed solution, including the structure and/or content of any proposed training products, BuildSkills will work to resolve these disputes before submission to the Assurance Body. Step 1 – Initial development Commencement notification – A notice will be issued on the BuildSkills website to alert stakeholders that training product development work is commencing. Meetings – BuildSkills will undertake virtual, face-to-face and email consultations with a broad network of stakeholders. Working Groups – Should deliverables require targeted consultation, BuildSkills will arrange a working group with appropriate Subject Matter Experts (SMEs). Technical Committee meetings – A Technical Committee will be established to provide technical advice and provide training product validation. The first meeting is anticipated to take place in July - August 2026. State-based Roundtables – BuildSkills will gather key stakeholders across each state and territory to communicate project progress and consultation outcomes and seek targeted feedback to draft revised training package products. Step 2 – Public and government consultation Draft products – BuildSkills will upload draft revised training package products to the website for public and government consultation between December 2026 - February 2027. Supporting documents – BuildSkills will provide a detailed Summary of Changes document, and a supporting draft Companion Volume Implementation Guide (CVIG) to support the draft revised training package products. Webinar – BuildSkills will conduct an informative webinar for all stakeholders to explain the intention of the project and provide direction for the public and government consultation period. Feedback – BuildSkills will provide a webform for stakeholders to record feedback about the draft revised training package products and supporting documents. Step 3 – Incorporating feedback Final draft products – After consultations have ended, feedback will be collated, analysed and incorporated (as required) into a final version of any draft revised training package products. This process is planned to take place in March - May 2027. Additional consultation – BuildSkills will determine whether further consultation is required based on the feedback received. Step 4 – Senior Officials’ check Initial review – BuildSkills will submit any draft revised training package products and required supporting documents to the Commonwealth and State/Territory Senior Responsible Officers (SROs). This is planned to occur in June 2027. Step 5 – Finalisation and submission to Assurance Body Formal review –BuildSkills will submit the final draft revised training package products and the required supporting documentation to the Assurance Body. Submission publication – BuildSkills will publish the final submission and a Consultation Log and any other documents required by the Training Package Organising Framework (TPOF) on its website. This process is tentatively proposed for 30 July 2027. Steps 6 & 7 - Assurance Body Consideration and Skills Ministers’ Endorsement Evaluation & Endorsement – After the Assurance Body reviews the draft training package products and supporting documents they are supplied to the Skills Ministers’ members for endorsement. This process is planned to commence in August 2027 with a tentative endorsement date of 29 October 2027. Implementation Technical Committee notification – BuildSkills will notify the Technical Committee of the Skills Ministers decision. Public notification – A notice will be issued on the BuildSkills website to alert stakeholders of the Skills Ministers decision. Product publishing – If the training products are endorsed by the Commonwealth, BuildSkills will upload the endorsed versions and the Companion Volume Implementation Guide (CVIG) on the National Register (training.gov.au) within 10 business days of endorsement. Webinar – BuildSkills will deliver an Informative webinar for all stakeholders on the implementation plan of the endorsed training products. This process is tentatively anticipated to take place in November 2027. |
|  | Project Manager; Peter Miller. Phone; 0457 551 116. Email; pete.e.miller@gmail.com. Industry Engagement Lead; Paul Muenchow. Phone; (07) 3073 6159. Email; paulm@buildskills.com.au. |
| Technical Committee Sign-off | The Home Energy Efficiency and Sustainability Technical Committee has reviewed and contributed to this Consultation Strategy as required, their support was received on 03 September 2026. |