## A. LETTER
G&H additional requirements & PPAP content document.
G&H PPAP Requirements
Part number(s): | PPAP #.: PPAP(insert project number)
Issue: | PPAP Level: (insert level number from Control Plan)
Special Flow Down Requirements: Finished supplied surfaces must always be protected to prevent surface scratches/damage.
Dear Supplier, Further to submitted PO's, please find a copy of the G&H production part approval submission. This is an initial level 3 production part approval submission for the purpose of allowing Supplier to supply Production Parts. Yours Sincerely G&H Supplier Quality
Supplier Information:
* The PPAP processes detailed MUST be conducted by a G&H approved supplier.
* Upon completion of PPAP all processes MUST be approved by G&H before delivery.
The supplier on receipt of an official G&H order is obliged to submit a Production Part Approval Process pack. The elements that are required are detailed over the page and must be signed off by G&H at the completion of each gate. The PPAP MUST be completed during normal production lead time, considering gate approvals.

## B. G&H Requirements Flowdown
G&H PPAP Level Flow Down & Check List
Gate One Requirements
Section | Document | Description | Required Yes / No
A | Formal Letter Triggering APQP Requirements | Acknowledgement of this document and intention to satisfy its content. The supplier should submit a letter of acknowledgement of the PPAP requirements and their intention to submit all information as required.
B | G&H Specific Requirements | Acknowledgement of this document and intention to satisfy its content. The supplier should submit a letter of acknowledgement of the PPAP requirements and their intention to submit all information as required.
C. | G&H Control Plan – Pre-Production | A formal control plan generated at G&H detailing additional controls the supplier will need to incorporate into their manufacturing and quality control.
I. | Contract, Drawing & Specification Review. | Formal documented Contract, Drawing & Specification Review. The contract review should cover all aspects of the suppliers business, Commercial, Purchasing, Engineering, Manufacturing, Quality. Each section should be signed by the relevant department representative. All aspects of the part number being reviewed should be stated on the review, material, tooling, resource, special processes etc.
II. | Review of Design | Formal Review of Design to confirm intent of (drawing number) is achievable.
III. | Predicted Timing Plan | Detailed timing plan for the production of part number(s).
Gate Two Requirements
| Document | Description | Required Yes / No
IV. | Team Feasibility Commitment | Formal document showing all elements of the processes required to complete the purchase order, where all persons responsible for their processes sign to state they can meet the requirements of the drawing or specification.
V. | Production Quality & Inspection Planning | Identifies at which operation any critical features identified within the G&H PPAP requirements have been covered.
Gate Three Requirements
| Document | Description | Required Yes / No
VI. | Manufacturing Process Flow | A top level pictorial process flow for the draft manufacturing instructions.
VII. | Process Failure Modes Effects Analysis (PFMEA) | A PFMEA is used to analyse that adequate controls are in place against a known risk
VIII. | Measurement System Evaluation (MSE) | Evaluation is used for equipment used to measure critical features. All equipment used must be measured as capable for the feature it is measuring. Elements from the Facilities, Tools, Gauges and Special processes, section will indicate this requirement.
Gate Four Requirements
| Document | Description | Required Yes / No
IX. | Facilities, Tools & Gauges | The supplier is required to detail all facilities, tools, gauges and special processes, to be used to manufacture and test this part number.
X. | Final Manufacturing Process Instructions | Approved final manufacturing instructions.
XI. | Packing & Traveller Details | Packing should have relevant instructions approved and documented.
Gate Five Requirements
| Document | Description | Required Yes / No
XII. | Control Plan- Production | Final approved Control Plan to be held as master document for this part number. Note, this is a live document and will be reviewed as and when required, it may also be subject to change based on first pass yield results at test.
XIII. | Statistical Process Control | Any Key Characteristics as detailed in the Control Plan will need their results reporting to G&H. Note these features are under review, once a feature is shown capable it will be assessed for reduction in frequency.
XIV. | First Article Inspection Report | FAIR on approved piece part to be completed.
XV. | Product Quality Sign Off & Appearance Approval Report | Samples bought off and reviewed by G&H. The appearance report will detail the requirement for either physical attributes or colour. The supplier should complete the report as stated.
XVI. | G&H Sample Sign Off | G&H must be notified 7 days before completion of part and PPAP Documentation Pack to conduct on-site approval.
XVII. | Assent Database | Confirm upload of part number information into Assent Database.
XVIII. | Part Submission Warrant | This document is the top sheet for the PPAP and as such is a statement by the supplier that all the content is correct and will not change without prior approval from Gooch and Housego.

## C. G&H Quality Control Plan
Quality Control Plan
Gooch & Housego Site
Part Number |  |  |  | Quality Control Plan Number |  |  |  |  | Production Engineer
Part Name / Description |  |  |  | Engineering change level (Revision level) |  |  |  |  | Quality Engineer
Plan Date |  |  |  | Current Phase (e.g Pre-production, production)
Part/Process Number | Process Name/ Operation Description | Machine, Device, Jig, Tools | Characteristics |  |  | CTQ | Methods |  |  |  |  | Reaction Plan | Owner
|  |  | NO. | Product | Process |  | Product/Process Specification/ Tolerance | Evaluation/ Measurement Technique | Sample |  | Control Method
[9 empty] | SIZE | FREQ

## I. Contract, Drawing & Spec.
CONTRACT REVIEW DOCUMENT – NEW PART(S) / TRANSITIONED PART(S)
Supplier |  | Drg No |  | Iss No
Part No |  | Part Number
DEPARTMENT | ACTION |  | COMMENTS
Sales | Cross check the order against the quote
Check price, quantity and delivery status
Check Terms and conditions
Check specific customer requirements (Quality Terms & Conditions FOSF 1462)
PRINT / SIGN / DATE
Operations | Confirm part number and issue status. Notate comments box with number and issue
Confirm delivery / schedule requirements can be met
Establish shop working capacity and launch dates to match delivery
PRINT / SIGN / DATE :
Engineering / Manufacturing | Material Required on Drawing
Material status: Brought in condition _______________________________
Final condition ____________________
Are test pieces required?
Check, create and confirm:
BOM and existing manufacturing layout
Assign part / serial / batch no’s
Review technical capabilities / constraints
Review drawings, specifications, standards, condition of supply, and classification
Consider Drg legibility, component marking, sub-contract processes, packaging and labelling requirements
Assign mfg engineer for any programming / production requirements
Are any of the following items required for production :
Jigs -
Tools -
Fixtures –
PRINT / SIGN / DATE :
Purchasing | Check, create and confirm:
order materials
Confirm delivery with operations
Acknowledge order to customer
PRINT / SIGN / DATE :
Quality | Check, create and confirm:
Quality and technical requirements, specifications and standards
Customer & sub-contract approvals
FAIR Required - Yes
If No when was last FAIR Completed
APQP Required
Quality plans, source inspections
Release conditions, special gauging / measuring requirements (APQP)
Specific customer requirements (FOSF 1462, APQP)
General; ALL Departments | All / any risks identified
Detail what actions planned / taken to mitigate the risks identified
Are these actions acceptable to G&H and the Customer?
PRINT / SIGN / DATE :
Comments

## II. Review of Design
PPAP - Review of Design II
Customer |  | XXX
Project |  | XXX
Description |  | XXX
Cust Doc No. |  | XXX
Cust Doc Rev |  | XXX
Rev status |  | XXX
DOC ID (Drawing #) | Title (Drawing) | DESCRIPTION OF DIMENSION/REQUIREMENT | DRAWING REFERENCE (GRID REF) | COMPLIANCE | COMPLIANCE JUSTIFICATION | VERIFICATION CODE |  |  | VERIFICATION METHOD | COMMENTS
|  |  |  | C / PC / NC |  | I | T | C
T
Note on G11: Jon Taylor: C=Comply PC=Partial Compliance NC=Non-Compliance
Note on I11: Jon Taylor: Inspection method
Note on J11: Jon Taylor: Test report
Note on K11: Jon Taylor: Certify

## III. Predicted Timing Plan
Project Plan
| Project lead: | [5 empty] | Project start: | [7 empty] | 2025-07-02 | [13 empty] | Display week: | [6 empty] | 1
Project Team:
[7 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-06-30 to 2025-08-24
 | time axis 2025-06-30 to 2025-08-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Define goals | Gokce Aslan | 50% | 2024-01-22 | 2024-02-20 | 30 | bar: 2025-06-30 to 2025-07-29
| Conduct studies | Hayden Cook | 60% | 2024-02-20 | 2024-02-22 | 3
| Establish comms | Jens Martensson | 50% | 2024-02-22 | 2024-02-26 | 5
| Develop charter | Nuria Acevedo | 25% | 2024-02-26 | 2024-03-02 | 6
| Set up team | Olivia Wilson |  | 2024-02-21 | 2024-02-23 | 3
Planning and design
| Create schedule | Gokce Aslan | 50% | 2024-02-22 | 2024-02-26 | 5
| Identify deliverables | Hayden Cook | 50% | 2024-02-24 | 2024-02-29 | 6
| Develop budget | Jens Martensson |  | 2024-02-29 | 2024-03-03 | 4
| Define scope | Nuria Acevedo |  | 2024-02-29 | 2024-03-02 | 3
| Identify risks | Olivia Wilson |  | 2024-02-29 | 2024-03-03 | 4
Execution
| Execute tasks | Gokce Aslan | 50% | 2024-02-06 | 2024-02-11 | 6
| Monitor progress | Hayden Cook | 60% | 2024-02-12 | 2024-02-16 | 5
| Manage resources | Jens Martensson | 50% | 2024-02-17 | 2024-02-22 | 6
| Provide updates | Nuria Acevedo | 25% | 2024-02-23 | 2024-02-27 | 5
| Testing and validation | Olivia Wilson | 25% | 2024-02-17 | 2024-02-21 | 5
Evaluation
| Monitor progress | Gokce Aslan | 25% | 2024-02-08 | 2024-02-11 | 4
| Track expenses | Hayden Cook | 25% | 2024-02-11 | 2024-02-15 | 5
| Evaluate progress | Jens Martensson | 50% | 2024-02-16 | 2024-02-19 | 4
| Address risks | Nuria Acevedo | 60% | 2024-02-13 | 2024-02-16 | 4
| Gather feedback | Olivia Wilson | 50% | 2024-02-15 | 2024-02-20 | 6

## IV. Team Feasibility Commitment
Team Feasibility Commitment
Supplier |  |  | Part No |  | Part Name
Drg No |  |  | Iss No
Feasibility Considerations:
Our product quality planning team have considered the following questions, not intended to be all-inclusive in performing a feasibility evaluation. The drawings and/or specifications provided have been used as a basis for analysing the ability to meet all specified requirements. All “no” answers are supported with attached comments identifying our concerns and/or proposed changes to enable us to meet the specified requirements.
Yes | No | Considerations
Is product adequately defined to enable feasibility evaluation?
Can drawing Specifications be met (drawing notes)?
Can product be manufactured to tolerances specified on drawing?
Is there adequate capacity to produce product?
Does the design allow the use of efficient material handling techniques?
Yes | No | Can the product be manufactured without incurring any unusual:
Costs for capital equipment?
Costs for tooling?
Alternative manufacturing methods?
Is statistical process control required on product?
Is statistical process control presently used on similar products?
Yes | No | Where statistical process control is used on similar process:
Are the processes in control and stable?
Are the CPK’s greater than 1.33?
Conclusion:
| Feasible |  | Product can be produced as specified with no revisions
| Feasible |  | Changes recommended (see attached)
| Not Feasible |  | Design revision required to produce product within the specified requirements
Sign Off:
Team Member |  |  |  | Title |  | Date
Team Member |  |  |  | Title |  | Date
Team Member |  |  |  | Title |  | Date
Team Member |  |  |  | Title |  | Date

## V. Quality & Insp. Plan
Process / Inspection Flow Chart
Product Information
Product Name |  |  |  | Part Number
Product Program |  |  |  | Revision
Organisation Name |  |  |  | Issue Date
Organisation Location |  |  |  | Prepared By
Legend
| Operation | Transportation | Inspection |  | Delay | Storage
Operation or Event |  | Description of Operation or Event (Key characteristic) |  |  | Evaluation and Analysis Methods

## VI. Process Flow
Process Flow Diagram
Product Information
Product Name | [6 empty] | Part Number
Product Program | [6 empty] | Revision
Organisation Name | [6 empty] | Issue Date
Organisation Location | [6 empty] | Prepared By
Step | Manufacture | Move | Store | Inspect | Operation Description | Item # | Product and Process Characteristics | Item # | Control Methods

## VII. PFMEA
Potential Failure Mode and Effects Analysis (Process FMEA)
FMEA Number | [8 empty] | Date originated |  |  | Dates Revised |  | Revised by |  | Issue
Part Number
Part Name / Description
Team
Process Responsibility
Step | Process Function / Requirments | Potential Failure Mode | Potential Effect (s) of Failure | Sev | Class | Potential Cause(s) Mechanism (s) of Failure | Occur | Current Specified Process Controls |  |  | Recommendations |  |  | Action Results
[7 empty] | Occur | Current Process Controls (Prevention) | Detect | RPN | Recommended Actions | Responsibility | Planned Completion Date | Action Taken | Sev | Occ | Det | RPN
Note on N12: Responsibility Name of person responsible for ensuring countermeasure / improvement action implementation / completion.
Note on O12: Planned Completion Date Planned Completion Date of the action(s)

## VII. PFMEA LISTS
FMEA LISTS
SEVERITY SCALE
10 Hazardous - w/o warning
9 Hazardous - w/ warning
8 Very High
7 High
6 Moderate
5 Low
4 Very Low
3 Minor
2 Very Minor
1 None
OCCURENCE SCALE
10 >1 in 2
9 1 in 3
8 1 in 8
7 1 in 20
6 1 in 80
5 1 in 400
4 1 in 2,000
3 1 in 15,000
2 1 in 150,000
1 1 in 1,500,000
DETECTION SCALE
10 Absolute Uncertainty
9 Very Remote
8 Remote
7 Very Low
6 Low
5 Moderate
4 Moderately High
3 High
2 Very High
1 Almost Certain

## VIII. Gauge R&R
Gauge Repeatability & Reproducability Report Short Form Attribute Results
Part Number |  |  | Gage Name | Appraiser A
Part Name |  |  | Gage Number | Appraiser B
Characterisitic/Specification |  |  | Gage Type | Date Performed
| APPRAISER A |  |  |  | APPRAISER B
PART # | TRIAL #1 | TRIAL #2 |  | PART # | TRIAL #1 | TRIAL #2
1 |  |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
5 |  |  |  | 5
6 |  |  |  | 6
7 |  |  |  | 7
8 |  |  |  | 8
9 |  |  |  | 9
10 |  |  |  | 10
11 |  |  |  | 11
12 |  |  |  | 12
13 |  |  |  | 13
14 |  |  |  | 14
15 |  |  |  | 15
16 |  |  |  | 16
17 |  |  |  | 17
18 |  |  |  | 18
19 |  |  |  | 19
20 |  |  |  | 20
All measurement decisions agree?
Remarks
Yes Accept Gauge
No Reject Gauge

## IX. Tools & Gauges
List of Checking Aids
| MSA Required |  | Entered onto Calibration System
Equipment Used | Yes | No | Yes | No

## X. Process Instructions
PRODUCTION PART
APPROVAL PROCESS
Section X - Final Manufacturing Process Instructions
Supplier to submit their process instruction documents.

## XI. Packing Instructions
Packaging and Traveller Details
Supplier |  | Part No. |  |  | Part Name
Drawing No. |  | Iss No,
Op No. | Detail | [5 empty] | Referenced on Layout
Picture Sketch or Diagram(s)
Submitted by (Print and Sign Name)
Reviewed by (Print and Sign Name) |  |  | Approved | Rejected |  | Comments

## XII. Quality Control Plan
Quality Control Plan
Gooch & Housego Site
Part Number |  |  |  | Quality Control Plan Number |  |  |  |  | Production Engineer
Part Name / Description |  |  |  | Engineering change level (Revision level) |  |  |  |  | Quality Engineer
Plan Date |  |  |  | Current Phase (e.g Pre-production, production)
Part/Process Number | Process Name/ Operation Description | Machine, Device, Jig, Tools | Characteristics |  |  | CTQ | Methods |  |  |  |  | Reaction Plan | Owner
|  |  | NO. | Product | Process |  | Product/Process Specification/ Tolerance | Evaluation/ Measurement Technique | Sample |  | Control Method
[9 empty] | SIZE | FREQ

## XIII. SPC
Initial Process Study Summary Sheet
(G&H will accept Mini tab or equivalent)
Acceptance Criteria for Initial Study
Results | Interpretation
Index > 1.67 | The process currently meets the acceptance criteria.
1.33 ≤ Index ≤ 1.67 | The process may be acceptable. Contact the authorised customer representative for a review of the study results.
Index < 1.33 | The process does not currently meet the acceptance criteria. Contact the authorised customer representative for a review of the study results.
Unstable Processes
Depending on the nature of the instability, an unstable process may not meet customer requirements. The organisation shall identify, evaluate and, wherever possible, eliminate special causes of variation prior to PPAP submission. The organisation shall notify the authorised customer representative of any unstable processes that exist and shall submit a corrective action plan to the customer prior to any submission.
Process With One-Sided Specifications or Non-Normal Distributions
The organisation shall determine with the authorised customer representative alternative acceptance criteria for processes with one-sided specifications or non-normal distributions.
Actions To Be Taken When Acceptance Criteria Are Not Satisfied
The organisation shall contact the authorised customer representative if the acceptance criteria cannot be attained by the required PPAP submission date. The organisation shall submit to the authorised customer representative for approval a corrective action plan and a modified Control Plan normally providing for 100% inspection. Variation reduction efforts shall continue until the acceptance criteria are met, or until customer approval is received.

## XIV. AS9102 FAIR
PRODUCTION PART
APPROVAL PROCESS
Section XIV - AS9102 FAIR
See Tabs:
9102RevB_1.1
9102RevB_2.1
9102RevB_3 Gauge.1

## 9102RevB_1.1
AS9102B FORM 1 - PART NUMBER ACCOUNTABILITY
1. Part Number: | 2. Part Name: | 3. Serial Number: | 4. FAIR Number:
5. Part Revision Level: | 6. Drawing Number: | 7. Drawing Revision Level: | 8. Additional Changes:
9. Manufacturing Process Reference: | 10. Organization Name: | 11. Supplier Code: | 12. P.O. Number:
X
13. Detail FAI | 14. Full FAI | Partial FAI:
Baseline Part Number (Including revision level):
Assembly FAI
Reason for Partial FAI:
a) if above part number is a detail part only, go to Field 19
b) if above part number is an assembly, go to the "INDEX" section below
INDEX of part numbers or sub-assembly numbers required to make the assembly noted above.
15. Part Number: | 16. Part Name: | 17. Part Serial Number: | 18. FAIR Number:
|  |  |  | 9 | ( R) Required | 10 | ( CR) Conditionally Req | 6 | (O) Optional
|  |  |  | 1 | 1. Part Number: | 1 | 3. Serial Number | 1 | 11. Supplier Code
|  |  |  | 1 | 2. Part Name: | 1 | 4. FAIR Number | 1 | 12. P.O. Number
|  |  |  | 1 | 9. Manufacturing Process Reference: | 1 | 5. Part Revision Level | 1 | 21. Reviewed By
|  |  |  | 1 | 10. Organization Name: | 1 | 6. Drawing Number | 1 | 22. Date
|  |  |  | 1 | 13. Detail FAI | 1 | 7. Drawing Revision Level | 1 | 23. Customer Approval
|  |  |  | 1 | 14. Full FAI | 1 | 8. Additional Changes | 1 | 24. Date
|  |  |  | 1 | FAI complete / not complete | 1 | 15. Part Number
|  |  |  | 1 | 19. Signature: | 1 | 16. Part Name
|  |  |  | 1 | 20. Date | 1 | 17. Part Serial Number
[6 empty] | 1 | 18. FAIR Number
19. Signature: |  |  | 20. Date:
| FAI Complete | FAI Not Complete |  | X
21. Reviewed By:
22. Date:
23. Customer Approval: |  |  | 24. Date:

## 9102RevB_2.1
AS9102B FORM 2 - PRODUCT ACCOUNTABILITY - MATERIALS, SPECIAL PROCESSES AND FUNCTIONAL TESTING
1. Part Number: | 2. Part Name: |  | 3. Serial Number: |  | 4. FAIR Number:
5. Material or Process Name: | 6. Specification Number: | 7. Code: | 8. Supplier: | 9. Customer Approval Verification: | 10. Certificate of Conformance Number:
[6 empty] | 4 | ( R) Required | 9 | ( CR) Conditionally Required | 2 | (O) Optional
[6 empty] | 1 | 1. Part Number: | 1 | 3. Serial Number: | 1 | 7. Code
[6 empty] | 1 | 2. Part Name: | 1 | 4. FAIR Number | 1 | 13. Comments
[6 empty] | 1 | 14. Signature | 1 | 5. Material or Process Name
[6 empty] | 1 | 15. Date | 1 | 6. Specification Number
[8 empty] | 1 | 8. Supplier
[8 empty] | 1 | 9. Customer Approval Verification
[8 empty] | 1 | 10. Certificate of Conformance Number
[8 empty] | 1 | 11. Functional Test Procedure Number
[8 empty] | 1 | 12. Acceptance Report Number
11. Functional Test Procedure Number: | 12. Acceptance Report Number:
13. Comments
14. Signature |  |  |  | 15. Date

## 9102RevB_3 Gauge.1
AS9102B FORM 3 - CHARACTERISTIC ACCOUNTABILITY, VERIFICATION, AND COMPATIBILITY EVALUATION
1. Part Number |  |  |  | 2. Part Name |  |  | 3. Serial Number | 4. FAIR Number
Characteristic Accountability |  |  |  | 3
5. Char No. | 6. Reference Location | 7. Characteristic Designator | 8. Requirement | 9. Results | 10. Designed / Qualified Tooling | 11. NonConformance Number | 14a. Measurement Equipment / Gauge No. | 14b. Comments
[9 empty] | 7 | ( R) Required | 6 | ( CR) Conditionally Required | 2 | (O) Optional
[9 empty] | 1 | 1.Part Number | 1 | 3.Serial Number | 1 | 14a. Measurement Equipment / Gauge No
[9 empty] | 1 | 2.Part Name | 1 | 4.FAIR Number | 1 | 14b.Comments
[9 empty] | 1 | 5.Char No. | 1 | 6.Ref Location
[9 empty] | 1 | 8.Requirement | 1 | 7.Char Desig
[9 empty] | 1 | 9.Result | 1 | 10.Designed / Qualified Tooling
[9 empty] | 1 | 12.Signature | 1 | 11.Non-Conformance Number
[9 empty] | 1 | 13.Date
12. Signature | [6 empty] | 13. Date:

## XV. Appearance & XVI product si
Appearance Approval Report
PART |  |  |  | DRAWING |  |  | APPLICATION
NUMBER |  |  |  | NUMBER |  |  | (PO NUMBER)
PART |  |  |  | BUYER |  | G&H SITE |  | DATE
NAME |  |  |  | CODE
ORGANISATION |  |  | MANUFACTURING |  |  |  |  | SUPPLIER/VENDOR
NAME |  |  | LOCATION |  |  |  |  | CODE |  | -
REASON FOR | PART SUBMISSION WARRANT |  | SPECIAL SAMPLE |  |  | RE-SUBMISSION |  | OTHER
SUBMISSION | ENGINEERING CHANGE |  | FIRST PRODUCTION SHIPMENT
APPEARANCE EVALUATION
Insert Image of Sample:
Comments:
G&H Sample Sign Off
[5 empty] | Yes | No
SUPPLIER |  | DATE |  | AUTHORISED CUSTOMER |  |  |  |  | DATE
SIGNATURE |  |  |  | REPRESENTATIVE SIGNATURE

## XVII. Assent Database Update
PRODUCTION PART
APPROVAL PROCESS
Section XVI - Assent Database Update
Component Compliance
As per G&H Global T's & C's, the suppleir shall submit all component compliance via the Assent supplier portal. Assent are a contracted 3rd party that supports component compliace on behalf of G&H. Details on how to access this portal are as per the links provided below. For any assistance, please contact Jon Taylor, Global Supplier Quality Manager - jtaylor@gandh.com or compliancesupport@assent.com
Here are a couple of helpful submission videos that suppliers can refer to:
General submission videos: https://assentcompliance.my.site.com/SupplierCustomerPortal/s/topic/0TO8X000000B5UtWAK/how-to-make-submissions-in-the-supplier-portal?language=en_US
CM Submissions: https://assentcompliance.my.site.com/SupplierCustomerPortal/s/topic/0TO8X000001Dme6WAC/responsible-minerals-rm-videos?language=en_US
General supplier helppage: https://assentcompliance.my.site.com/SupplierCustomerPortal/s/?language=en_US
Assent support details:
Email: compliancesupport@assent.com
Web: Supplier Help Center
Chat: English Live Support Chat can be accessed through the supplier portal
Phone: +1 855-277-3681 / +31 (20) 399 1700 (Phone Support Available In: English, Deutsch, 中文热线, Français, Italiano, 日本語, Español, Português)

## XVIII. PSW
[6 empty] | Production Submission Warrant - PSW Form | [9 empty] | PSW No.
PRODUCT INFORMATION | [15 empty] | Page No. 1 of 2
Product Name: | [10 empty] | Product Number:
PSO Reference / Vendor Code: | [10 empty] | Drawing Number:
Agreement Reference: | [10 empty] | Engineering Change / Issue Level:
PRODUCTION SUPPLY ORGANISATION (PSO) | [9 empty] | INTERNAL CUSTOMER ORGANISATION
Organisation Name | [10 empty] | Customer Name / Division
Street Address | [10 empty] | Customer Authorised Representative (Name)
City |  |  |  |  | Region
Postal Code |  |  |  |  | Country | [5 empty] | Application (Project / Programme)
REASON FOR SUBMISSION
Comments
APPROVAL SUBMISSION LEVEL (Also use section 1 of sheet 2)
|  | Level 1 |  |  |  | Level 2 |  |  | Level 3 |  |  |  |  | Level 4 |  |  |  | Level 5
DECLARATION (Also use section 2 of sheet 2, and when appliable section 3)
I submit this Production Submission Warrant (PSW) and accompanying data to provide objective evidence of compliance to all Production Product Approval Process (PPAP) requirements and as confirmation of the product / process capability and capacity to support ongoing supply. I also certify that documented evidence is on file and available for review. I have noted any deviations from this declaration using sheet 2.
PSO Authorisation: (Print Name/Sign) | [7 empty] | Title | [5 empty] | Date |  |  | Phone Number
FOR GOOCH AND HOUSEGO USE ONLY
| Approved |  |  | Interim Approval | [7 empty] | Rejected
[7 empty] | Interim Approval Status |  |  | B |  | C | D |  | E
| Agreed period or quantity for shipment: | [11 empty] | Specific actions required (see comments box)
|  |  | Concession required for shipment | [5 empty] | Concession No.
Accept
Reject
Not Required
Comments
Customer Authorised Representative (Print Name/Sign) | [7 empty] | Title | [5 empty] | Date |  |  | Phone Number
[6 empty] | Production Submission Warrant [PSW] - Approval form | [9 empty] | PSW No.
SECTION 1: SUBMISSION CONTENT | [16 empty] | Page No. 2 of 2
Note: For boxes ticked "No" and where the element is applicable use section 3.
Yes | No | ELEMENT DESCRIPTION (tick) | [6 empty] | Yes | No | ELEMENT DESCRIPTION (tick)
|  | 1 G&H Specific Requirements | [8 empty] | 10 Process Failure Modes Effects Analysis (PFMEA)
|  | 2 Contract, Drawing and Specification Review | [8 empty] | 11 Measurement System Evaluation (MSE)
|  | 3 Review of Design | [8 empty] | 12 Packing & Traveller Details
|  | 4 Manufacturing Process Flow & Predicted Timing Plan | [8 empty] | 13 Final Manufacturing Process Instructions
|  | 5 Draft Manufacturing Instructions | [8 empty] | 14 Control Plan- Production
|  | 6 Facilities, Tools and Gauges | [8 empty] | 15 Statistical Process Control
|  | 7 Control Plan – Pre-Production | [8 empty] | 16 Product Quality Sign Off & Appearance Approval Report
|  | 8 Production Quality & Inspection Planning | [8 empty] | 17 First Article Inspection Report
|  | 9 Team Feasibility Commitment | [8 empty] | 18 Production Submission Warrant (Approval form)
SECTION 2: DECLARATIONS CONTINUED
Note: For boxes ticked "No" and where the element is applicable use section 3.
Yes | No
All Customer / Design Engineering requirements are properly understood and recorded.
The requirements of the Production Process Run have been satisfied and associated data evaluated.
All the results demonstrate conformance to Customer / Design Engineering requirements.
Satisfactory Process Control Surveillance has been carried out and conformity to requirements is deployed within the production manufacturing process.
Initial Manufacturing Studies demonstrate rate potential to customer demand rate requirements .
|  |  | Please state Customer demand rate | [8 empty] | Unit
If there are any deviations from the declarations made (sheet 1 and 2) tick and state specifics below
Comments
SECTION 3: FOR INTERIM SUBMISSIONS ONLY
Yes | No
|  | Interim Corrective Action Plan included | [6 empty] | Commitment date of re-submission: (state date)
Comments
1
2
3
4
5
6
7
8
9
10
11
12
132
142
152
162
Other - please specify below
Products produced at additional or alternative Location
Change in Product Processing (manufacture, assembly)
Subcontractor/Sub-tier or Material Source Change
Customer requested production verification
Correction of Discrepancy
Tooling: Transfer, Replacement, Refurbishment, or additional
Engineering Change(s)
Initial submission
Other - please specify below
172
182

## Retention
Retention/Submission Requirements Table
Requirement |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
A | Formal Letter Triggering APQP Requirements | S | S | S | S | S
B | G&H Specific Requirements | S | S | S | S | S
C | Control Plan- Pre - Production | R | S | S | S | S
1 | Contract, Drawing and Specification Review | S | S | S | S | S
2 | Review of Design | R | R | R | R | S
3 | Predicted Timing Plan | S | S | S | S | S
4 | Team Feasibility Commitment | R | R | R | R | S
5 | Production Quality & Inspection Planning | R | R | R | S | S
6 | Manufacturing Process Flow | R | S | S | S | S
7 | Process Failure Modes Effects Analysis (PFMEA) | R | S | S | S | S
8 | Measurement System Evaluation (MSE) | R | R | R | S | S
9 | Facilities, Tools and Gauges | R | R | R | R | S
10 | Final Manufacturing Process Instructions | R | R | R | R | S
11 | Packing & Traveller Details | S | S | S | S | S
12 | Control Plan- Production | R | S | S | S | S
13 | Statistical Process Control | R | R | R | R | S
14 | First Article Inspection Report | S | S | S | S | S
15 | Product Quality Sign Off & Appearance Approval Report | R | R | R | R | S
16 | G&H Sample Sign Off | R | R | R | R | S
17 | Assent Database | S | S | S | S | S
18 | Production Submission Warrant (Approval form) | S | S | S | S | S
S = The organisation shall submit to the customer and retain a copy of records or documentation items at appropriate locations.
R = The organisation shall retain at appropriate locations and make available to the customer upon request.
* = The organisation shall retain at appropriate locations and submit to the customer upon request.

## Log
Revision | History change
1 | Introduction
2 | Update retention