## A. Work Plan - (hidden)
WORK PLAN
Joint SDG Fund - GFCR Fiji
Outcome | Output | Outcome/Output Description | TIME FRAME |  |  |  | PLANNED BUDGET |  |  | Recipient UN organization | Implementing Partners
|  |  | Y1 | Y2 | Y3 | Y4 | Joint SDG Fund | Global Fund for Coral Reefs | Total USD
A. PROGRAMME OUTCOME COSTS
1 | Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia
1 | 1.1 | Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | x | x | x | x |  |  | 0
1 | 1.2 | Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector | x | x | x | x |  |  | 0
1 | 1.3 | Output 1.2: Strengthened management, enforcement and monitoring systems of MPAs by SPEs. | x | x | x | x |  |  | 0
1 | 1.4 | Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats. | x | x | x | x |  |  | 0
Sub-total Outcome 1 | [6 empty] | 0 | 0 | 0
2 | Outcome 2: Transforming the livelihoods of coral reef-dependent communities
2 | 2.1 | Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth | x | x | x | x |  |  | 0
2 | 2.2 | Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers | x | x | x | x |  |  | 0
2 | 2.3 | Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection | x | x | x | x |  |  | 0
2 | 2.4 | Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably | x | x | x | x |  |  | 0
Sub-total Outcome 2 | [6 empty] | 0 | 0 | 0
TOTAL PROGRAMME OUTCOME COSTS | [6 empty] | 0 | 0 | 0
B. PROGRAMME MANAGMENT COSTS
UNDP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNDP | N/A
UNCDF
N/A | N/A |  | x | x | x | x |  |  | 0 | UNCDF | N/A
UNEP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNEP | N/A
EVALUATION
N/A | N/A |  | x | x | x | x |  |  | 0 | Evaluation | N/A
TOTAL PROGRAMME MANAGMENT COSTS | [6 empty] | 0 | 0 | 0
TOTAL DIRECT PROGRAMME COSTS | [6 empty] | 0 | 0 | 0
Total Indirect Support Cost - GMS (7%) | [6 empty] | 0 | 0 | 0
TOTAL COSTS | [6 empty] | 0 | 0 | 0

## A. Budget UNDG Categories - (hidden)
BUDGET BY UNDG CATEGORIES
Joint SDG Fund - GFCR Fiji
UNDG BUDGET CATEGORIES | UNDP |  | UNCDF |  | UNEP |  | TOTAL USD |  | TOTAL % by UNDG category
| Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund | GFCR | Combined
1. Staff and other personnel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
2. Supplies, Commodities, Materials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
3. Equipment, Vehicles, and Furniture (including Depreciation) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
4. Contractual services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
5.Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
6. Transfers and Grants to Counterparts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
7. General Operating and other Direct Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total Direct Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
8. Indirect Support Costs (Max. 7%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
TOTAL Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Total budget combined | 0 |  | 0 |  | 0 |  | 0
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! |  | #VALUE! |  | #VALUE! | #REF!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! |  | #VALUE! |  | #VALUE! | #REF!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## B. Budget per SDG targets (hidden)
4.2 Budget per SDG Targets
SDG TARGETS |  | % | Total (USD) | GFCR | Joint SDG Fund
1 | SDG 1.a and SDG 1.b | 10% | 15065.6 | 13118.2 | 1947.4
5 | SDG 5.5 | 5% | 7532.8 | 6559.1 | 973.7
8 | SDG 8.3, SDG 8.5 and SDG 8.9 | 10% | 15065.6 | 13118.2 | 1947.4
10 | SDG 10.b | 5% | 7532.8 | 6559.1 | 973.7
14 | SDG 14.1, 14.2, 14.3, 14.4, 14.5, 14.7 | 60% | 90393.6 | 78709.2 | 11684.4
17 | SDG 17.1 and 17.3 | 10% | 15065.6 | 13118.2 | 1947.4
TOTAL |  | 100% | 150656 | 131182 | 19474

## C. Workplan (hidden)
4.3 Work plan
Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia
Output | Annual target/s* |  |  |  | List of activities | Time frame | [15 empty] | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | Area of new climate refugia and priority sites designated as MPAs = 0 | Area of new climate refugia and priority sites designated as MPAs = 500 | Area of new climate refugia and priority sites designated as MPAs = 1000 | Area of new climate refugia and priority sites designated as MPAs = 1500 | Activity 1.1.3: MPA screening, feasibility study and selection of new priority sites in Philippines | [16 empty] | #VALUE! | 0 | 0 | 0 | UNDP | MoE, Blue Finance | bar: Time frame Q1 to Time frame Q2
[5 empty] | Activity 1.1.1: Design of the MPAs high-level business plan and set-up of the Special Purpose Entities (SPEs - co-management body for the MPAs) in the 3 MPA networks | [16 empty] | #VALUE! | bar: Time frame Q3 to Time frame Q2; Time frame Q1 to Time frame Q2
[5 empty] | #VALUE! | [16 empty] | #VALUE! | bar: Time frame Q4 to Time frame Q2; Time frame Q1 to Time frame Q3
[5 empty] | Activity 1.1.2: Stakeholder engagement and advocacy in the 3 MPA networks | [16 empty] | #VALUE! | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
#VALUE! | 0 | 1 SPE | 2 SPE | 2 SPE | #VALUE! | [16 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | UNDP and UNCDF | MoE, Blue Finance, Althelia/SOF, GFCR, Fiji Hotel and Tourism Association | bar: Time frame Q1 to Time frame Q2
[5 empty] | #VALUE! | [16 empty] | #VALUE! | bar: Time frame Q1 to Time frame Q2
[5 empty] | #VALUE! | [16 empty] | #VALUE! | bar: Time frame Q1 to Time frame Q2
Output 1.2: Strengthened management, enforcement and monitoring systems of MPAs by SPEs. | 1 MPA with METT score >60 | 2 MPAs with METT score >70 | 3 MPAs with METT score >70 | 4 MPAs with METT score >70 | Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation and natural resource management | [16 empty] | #VALUE! | 15500 | 5000 | 20500 | UNDP and UNEP | Blue Finance, FLMMA | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
[5 empty] | #VALUE! | [16 empty] | #VALUE! | bar: Time frame Q1 to Time frame Q2
#VALUE! | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 0 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 1 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 2 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 3 | #VALUE! | [16 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | UNDP | MoE, Invest Fiji | bar: Time frame Q1 to Time frame Q2
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output | Annual target/s* |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Output 2.1: Established Development Facility to structure a pipeline of investment ready reef-positive sustainable businesses and projects within and around the MPA networks of Calamian Island, Tañon Strait and Verde Island Passage | Number of TAF incubated blue economy SMEs that become investment ready = 2 | Number of TAF incubated blue economy SMEs that become investment ready = 3 | Number of TAF incubated blue economy SMEs that become investment ready = 4 | Number of TAF incubated blue economy SMEs that become investment ready = 6 | Activity 2.1.1: Scoping, technical assistance and training to develop a pipeline of investment ready projects in Blue economy sectors | [16 empty] | This output covers feasibility and implementation plan for nature-based businesses in VIP (phase 2), Calamian and TSPS. Business approaches will include MPA admission fees, visitor centers, eco-tourism products, tourism facilities, unerwater attractions, etc. Activities include scoping, pre-selection, market analysis, due diligence, data gathering, need assessment, community and other stakeholder engagement, high-level business plan, regulatory strategy and financial structuring. Preliminary project design and implementation plan | 96000 | 10000 | 106000 | UNCDF and UNEP | Matanataki,
[5 empty] | #VALUE! | [16 empty] | #VALUE!
#VALUE! | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | #VALUE! | [16 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | UNCDF
[5 empty] | #VALUE! | [16 empty] | #VALUE!
[5 empty] | #VALUE! | [16 empty] | #VALUE!
#VALUE! | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 3 | #VALUE! | [16 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | UNDP
#VALUE! | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | #VALUE! | [16 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | UNDP
B. PROGRAMME MANAGEMENT COSTS |  |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Management and Operations | N/A | N/A | N/A | N/A | Management of the implementation of the JP | [16 empty] | Staff: Project Mgr, Admin/Support officer, Project Support officer, office rent, utilities etc | 9600 | 3200 | 12800 | UNDP, UNCDF and UNEP
Communications and Learning | N/A | N/A | N/A | N/A | See Annex 6 Communication Plan and Annex 7 Learning and Sharing Plan | [16 empty] | Staff: Communications officer, event costs (venue etc), printing, photography, etc | 1500 | 0 | 1500 | UNDP
Evaluation | N/A | N/A | N/A | N/A | Mid-term and end-evaluation + ongoing RM activities | [16 empty] | Staff: M&E Officer, Mid-term and end evaluation | 0 | 0 | 0 | UNDP
| *Targets are cumulative. For details on these targets and other indicators, see Annex 2.2 Results Framework | [20 empty] | *For details on UNDG budget categories per activity, see sheet D. Budget by Outcome

## Sheet1 (hidden)
| Timeline | Milestones
Activity 1.1.1: Design of the MPAs high-level business plan and set-up of the Special Purpose Entities in the MPA networks of Calamian Island, Tañon Strait and Verde Island Passage
Activity 1.1.2: Stakeholder engagement and advocacy in the 3 MPA networks
Activity 1.1.3: MPA screening, feasibility study and selection of new priority sites in Philippines
Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation and natural resource management
Activity 1.2.2: Project Management Office for the SPEs and capacity building
Activity 2.1.1: Scoping, technical assistance and training to develop a pipeline of investment ready projects in Blue economy sectors.
Activity 2.1.2: Technical assistance and training to upskill local businesses on methodology to measure, monitor and manage the environmental impact of their business operations
Activity 2.2.1: Provide early stage costs of the SPE Blue Alliance for North Oriental Mindoro MPA network with leverage from the private sector
Activity 2.2.2: Design of the blended finance facility for aggregating the investments in blue economy within and around the 3 MPA networks of Calamian Island, Tañon Strait and Verde Island Passage.
Activity 2.2.3: Fundraising for the blended finance facility with donors, DFIs and impact investors. ?? NEEDED with GFCR investment window?

## A. Budget UNDG Categories - (2)
BUDGET BY UNDG CATEGORIES
GFCR Philippines
UNDG BUDGET CATEGORIES | Amount (US$)
1. Staff and other personnel | 0
2. Supplies, Commodities, Materials | 0
3. Equipment, Vehicles, and Furniture (including Depreciation) | 0
4. Contractual services | 100000
5.Travel | 11500
6. Transfers and Grants to Counterparts
7. General Operating and other Direct Costs | 11100
Total Direct Costs | 122600
8. Indirect Support Costs (Max. 7%) | 8582
TOTAL Budget | 131182

## D. Budget by Outcome Febjun2021
BUDGET BY OUTCOME
GFCR Philippines
Outcome | Output | Activity | Budget Lines | Organization | Unit quantity | Unit Cost (USD) | Duration | Time unit (Time units or Lump sum) | % Charged to Programme | UNDG Budget Category (1-7) | Budget | [6 empty] | Narrative description of budget lines
[11 empty] | Total (USD) | GFCR | Co-financing | Feb | Mar | Apr | May |  | Budget Bf + partners 2021 Q2-Q3
A. PROGRAMME OUTCOME COSTS
Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs
Activity 1.1.1: Design of the MPAs high-level business plan and set-up of the Special Purpose Entities (SPEs - co-management body for the MPAs) in the 3 MPA networks
|  |  | Sub-Total Activity 1.1.1: | [7 empty] | 0 | 0 | 0
Activity 1.1.2: Stakeholder engagement and advocacy in the 3 MPA networks
|  |  | Sub-Total Activity 1.1.2: | [7 empty] | 0 | 0 | 0
Activity 1.1.3: MPA screening, feasibility study and selection of new priority sites in Philippines
|  |  | Sub-Total Activity 1.1.3: | [7 empty] | 0 | 0 | 0
|  |  | Sub-Total Output 1.1: | [7 empty] | 0 | 0 | 0
Output 1.2: Strengthened management, enforcement and monitoring systems of MPAs by SPEs.
Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation and natural resource management
|  | 1.2.1.1 | Contractual Services | Conservation International | 1 | 7000 |  |  | 100% | 4 | 7000 | 7000 |  |  |  | x |  | Update and strengthen MPA Management Plans in VIP Phase 1 in connection and preparation for new activities such as nature based-tourism, mud crab, blue carbon, mangrove-shrimp aquaculture.
|  | 1.2.1.2 | Travel | Conservation International | 1 | 2500 |  |  | 100% | 5 | 2500 | 2500 |  |  |  | x |  | Travel and food&accomodations
|  |  | Sub-Total Activity 1.2.1: | [7 empty] | 9500 | 9500 | 0
Activity 1.2.2: Project Management Office for the SPEs and capacity building to upskill SPEs and MPAs on social entrepreneurship and sustainable business management
|  | 1.2.2.1 | Contractual Services | Blue finance | 1 | 10000 |  |  | 100% | 4 | 10000 | 5000 | 5000 | x | x | x | x | Provide initial support for the SPE in VIP Mindoro to ensure management focus on strategy execution: project planning and reporting, resource forecasting, facilitate & ensure communication to key stakeholders, alignment of interrelations between activities, management of project risks; | 30000
|  | 1.2.2.3 | Travel | Blue finance | 1 | 1000 |  |  | 100% | 5 | 1000 | 1000 |  | x | x | x | x | Travel, DSA etc
|  |  | Sub-Total Activity 1.2.2: | [7 empty] | 11000 | 6000 | 5000
|  |  | Sub-Total Output 1.2: | [7 empty] | 20500 | 15500 | 5000
Sub-Total OUTCOME 1: | [10 empty] | 20500 | 15500 | 5000
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output 2.1: Established Development Facility to structure a pipeline of investment ready reef-positive sustainable businesses and projects within and around the MPA networks of Calamian Island, Tañon Strait and Verde Island Passage
Activity 2.1.1: Scoping, technical assistance and training to develop a pipeline of investment ready projects in Blue economy sectors
|  | 2.1.1.1 | Contractual Services | UBA Sustainability institute | 1 | 5000 |  |  | 100% | 4 | 5000 | 5000 |  | X | X | X | X | Includes pre-feasibility study in VIP and Calamian for blue carbon credits through mangrove restoration and conservation projects.. and supports to the initial steps for certification and implementation of the blue carbon project. The study allows to analyse additionality, conditions to fit the eligibility and to apply internationally recognized methodologies and standards, Social, economic and land use history and due diligence, Legal framework analysis, Economic viability analysis, GHGs impacts, SDGs impacts, market potential, gaps and risks analysis and strategy, Action plan and project design. | 30000
|  | 2.1.1.2 | Contractual Services | Blue finance, | 1 | 20000 |  |  | 100% | 4 | 20000 | 10000 | 10000 | X | X | X | X | This output covers feasibility and implementation plan for nature-based businesses in VIP (phase 2), Calamian and TSPS. Business approaches will include MPA admission fees, visitor centers, eco-tourism products, tourism facilities, unerwater attractions, etc. Activities include scoping, pre-selection, market analysis, due diligence, data gathering, need assessment, community and other stakeholder engagement, high-level business plan, regulatory strategy and financial structuring. Preliminary project design and implementation plan | 50000
|  | 2.1.1.3 | Contractual Services | Blue you | 1 | 35000 |  |  | 100% | 4 | 35000 | 35000 |  | X | X | X | X | This output covers the feasibility study of the mud crab farming in Mindoro (VIP Phase 1). Activities include Scoping and mapping of eligible farming areas , Identification of community leaders / stakeholders, Identification of leaders for investable entity, Impact intervention: mangrove restoration, Build business model with growout farms, Technical hatchery engineering & design (scalable), CAPEX and OPEX. | 30000
|  | 2.1.1.4 | Contractual Services | Blue you | 1 | 18000 |  |  | 100% | 4 | 18000 | 18000 |  | X | X | X | X | This output covers the scoping study for aquaculture and fishery businesses in VIP (Phase 2), Calamian islands and TSPS. Target species for scoping include Reef fish / Mud Crab/ Mollusks / other Crustaceans. Activities include resource assessment, Identification of community leaders, Build business model, Project business case outline for 1-2 cases with reef fish/mollusks/crustaceans, Prelim CAPEX and OPEX plan, Prelim business plan outline and interventions and Prelim financial projection | 30000
|  | 2.1.1.5 | Contractual Services | Rare Blended finance | 1 | 10000 |  |  |  |  | 10000 | 10000 |  | X | X | X | X | This output covers the feasibility study of the fish suplly chain improivement in TSPS (Fisjh landing center(s) in Bantayan LGU). Activities include target market assessment (e.g. Cebu), new niches, market linkages, identification of community leaders / stakeholders, assessment of policy improvement needs for formalizing businesses engagement in seafood supply and trading, post harvest added value, build business model for fish landing center , Technical hatchery engineering & design (scalable), CAPEX and OPEX.
|  | 2.1.1.6 | Contractual Services | Blue finance | 1 | 10000 |  |  |  |  | 10000 | 10000 |  |  |  | X | X | Full project proposal with high-level business plans for the MPAs in the 3 networks will be developed with revenues from eco-tourism, nature fee solutions, blue carbon, aquaculture and other businesses linked to Blue Economy. Plans will include preliminary business model, budgets (Capex and Opex), financial strategy and de-risking aspects. Plans will be developed in consultations with local stakeholders. A coalition of local stakeholders (e.g. NGOs, associations, cooperatives, foundations) will be selected to become members of the SPE. Proper due diligence will be conducted beforehand on stakeholders.
|  | 2.1.1.7 | Travel | Blue finance | 1 | 2500 |  |  | 100% | 5 | 2500 | 2500 |  | X | X | X | X | Travel, DSA etc
|  | 2.1.1.8 | Travel | Blue you | 1 | 3000 |  |  | 100% | 5 | 3000 | 3000 |  | X | X | X | X | Travel, DSA etc
|  | 2.1.1.8 | Travel | Rare Blended finance | 1 | 2500 |  |  |  |  | 2500 | 2500
|  |  | Sub-Total Activity 2.1.1: | [7 empty] | 106000 | 96000 | 10000
|  |  | Sub-Total Output 2.1: | [7 empty] | 106000 | 96000 | 10000
Sub-Total OUTCOME 2: | [10 empty] | 106000 | 96000 | 10000
Total PROGRAMME OUTCOME COSTS: | [10 empty] | 126500 | 111500 | 15000
B. PROGRAMME MANAGEMENT COSTS | [17 empty] | Narrative description of budget lines
Management and Operations
|  |  | Staff and Personnel | Blue finance | 1 |  |  |  | 30% | 1 | 4000 | 4000 |  | x | x | x | x | Director
|  |  | Staff and Personnel |  | 1 |  |  |  | 100% | 1 | 6400 | 3200 | 3200 | x | x | x | x | Programme Manager
|  |  | Travel |  | 1 |  | 1 | Lump Sum | 100% | 5 | 0 | 0 | 0 |  |  |  |  | Travel, DSA etc
|  |  | General Operating and Other Direct Cost |  | 1 |  | 1 | Lump Sum | 100% | 7 | 2400 | 2400 | [5 empty] | Operations (rental, internet, phone, laptop etc)
|  |  | Sub-Total Management and Operations | [7 empty] | 12800 | 9600 | 3200
Communications and Learning
|  |  | General Operating and Other Direct Cost |  | 1 |  | 1 | Lump Sum | 100% | 7 | 1000 | 1000 | [5 empty] | COMMUNICATIONS: Design and Printing costs
|  |  | Contractual Services |  | 1 |  | 1 | Lump Sum | 100% | 4 | 500 | 500 | [5 empty] | Consultant to draft Learning and Sharing Plan
|  |  | Sub-Total Communications and Learning | [7 empty] | 1500 | 1500 | 0
Evaluation
|  |  | Contractual Services | [6 empty] | 4 | 0 | 0 | 0 |  |  |  |  | Mid-term and End Evaluation
|  |  | Staff and Personnel | [6 empty] | 1 | 0 | 0 | 0 |  |  |  |  | M&E officer - SB4-3 (responsible for implementation of RM and Evaluation)
|  |  | Sub-Total Evaluation | [7 empty] | 0 | 0 | 0
|  |  | TOTAL PROGRAMME MANAGEMENT COSTS: | [7 empty] | 14300 | 11100 | 3200
|  |  | TOTAL DIRECT PROGRAMME COSTS | [7 empty] | 140800 | 122600 | 18200 | [5 empty] | 170000
| 7% |  | Indirect Programme Support Costs (7%) | [7 empty] | 9856 | 8582 | 1274
|  |  | TOTAL COSTS | [7 empty] | 150656 | 131182 | 19474

## C. Workplan (2)
4.3 Work plan
Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia | 0 | 0 | 0 | 0
Output | Monthly Target |  |  |  | List of activities | PLANNED BUDGET |  |  |  | Implementing partner/s involved
| June | July | August | Sept. |  | Overall budget description | GFCR (USD) | Co-financing (USD) | Total Cost (USD)
Output 1.2: Strengthened management, enforcement and monitoring systems of MPAs by SPEs. |  |  | X |  | Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation and natural resource management | Update and strengthen MPA Management Plans in VIP Phase 1 in connection and preparation for new activities such as nature based-tourism, mud crab, blue carbon, mangrove-shrimp aquaculture. | 15500 | 5000 | 20500 | Conservation Internartional / Blue finance
| x | x | x | x | Activity 1.2.2: Project Management Office for the SPEs and capacity building to upskill SPEs and MPAs on social entrepreneurship and sustainable business management | Provide initial support for the SPE in VIP Mindoro to ensure management focus on strategy execution: project planning and reporting, resource forecasting, facilitate & ensure communication to key stakeholders, alignment of interrelations between activities, management of project risks;
Outcome 2: Transforming the livelihoods of coral reef-dependent communities | 0 | 0 | 0 | 0
Output | Monthly Target |  |  |  | List of activities | PLANNED BUDGET |  |  |  | Implementing partner/s involved
| June | July | August | Sept. |  | Overall budget description | GFCR (USD) | Co-financing (USD) | Total Cost (USD)
Output 2.1: Established Development Facility to structure a pipeline of investment ready reef-positive sustainable businesses and projects within and around the MPA networks of Calamian Island, Tañon Strait and Verde Island Passage |  |  |  |  | Activity 2.1.1: Scoping, technical assistance and training to develop a pipeline of investment ready projects in Blue economy sectors | Full project proposal for the MPAs in the 3 networks with business scoping and feasibility studies for nature based-tourism, nature fee solutions, blue carbon, aquaculture and other businesses linked to Blue Economy. | 96000 | 10000 | 106000 | Blue you / Blue finance / Ubá / Rare Blended finance
0
0
0 |  |  |  |  | List of activities | PLANNED BUDGET |  |  |  | Implementing partner/s involved
[6 empty] | Overall budget description | GFCR (USD) | Co-financing (USD) | Total Cost (USD)
Management and Operations | x | x | x | x | Staff and Personnel, general operating costs |  | 9600 | 3200 | 12800 | Blue finance / Blue Alliance
Communications and Learning | x | x | x | x | General Operating and Other Direct Cost, Contractual servies |  | 1500 | 0 | 1500 | Blue Alliance NGO
Evaluation | [8 empty] | 0
[6 empty] | TOTAL | 122600 | 18200 | 140800