## A. Work Plan - (hidden)
WORK PLAN
Joint SDG Fund - GFCR Fiji
Outcome | Output | Outcome/Output Description | TIME FRAME |  |  |  | PLANNED BUDGET |  |  | Recipient UN organization | Implementing Partners
|  |  | Y1 | Y2 | Y3 | Y4 | Joint SDG Fund | Global Fund for Coral Reefs | Total USD
A. PROGRAMME OUTCOME COSTS
1 | Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia
1 | 1.1 | Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | x | x | x | x |  |  | 0
1 | 1.2 | Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector | x | x | x | x |  |  | 0
1 | 1.3 | Output 1.2: Strengthened management, enforcement and monitoring systems of MPAs by SPEs. | x | x | x | x |  |  | 0
1 | 1.4 | Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats. | x | x | x | x |  |  | 0
Sub-total Outcome 1 | [6 empty] | 0 | 0 | 0
2 | Outcome 2: Transforming the livelihoods of coral reef-dependent communities
2 | 2.1 | Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth | x | x | x | x |  |  | 0
2 | 2.2 | Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers | x | x | x | x |  |  | 0
2 | 2.3 | Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection | x | x | x | x |  |  | 0
2 | 2.4 | Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably | x | x | x | x |  |  | 0
Sub-total Outcome 2 | [6 empty] | 0 | 0 | 0
TOTAL PROGRAMME OUTCOME COSTS | [6 empty] | 0 | 0 | 0
B. PROGRAMME MANAGMENT COSTS
UNDP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNDP | N/A
UNCDF
N/A | N/A |  | x | x | x | x |  |  | 0 | UNCDF | N/A
UNEP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNEP | N/A
EVALUATION
N/A | N/A |  | x | x | x | x |  |  | 0 | Evaluation | N/A
TOTAL PROGRAMME MANAGMENT COSTS | [6 empty] | 0 | 0 | 0
TOTAL DIRECT PROGRAMME COSTS | [6 empty] | 0 | 0 | 0
Total Indirect Support Cost - GMS (7%) | [6 empty] | 0 | 0 | 0
TOTAL COSTS | [6 empty] | 0 | 0 | 0

## A. Budget UNDG Categories - (hidden)
BUDGET BY UNDG CATEGORIES
Joint SDG Fund - GFCR Fiji
UNDG BUDGET CATEGORIES | UNDP |  | UNCDF |  | UNEP |  | TOTAL USD |  | TOTAL % by UNDG category
| Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund | GFCR | Combined
1. Staff and other personnel | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2. Supplies, Commodities, Materials | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3. Equipment, Vehicles, and Furniture (including Depreciation) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4. Contractual services | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5.Travel | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6. Transfers and Grants to Counterparts | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7. General Operating and other Direct Costs | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total Direct Costs | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8. Indirect Support Costs (Max. 7%) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TOTAL Budget | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Total budget combined | #REF! |  | #REF! |  | #REF! |  | #REF!
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! |  | #REF! |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
0
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! |  | #REF! |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
0
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!

## B. Budget per SDG targets (hidden)
4.2 Budget per SDG Targets
SDG TARGETS |  | % | Total (USD) | GFCR | Joint SDG Fund
1 | SDG 1.a and SDG 1.b | 10% | #REF! | #REF! | #REF!
5 | SDG 5.5 | 5% | #REF! | #REF! | #REF!
8 | SDG 8.3, SDG 8.5 and SDG 8.9 | 10% | #REF! | #REF! | #REF!
10 | SDG 10.b | 5% | #REF! | #REF! | #REF!
14 | SDG 14.1, 14.2, 14.3, 14.4, 14.5, 14.7 | 60% | #REF! | #REF! | #REF!
17 | SDG 17.1 and 17.3 | 10% | #REF! | #REF! | #REF!
TOTAL |  | 100% | #REF! | #REF! | #REF!

## C. Workplan (hidden)
4.3 Work plan
#REF!
Output | Annual target/s* |  |  |  | List of activities | Time frame | [15 empty] | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
#REF! | Area of new climate refugia and priority sites designated as MPAs = 0 | Area of new climate refugia and priority sites designated as MPAs = 500 | Area of new climate refugia and priority sites designated as MPAs = 1000 | Area of new climate refugia and priority sites designated as MPAs = 1500 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP | MoE, Blue Finance | bar: Time frame Q1 to Time frame Q2
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q3 to Time frame Q2; Time frame Q1 to Time frame Q2
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q4 to Time frame Q2; Time frame Q1 to Time frame Q3
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
#REF! | 0 | 1 SPE | 2 SPE | 2 SPE | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP and UNCDF | MoE, Blue Finance, Althelia/SOF, GFCR, Fiji Hotel and Tourism Association | bar: Time frame Q1 to Time frame Q2
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q1 to Time frame Q2
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q1 to Time frame Q2
#REF! | 1 MPA with METT score >60 | 2 MPAs with METT score >70 | 3 MPAs with METT score >70 | 4 MPAs with METT score >70 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP and UNEP | Blue Finance, FLMMA | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
[5 empty] | #REF! | [16 empty] | #REF! | bar: Time frame Q1 to Time frame Q2
#REF! | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 0 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 1 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 2 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 3 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP | MoE, Invest Fiji | bar: Time frame Q1 to Time frame Q2
#REF!
Output | Annual target/s* |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
#REF! | Number of TAF incubated blue economy SMEs that become investment ready = 2 | Number of TAF incubated blue economy SMEs that become investment ready = 3 | Number of TAF incubated blue economy SMEs that become investment ready = 4 | Number of TAF incubated blue economy SMEs that become investment ready = 6 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNCDF and UNEP | Matanataki,
[5 empty] | #REF! | [16 empty] | #REF!
#REF! | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNCDF
[5 empty] | #REF! | [16 empty] | #REF!
[5 empty] | #REF! | [16 empty] | #REF!
#REF! | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 3 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP
#REF! | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | #REF! | [16 empty] | #REF! | #REF! | #REF! | #REF! | UNDP
#REF! |  |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
#REF! | N/A | N/A | N/A | N/A | Management of the implementation of the JP | [16 empty] | Staff: Project Mgr, Admin/Support officer, Project Support officer, office rent, utilities etc | #REF! | #REF! | #REF! | UNDP, UNCDF and UNEP
#REF! | N/A | N/A | N/A | N/A | See Annex 6 Communication Plan and Annex 7 Learning and Sharing Plan | [16 empty] | Staff: Communications officer, event costs (venue etc), printing, photography, etc | #REF! | #REF! | #REF! | UNDP
#REF! | N/A | N/A | N/A | N/A | Mid-term and end-evaluation + ongoing RM activities | [16 empty] | Staff: M&E Officer, Mid-term and end evaluation | #REF! | #REF! | #REF! | UNDP
| *Targets are cumulative. For details on these targets and other indicators, see Annex 2.2 Results Framework | [20 empty] | *For details on UNDG budget categories per activity, see sheet D. Budget by Outcome

## Sheet1 (hidden)
| Timeline | Milestones
Activity 1.1.1: Design of the MPAs high-level business plan and set-up of the Special Purpose Entities in the MPA networks of Calamian Island, Tañon Strait and Verde Island Passage
Activity 1.1.2: Stakeholder engagement and advocacy in the 3 MPA networks
Activity 1.1.3: MPA screening, feasibility study and selection of new priority sites in Philippines
Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation and natural resource management
Activity 1.2.2: Project Management Office for the SPEs and capacity building
Activity 2.1.1: Scoping, technical assistance and training to develop a pipeline of investment ready projects in Blue economy sectors.
Activity 2.1.2: Technical assistance and training to upskill local businesses on methodology to measure, monitor and manage the environmental impact of their business operations
Activity 2.2.1: Provide early stage costs of the SPE Blue Alliance for North Oriental Mindoro MPA network with leverage from the private sector
Activity 2.2.2: Design of the blended finance facility for aggregating the investments in blue economy within and around the 3 MPA networks of Calamian Island, Tañon Strait and Verde Island Passage.
Activity 2.2.3: Fundraising for the blended finance facility with donors, DFIs and impact investors. ?? NEEDED with GFCR investment window?

## Guidance
Guidance Sheet: Budget by Outcome
Overview | The purpose of this sheet is for the Convening Agent to provide a detailed budget of the programme, down to the level of budget lines per activity. It is recommended to begin with Sheet A as it will auto-populate Sheets B and C with Outcome and Output names as well as financial sums. The budget should mirror the Outcomes, Outputs and Activities in the Programme Document or Concept Note. Outcome/Output/Activity lines can be hidden if they are not needed.
Outcome | Indicate the Name of the Outcome.
Output | Indicate the Name of the Output.
Activity | Provide the name of the Output's activity that adequately describes the objective of the activity.
Budget Lines | Short description of the budget line within the activity.
UNDG Budget Category (1-7) | UNDG Budget Categories are used by the UN Multi-Partner Trust Fund Office for accounting purposes. In Sheet C you will find a summary of the Budget by UNDG Categories. The Convening Agent should indicate the UNDG Budget Category with only a number between 1-7. This will ensure that the formulas in sheet C. Budget UNDG Categories are able to populate correctly. For guidance on what category to use, refer to the link on the right.
https://proposals.sdgfund.org/node/69
Recipient Organization | Organizations that will receive funding directly from the GFCR. This includes the Convening Agent, and can also include UNCDF, or another core partner. There should not be more than three recipient organizations. If UNCDF is a Recipient Organization do not include any staff costs, this is accounted for at the UNCDF Blue Bridge Global Level. The only budget category that should be used for UNCDF is #6 Transfers and Grants to Counterparts.
Implementing Partner (if any) | For implementing partners that do not recieve grants from the GFCR but have funding flow through a Recipient Organization , indicate the implementing organisation in the column. Leave blank if there is no additional Implementing Partner besides the Recipient Organisation. Country governments cannot receive GFCR funding for implementation.
Unit Quantity | How many units are needed for the Budget Line activity. The unit reflects the number of times the budget line activity is needed. For example, if two MPA business plans need to be completed, the number “2” can be inserted. It can also refer to the number of consultants.
Unit Cost (USD) | The per unit cost in USD.
Duration | The duration (i.e., how many months/years) will it take to complete. Enter only a number.
Time Unit or Lump Sums | Indicate if the number inserted in the "Duration Column" represents days, months, or years.
Total Budget - Grant Amount | The total budget for that budget line
Total Budget - Grant Instrument Type | Indicate if the grant for this budget line will be deployed as a pure grant, repayable grant, concessional loan, guarantee, or other financial instrument.
Narrative Budget Description of Budget Lines | Describe in more detail the purpose, process and objective of the budget line in 2-5 sentences. If the budget line is for staff costs - indicate the Title of the staff members being paid and the percentage of their time. If a budget line is a transfer to an implementing partner and thus uses UNDG Budget Category #6 Transfers and Grants to Counterparts, indicate the proportion of the budgetline that will be used for the implementing partner staff costs.
Year 1 Budget - Grant Amount | The GFCR requires an indication of grants that are needed for Year 1 and Year 2 to determine the tranches of funding to the programme.
Year 1 Budget - Grant Instrument Type | Indicate if the grant for this budget line will be deployed as a pure grant, repayable grant, concessional loan, guarantee, or other financial instrument.
Year 2 Budget - Grant Amount | The GFCR requires an indication of grants that are needed for Year 1 and Year 2 to determine the tranches of funding to the programme.
Year 2 Budget - Grant Instrument Type | Indicate if the grant for this budget line will be deployed as a pure grant, repayable grant, concessional loan, guarantee, or other financial instrument.
Programme Management Costs
Overview | Programme Management costs are not to exceed 18% of the total programme budget.
Management and Operations | Management and Operations include the costs for coordinating and managing at the programme level. This includes a Programme Manager, support staff, operations (rental, internet, etc.).
Communication and Learning | Budget for communications and learning should be included here. This can include the cost for printing material, journalists, events, etc.
Programme Oversight | This includes staffing cost for an M&E officer if needed, budgeting for audits, and other oversight activities.
Audits | The Convening Agent should budget for independent audits of the programme. This budget line should be included in the Programme Management Costs in the Programme Oversight category.
Indirect Costs
Overview | Indirect costs are not to exceed 7% of the total programme budget.
Guidance: Workplan
Overview | The workplan sheet is for the Convening Agent to communicate the annual targets and workplan for the programme. To note, Outcome, Output, Activity and budget amounts will be automatically populated through input to Sheet A: Budget by Outcome.
Annual Targets | Indicate the Annual Targets for each output, corresponding, when possible, with the results indicators in the programme document.
Time Frame | Indicate the timeframe for each activity by color filling the corresponding cells. A quarterly timeline is needed for the first two years.
Overall Budget Description | Provide an overall description of the activity and the associated process and objectives in 2-5 sentences.
Guidance: Budget by UNDG Categories
Overview | UNDG Budget Categories are used by the UN Multi-Partner Trust Fund Office for accounting purposes. The values should be autopoulated based on the input to Sheet A. For guidance on what category to use, refer to the link on the right. | https://proposals.sdgfund.org/node/69
Co-Recipient (if any) | Additional Co-Recipient columns can be added if they are receiving grants directly from the GFCR. The formulas to populate the Co-recipient columns will need to be revised to include the name of the organisation entered in the Recipient Organisation column Sheet A.
Additional Guiding Principles
Travel | Travel must be strictly related to implementation of the programme. However, if travel is requested for international events or conferences, the GFCR Secretariat must pre-approve the trip through a written request. No first class/business class travel is permitted.
Policy Work | Policy work is not the focus of the GFCR but does play an important role in creating the proper enabling conditions for blue economy investments. We encourage Convening Agents to identify other sources of co-financing for policy work and embed it within the larger GFCR vision. The GFCR can support some policy work but rather than a percentage of the total project it would be a total cost over a specific period. For reference, a hypothetical GFCR programme in the Caribbean would not be granted more than US$200k for policy work over a period of four years.
Staff Costs | Staff costs of the Convening Agent should aim to be within the 20-25% range of the total budget. This includes staff costs under Programme Management Costs as well as the staff costs in Programme Outcome Costs section in Sheet A. The GFCR Secretariat will also carefully assess the level of staff costs to co-implementers.

## A. Budget by Outcome
BUDGET BY OUTCOME
GFCR Philippines
Outcome | Output | Activity | Budget Lines | UNDG Budget Category (1-7) | Recipient Organization | Implementing Partner (if any) | Unit quantity | Unit Cost (USD) | Duration | Time unit (Time units or Lump sum) | GFCR BUDGET Phase 1 07/22-06/24 |  |  | GFCR REPLENISHMENT MM/YY-MM/YY |  | Narrative description of budget lines | Deliverables, objectives and targets of activity | GFCR BUDGET Phase 1 07/22-06/24
[11 empty] | Phase I Approved GFCR Grant | Expenditures & Commitments (Output-level only) |  | Replenishment Request | New TOTAL (Phase I + Replenishment) |  |  | Phase I Approved GFCR Grant | Expenditures & Commitments (Output-level only)
Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs and under delegation of management
Activity 1.1.1: Design of the co-management arrangements and set-up of the Special Purpose Entities (SPEs – formed by local partners and Blue finance) that will co-manage 2 additional MPA networks on behalf of Governments.
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 3 | 17500 | 1 | Years |  |  |  | 17500 |  | Senior local management team + local technical staff . | D1.1.1a: 2 co-management agreement signed with LGUs for MPA network in Palawan D1.1.1b: co-management agreement signed with LGUs for MPA network in Calamian or other location Preparatory activities include MPA legal co-management arrangements, alignment with local policy priorities, legal design of the Special Purpose Entities (SPEs) and their by-laws, identification of community leadership, entrepreneurial capacity building, expert knowledge exchange, governance approaches, due diligence on local partners’ capacities, sustainable management strategy (rooted in science). Plans will be developed in consultations with local stakeholders. A coalition of local stakeholders (e.g. NGOs, associations, cooperatives, foundations) will be selected to become members of the SPE. Proper due diligence will be conducted beforehand on stakeholders.
|  |  | Travel | 5 | Blue finance | Blue Alliance PHI | 3 | 6000 | 1 | Years |  |  |  | 6000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.1.1: | [7 empty] | 62775 |  |  | 23500 | 86275 |  |  | 62775
Activity 1.1.2: Consolidation of the SPEs ‘Blue Alliance VIP’
|  |  | Staff and Personnel | 1 | Blue finance | [8 empty] | 0 | [5 empty] | 2
|  |  | Travel | 5 | Blue finance | [8 empty] | 0 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.1.2: | [7 empty] | 34000 |  |  | 0 | 34000 |  |  | 34000
Activity 1.1.3: Stakeholder engagement and advocacy in the MPA networks
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 3 | 5000 | 2 | Years |  |  |  | 10000 |  | Senior local management team + local technical staff . | D1.1.3 8 stakeholder meetings To ensure alignment with all the various stakeholders involved, consultations process will be organized with stakeholders from central, province and local governments, tourism industry, fishing sector, local communities and other public institutions.
[10 empty] | Years |  |  |  | 0
|  |  | Travel | 5 | Blue finance | Blue Alliance PHI | 3 | 2000 | 2 | Years |  |  |  | 4000 |  | Travel, DSA etc
|  |  | Travel | 5 | [5 empty] | Years |  |  |  | 0 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.1.3: | [7 empty] | 34625 |  |  | 14000 | 48625 |  |  | 34625
Activity 1.1.4: MPA screening, feasibility study and selection of new priority sites in Philippines
|  |  | Staff and Personnel | 1 | Blue finance |  | 1 | 15000 | 1 | Years |  |  |  | 15000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.1.4: Feasibility study for 1 MPA location . The project will identify projects based on ecological, legal, management and business criteria through desk study and preliminary consultations with local stakeholders. Priority MPA(s) will be selected in collaboration with Government and UNDP partners and based on the 50 reefs priority listing. A scoring decision tool describing the rationale for site prioritization will be shared with participating sites. The priority sites will be selected in agreement with participating stakeholders (inception meeting in the selected site). The scoring tool used has three major components – Impact Feasibility, Legal Feasibility, and Business Feasibility with a total of 54 indicators.
|  |  | Travel | 5 | Blue finance |  | 2 | 5000 | 1 | Years |  |  |  | 5000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.1.4: | [7 empty] | 0 |  |  | 20000 | 20000 |  |  | 0
|  |  | Sub-Total Output 1.1: | [7 empty] | 131400 |  |  | 57500 | 188900 |  |  | 131400
Output 1.2: Increase in well managed and enforced LMMAs that protect and promote healthy reefs
Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation, natural resource management and MPA management
|  |  | Staff and Personnel | 1 | Blue finance |  | 2 | 55000 | 2 | years |  |  |  | 110000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.2.1a: Minimum increase of +20% in the average score for Mindoro MPA management performance compared to baseline in 2022. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1b: Minimum increase of +20% in the average score for Palwan MPA management performance compared to baseline in 2024. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1c: Minimum increase of +20% in the average score for CIG MPA management performance compared to baseline in 2025. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1d: 120 jobs created in 2026 as MPA staffThe final objective is to have BA PHI managing effectively the MPAs. Targets include continuous capacity-building activities for the SPE local staff in science, conservation, fishery management, marine spatial planning processes, coral reef high-res mapping, community based coral reef monitoring, compliance strategies, mangrove restoration and conservation, aquaculture, water quality, management, HR issue resolution, procurement, patrolling, communication, maintenance, etc.. Through training, coaching, and regular follow-up, the capabilities and capacities of our partners will be buit to implement on-the-ground MPA management and financing activities and to strengthen their scientifc expertise.
0
|  |  | Travel | 5 | Blue finance |  | 2 | 6000 | 2 | years |  |  |  | 12000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.2.1: | [7 empty] | 39375 | 0 |  | 122000 | 161375 |  |  | 39375
Activity 1.2.2: Commercial and management technical assistance through project Management Office (PMO) services for the SPEs.
|  |  | Staff and Personnel | 1 | Blue finance | [8 empty] | 0 | [5 empty] | 30000
|  |  | Travel | 5 | Blue finance | [8 empty] | 0
|  |  | Sub-Total Activity 1.2.2: | [7 empty] | 48000 | 0 |  | 0 | 48000 |  |  | 48000
Activity 1.2.3: Support to SPE activities in conservation, enforcement, community engagement and monitoring
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 140000 | 2 | Years |  |  |  | 280000 |  | Budget covers the annual Blue Alliance PHI costs in operations, staff, equipment and maintenance to co-manage the VIP MPA networks . | D1.2.1a: Minimum increase of +20% in the average score for Mindoro MPA management performance compared to baseline in 2022. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1b: Minimum increase of +20% in the average score for Palwan MPA management performance compared to baseline in 2024. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1c: Minimum increase of +20% in the average score for CIG MPA management performance compared to baseline in 2025. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1d: 120 jobs created in 2026 as MPA staff The objective is to implement MPA day-to-day work in 5 fundamental and interrelated fields of operation: i. Compliance through patrolling and enforcement ; ii. Community engagement through trainings and awareness campaigns; iii. Wildlife monitoring and conservation through robust science; iv. Conservation of coral reefs and associated ecosystems ; v. Management and HR Activities include: A. Regular Patrolling and compliance activities to reduce illegal and destructive fishing. Development of information and engagement campaigns with local communities. Monitoring & Evaluation of performances; B. Community engagement through training on conservation and fishery regulations for rangers and community members ; collaboration arrangements with local Government Units and authorities ; deputization of community rangers; C. Wildlife monitoring through (i) regular underwater survey campaigns on fish biomass, coral cover, biodiversity (ii) through mangrove and seagrass health assessments, (iii) through regular Catch-Per-Unit-Effort campaigns with fishers; D. Conservation of coral reef and mangrove ecosystems through removal of invasive species, reduction of by-catch in fisheries, setup of hatcheries for turtles and education content ;E. General management, maintenance and HR |  |  | 30000
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 75000 | 2 | Years |  |  |  | 150000 |  | Budget covers the annual Blue Alliance PHI costs in operations, staff, equipment and maintenance to co-manage the Palawan MPA network .
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 65000 | 1 | Years |  |  |  | 65000 |  | Budget covers the annual Blue Alliance PHI costs in operations, staff, equipment and maintenance to co-manage the Calamian MPA network (or other) .
|  |  | Sub-Total Activity 1.2.3: | [8 empty] | 0 |  | 495000 | 495000 |  |  | 48000
|  |  | Sub-Total Output 1.2: | [7 empty] | 87375 | 0 |  | 617000 | 704375 | 0 |  | 87375 | 0
Output 1.3: Preparation and management of a blended finance vehilce for MPAs to address some of the key drivers of coral reef degradation
Activity 1.3.1: Design and implementation of the business plans for the 3 MPA networks with main revenue strategy based on 3 interventions:
|  |  | Staff and Personnel | 1 | Blue finance |  | 1 | 10000 | 1 |  |  |  |  | 10000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.3.1 1 Business plan for MPA network Design of the business plans for the MPA networks with main revenue strategy based on reef positive businesses. Activities include robust financial projections and scenario analyses, investment structures, detailed commercial strategies, market analyses, international & local expert consultations, mangrove GIS, carbon assessments, carbon ownership, design and development of MRV (Monitoring, Reporting and Verification) carbon methods. Plans will be developed in consultations with local stakeholders. |  |  | 30000
|  |  | Travel | 5 | Blue finance | [8 empty] | 0 |  | Travel, DSA etc |  |  |  |  | 2
|  |  | Sub-Total Activity 1.3.1: | [7 empty] | 45000 | 0 |  | 10000 | 55000 |  |  | 45000
Activity 1.3.2: Design of the MPA blended investment finance facility for aggregating the investments in the SPEs
|  |  | Staff and Personnel | 1 | Blue finance |  | 1 | 25000 | 1 | years |  |  |  | 25000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.3.2. Summary scheme of the blended finance vehicle. Activities include complete the structuring of all the elements of the blended finance facility, comprising the investment vehicle, and the loan facility; guarantees, climate insurance, risk hedging and tax assessment |  |  | 30000
|  |  | Contractual Services | 4 | Blue finance | Legal advisers |  | 15000 | 1 | years |  |  |  | 15000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.3.2: | [7 empty] | 41250 | 0 |  | 40000 | 81250 |  |  | 41250
Activity 1.3.3: Fundraising with a pool of investors & donors
|  |  | Staff and Personnel | 1 | Blue finance |  | 2 | 35000 | 2 | years |  |  |  | 70000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.3.3 At least 2 new investors with interest in the blended finance vehicle for MPAs Fundraising with a pool of investors & donors in order to blend donations, concessionary loans and impact investments. Activities include funder mapping (identify long-list of philanthropic institutions, family offices, impact investors, donor agencies, climate funds and development banks), facilitate introductions with short-list of priority funders, pitch material, funder meetings." |  |  | 30000
|  |  | Travel | 5 | Blue finance |  | 2 | 6000 | 2 | years |  |  |  | 12000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.3.3: | [7 empty] | 45000 | 0 |  | 82000 | 127000 |  |  | 45000
Activity 1.3.4: Design, development and monitoring of Key Performance Indicators (KPIs) and results metrics for MPAs
|  |  | Staff and Personnel | 1 | Blue finance |  | 2 | 15000 | 2 | years |  |  |  | 30000 |  | Senior international management team BF + junior management team + expert technical staff . | D1.3.4 Harmonised table of Key Performance Indicators Social and environmental KPIs will be designed, tested and collected with impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). |  |  | 30000
|  |  | Travel | 5 | Blue finance |  | 2 | 4000 | 2 | years |  |  |  | 8000 |  | Travel, DSA etc
|  |  | Sub-Total Activity 1.3.4: | [7 empty] | 14250 | 0 |  | 38000 | 52250 |  |  | 14250
0
0
|  |  | Sub-Total Activity 1.3.5: | [8 empty] | 0 |  | 0 | 0
|  |  | Sub-Total Output 1.3: | [7 empty] | 145500 | 0 |  | 170000 | 315500 |  |  | 145500
Output 1.4: MPA blended finance investment facilities mobilise public and private investment for MPAs to address some of thekey drivers of coral reef degradation
Activity 1.4.1: Co-fund early-stage CAPEX of the SPEs managing the MPA networks
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 55000 | 1 |  |  |  |  | 55000 |  | Capital expenditures in fixed assets for MPAs | D1.2.1a: Minimum increase of +20% in the average score for Mindoro MPA management performance compared to baseline in 2022. This is measured with MEAT (Management Effectiveness Assessment Tool) Support includes CAPEX for MPAs in VIP such as MPA scientific and enforcement equipment, vessels, moorings, buoys, vehicles, mangrove restoration and credit certifcation and services to improve visitors’ experience and safety
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 85000 | 1 |  |  |  |  | 85000 |  | Capital expenditures in fixed assets for MPAs | D1.2.1b: Minimum increase of +20% in the average score for Palwan MPA management performance compared to baseline in 2024. This is measured with MEAT (Management Effectiveness Assessment Tool) fSupport includes CAPEX for MPAs in Palawan such as MPA scientific and enforcement equipment, vessels, moorings, buoys, vehicles, mangrove restoration and credit certifcation and services to improve visitors’ experience and safety
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 50000 | 1 |  |  |  |  | 50000 |  | Capital expenditures in fixed assets for MPAs | D1.2.1c: Minimum increase of +20% in the average score for CIG MPA management performance compared to baseline in 2025. This is measured with MEAT (Management Effectiveness Assessment Tool) Support includes CAPEX for MPAs in Calamian (or other) such as MPA scientific and enforcement equipment, vessels, moorings, buoys, vehicles, mangrove restoration and credit certifcation and services to improve visitors’ experience and safety
0
|  |  | Sub-Total Activity 1.4.1: | [7 empty] | 1450000 | 0 |  | 190000 | 1640000 |  |  | 1450000
30000
30000
|  |  | Sub-Total Activity 1.4.2: | [7 empty] | 0 | 0 |  | 0 | 0 |  |  | 0
[11 empty] | 0 | 0 | [5 empty] | 0 |  | 30000
[11 empty] | 0 | 0 | [5 empty] | 0
|  |  | Sub-Total Output 1.4: | [7 empty] | 1450000 | 0 |  | 190000 | 1640000 |  |  | 1450000
Sub-Total OUTCOME 1: | [10 empty] | 1814275 | 0 |  | 1034500 | 2848775 |  |  | 1814275
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output 2.1: A pipeline of reef-positive businesses that generate returns for MPAs and address key drivers of coral reef degradation in & around the MPAs is developed
Activity 2.1.1: Finalise the preparation for an investment transaction in a hatchery and extensive aquaculture for mangrove crab in the VIP (around the MPAs of North Oriental Mindoro, VIP).
[12 empty] | 0 |  | 0
[14 empty] | 0 |  | Travel, DSA etc
|  |  | Sub-Total Activity 2.1.1: | [7 empty] | 104250 | 0 |  | 0 | 104250 |  |  | 104250
Activity 2.1.2: Scoping and development of a pipeline of reef-positive businesses that will produce investment returns to the MPAs
|  |  | Staff and Personnel | 1 | Blue finance |  |  | 25000 | 2 | years |  |  |  | 50000 |  | Budget covers the costs of the senior management team from Blue finance International. | D2.1.2a Business plans of a second cohort of reef-positive businesses. Scoping and design activities include robust financial projections and scenario analyses for new businesses in ecotourism (eco-cruise, ecolodge), extension blue carbon in other locations, new aquaculture sectors and fishery supply chain facilities. In particular, analysis will cover investment structures, detailed commercial strategies, market analyses, expert consultations, mangrove GIS, carbon assessments, aquaculture technical and ecological feasibility, fishery market assessment, screening and feasibility of other investible projects. Whenever possible, activities are conducted in consultations with local stakeholders. Preparation activities include various kinds of technical support in science and management, preparation of all relevant interventions on policy, governance, fishery and farming governance and seafood processing, levels including the underlying detailed investment and business plans subject to detailed financial analysis and due diligence. It also includes also entrepreneurial capacity-building and finalisation of legal and financial arrangements on both project and investment sides (due diligence, local vehicles to channel investment). This activity specifically focuses on improving the capacity of businesses that have received support and investment through this project to be able to understand the outcomes of the environmental impact assessments and going forward measure and manage the environmental impact of their operations. Project will support in the upskilling through training and technical assistance during the course of the implementation of each of the projects selected from the pipeline. Additionally, this activity will also cater for environmental impact assessments for each of the projects |  |  | 30000
|  |  | Contractual Services | 4 | Blue finance |  |  | 15000 | 1 | years |  |  |  | 15000 |  | Budget covers the costs of the senior experts in aquaculture
|  |  | Contractual Services | 4 | Blue finance |  |  | 15000 | 1 | years |  |  |  | 15000 |  | Budget covers the costs of the senior experts in tourism |  |  |  | 20000
|  |  | Contractual Services | 4 | Blue finance |  |  | 15000 | 1 | years |  |  |  | 15000 |  | Budget covers the costs of the senior experts in blue carbon .
|  |  | Contractual Services | 4 | Blue finance |  |  | 10000 | 1 | years |  |  |  | 10000 |  | Budget covers the costs of the senior experts in fisheries.
0
|  |  | Sub-Total Activity 2.1.2: | [7 empty] | 85500 | 0 |  | 105000 | 190500 |  |  | 85500
Activity 2.1.3: Preparation and implementation of the pipeline of reef-positive businesses.
|  |  | Staff and Personnel | 1 | Blue finance |  |  | 40000 | 2 | years |  |  |  | 80000 |  | Budget covers the costs of the senior management team from Blue Alliance International. | Activities include facilitating the signing of the investment instruments for each intervention, arranging long-term Project Management Office (PMO) contracts for each intervention to ensure “on-the- ground” management focus on revenue and implementation of the strategy. sustainability. Activities include Writing of project design documents and submission to the standard (project listing), Start of validation, Validation audit and finalisation of validation (project registration), Field visit, Implementation of project activities – conservation and planting as per defined on the action plan, Implementation of monitoring and reporting activities; Audits (verifications) and carbon standards communications, Continous management of project impacts,notably carbon assets and issuances" |  |  | 30000
|  |  | Staff and Personnel | 1 | Blue finance |  |  |  | 2 | years |  |  |  | 0 |  | Budget covers the costs of the senior experts in aquaculture
|  |  | Contractual Services | 4 | Blue finance |  |  | 15000 | 2 | years |  |  |  | 30000 |  | Budget covers the costs of the senior experts in tourism |  |  |  | 20000
|  |  | Contractual Services | 4 | Blue finance |  |  | 20000 | 2 | years |  |  |  | 40000 |  | Budget covers the costs of the senior experts in blue carbon .
|  |  | Contractual Services | 4 | Blue finance |  |  | 20000 | 2 | years |  |  |  | 40000 |  | Budget covers the costs of the senior experts in fisheries.
[10 empty] | years |  |  |  | 0
|  |  | Sub-Total Activity 2.1.3: | [7 empty] | 56250 | 0 |  | 190000 | 246250 |  |  | 56250
Activity 2.1.4: Technical assistance for Investment implementation.
[10 empty] | years |  |  |  | 0 | [5 empty] | 30000
[10 empty] | years |  |  |  | 0
[10 empty] | years |  |  |  | 0 | [5 empty] | 20000
0
0
0
|  |  | Sub-Total Activity 2.1.4: | [7 empty] | 55500 | 0 |  | 0 | 55500 |  |  | 55500
Activity 2.1.5: Upskilling local businesses and communities through trainings and mentorship programmes
|  |  | Contractual Services | 4 | Blue finance | Blue Alliance PHI |  | 30000 | 2 | years |  |  |  | 60000 |  | Budget covers part of partner costs in operations, staff, equipment to implement community development activities | D2.1.1: 1000 beneficiaries of the programmes (with details on sex, age, community origin) The objective is create alternative livelihood for fishers, creating an incentive to fish less (or better) on the reef . Programme includes 2 components: (i) design and implementation of Income Generating Activities with fisher households in & around the MPAs (usually linked to the reef-positive businesses and (ii) a community savings and lending programme with incubation support, and micro-finance loans. Activities include meetings with communities to identify needs, past experiences, identification of champions / entrepreneurs, planning , business plans and initial development of the programmesIncreased access to finance and other resources, is key element to reducing risks, enabling capacities, and supporting community members to apply their capacities. A community savings and lending programme fosters savings, incubation support, and micro-finance loans. Coupled with training and market linkages this enhances the capabilities and capacities of local participants to develop marine-positive microenterprises, encourages local entrepreneurship, and builds greater appreciation for ecosystem services.
[14 empty] | 0 |  | Travel, DSA etc
|  |  | Sub-Total Activity 2.1.5: | [7 empty] | 30000 | 0 |  | 60000 | 90000 |  |  | 30000
|  |  | Sub-Total Output 2.1: | [7 empty] | 331500 | 0 |  | 355000 | 686500 |  |  | 331500
Output 2.2: The MPA blended finance investment facilities mobilise public and private investments for reef-positive businesses that generate investment returns for MPAs and address specific drivers of coral reef degradation
Activity 2.2.1: Co-fund CAPEX costs of the mangrove crab aquaculture business.
|  |  | Contractual Services | 4 | Blue finance | Aquahub | 1 | 250000 | 1 | years |  |  |  | 250000 |  | Materials and equipment, working capital | "Support includes CAPEX for the construction of the hatchery, nursery and processing facilities, Support includes Initial OPEX for the pilot project (staff, community farmers, fingerlings, materials, insurance, back office, etc..)
[7 empty] | 1 | [6 empty] | 0
|  |  | Sub-Total Activity 2.2.1: | [7 empty] | 200000 | 0 |  | 250000 | 450000 |  |  | 200000
Activity 2.2.2: Co-fund early-stage CAPEX costs of the pipeline of reef-positive businesses of nature-based ecotourism
|  |  | Contractual Services | 4 | Blue finance | Bluewild | 1 | 50000 | 1 | years |  |  |  | 50000 |  | Materials and equipment, working capital | Support includes CAPEX for the coral safari programme (e.g. vessel, UW communication and gears, land facilities, sales office) Support includes OPEX for the coral safari programme (staff, eco-guides, COS, fuel, food, insurance, marketing, etc..)
|  |  | Sub-Total Activity 2.2.2: | [7 empty] | 300000 | 0 |  | 50000 | 350000 |  |  | 300000
Activity 2.2.3: Co-fund early-stage CAPEX costs of the seacucumber community based aquaculture
|  |  | Contractual Services | 4 | Blue finance | Aquahub | 1 | 300000 | 1 | years |  |  |  | 300000 |  | Materials and equipment, working capital | "Support includes CAPEX for the commercial grow-out farms (vehicles, fencing, materials, floating cages, etc.) Support includes CAPEX for the design and construction of the hatchery, nursery and processing facilities, Support includes Initial OPEX for the pilot project (staff, community farmers, fingerlings, materials, insurance, back office, etc..)
|  |  | Sub-Total Activity 2.2.3: | [7 empty] | 0 | 0 |  | 300000 | 300000 |  |  | 0
Activity 2.2.4: Co-fund early-stage CAPEX costs of the pipeline of fishery supply chain improvement for fisher communities .
|  |  | Contractual Services | 4 | Blue finance | Aquahub | 1 | 100000 | 1 | years |  |  |  | 100000 |  | Materials and equipment, working capital | "Support includes initial CAPEX for the fish processing facility (building, cold chain, tracability, vehicles, etc.) Support includes initial OPEX for the fish processing facility (staff, fisher training, transport, etc.)"
[7 empty] | 1 | [6 empty] | 0
|  |  | Sub-Total Activity 2.2.4: | [7 empty] | 0 | 0 |  | 100000 | 100000 |  |  | 0
Activity 2.2.5: Co-fund CAPEX costs of reef-positive businesses belonging to the second cohort
|  |  | Contractual Services | 4 | Blue finance | Bluewild | 1 | 100000 | 1 |  |  | Materials and equipment, working capital |  | 100000 |  | Materials and equipment, working capital | Support includes initial CAPEX for reef-positive businesses in aquaculture and ecotourism identified through activity 2.2.1 Support includes initial OPEX for reef-positive businesses in aquaculture and ecotoruism
|  |  |  | 4 | Blue finance | Aquahub | 1 | 100000 | 1 |  |  | 0 |  | 100000
[11 empty] | 0 | 0 |  | 200000 | 200000 |  |  | 0
|  |  | Sub-Total Output 2.2: | [7 empty] | 500000 | 0 |  | 900000 | 1400000 |  |  | 500000
Sub-Total OUTCOME 2: | [10 empty] | 831500 | 0 |  | 1255000 | 2086500 |  |  | 831500
Monitoring and Evaluation Costs
5.1 Baseline Assessments
Activity 5.1.1: Baseline Assessment for Palawan and Calamian (or other): Biodiversity metrics and fishery
|  | 5.1.1.1 | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 42000 | 1 |  |  |  |  | 42000 |  | Senior local management team + local technical staff in 2 MPA netwroks | Social and environmental KPIs will be assessed (baseline) through impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). Activities include UW survey campaigns, CPUE campaigns, e-DNA campaigns and mangrove GIS surveys
|  | 5.1.1.2 | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 80000 | 1 |  |  |  |  | 80000 |  | Senior Central team science team
|  | 5.1.1.3 | [11 empty] | 0
|  | 5.1.1.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.1.1 | [7 empty] | 0 | 0 | 0 | 122000
Activity 5.1.2: Name of type of Baseline Assessment
|  | 5.1.2.1 | [11 empty] | 0
|  | 5.1.2.2 | [11 empty] | 0
|  | 5.1.2.3 | [11 empty] | 0
|  | 5.1.2.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.1.2: | [7 empty] | 0 | 0 | 0 | 0
Activity 5.1.3: Name of type of Baseline Assessment
|  | 5.1.3.1 | [11 empty] | 0
|  | 5.1.3.2 | [11 empty] | 0
|  | 5.1.3.3 | [11 empty] | 0
|  | 5.1.3.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.1.3: | [7 empty] | 0 | 0 | 0 | 0
Activity 5.1.4: Name of type of Baseline Assessment
|  | 5.1.4.1 | [11 empty] | 0
|  | 5.1.4.2 | [11 empty] | 0
|  | 5.1.4.3 | [11 empty] | 0
|  | 5.1.4.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.1.4: | [7 empty] | 0 | 0 | 0 | 0
|  |  | Sub-Total Baseline Assessments: | [7 empty] | 0 | 0 | 0 | 122000
5.2 Impact Monitoring
Activity 5.2.1: Impact Monitoring in Mindoro, Palawan and Calamian MPA network
|  | 5.1.1.1 | Contractual Services | 4 | Blue finance | Blue Alliance PHI | 1 | 82000 | 1 |  |  |  |  | 82000 |  | Senior local management team + local technical staff in 2 MPA netwroks | Social and environmental KPIs will be monitored through impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). Activities include UW survey campaigns, CPUE campaigns, e-DNA campaigns and mangrove GIS surveys
|  | 5.2.1.2 | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 94000 | 1 |  |  |  |  | 94000 |  | Senior Central team science team
|  | 5.2.1.3 | [11 empty] | 0
|  | 5.2.1.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.2.1 | [7 empty] | 0 | 0 | 0 | 176000
Activity 5.2.2: Name of type of Impact Monitoring
|  | 5.2.2.1 | [11 empty] | 0
|  | 5.2.2.2 | [11 empty] | 0
|  | 5.2.2.3 | [11 empty] | 0
|  | 5.2.2.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.2.2: | [7 empty] | 0 | 0 | 0 | 0
Activity 5.2.3: Name of type of Impact Monitoring
|  | 5.2.3.1 | [11 empty] | 0
|  | 5.2.3.2 | [11 empty] | 0
|  | 5.2.3.3 | [11 empty] | 0
|  | 5.2.3.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.2.3: | [7 empty] | 0 | 0 | 0 | 0
Activity 5.2.4: Name of type of Impact Monitoring
|  | 5.2.4.1 | [11 empty] | 0
|  | 5.2.4.2 | [11 empty] | 0
|  | 5.2.4.3 | [11 empty] | 0
|  | 5.2.4.4 | [11 empty] | 0
|  |  | Sub-Total Activity 5.2.4: | [7 empty] | 0 | 0 | 0 | 0
|  |  | Sub-Total Impact Monitring: | [7 empty] | 0 | 0 | 0 | 176000
Sub-Total MONITORING | [11 empty] | 0 |  | 298000 | 0 |  |  | 831500
0
Total PROGRAMME OUTCOME COSTS: | [10 empty] | 2645775 | 0 |  | 2587500 | 4935275 |  |  | 2645775
B. PROGRAMME MANAGEMENT COSTS | [15 empty] | Narrative description of budget lines
Management and Operations
N/A | N/A | N/A | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 85000 | 2 | Years |  |  |  | 170000 |  | Programme Manager - SB4-3 |  |  |  | 2
N/A | N/A | N/A | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 65000 | 2 | Years |  |  |  | 130000 |  | Admin Support Officer - SB3-3
N/A | N/A | N/A | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 45000 | 2 | Years |  |  |  | 90000 |  | Programme Support Officer - SB3-3
N/A | N/A | N/A | Travel | 5 | Blue finance | Blue finance | 2 | 6000 | 2 | Lump Sum |  |  |  | 12000 |  | Travel, DSA etc
N/A | N/A | N/A | General Operating and Other Direct Cost | 7 | Blue finance | Blue finance | 2 | 12000 | 2 | Lump Sum |  |  |  | 24000 |  | Operations (rental, internet, phone, laptop etc)
N/A | N/A | N/A | General Operating and Other Direct Cost | 7 | Blue finance | Blue finance | 1 |  | 2 | Years |  |  |  | 0 |  | Operations (rental, internet, phone, laptop etc)
N/A | N/A | N/A | General Operating and Other Direct Cost | 7 | Blue finance | Blue finance | 1 |  | 2 | Years |  |  |  | 0 |  | Operations (rental, internet, phone, laptop etc)
|  |  | Sub-Total Management and Operations | [7 empty] | 166800 | 0 |  | 426000 | 592800 |  |  | 166800
Communications and Learning
N/A | N/A | N/A | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 35000 | 2 | Years |  |  |  | 70000 |  | Communications officer - SB4-3 (responsible for development and implementation of comms plan)
N/A | N/A | N/A | General Operating and Other Direct Cost | 7 | Blue finance | Blue finance | 1 | 2000 | 2 | Lump Sum |  |  |  | 4000 |  | COMMUNICATIONS: Printing costs
N/A | N/A | N/A | Contractual Services | 4 | Blue finance | Blue finance | 1 | 10000 | 1 | Lump Sum |  |  |  | 10000 |  | Consultant to draft Learning and Sharing Plan
N/A | N/A | N/A | General Operating and Other Direct Cost | 7 | Blue finance | Blue finance | 1 |  | 2 | Years |  |  |  | 0
N/A | N/A | N/A | Contractual Services | 4 | Blue finance | Blue finance | 1 | 10000 | 2 | Lump Sum |  |  |  | 20000 |  | COMMUNICATIONS: Hire photographers, story writers, translators, interpreters, video producers, etc.
|  |  | Sub-Total Communications and Learning | [7 empty] | 42000 | 0 |  | 104000 | 146000 |  |  | 42000
Project audit, ESG, PSEAH
N/A | N/A | N/A | Staff and Personnel | 1 | Blue finance | Blue finance | 1 | 15000 | 2 | Years |  |  |  | 30000 |  | ESG offcer and PSEAH safeguards
N/A | N/A | N/A | Contractual Services | 4 | Blue finance | Blue finance | 1 | 8000 | 2 | Years |  |  |  | 16000 |  | Programme audit - external consultant
|  |  | Sub-Total Evaluation | [7 empty] | 37500 | 0 |  | 46000 | 83500 |  |  | 37500
|  |  | TOTAL PROGRAMME MANAGEMENT COSTS: | [7 empty] | 246300 |  |  | 576000 | 822300 |  |  | 246300
|  |  | TOTAL DIRECT PROGRAMME COSTS | [7 empty] | 2892075 |  |  | 3163500 | 5757575 |  |  | 2892075
|  |  | Indirect Programme Support Costs (7%) | [7 empty] | 202445.25 |  |  | 221445 | 403030.25 |  |  | 202445.25
|  |  | TOTAL COSTS | [7 empty] | 3094520.25 |  |  | 3384945 | 6160605.25 |  |  | 3094520.25

## B. Workplan
Outcome and Output
Outcome 1: Protection, effective management and sustainable financing of priority coral reef sites and climate change-affected refugia | List of activities | Time Frame (Quarterly) | [24 empty] | PLANNED BUDGET (USD)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Overall budget description | Deliverable, objectives and targets of activity | Replenishment Request | New TOTAL (Phase I + Replenishment)
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs and under delegation of management | Activity 1.1.1: Design of the co-management arrangements and set-up of the Special Purpose Entities (SPEs – formed by local partners and Blue finance) that will co-manage 2 additional MPA networks on behalf of Governments. | [24 empty] | Senior local management team + local technical staff . | D1.1.1a: 2 co-management agreement signed with LGUs for MPA network in Palawan D1.1.1b: co-management agreement signed with LGUs for MPA network in Calamian or other location Preparatory activities include MPA legal co-management arrangements, alignment with local policy priorities, legal design of the Special Purpose Entities (SPEs) and their by-laws, identification of community leadership, entrepreneurial capacity building, expert knowledge exchange, governance approaches, due diligence on local partners’ capacities, sustainable management strategy (rooted in science). Plans will be developed in consultations with local stakeholders. A coalition of local stakeholders (e.g. NGOs, associations, cooperatives, foundations) will be selected to become members of the SPE. Proper due diligence will be conducted beforehand on stakeholders. | 57500 | 188900 | bar: 1 to 18
| Activity 1.1.2: Consolidation of the SPEs ‘Blue Alliance VIP’ | [24 empty] | 0 | 0
| Activity 1.1.3: Stakeholder engagement and advocacy in the MPA networks | [24 empty] | Senior local management team + local technical staff . | D1.1.3 8 stakeholder meetings To ensure alignment with all the various stakeholders involved, consultations process will be organized with stakeholders from central, province and local governments, tourism industry, fishing sector, local communities and other public institutions. | bar: 1 to 3; 12 to 14; 22 to 24
| Activity 1.1.4: MPA screening, feasibility study and selection of new priority sites in Philippines | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.1.4: Feasibility study for 1 MPA location . The project will identify projects based on ecological, legal, management and business criteria through desk study and preliminary consultations with local stakeholders. Priority MPA(s) will be selected in collaboration with Government and UNDP partners and based on the 50 reefs priority listing. A scoring decision tool describing the rationale for site prioritization will be shared with participating sites. The priority sites will be selected in agreement with participating stakeholders (inception meeting in the selected site). The scoring tool used has three major components – Impact Feasibility, Legal Feasibility, and Business Feasibility with a total of 54 indicators. | bar: 1 to 11
Output 1.2: Well-managed LMMAs and no-take zones | Activity 1.2.1: Technical & Scientific assistance and trainings in coral reef conservation, natural resource management and MPA management | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.2.1a: Minimum increase of +20% in the average score for Mindoro MPA management performance compared to baseline in 2022. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1b: Minimum increase of +20% in the average score for Palwan MPA management performance compared to baseline in 2024. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1c: Minimum increase of +20% in the average score for CIG MPA management performance compared to baseline in 2025. This is measured with MEAT (Management Effectiveness Assessment Tool) D1.2.1d: 120 jobs created in 2026 as MPA staffThe final objective is to have BA PHI managing effectively the MPAs. Targets include continuous capacity-building activities for the SPE local staff in science, conservation, fishery management, marine spatial planning processes, coral reef high-res mapping, community based coral reef monitoring, compliance strategies, mangrove restoration and conservation, aquaculture, water quality, management, HR issue resolution, procurement, patrolling, communication, maintenance, etc.. Through training, coaching, and regular follow-up, the capabilities and capacities of our partners will be buit to implement on-the-ground MPA management and financing activities and to strengthen their scientifc expertise. | 617000 | 704375 | bar: 1 to 24
| Activity 1.2.2: Commercial and management technical assistance through project Management Office (PMO) services for the SPEs. | [24 empty] | 0 | 0 | bar: 1 to 24
Output 1.3: Preparation and management of public and private investment for MPAs to address some of the key drivers of coral reef degradation | Activity 1.3.1: Design and implementation of the business plans for the 3 MPA networks with main revenue strategy based on 3 interventions: | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.3.1 1 Business plan for MPA network Design of the business plans for the MPA networks with main revenue strategy based on reef positive businesses. Activities include robust financial projections and scenario analyses, investment structures, detailed commercial strategies, market analyses, international & local expert consultations, mangrove GIS, carbon assessments, carbon ownership, design and development of MRV (Monitoring, Reporting and Verification) carbon methods. Plans will be developed in consultations with local stakeholders. | 170000 | 315500 | bar: 1 to 12
| Activity 1.3.2: Design of the MPA blended investment finance facility for aggregating the investments in the SPEs | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.3.2. Summary scheme of the blended finance vehicle. Activities include complete the structuring of all the elements of the blended finance facility, comprising the investment vehicle, and the loan facility; guarantees, climate insurance, risk hedging and tax assessment | bar: 1 to 8
| Activity 1.3.3: Fundraising with a pool of investors & donors | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.3.3 At least 2 new investors with interest in the blended finance vehicle for MPAs Fundraising with a pool of investors & donors in order to blend donations, concessionary loans and impact investments. Activities include funder mapping (identify long-list of philanthropic institutions, family offices, impact investors, donor agencies, climate funds and development banks), facilitate introductions with short-list of priority funders, pitch material, funder meetings." | bar: 1 to 24
| Activity 1.3.4: Design, development and monitoring of Key Performance Indicators (KPIs) and results metrics for MPAs | [24 empty] | Senior international management team BF + junior management team + expert technical staff . | D1.3.4 Harmonised table of Key Performance Indicators Social and environmental KPIs will be designed, tested and collected with impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). | bar: 1 to 6
Output 1.4: MPA blended finance investment facilities mobilise public and private investment for MPAs to address some of thekey drivers of coral reef degradation | Activity 1.4.1: Co-fund early-stage CAPEX of the SPEs managing the MPA networks | [24 empty] | Capital expenditures in fixed assets for MPAs | D1.2.1a: Minimum increase of +20% in the average score for Mindoro MPA management performance compared to baseline in 2022. This is measured with MEAT (Management Effectiveness Assessment Tool) Support includes CAPEX for MPAs in VIP such as MPA scientific and enforcement equipment, vessels, moorings, buoys, vehicles, mangrove restoration and credit certifcation and services to improve visitors’ experience and safety | 190000 | 1640000 | bar: 1 to 17
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output 2.1: A pipeline of reef-positive businesses that generate returns for MPAs and address key drivers of coral reef degradation in & around the MPAs is developed | [25 empty] | 0 | 0 | 355000 | 686500
| Activity 2.1.2: Scoping and development of a pipeline of reef-positive businesses that will produce investment returns to the MPAs | [24 empty] | Budget covers the costs of the senior management team from Blue finance International. | D2.1.2a Business plans of a second cohort of reef-positive businesses. Scoping and design activities include robust financial projections and scenario analyses for new businesses in ecotourism (eco-cruise, ecolodge), extension blue carbon in other locations, new aquaculture sectors and fishery supply chain facilities. In particular, analysis will cover investment structures, detailed commercial strategies, market analyses, expert consultations, mangrove GIS, carbon assessments, aquaculture technical and ecological feasibility, fishery market assessment, screening and feasibility of other investible projects. Whenever possible, activities are conducted in consultations with local stakeholders. Preparation activities include various kinds of technical support in science and management, preparation of all relevant interventions on policy, governance, fishery and farming governance and seafood processing, levels including the underlying detailed investment and business plans subject to detailed financial analysis and due diligence. It also includes also entrepreneurial capacity-building and finalisation of legal and financial arrangements on both project and investment sides (due diligence, local vehicles to channel investment). This activity specifically focuses on improving the capacity of businesses that have received support and investment through this project to be able to understand the outcomes of the environmental impact assessments and going forward measure and manage the environmental impact of their operations. Project will support in the upskilling through training and technical assistance during the course of the implementation of each of the projects selected from the pipeline. Additionally, this activity will also cater for environmental impact assessments for each of the projects | bar: 1 to 18
| Activity 2.1.3: Preparation and implementation of the pipeline of reef-positive businesses. | [24 empty] | Budget covers the costs of the senior management team from Blue Alliance International. | Activities include facilitating the signing of the investment instruments for each intervention, arranging long-term Project Management Office (PMO) contracts for each intervention to ensure “on-the- ground” management focus on revenue and implementation of the strategy. sustainability. Activities include Writing of project design documents and submission to the standard (project listing), Start of validation, Validation audit and finalisation of validation (project registration), Field visit, Implementation of project activities – conservation and planting as per defined on the action plan, Implementation of monitoring and reporting activities; Audits (verifications) and carbon standards communications, Continous management of project impacts,notably carbon assets and issuances" | bar: 1 to 18
| Activity 2.1.4: Technical assistance for Investment implementation. | [24 empty] | 0 | 0
| Activity 2.1.5: Upskilling local businesses and communities through trainings and mentorship programmes | [24 empty] | Budget covers part of partner costs in operations, staff, equipment to implement community development activities | D2.1.1: 1000 beneficiaries of the programmes (with details on sex, age, community origin) The objective is create alternative livelihood for fishers, creating an incentive to fish less (or better) on the reef . Programme includes 2 components: (i) design and implementation of Income Generating Activities with fisher households in & around the MPAs (usually linked to the reef-positive businesses and (ii) a community savings and lending programme with incubation support, and micro-finance loans. Activities include meetings with communities to identify needs, past experiences, identification of champions / entrepreneurs, planning , business plans and initial development of the programmesIncreased access to finance and other resources, is key element to reducing risks, enabling capacities, and supporting community members to apply their capacities. A community savings and lending programme fosters savings, incubation support, and micro-finance loans. Coupled with training and market linkages this enhances the capabilities and capacities of local participants to develop marine-positive microenterprises, encourages local entrepreneurship, and builds greater appreciation for ecosystem services. | bar: 1 to 24
Output 2.2: The MPA blended finance investment facilities mobilise public and private investments for reef-positive businesses that generate investment returns for MPAs and address specific drivers of coral reef degradation | Activity 2.2.1: Co-fund CAPEX costs of the mangrove crab aquaculture business. | [24 empty] | Materials and equipment, working capital | "Support includes CAPEX for the construction of the hatchery, nursery and processing facilities, Support includes Initial OPEX for the pilot project (staff, community farmers, fingerlings, materials, insurance, back office, etc..) | 900000 | 1400000 | bar: 1 to 12
| Activity 2.2.2: Co-fund early-stage CAPEX costs of the pipeline of reef-positive businesses of nature-based ecotourism | [24 empty] | Materials and equipment, working capital | Support includes CAPEX for the coral safari programme (e.g. vessel, UW communication and gears, land facilities, sales office) Support includes OPEX for the coral safari programme (staff, eco-guides, COS, fuel, food, insurance, marketing, etc..) | bar: 1 to 16
| Activity 2.2.4: Co-fund early-stage CAPEX costs of the pipeline of fishery supply chain improvement for fisher communities . | [24 empty] | Materials and equipment, working capital | "Support includes initial CAPEX for the fish processing facility (building, cold chain, tracability, vehicles, etc.) Support includes initial OPEX for the fish processing facility (staff, fisher training, transport, etc.)" | bar: 1 to 16
| Activity 2.2.5: Co-fund CAPEX costs of reef-positive businesses belonging to the second cohort | [24 empty] | Materials and equipment, working capital | Support includes initial CAPEX for reef-positive businesses in aquaculture and ecotourism identified through activity 2.2.1 Support includes initial OPEX for reef-positive businesses in aquaculture and ecotoruism | bar: 13 to 24
Monitoring and Evaluation Costs
5.1 Baseline Assessments | Activity 5.1.1: Baseline Assessment for Palawan and Calamian (or other): Biodiversity metrics and fishery | [24 empty] | Senior local management team + local technical staff in 2 MPA netwroks | Social and environmental KPIs will be assessed (baseline) through impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). Activities include UW survey campaigns, CPUE campaigns, e-DNA campaigns and mangrove GIS surveys | 122000 | 0 | bar: 1 to 4
5.2 Impact Monitoring | Activity 5.2.1: Impact Monitoring in Mindoro, Palawan and Calamian MPA network | [24 empty] | Senior local management team + local technical staff in 2 MPA netwroks | Social and environmental KPIs will be monitored through impact metrics on recovery of coral reef ecosystems, protection of endangered species, livelihood enhancement & sustainable enterprise, equity improvement and new MPA jobs. The approach follows GFCR investment principles and guided by international best practice impact standards (GIIN, IUCN, BNCFF, SOCMON, METT) and verified by independent external partners (such as Verra – VCS and CCB, UNEP). Activities include UW survey campaigns, CPUE campaigns, e-DNA campaigns and mangrove GIS surveys | 176000 | 0 | bar: 21 to 24
#REF!
#REF!
B. PROGRAMME MANAGEMENT COSTS
Management and Operations | [27 empty] | 426000 | 592800
#REF!
#REF!
Communications and Learning | Develop logo and brand; build online presence (website, social media etc.); newsletter; create photographic and video content; internal knowledge management systems | [26 empty] | 104000 | 146000
Manufacture and deploy standardised signages across project sites
Develop materials targeted at specific audiences: educational materials for schools, colleges (e.g. activity books and guides, student focused competitions etc.); materials for investors (e.g. investor prospectus)
#REF!
Programme Overseight Support | [27 empty] | 46000 | 83500
[27 empty] | CONTRO:L | 0 | 0

## C. Budget UNDG Categories -
Budget by United Nations Sustainable Development Group (UNDG) Categories
All in USD
Total Programme Costs Budget Breakdown | Replenishment Request (24m) | Phase I Budget (18m) |  | Total Convening Agent | Total UNCDF | Total
| Convening Agent | Convening Agent | UNCDF |  |  | Total
1. Staff and other personnel | 1054000 |  | 259700 | 1054000 | 259700 | 1313700
2. Supplies, Commodities, Materials | 0 |  | 0 | 0 | 0 | 0
3. Equipment, Vehicles, and Furniture (including Depreciation) | 0 |  | 0 | 0 | 0 | 0
4. Contractual services | 2022500 |  | 0 | 2022500 | 0 | 2022500
5. Travel | 59000 |  | 83250 | 59000 | 83250 | 142250
6. Transfers and Grants to Counterparts | 0 |  | 2808825 | 0 | 2808825 | 2808825
7. General Operating and other Direct Costs | 28000 |  | 0 | 28000 | 0 | 28000
Total Direct Costs | 3163500 |  | 3151775 | 3163500 | 3151775 | 6315275
8. Indirect Support Costs (Max. 7%) | 221445 |  | 220624 | 221445 | 220624 | 442069
TOTAL Budget | 3384945 |  | 3372399 | 3384945 | 3372399 | 6757344