## 6-MONTH GANTT
6-MONTH PATHWAY 5 DEVELOPMENT GANTT
|  |  | Q4 |  |  |  |  | Q1 | [14 empty] | Q2
|  |  | DECEMBER |  |  |  |  | JANUARY |  |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE
|  |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 3 | 10 | 17 | 24 | 31 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 |  | 2 | 9 | 16 | 23 | 30
OUTPUTS | ACTIVITIES | LEAD AGENCY |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
OUTPUT 1 |  | UNCDF
The political and strategic groundwork needed to secure buy-in of public-private stakeholders is established. |  | ALL
ALL
ALL
ALL
ALL
ALL
OUTPUT 2 |  | CF, GC
The foundational strategic and technical documentation required to steer the development of the ocean finance platform is developed. |  | IUCN, UNCDF
UNDP
CF
UNEP
UNDP
UNCDF
OUTPUT 3 |  | ALL
A high-level political recommendation to the UN Ocean Conference (UNOC3) through the Blue Economy and Finance Forum (BEFF) is issued. |  | UNCDF
UNCDF, IUCN
ALL
ALL
ALL
ALL
PROJECT END
EB4 2024
2.7 Full OOF project document
2.1 Two industry engagement strategies
2.2 One financial architecture strategy & de-risking tools
2.4 Legal modelling
2.5 One scientific paper on conservation needs
1.2 Stakeholder mapping & prioritization
1.3 One stakeholder engagement strategy
1.4 Five-days high-level dialogues with priority stakeholders
1.5 One workshop to validate declaration
1.7 Events, workshops, and dialogues
3.2 Five meetings with BEFF and UNOC co-organizers
3.3 Political and strategic communication materials
3.5 Official submission of reccomendation to UNOC
3.6 Event at BEFF
3.7 Two high-level events and declaration signing
at UNOC
Drafting stage
Refinement & finalization stage
Submission to EB
Recruitment of consultant & initial drafting stage
Recruitment of consultant & initial drafting stage
1 financial pathway
2 engagement strategies
Refinement & finalization stage
Refinement & finalization stage
Recruitment of consultant & initial drafting stage
1 scientific paper
Refinement & finalization stage
Recruitment of legal counsel, consultations, legal model drafting
1 legal model
1 Stakeholder
mapping
1 Stakeholder
Engagement Strategy
Organization of high-level dialogues in Paris
5 High-level dialogues
1 declaration & report
1 validation workshop
Organization of workshop in Busan, South Korea
Final submission of reccomendation
2 UNOC Events
BEFF
Event
Preparation of submission
UNOC Comms
UNDESA Retreat
UNDESA
5th Oceans Forum
World Ocean Summit
Our Ocean
Organization of events, workshops, meetings, etc.
Organization of events, workshops, meetings, etc.
Govt of Costa Rica
Govt of France
Govt of Monaco
High-level Panel
Invite by Amb. Thomson
Bilat/multilat organization
BEFF Comms
Comms plan
Internal comms in the lead-up to UNOC
2.3 One investment plan/analysis of bottom-up investment needs
Recruitment of consultant & initial drafting stage
1 investment plan
Refinement & finalization stage
1.1 Coordination group
3.1 One leadership engagement strategy & execution of coalition building
1 coordination
group
Recruitment of necessary personnel
Ongoing coordination in the lead-up to UNOC3
1 Leadership Engagement Strategy
2.6 One comprehensive narrative document
Drafting & compiling stage
1 comprehensive narrattive
1.6 One high-level outcomes report & validated declaration
3.4 Twenty high-level engagements with governments and industries
Govt of Palau
ORRAA
Bilat/multilat organization
Coalition building
1 financial architecture

## 12-MONTH BUDGET UN
UNDG CATEGORY | FUNDING REQUEST (JAN 2025 - DEC 2025) |  |  | TOTAL
| UNCDF | UNDP | UNEP
1. Staff and other personnel
GFCR Director (50% FTE) | 172500 |  |  | 172500
Engagement & Development Analyst IPSA9 (50% FTE) | 48869 |  |  | 48869
Coordination Support Consultant (IPSA9) | 90000 |  |  | 90000
Policy & Development IPSA12 (6mos) |  | 82900 |  | 82900
2. Supplies, Commodities, Materials
3. Equipment, Vehicles, and Furniture (including Depreciation)
4. Contractual services
UN Global Compact Support for Shipping Industry engagement |  |  |  | 0
Development consultant(s) Investment Plan |  | 90000 |  | 90000
Environmental finance consultant(s) UNEP FI |  |  | 60000 | 60000
Science consultant(s) UNEP |  |  | 60000 | 60000
Strategic Engagement Forums High Priority | 70000 |  |  | 70000
UNCTAD support | 50000 |  |  | 50000
5. Travel
Policy & Development IPSA12 |  | 10000 |  | 10000
Conservation & Environmental Finance Consultants |  |  | 30000 | 30000
6. Transfers and Grants to Counterparts
7. General Operating and Other Direct Costs
Subtotal | 431369 | 182900 | 150000 | 764269
Indirect Cost (7%) | 30195.83 | 12803 | 10500 | 53498.83
Total | 461564.83 | 195703 | 160500 | 817767.83

## 12-MONTH BUDGET (IUCN & CF)
UNDG CATEGORY | FUNDING REQUEST (JAN 2025 - DEC 2025) |  |  |  |  | TOTAL
| UNCDF | UNDP | UNEP | IUCN | CF
1. Staff and other personnel
GFCR Director (50% FTE) | 172500 |  |  |  |  | 172500
Engagement & Development Analyst IPSA9 (50% FTE) | 48869 |  |  |  |  | 48869
Coordination Support Consultant (UNV) | 90000 |  |  |  |  | 90000
Policy & Development IPSA12 (6mos) |  | 82900 |  |  |  | 82900
IUCN staff (Director 20% FTE and support staff) | [5 empty] | 0
2. Supplies, Commodities, Materials
3. Equipment, Vehicles, and Furniture (including Depreciation)
4. Contractual services
UN Global Compact Support for Shipping Industry engagement |  |  |  |  | 75000 | 75000
Development consultant(s) Investment Plan |  | 90000 |  |  |  | 90000
Environmental finance consultant(s) UNEP FI |  |  | 60000 |  |  | 60000
Science consultant(s) UNEP |  |  | 60000 |  |  | 60000
Strategic Engagement Forums High Priority | 70000 |  |  |  |  | 70000
IUCN support (Director 20%, financial consultant, support staff) |  |  |  | 231716 |  | 231716
Catalytic Finance support for: shipping & submarine cable industry engagement, legal analysis, events and logistics |  |  |  |  | 810000 | 810000
UNCTAD support | 50000 |  |  |  |  | 50000
5. Travel
Policy & Development IPSA12 |  | 10000 |  |  |  | 10000
Conservation & Environmental Finance Consultants |  |  | 30000 |  |  | 30000
6. Transfers and Grants to Counterparts
7. General Operating and Other Direct Costs
Subtotal | 431369 | 182900 | 150000 | 231716 | 885000 | 1880985
Indirect Cost (7%) | 30195.83 | 12803 | 10500 | 16220.12 | 61950 | 131668.95
Total | 461564.83 | 195703 | 160500 | 247936.12 | 946950 | 2012653.95