## A. Work Plan - (hidden)
WORK PLAN
Joint SDG Fund - GFCR Fiji
Outcome | Output | Outcome/Output Description | TIME FRAME |  |  |  | PLANNED BUDGET |  |  | Recipient UN organization | Implementing Partners
|  |  | Y1 | Y2 | Y3 | Y4 | Joint SDG Fund | Global Fund for Coral Reefs | Total USD
A. PROGRAMME OUTCOME COSTS
1 | Outcome 1: Protection and effective management of Fijian priority coral reef sites and climate change-affected refugia are sustainably financed
1 | 1.1 | Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | x | x | x | x |  |  | 0
1 | 1.2 | Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector | x | x | x | x |  |  | 0
1 | 1.3 | Output 1.3: Strengthened management, enforcement and monitoring systems of LMMAs by SPEs. | x | x | x | x |  |  | 0
1 | 1.4 | Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats. | x | x | x | x |  |  | 0
Sub-total Outcome 1 | [6 empty] | 0 | 0 | 0
2 | Outcome 2: Transforming the livelihoods of coral reef-dependent communities
2 | 2.1 | Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth | x | x | x | x |  |  | 0
2 | 2.2 | Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers | x | x | x | x |  |  | 0
2 | 2.3 | Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection | x | x | x | x |  |  | 0
2 | 2.4 | Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably | x | x | x | x |  |  | 0
Sub-total Outcome 2 | [6 empty] | 0 | 0 | 0
TOTAL PROGRAMME OUTCOME COSTS | [6 empty] | 0 | 0 | 0
B. PROGRAMME MANAGMENT COSTS
UNDP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNDP | N/A
UNCDF
N/A | N/A |  | x | x | x | x |  |  | 0 | UNCDF | N/A
UNEP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNEP | N/A
EVALUATION
N/A | N/A |  | x | x | x | x |  |  | 0 | Evaluation | N/A
TOTAL PROGRAMME MANAGMENT COSTS | [6 empty] | 0 | 0 | 0
TOTAL DIRECT PROGRAMME COSTS | [6 empty] | 0 | 0 | 0
Total Indirect Support Cost - GMS (7%) | [6 empty] | 0 | 0 | 0
TOTAL COSTS | [6 empty] | 0 | 0 | 0

## A. Budget UNDG Categories -
BUDGET BY UNDG CATEGORIES
Joint SDG Fund - GFCR Fiji
UNDG BUDGET CATEGORIES | UNDP |  | UNCDF |  | UNEP |  | TOTAL USD |  | TOTAL % by UNDG category
| Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund | GFCR | Combined
1. Staff and other personnel | 211798.5 | 211798.5 | 200997 | 200997 | 103333.25 | 0 | 516128.75 | 412795.5 | 9.666% | 8.906% | 9.313%
2. Supplies, Commodities, Materials | [6 empty] | 0 | 0 | 0% | 0% | 0%
3. Equipment, Vehicles, and Furniture (including Depreciation) | [6 empty] | 0 | 0 | 0% | 0% | 0%
4. Contractual services | 244000 | 364000 | 465000 | 165000 | 200000 | 0 | 909000 | 529000 | 17.02% | 11.41% | 14.42%
5.Travel | 29000 | 33000 | 16000 | 16000 | 31000 | 0 | 76000 | 49000 | 1.423% | 1.057% | 1.253%
6. Transfers and Grants to Counterparts |  |  | 3419000 | 3291000 |  |  | 3419000 | 3291000 | 64.03% | 71% | 67.27%
7. General Operating and other Direct Costs | 40000 | 40000 | 10000 | 10000 | 20000 | 0 | 70000 | 50000 | 1.311% | 1.079% | 1.203%
Total Direct Costs | 524798.5 | 648798.5 | 4110997 | 3682997 | 354333.25 | 0 | 4990128.75 | 4331795.5 | 93.46% | 93.46% | 93.46%
8. Indirect Support Costs (Max. 7%) | 36735.895 | 45415.895 | 287769.79 | 257809.79 | 24803.3275 | 0 | 349309.0125 | 303225.685 | 6.542% | 6.542% | 6.542%
TOTAL Budget | 561534.395 | 694214.395 | 4398766.79 | 3940806.79 | 379136.5775 | 0 | 5339437.7625 | 4635021.185 | 100% | 100% | 100%
Total budget combined | 1255748.79 |  | 8339573.58 |  | 379136.5775 |  | 9974458.9475
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! |  | #REF! |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
0
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | UNFPA |  | UN WOMEN |  | TOTAL USD
|  |  | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD) | Spotlight (USD) | RUNO Contrib. (USD)
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! |  | #REF! |  | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | UN Women | UNICEF | UNHCR | TOTAL USD
|  |  | Spotlight (USD) | Spotlight (USD) | Spotlight (USD) | Spotlight (USD)
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
0
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | #REF!
2021 Budget Breakdown
UNDG BUDGET CATEGORIES | UNDP |  | UNCDF |  | UNEP |  | TOTAL USD |  | TOTAL % by UNDG category
| Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund (USD) | GFCR (USD) | Joint SDG Fund | GFCR | Combined
1. Staff and other personnel | 105899.25 | 0 | 150747.75 | 0 | 33370.7 | 0 | 290017.7 | 0 | 13.9% | 0% | 9.367%
2. Supplies, Commodities, Materials | [6 empty] | 0 | 0 | 0% | 0% | 0%
3. Equipment, Vehicles, and Furniture (including Depreciation) | [6 empty] | 0 | 0 | 0% | 0% | 0%
4. Contractual services | 10000 | 153500 | 400000 | 80000 | 200000 | 0 | 610000 | 233500 | 29.24% | 23.13% | 27.24%
5.Travel | 5000 | 17000 | 8000 | 0 | 10000 | 0 | 23000 | 17000 | 1.102% | 1.684% | 1.292%
6. Transfers and Grants to Counterparts |  |  | 997000 | 693000 |  |  | 997000 | 693000 | 47.78% | 68.64% | 54.59%
7. General Operating and other Direct Costs | 20000 | 0 | 5000 | 0 | 5000 | 0 | 30000 | 0 | 1.438% | 0% | 0.969%
Total Direct Costs | 140899.25 | 170500 | 1560747.75 | 773000 | 248370.7 | 0 | 1950017.7 | 943500 | 93.46% | 93.46% | 93.46%
8. Indirect Support Costs (Max. 7%) | 9862.9475 | 11935 | 109252.3425 | 54110 | 17385.949 | 0 | 136501.239 | 66045 | 6.542% | 6.542% | 6.542%
TOTAL Budget | 150762.1975 | 182435 | 1670000.0925 | 827110 | 265756.649 | 0 | 2086518.939 | 1009545 | 100% | 100% | 100%
Total budget combined | 333197.1975 |  | 2497110.0925 |  | 265756.649 |  | 3096063.939
| GFCR transfer (25.03.2021) | SDG Fund request | Total
UNCDF | 827110 | 1670000 | 2497110
UNDP | 182435 | 150762 | 333197
UNEP | 0 | 265756.649 | 265756.649
| 1009545 | 2086518.649 | 3096063.649

## B. Budget per SDG targets
4.2 Budget per SDG Targets
SDG TARGETS |  | % | Total (USD) | GFCR | Joint SDG Fund
1 | SDG 1.a and SDG 1.b | 10% | 997445.8947 | 463502.1185 | 533943.7762
5 | SDG 5.5 | 5% | 498722.9474 | 231751.0593 | 266971.8881
8 | SDG 8.3, SDG 8.5 and SDG 8.9 | 10% | 997445.8947 | 463502.1185 | 533943.7762
10 | SDG 10.b | 5% | 498722.9474 | 231751.0593 | 266971.8881
14 | SDG 14.1, 14.2, 14.3, 14.4, 14.5, 14.7 | 60% | 5984675.3685 | 2781012.711 | 3203662.6575
17 | SDG 17.1 and 17.3 | 10% | 997445.8947 | 463502.1185 | 533943.7762
TOTAL |  | 100% | 9974458.9475 | 4635021.185 | 5339437.7625

## C. Workplan
4.3 Work plan
Outcome 1: Protection and effective management of Fijian priority coral reef sites and climate change-affected refugia are sustainably financed
Output | Annual target/s* |  |  |  | List of activities | Time frame | [15 empty] | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | Area of new climate refugia and priority sites designated as MPAs or LMMAs = 0 | Area of new climate refugia and priority sites designated as MPAs or LMMAs = 500 | Area of new climate refugia and priority sites designated as MPAs or LMMAs = 1000 | Area of new climate refugia and priority sites designated as MPAs or LMMAs = 1500 | Activity 1.1.1: LMMA screening, feasibility study and selection of priority sites | [16 empty] | The project, with guidance from Blue Finance, will identify projects based on ecological, legal, management and business criteria through desk study and preliminary consultations with local stakeholders. Priority MPA(s) will be selected in collaboration with Government and UNDP partners. A scoring decision tool describing the rationale for site prioritization will be shared with participating sites. The priority sites will be selected in agreement with participating stakeholders (inception meeting in the selected site). The scoring tool used has three major components – Impact Feasibility, Legal Feasibility, and Business Feasibility with a total of 54 indicators. | 70000 | 70000 | 140000 | UNDP | MoE, Blue Finance | bar: Time frame Q1 to Time frame Q2
[5 empty] | Activity 1.1.2: Design of the LMMAs high-level business plan and set-up of the Special Purpose Entities (SPEs - co-management body for the LMMAs) | [16 empty] | Business plans for the nature tourism enterprise, nature fee solutions, digital visitor centre and other tourism facilities will be developed. Plans will include aspects of the marketing approach, business model, detailed budgets of the management plan activities (Capex and Opex), financial strategy and de-risking aspects. Plans will be developed in consultations with local stakeholders. This also includes the design of realistic revenue strategies based (at minima) on nature fees, eco-tourism activities such as eco-dive and innovative visitor centre. A coalition of local stakeholders (e.g. NGOs, associations, cooperatives, foundations) will be proposed to become members of the SPE. Proper due diligence will be conducted beforehand on stakeholders. | bar: Time frame Q3 to Time frame Q2; Time frame Q1 to Time frame Q2
[5 empty] | Activity 1.1.3: Design of the blended finance solution and fundraising | [16 empty] | This activity will cover the design of the strategy for the investment vehicle, including aspects of governance of the SPE, business model, legal approach, potential commercial investors and de-risking aspects. The investment proposal will be co-funded by this JP, the Global Fund for Coral Reefs (GFCR) and investment from the SOF (Mirova). The investment proposal will be presented to an additional pool of investors & donors with the objective to blend donations, concessionary loans and impact investments. Other related activities that will be covered are: Funder mapping, facilitate introductions and meetings with funders and investors and development of pitch material. | bar: Time frame Q4 to Time frame Q2; Time frame Q1 to Time frame Q3
[5 empty] | Activity 1.1.4: Stakeholder engagement and advocacy | [16 empty] | To ensure alignment with all the various stakeholders involved a consultation process will be organized with the support of UNDP with stakeholders from central, province and local governments, tourism industry, fishing sector, local communities and other public institutions. | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector | 0 | 1 SPE | 2 SPE | 2 SPE | Activity 1.2.1: Investment readiness of the SPEs for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve (Business planning and SPE incorporation) | [16 empty] | Technical Assistance will be provided by Blue Finance and UNCDF for the incorporation of the SPEs and for the development of the business plans of the Special Purpose Entity (SPE) including: Design and development of the revenue collection mechanism, visitor center feasibility analysis, marketing and communication plan of the SPE; communication elements, image design, media strategy, partnerships, planning and budget. | 583000 | 583000 | 1166000 | UNDP and UNCDF | MoE, Blue Finance, Althelia/SOF, GFCR, Fiji Hotel and Tourism Association | bar: Time frame Q1 to Time frame Q2
[5 empty] | Activity 1.2.2: Environmental readiness of the SPEs for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve | [16 empty] | Development of environmental & social planning of the Special Purpose Entity (SPE), including preliminary compliance and enforcement plan of the MPAs, first-year work plan of the SPE, support to the Management plans and Marine Spatial Plans of the MPAs. This will be developed in collaboration with SPE members and selected tourism stakeholders. | bar: Time frame Q1 to Time frame Q2
[5 empty] | Activity 1.2.3: Concessional debt and other blended finance instruments to the SPE for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve | [16 empty] | Combined value of concessional debt and performance grants required for first two years | bar: Time frame Q1 to Time frame Q2
Output 1.3: Strengthened management, enforcement and monitoring systems of LMMAs by SPEs. | 1 MPA with METT score >60 | 2 MPAs with METT score >70 | 3 MPAs with METT score >70 | 4 MPAs with METT score >70 | Activity 1.3.1: Project Management Office for the SPEs and capacity building to upskill SPEs and LMMAs on social entrepreneurship and sustainable business management | [16 empty] | The PMO entity for the SPEs will ensure management focus on strategy execution: project planning and reporting, resource forecasting, facilitate & ensure communication to key stakeholders (UNDP support for government outreach), alignment of interrelations between activities, management of project risks. | 30000 | 63049.85 | 93049.85 | UNDP and UNEP | Blue Finance, FLMMA | bar: Time frame Q1 to Time frame Q2; Time frame Q1 to Time frame Q4
[5 empty] | Activity 1.3.2: Performance indicators for the SPE and Environmental and Social Action Plan (ESAP) | [16 empty] | This activity entails the development of Key Performance Indicators (KPIs), result metrics and Environmental and Social Action Plan (ESAP) for the SPEs. These will be developed in collaboration with SPE members and government agencies then reviewed and certified by UNEP. | bar: Time frame Q1 to Time frame Q2
Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats. | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 0 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 1 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 2 | Number of coral reef and ridge to reef conservation related resolutions, declarations and laws passed = 3 | Activity 1.4.1: Support the development of a comprehensive legal framework for establishment, management and financing of MPAs | [16 empty] | This activity covers a review of the existing legal and regulatory framework on MPA’s and the financing thereof and defines a clear set of recommendations to support the development of a comprehensive legal framework for the establishment, management and financing of an effective network of MPAs in Fiji which is based on science and suited to the Fiji context. UNDP and UNEP will collaborate with the Fijian government to build the legal framework for protection of marine areas. The framework will serve to facilitate the replication of the SPE co-management agreement model for other MMAs in Fiji. | 20000 | 20000 | 40000 | UNDP | MoE, Invest Fiji | bar: Time frame Q1 to Time frame Q2
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output | Annual target/s* |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
| 2021 | 2022 | 2023 | 2024 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth | Number of TAF incubated blue economy SMEs that become investment ready = 2 | Number of TAF incubated blue economy SMEs that become investment ready = 3 | Number of TAF incubated blue economy SMEs that become investment ready = 4 | Number of TAF incubated blue economy SMEs that become investment ready = 6 | Activity 2.1.1: Pipeline development through scoping, technical assistance and training to upskill local businesses operating in the blue economy on social entrepreneurship, sustainable business and financial management to build a portfolio of investment ready businesses and projects | [16 empty] | This output covers the set up and management of an origination and technical assistance facility, whereby origination activities include: scoping, pre-selection, due diligence, community and other stakeholder engagement, business plan development, regulatory approvals and financial structuring. Technical Assistance covers activities and services to plug capacity gaps with respect to business development and planning, product development and access to market support, financial planning and management, as well as reporting. | 8000 | 556199.4 | 564199.4 | UNCDF and UNEP | Matanataki,
[5 empty] | Activity 2.1.2: Technical assistance and training to upskill local businesses on methodology to measure, monitor and manage the environmental impact of their business operations | [16 empty] | This activity specifically focuses on improving the capacity of businesses that have received support and investment through this project to be able to understand the outcomes of the environmental impact assessments and going forward measure and manage the environmental impact of their operations. UNEP will support in the upskilling through training and technical assistance during the course of the implementation of each of the projects selected from the pipeline. Additionally, this activity will also cater for environmental impact assessments for each of the projects
Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Increased private investment in sustainable initiatives and blue economy SMEs related to Coral Reefs = TBD | Activity 2.2.1: Provide blended finance and technical support to unlock private capital for Fertile Factory | [16 empty] | Concessional debt for establishment of fertile factory | 3114997 | 3242997 | 6357994 | UNCDF
[5 empty] | Activity 2.2.2: Provide blended finance and technical support to unlock private capital for Western Landfill and Regional Transfer Stations project | [16 empty] | Liquidity support facility and subordinated debt for establishment of Western Landfill and RTS's
[5 empty] | Activity 2.2.3: Concessional debt and other blended finance instruments to crowd in private sector capital for investment ready projects from developed pipeline under activity 2.1.1 | [16 empty] | A financial support facility will be created by UNCDF to provide concessional capital and other blended finance from the GFCR and GCF in support for the projects developed under activity 2.1.1.
Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government strategies and plans to support financing for improved marine biodiversity protection and the blue economy = 3 | Activity 2.3.1: Develop financing strategy for Government of Fiji focused on protecting coastal ecosystems and investment in the blue economy | [16 empty] | This activity will use the analytical framework of UNDP’s Development Finance Assessment 3.0 (DFA) applying a modular framework to assess financing options and to inform the design of a financing strategy to mobilize resources, manage risks, such as debt sustainability, and achieve development targets linked to a sustainable blue economy in line with coral reef conservation objectives. | 72000 | 0 | 72000 | UNDP
Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 0 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 1 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | Number of new government incentives to support financing for improved marine biodiversity protection and the blue economy = 2 | Activity 2.4.1: Support the development and promotion of a government incentive scheme to attract additional investment in the blue economy | [16 empty] | This activity will support the Government of Fiji with the development and promotion of an incentive scheme covering regulations, subsidies, and other incentives that can attract private sector investment. These can include reductions in duty and VAT, or offering accelerated depreciation, tax credits, biodiversity offsets and other incentives could be used to encourage investments in protection of coastal eco-systems and the associated blue economy. | 52000 | 0 | 52000 | UNDP
B. PROGRAMME MANAGEMENT COSTS |  |  |  |  | List of activities | Time frame Q1: Time frame | PLANNED BUDGET |  |  |  | PUNO/s involved | Implementing partner/s involved
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Overall budget description* | GFCR (USD) | Joint SDG Fund (USD) | Total Cost (USD)
Management and Operations | N/A | N/A | N/A | N/A | Management of the implementation of the JP | [16 empty] | Staff: Project Mgr, Admin/Support officer, Project Support officer, office rent, utilities etc | 173778 | 246862 | 420640 | UNDP, UNCDF and UNEP
Communications and Learning | N/A | N/A | N/A | N/A | See Annex 6 Communication Plan and Annex 7 Learning and Sharing Plan | [16 empty] | Staff: Communications officer, event costs (venue etc), printing, photography, etc | 95347 | 95347 | 190694 | UNDP
Programme Oversight support | N/A | N/A | N/A | N/A | Mid-term and end-evaluation + ongoing RM activities | [16 empty] | Staff: M&E Officer, Mid-term and end evaluation | 112673.5 | 112673.5 | 225347 | UNDP
| *Targets are cumulative. For details on these targets and other indicators, see Annex 2.2 Results Framework | [20 empty] | *For details on UNDG budget categories per activity, see sheet D. Budget by Outcome

## D. Budget by Outcome
BUDGET BY OUTCOME | [8 empty] | Available budget |  | 10040000 | 4700000 | 5340000 |  | Available | 1000000 | 1869000
Joint SDG Fund - GFCR Fiji | [8 empty] | Delta |  | 65541.0525 | 64978.815 | 562.2375 |  | Delta | -9545 | -217518.939 | 39.07%
Outcome | Output | Activity | Budget Lines | UN Organization | Unit quantity | Unit Cost (USD) | Duration | Time unit (Time units or Lump sum) | % Charged to Programme | UNDG Budget Category (1-7) | Budget |  |  | Narrative description of budget lines | Budget 2021
[11 empty] | Total (USD) | GFCR | Joint SDG Fund |  | Total (USD) | GFCR | Joint SDG Fund
A. PROGRAMME OUTCOME COSTS
Outcome 1: Protection and effective management of Fijian priority coral reef sites and climate change-affected refugia are sustainably financed
Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs
Activity 1.1.1: LMMA screening, feasibility study and selection of priority sites
|  | 1.1.1.1 | Contractual Services | UNDP | 1 | 10000 | 2 | Years | 100% | 4 | 20000 | 10000 | 10000 | The project, with guidance from Blue Finance, will identify projects based on ecological, legal, management and business criteria through desk study and preliminary consultations with local stakeholders. Priority MPA(s) will be selected in collaboration with Government and UNDP partners. A scoring decision tool describing the rationale for site prioritization will be shared with participating sites. The priority sites will be selected in agreement with participating stakeholders (inception meeting in the selected site). The scoring tool used has three major components – Impact Feasibility, Legal Feasibility, and Business Feasibility with a total of 54 indicators. | 10000 | 10000 | 0
|  | 1.1.1.2 | Travel | UNDP | 1 | 2000 | 2 | Years | 100% | 5 | 4000 | 2000 | 2000 | Travel, DSA etc | 2000 | 2000 | 0
|  |  | Sub-Total Activity 1.1.1: | [7 empty] | 24000 | 12000 | 12000 |  | 12000 | 12000 | 0
Activity 1.1.2: Design of the LMMAs high-level business plan and set-up of the Special Purpose Entities (SPEs - co-management body for the LMMAs)
|  | 1.1.2.1 | Contractual Services | UNDP | 1 | 20000 | 2 | Years | 100% | 4 | 40000 | 20000 | 20000 | Business plans for the nature tourism enterprise, nature fee solutions, digital visitor centre and other tourism facilities will be developed. Plans will include aspects of the marketing approach, business model, detailed budgets of the management plan activities (Capex and Opex), financial strategy and de-risking aspects. Plans will be developed in consultations with local stakeholders. This also includes the design of realistic revenue strategies based (at minima) on nature fees, eco-tourism activities such as eco-dive and innovative visitor centre. A coalition of local stakeholders (e.g. NGOs, associations, cooperatives, foundations) will be proposed to become members of the SPE. Proper due diligence will be conducted beforehand on stakeholders. | 10000 | 10000 | 0
|  | 1.1.2.2 | Travel | UNDP | 1 | 3000 | 2 | Years | 100% | 5 | 6000 | 3000 | 3000 | Travel, DSA etc | 3000 | 3000 | 0
|  |  | Sub-Total Activity 1.1.2: | [7 empty] | 46000 | 23000 | 23000 |  | 13000 | 13000 | 0
Activity 1.1.3: Design of the blended finance solution and fundraising
|  | 1.1.3.1 | Contractual Services | UNDP | 1 | 22500 | 2 | Years | 100% | 4 | 45000 | 22500 | 22500 | This activity will cover the design of the strategy for the investment vehicle, including aspects of governance of the SPE, business model, legal approach, potential commercial investors and de-risking aspects. The investment proposal will be co-funded by this JP, the Global Fund for Coral Reefs (GFCR) and investment from the SOF (Mirova). The investment proposal will be presented to an additional pool of investors & donors with the objective to blend donations, concessionary loans and impact investments. Other related activities that will be covered are: Funder mapping, facilitate introductions and meetings with funders and investors and development of pitch material. | 20000 | 20000 | 0
|  | 1.1.3.2 | Travel | UNDP | 1 | 2000 | 2 | Years | 100% | 5 | 4000 | 2000 | 2000 | Travel, DSA etc | 2000 | 2000 | 0
|  |  | Sub-Total Activity 1.1.3: | [7 empty] | 49000 | 24500 | 24500 |  | 22000 | 22000 | 0
Activity 1.1.4: Stakeholder engagement and advocacy
|  | 1.1.4.1 | Contractual Services | UNDP | 1 | 5000 | 3 | Years | 100% | 4 | 15000 | 7500 | 7500 | To ensure alignment with all the various stakeholders involved a consultation process will be organized with the support of UNDP with stakeholders from central, province and local governments, tourism industry, fishing sector, local communities and other public institutions. | 2500 | 2500 | 0
|  | 1.1.4.2 | Travel | UNDP | 1 | 2000 | 3 | Years | 100% | 5 | 6000 | 3000 | 3000 | Travel, DSA etc | 2000 | 2000 | 0
|  |  | Sub-Total Activity 1.1.4: | [7 empty] | 21000 | 10500 | 10500 |  | 4500 | 4500 | 0
|  |  | Sub-Total Output 1.1: | [7 empty] | 140000 | 70000 | 70000 |  | 51500 | 51500 | 0
Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector
Activity 1.2.1: Investment readiness of the SPEs for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve (Business planning and SPE incorporation)
|  | 1.2.1.1 | Contractual Services | UNDP | 1 | 30000 | 1 | Years | 100% | 4 | 30000 | 15000 | 15000 | Technical Assistance will be provided by Blue Finance and UNCDF for the incorporation of the SPEs and for the development of the business plans of the Special Purpose Entity (SPE) including: Design and development of the revenue collection mechanism, visitor center feasibility analysis, marketing and communication plan of the SPE; communication elements, image design, media strategy, partnerships, planning and budget. | 15000 | 15000 | 0
|  | 1.2.1.2 | Travel | UNDP | 1 | 2000 | 1 | years | 100% | 5 | 2000 | 1000 | 1000 | Travel, DSA etc |  |  | 0
|  |  | Sub-Total Activity 1.2.1: | [7 empty] | 32000 | 16000 | 16000 |  | 15000 | 15000 | 0
Activity 1.2.2: Environmental readiness of the SPEs for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve
|  | 1.2.2.1 | Contractual Services | UNDP | 1 | 30000 | 1 | Years | 100% | 4 | 30000 | 15000 | 15000 | Development of environmental & social planning of the Special Purpose Entity (SPE), including preliminary compliance and enforcement plan of the MPAs, first-year work plan of the SPE, support to the Management plans and Marine Spatial Plans of the MPAs. This will be developed in collaboration with SPE members and selected tourism stakeholders. | 30000 | 30000 | 0
|  | 1.2.2.2 | Travel | UNDP | 1 | 4000 | 1 | Years | 100% | 5 | 4000 | 2000 | 2000 | Travel, DSA etc | 4000 | 4000 | 0
|  |  | Sub-Total Activity 1.2.2: | [7 empty] | 34000 | 17000 | 17000 |  | 34000 | 34000 | 0
Activity 1.2.3: Concessional debt and other blended finance instruments to the SPE for investment in Korolevu-i-wai MMA, and Shark Reef Marine Reserve
|  | 1.2.3.1 | Transfers and Grant to Counterparts | UNCDF | 1 | 550000 | 2 | years | 100% | 6 | 1100000 | 550000 | 550000 | Combined value of concessional debt and performance grants required for first two years | 700000 | 150000 | 550000
|  |  | Sub-Total Activity 1.2.3: | [7 empty] | 1100000 | 550000 | 550000 |  | 700000 | 150000 | 550000
|  |  | Sub-Total Output 1.2: | [7 empty] | 1166000 | 583000 | 583000 |  | 749000 | 199000 | 550000
Output 1.3: Strengthened management, enforcement and monitoring systems of LMMAs by SPEs.
Activity 1.3.1: Project Management Office for the SPEs and capacity building to upskill SPEs and LMMAs on social entrepreneurship and sustainable business management
|  | 1.3.1.1 | Contractual Services | UNDP | 1 | 16000 | 3 | years | 100% | 4 | 48000 | 24000 | 24000 | The PMO entity for the SPEs will ensure management focus on strategy execution: project planning and reporting, resource forecasting, facilitate & ensure communication to key stakeholders (UNDP support for government outreach), alignment of interrelations between activities, management of project risks. | 16000 | 16000 | 0
|  | 1.3.1.2 | Travel | UNDP | 1 | 4000 | 3 | years | 100% | 5 | 12000 | 6000 | 6000 | Travel, DSA etc | 4000 | 4000 | 0
|  |  | Sub-Total Activity 1.3.1: | [7 empty] | 60000 | 30000 | 30000 |  | 20000 | 20000 | 0
Activity 1.3.2: Performance indicators for the SPE and Environmental and Social Action Plan (ESAP)
|  | 1.3.2.1 | Staff and Personnel | UNEP | 1 | 200997 | 1 | years | 5% | 1 | 10049.85 | 0 | 10049.85 | Technical support and quality assurance by UNEP on measurement, monitoring and management of impact (5% of P3 technical specialist for 1 year) | 10049.85 |  | 10049.85
|  | 1.3.2.2 | Contractual Services | UNEP | 1 | 20000 | 1 | years | 100% | 4 | 20000 | 0 | 20000 | This activity entails the development of Key Performance Indicators (KPIs), result metrics and Environmental and Social Action Plan (ESAP) for the SPEs. These will be developed in collaboration with SPE members and government agencies then reviewed and certified by UNEP. | 20000 |  | 20000
|  | 1.3.2.3 | Travel | UNEP | 1 | 3000 | 1 | years | 100% | 5 | 3000 | 0 | 3000 | Travel, DSA etc | 3000 |  | 3000
|  |  | Sub-Total Activity 1.3.2: | [7 empty] | 33049.85 | 0 | 33049.85 |  | 33049.85 | 0 | 33049.85
|  |  | Sub-Total Output 1.3: | [7 empty] | 93049.85 | 30000 | 63049.85 |  | 53049.85 | 20000 | 33049.85
Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats.
Activity 1.4.1: Support the development of a comprehensive legal framework for establishment, management and financing of MPAs
|  | 1.4.1.1 | Contractual Services | UNDP | 1 | 40000 | 1 | years | 100% | 4 | 40000 | 20000 | 20000 | This activity covers a review of the existing legal and regulatory framework on MPA’s and the financing thereof and defines a clear set of recommendations to support the development of a comprehensive legal framework for the establishment, management and financing of an effective network of MPAs in Fiji which is based on science and suited to the Fiji context. UNDP and UNEP will collaborate with the Fijian government to build the legal framework for protection of marine areas. The framework will serve to facilitate the replication of the SPE co-management agreement model for other MMAs in Fiji. |  |  | 0
|  |  | Sub-Total Activity 1.4.1: | [7 empty] | 40000 | 20000 | 20000 |  | 0 | 0 | 0
|  |  | Sub-Total Output 1.4: | [7 empty] | 40000 | 20000 | 20000 |  | 0 | 0 | 0
Sub-Total OUTCOME 1: | [10 empty] | 1439049.85 | 703000 | 736049.85 |  | 853549.85 | 270500 | 583049.85
Outcome 2: Transforming the livelihoods of coral reef-dependent communities
Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth
Activity 2.1.1: Pipeline development through scoping, technical assistance and training to upskill local businesses operating in the blue economy on social entrepreneurship, sustainable business and financial management to build a portfolio of investment ready businesses and projects
|  | 2.1.1.1 | Contractual Services | UNCDF | 1 | 75000 | 4 | years | 100% | 4 | 300000 | 0 | 300000 | This output covers the set up and management of an origination and technical assistance facility, whereby origination activities include: scoping, pre-selection, due diligence, community and other stakeholder engagement, business plan development, regulatory approvals and financial structuring. Technical Assistance covers activities and services to plug capacity gaps with respect to business development and planning, product development and access to market support, financial planning and management, as well as reporting. | 150000 | 0 | 150000
|  | 2.1.1.2 | Travel | UNCDF | 1 | 4000 | 4 | years | 100% | 5 | 16000 | 8000 | 8000 | Travel, DSA etc | 0 |  | 0
|  |  | Sub-Total Activity 2.1.1: | [7 empty] | 316000 | 8000 | 308000 |  | 150000 | 0 | 150000
Activity 2.1.2: Technical assistance and training to upskill local businesses on methodology to measure, monitor and manage the environmental impact of their business operations
|  | 2.1.2.1 | Staff and Personnel | UNEP | 1 | 200997 | 4 | years | 5% | 1 | 40199.4 | 0 | 40199.4 | Technical support and quality assurance by UNEP on measurement, monitoring and management of environmental impact (5% of P3 technical specialist for 4 years) | 10049.85 |  | 10049.85
|  | 2.1.2.2 | Contractual Services | UNEP | 1 | 45000 | 4 | years | 100% | 4 | 180000 | 0 | 180000 | This activity specifically focuses on improving the capacity of businesses that have received support and investment through this project to be able to understand the outcomes of the environmental impact assessments and going forward measure and manage the environmental impact of their operations. UNEP will support in the upskilling through training and technical assistance during the course of the implementation of each of the projects selected from the pipeline. Additionally, this activity will also cater for environmental impact assessments for each of the projects | 180000 |  | 180000
|  | 2.1.2.3 | Travel | UNEP | 1 | 7000 | 4 | years | 100% | 5 | 28000 | 0 | 28000 | Travel, DSA etc | 7000 |  | 7000
|  |  | Sub-Total Activity 2.1.2: | [7 empty] | 248199.4 | 0 | 248199.4 |  | 197049.85 | 0 | 197049.85
|  |  | Sub-Total Output 2.1: | [7 empty] | 564199.4 | 8000 | 556199.4 |  | 347049.85 | 0 | 347049.85
Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers
Activity 2.2.1: Provide blended finance and technical support to unlock private capital for Fertile Factory
|  | 2.2.1.1 | Transfers and Grant to Counterparts | UNCDF | 1 | 375000 | 2 | years | 100% | 6 | 750000 | 303000 | 447000 | Concessional debt for establishment of fertile factory | 750000 | 303000 | 447000
|  | 2.2.1.2 | Contractual Services | UNCDF | 1 | 115000 | 2 | years | 100% | 4 | 230000 | 115000 | 115000 | Implementation and development activities by Matanataki to support the development of the Fertile Factory project, which cover product co-development and business planning, financial modelling, fundraising and product positioning with coastal based farmers. Additional implementation activities include, but are not limited to strategic business development, financing relationship management and impact measurement and reporting. | 230000 | 30000 | 200000
|  | 2.2.1.3 | Travel | UNCDF | 1 | 3000 | 2 | years | 100% | 5 | 6000 | 3000 | 3000 | Travel, DSA etc | 3000 |  | 3000
|  |  | Sub-Total Activity 2.2.1: | [7 empty] | 986000 | 421000 | 565000 |  | 983000 | 333000 | 650000
Activity 2.2.2: Provide blended finance and technical support to unlock private capital for Western Landfill and Regional Transfer Stations project
|  | 2.2.2.1 | Transfers and Grant to Counterparts | UNCDF | 1 | 175000 | 2 | years | 100% | 6 | 350000 | 350000 | 0 | Grant for pre-construction project development activities | 240000 | 240000 | 0
|  | 2.2.2.2 | Transfers and Grant to Counterparts | UNCDF | 1 | 1750000 | 2 | years | 100% | 6 | 3500000 | 1688000 | 1812000 | Liquidity support facility and subordinated debt for establishment of Western Landfill and RTS's |  |  | 0
|  | 2.2.2.3 | Contractual Services | UNCDF | 1 | 50000 | 2 | years | 100% | 4 | 100000 | 50000 | 50000 | Implementation and development activities by Matanataki to support the development of the Landfill project, which cover preparation of waste audits and other technical reports, arrangements with Government of Fiji and other major clients, landfill site selection and analysis, negotiation of construction and O&M contract with the operator, coordination of financing consortium and preparation of respective investor marketing materials, establishment of project SPV and contracting, oversight of the construction and O&M contract implementation, support with major contracts and ancillary businesses, financial and impact reporting. | 100000 | 50000 | 50000
|  | 2.2.2.4 | Travel | UNCDF | 1 | 5000 | 2 | years | 100% | 5 | 10000 | 5000 | 5000 | Travel, DSA etc | 5000 |  | 5000
|  |  | Sub-Total Activity 2.2.2: | [7 empty] | 3960000 | 2093000 | 1867000 |  | 345000 | 290000 | 55000
Activity 2.2.3: Concessional debt and other blended finance instruments to crowd in private sector capital for investment ready projects from developed pipeline under activity 2.1.1
|  | 2.2.3.1 | Staff and Personnel | UNCDF | 1 | 200997 | 4 | Years | 50% | 1 | 401994 | 200997 | 200997 | Technical support and quality assurance by UNCDF to develop the investment cases for the facilities. Specific activities include to take lead on structuring the finance transactions for this facility: deal screening, term sheet negotiation, due diligence, financial modeling and analysis, investment structuring and risk mitigation, manage the approval process, including presentation of deals to credit committee, proper management and execution of all investment legal documents, management and follow up on repayments and collections, monitor on-going financial and operational performance of investments, analyze and monitor risks and trends in the portfolio, manage restructurings and workouts. (50% of P3 technical specialist for 4 years) | 150747.75 |  | 150747.75
|  | 2.2.3.2 | Transfers and Grant to Counterparts | UNCDF | 1 | 252500 | 4 | years | 100% | 6 | 1010000 | 400000 | 610000 | A financial support facility will be created by UNCDF to provide concessional capital and other blended finance from the GFCR and GCF in support for the projects developed under activity 2.1.1. |  |  | 0
|  |  | Sub-Total Activity 2.2.3: | [7 empty] | 1411994 | 600997 | 810997 |  | 150747.75 | 0 | 150747.75
|  |  | Sub-Total Output 2.2: | [7 empty] | 6357994 | 3114997 | 3242997 |  | 1478747.75 | 623000 | 855747.75
Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection
Activity 2.3.1: Develop financing strategy for Government of Fiji focused on protecting coastal ecosystems and investment in the blue economy
|  | 2.3.1.1 | Contractual Services | UNDP | 1 | 70000 | 1 | years | 100% | 4 | 70000 | 70000 | 0 | This activity will use the analytical framework of UNDP’s Development Finance Assessment 3.0 (DFA) applying a modular framework to assess financing options and to inform the design of a financing strategy to mobilize resources, manage risks, such as debt sustainability, and achieve development targets linked to a sustainable blue economy in line with coral reef conservation objectives. |  |  | 0
|  | 2.3.1.2 | Travel | UNDP | 1 | 2000 | 1 | years | 100% | 5 | 2000 | 2000 | 0 | Travel, DSA etc |  |  | 0
|  |  | Sub-Total Activity 2.3.1: | [7 empty] | 72000 | 72000 | 0 |  | 0 | 0 | 0
|  |  | Sub-Total Output 2.3: | [7 empty] | 72000 | 72000 | 0 |  | 0 | 0 | 0
Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably
Activity 2.4.1: Support the development and promotion of a government incentive scheme to attract additional investment in the blue economy
|  | 2.4.1.1 | Contractual Services | UNDP | 1 | 50000 | 1 | years | 100% | 4 | 50000 | 50000 | 0 | This activity will support the Government of Fiji with the development and promotion of an incentive scheme covering regulations, subsidies, and other incentives that can attract private sector investment. These can include reductions in duty and VAT, or offering accelerated depreciation, tax credits, biodiversity offsets and other incentives could be used to encourage investments in protection of coastal eco-systems and the associated blue economy. |  |  | 0
|  | 2.4.1.2 | Travel | UNDP | 1 | 2000 | 1 | years | 100% | 5 | 2000 | 2000 | 0 | Travel, DSA etc |  |  | 0
|  |  | Sub-Total Activity 2.4.1: | [7 empty] | 52000 | 52000 | 0 |  | 0 | 0 | 0
|  |  | Sub-Total Output 2.4: | [7 empty] | 52000 | 52000 | 0 |  | 0 | 0 | 0
Sub-Total OUTCOME 2: | [10 empty] | 7046193.4 | 3246997 | 3799196.4 |  | 1825797.6 | 623000 | 1202797.6
Total PROGRAMME OUTCOME COSTS: | [10 empty] | 8485243.25 | 3949997 | 4535246.25 |  | 2679347.45 | 893500 | 1785847.45
B. PROGRAMME MANAGEMENT COSTS | [13 empty] | Narrative description of budget lines
Management and Operations
N/A | N/A | N/A | Staff and Personnel | UNDP | 1 | 45347 | 4 | Years | 100% | 1 | 181388 | 90694 | 90694 | Programme Manager - SB4-3 | 45347 |  | 45347
N/A | N/A | N/A | Staff and Personnel | UNDP | 1 | 26542 | 4 | Years | 100% | 1 | 106168 | 53084 | 53084 | Admin Support Officer - SB3-3 | 26542 |  | 26542
N/A | N/A | N/A | Travel | UNDP | 1 | 20000 | 1 | Lump Sum | 100% | 5 | 20000 | 10000 | 10000 | Travel, DSA etc | 5000 |  | 5000
N/A | N/A | N/A | General Operating and Other Direct Cost | UNDP | 1 | 20000 | 1 | Lump Sum | 100% | 7 | 20000 | 10000 | 10000 | Operations (rental, internet, phone, laptop etc) | 5000 |  | 5000
N/A | N/A | N/A | Staff and Personnel | UNEP | 1 | 26542 | 4 | Years | 50% | 1 | 53084 | 0 | 53084 | Programme Support Officer - SB3-3 | 13271 |  | 13271
N/A | N/A | N/A | General Operating and Other Direct Cost | UNCDF | 1 | 5000 | 4 | Years | 100% | 7 | 20000 | 10000 | 10000 | Operations (rental, internet, phone, laptop etc) | 5000 |  | 5000
N/A | N/A | N/A | General Operating and Other Direct Cost | UNEP | 1 | 5000 | 4 | Years | 100% | 7 | 20000 | 0 | 20000 | Operations (rental, internet, phone, laptop etc) | 5000 |  | 5000
|  |  | Sub-Total Management and Operations | [7 empty] | 420640 | 173778 | 246862 |  | 105160 | 0 | 105160
Communications and Learning
N/A | N/A | N/A | General Operating and Other Direct Cost | UNDP | 1 | 15000 | 1 | Lump Sum | 100% | 7 | 15000 | 7500 | 7500 | COMMUNICATIONS: Printing costs | 3750 |  | 3750
N/A | N/A | N/A | Contractual Services | UNDP | 1 | 20000 | 1 | Lump Sum | 100% | 4 | 20000 | 10000 | 10000 | Consultant to draft Learning and Sharing Plan | 5000 |  | 5000
N/A | N/A | N/A | General Operating and Other Direct Cost | UNDP | 1 | 15000 | 3 | Years | 100% | 7 | 45000 | 22500 | 22500 | COMMUNICATIONS: Venue for incubation and acceleration events | 11250 |  | 11250
N/A | N/A | N/A | Staff and Personnel | UNDP | 1 | 45347 | 4 | Years | 50% | 1 | 90694 | 45347 | 45347 | Communications officer - SB4-3 (responsible for development and implementation of comms plan) | 22673.5 |  | 22673.5
N/A | N/A | N/A | Contractual Services | UNDP | 1 | 20000 | 1 | Lump Sum | 100% | 4 | 20000 | 10000 | 10000 | COMMUNICATIONS: Hire photographers, story writers, translators, interpreters, video producers, etc. | 5000 |  | 5000
|  |  | Sub-Total Communications and Learning | [7 empty] | 190694 | 95347 | 95347 |  | 47673.5 | 0 | 47673.5
Programme Oversight support
N/A | N/A | N/A | Contractual Services | UNDP | 1 | 90000 | 2 | years | 100% | 4 | 180000 | 90000 | 90000 | Programmatic oversight and support by BPPS RTA | 50000 | 50000 | 0
N/A | N/A | N/A | Staff and Personnel | UNDP | 1 | 45347 | 4 | Years | 25% | 1 | 45347 | 22673.5 | 22673.5 | M&E officer - SB4-3 (responsible for implementation of RM and Evaluation) | 11336.75 |  | 11336.75
|  |  | Sub-Total Evaluation | [7 empty] | 225347 | 112673.5 | 112673.5 |  | 61336.75 | 50000 | 11336.75
|  |  | TOTAL PROGRAMME MANAGEMENT COSTS: | [7 empty] | 836681 | 381798.5 | 454882.5 |  | 214170.25 | 50000 | 164170.25
|  |  | TOTAL DIRECT PROGRAMME COSTS | [7 empty] | 9321924.25 | 4331795.5 | 4990128.75 |  | 2893517.7 | 943500 | 1950017.7
|  |  | Indirect Programme Support Costs (7%) | [7 empty] | 652534.6975 | 303225.685 | 349309.0125 |  | 202546.239 | 66045 | 136501.239
|  |  | TOTAL COSTS | [5 empty] | TOTAL COST |  | 9974458.9475 | 4635021.185 | 5339437.7625 |  | 3096063.939 | 1009545 | 2086518.939
[11 empty] | Final approved budget |  |  |  | GFCR 2021 Allocation |  | 1009545
[11 empty] | GFCR Total Allocation | -64200 | 4635021
[11 empty] | SDG Fund Total Allocation |  | 5339438
[12 empty] | -64200 | 9974459
JP original budget
[11 empty] | GFCR |  | 4699221
[11 empty] | Joint SDG Fund |  | 5339438
10038659
Note on L70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 90K for Matanataki's work to set up SPV, 140K to SPV
Note on P70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Matanataki requesting full amount. Before asked for 120K.
Note on P74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Matanataki: To offset the increase as per above we suggest splitting 2.2.2.1 (Western Landfill grant of 350k) into 235k in 2021 and 115k in 2022
Note on M75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $62 K deducted from GFCR
Note on N75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 62K added to Joint SDG Fund
Note on P76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In total , 50:50 split between GFCR and Joint SDG. Now it's all under Joint SDG
Note on G81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: adjusted after adding 10K
Note on N81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: added 10K to Joint SDG Fund
Note on N86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 35K (contractual service) + 1K = 36K(travel) under Joint SDG moved under GFCR
Note on N92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 25K (contractual service) + 1K (travel) = 26K under Joint SDG moved under GFCR