## A. Work Plan - (hidden)
WORK PLAN
Joint SDG Fund - GFCR Fiji
Outcome | Output | Outcome/Output Description | TIME FRAME |  |  |  | PLANNED BUDGET |  |  | Recipient UN organization | Implementing Partners
|  |  | Y1 | Y2 | Y3 | Y4 | Joint SDG Fund | Global Fund for Coral Reefs | Total USD
A. PROGRAMME OUTCOME COSTS
1 | Outcome 1: Protection and effective management of Fijian priority coral reef sites and climate change-affected refugia are sustainably financed
1 | 1.1 | Output 1.1: Increased area of new climate refugia and priority sites designated as MPAs or LMMAs | x | x | x | x |  |  | 0
1 | 1.2 | Output 1.2: Established SPEs financed by revenue generation activities within and around LMMAs and a blended finance facility with high leverage potential for the private sector | x | x | x | x |  |  | 0
1 | 1.3 | Output 1.3: Strengthened management, enforcement and monitoring systems of LMMAs by SPEs. | x | x | x | x |  |  | 0
1 | 1.4 | Output 1.4: Established coral reef and ridge to reef conservation legal and regulatory frameworks to promote protection and mitigation of local threats. | x | x | x | x |  |  | 0
Sub-total Outcome 1 | [6 empty] | 0 | 0 | 0
2 | Outcome 2: Transforming the livelihoods of coral reef-dependent communities
2 | 2.1 | Output 2.1: Established Technical Assistance Facility, managed by local investment manager Matanataki, supported by UNCDF to develop a pipeline of investment ready reef-positive sustainable businesses and projects with an emphasis on employing local community members, especially women and youth | x | x | x | x |  |  | 0
2 | 2.2 | Output 2.2: Mobilized public and private investment in priority sustainable initiatives related to addressing coral reef degradation drivers | x | x | x | x |  |  | 0
2 | 2.3 | Output 2.3: Strengthened and harmonized policies, strategies, plans and financing from the government of Fiji for improved environmental biodiversity protection | x | x | x | x |  |  | 0
2 | 2.4 | Output 2.4: Establish recognition, rewards and monitoring systems to incentivize the private sector to act sustainably | x | x | x | x |  |  | 0
Sub-total Outcome 2 | [6 empty] | 0 | 0 | 0
TOTAL PROGRAMME OUTCOME COSTS | [6 empty] | 0 | 0 | 0
B. PROGRAMME MANAGMENT COSTS
UNDP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNDP | N/A
UNCDF
N/A | N/A |  | x | x | x | x |  |  | 0 | UNCDF | N/A
UNEP
N/A | N/A |  | x | x | x | x |  |  | 0 | UNEP | N/A
EVALUATION
N/A | N/A |  | x | x | x | x |  |  | 0 | Evaluation | N/A
TOTAL PROGRAMME MANAGMENT COSTS | [6 empty] | 0 | 0 | 0
TOTAL DIRECT PROGRAMME COSTS | [6 empty] | 0 | 0 | 0
Total Indirect Support Cost - GMS (7%) | [6 empty] | 0 | 0 | 0
TOTAL COSTS | [6 empty] | 0 | 0 | 0

## A. Budget UNDG Categories -
BUDGET BY UNDG CATEGORIES
GFCR Indonesia
All in USD
GFCR
1. Staff and other personnel | 23239.43
2. Supplies, Commodities, Materials | 0
3. Equipment, Vehicles, and Furniture (including Depreciation) | 0
4. Contractual services | 66000
5. Travel | 2000
6. Transfers and Grants to Counterparts | 0
7. General Operating and other Direct Costs | 2218.38
Total Direct Costs | 93457.81
8. Indirect Support Costs (Max. 7%) | 6542.0467
TOTAL Budget | 99999.8567

## C. Workplan
Outcome 1: Joint programme for Indonesia collaboratively designed and proposal submitted to the Global Fund for Coral Reefs
Output | Monthly Target |  |  |  | List of activities | PLANNED BUDGET
| March | April | May | June |  | Overall budget description* | GFCR (USD)
Output 1.1: Potential partners convened to contribute to project design |  |  |  |  | Activity 1.1.1: Hold initial partner dialogues with civil society partners working in target geographies to solicit input into project design and begin to aggregate potential ideas for the funding and project pipeline. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 0
[5 empty] | Activity 1.1.2: Targeted outreach to specialist finance and investment professionals to inform design of blended financing approach(es) (see Activity 1.4.2 for additional detail) | The costs for this activity are budgeted in 1.4.2
[5 empty] | Activity 1.1.3: Agree upon a mechanism for continued partner engagement in the project, including a mechanism to gather and vet additional potential investable and fundable projects as they emerge. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
Output 1.2: Project consultation conducted with relevant National, Provincial, and Regency Governments |  |  |  |  | Activity 1.2.1: Consult on project design with relevant agencies with the National Government, including but not limited to the Coordinating Ministry of Maritime and Investment Affairs, Ministry of Environment and Forestry Ministry of Maritime Affairs and Fisheries, Ministry of Finance, Ministry of National Development Planning (BAPPENAS), and the Peat and Mangrove Restoration Agency. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 2000
[5 empty] | Activity 1.2.2: Consult on project design with relevant governments in the Bird’s Head Seascape, possibly including but not limited to the West Papua Provincial Government, Regency Governments in Raja Ampat, Kaimana, FakFak, Tambrauw, South Sorong, Wondoma Bay, and Bintuni Bay. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.2.3: Consult on project design with relevant governments in the Lesser Sunda Seascape. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.2.4: As part of Activities 1.2.1-1.2.3, specifically consult agencies, ministries and focal points related to economic development, finance, trade and investment, in order to identify policy and regulatory parameters related to investment in key verticals and to identify potential incentives, synergies and opportunities to facilitate private investment within existing legal, policy frameworks. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.2.5: If other geographies emerge through partner dialogues, CI or the relevant partner consult with relevant governments. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
Output 1.3: Negotiations for the Blue Abadi Debt for Nature Swap are progressing; the detailed opportunity and business case for GFCR investment is submitted with the full proposal. |  |  |  |  | Activity 1.3.1: As invited, participate in negotiations for the debt for nature swap between the Government of Indonesia, the Government of the United States, and CI and TNC for coral reef conservation in West Papua. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 6014.97
[5 empty] | Activity 1.3.2: Map the flow of proceeds (sources and uses) from Debt for Nature Swap investment and describe options for earmarking the GFCR proceeds within Blue Abadi to support local businesses with coral-positive business models, including building their technical capacity to access private investment. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.3.3: Compile any necessary additional documentation on Blue Abadi and/or the debt for nature swap mechanism for the Global Fund for Coral Reef joint programme proposal submission. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
Output 1.4: Blueprints of promising direct investment opportunities for coral reef positive economic development, including actionable business and finance and investment models, submitted with full proposal. |  |  |  |  | Activity 1.4.1: Commission landscape assessment and mapping of relevant financing and investment institutions, including domestic, regional, and international entities across both public and private sectors. | CI has budgeted the costs for an external consultant to conduct the analysis, as well as staff time and related occupancy costs to oversee the contract deliverables. | 48000
[5 empty] | Activity 1.4.2: In conjunction with landscape assessment, conduct targeted outreach with relevant financial sector institutions to identify new and existing relevant existing initiatives, and “coral reef positive” finance and investment ecosystem opportunities, gaps and synergies to inform design of blended financing approach (vehicles, instruments, etc.) | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.4.3: Document design alternatives and key implementation partners and stakeholders | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.4.4: Commission industry and market assessment(s) for coral reef positive small and mid-sized enterprises across relevant GFCR thematic priorities and verticals, with emphasis on but not exclusive to initial site priorities of the Bird's Head Seascape and Lesser Sunda Seascape. | CI has budgeted the costs for an external consultant to conduct the analysis, as well as staff time and related occupancy costs to oversee the contract deliverables.
[5 empty] | Activity 1.4.5: Based on results of preliminary targeted industry and market analyses (see Activity 1.4.4), map key stakeholders across significant value chains (e.g. ecotourism, surf tourism, fisheries, aquaculture, restoration technology, water and waste management, clean energy, coastal agriculture, forestry, and other land use, etc.) | CI has budgeted the costs for an external consultant to conduct the analysis, as well as staff time and related occupancy costs to oversee the contract deliverables.
[5 empty] | Activity 1.4.6: Time permitting, conduct initial targeted outreach to key industry and enterprise development leaders to identify opportunities for expanding “coral reef positive” enterprises and/or market activities at multiple scales (SME to industrial). This activity will be ongoing throughout the life of the project. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.4.7: Identify 3-5 potentially actionable market-based opportunities for early investment by GFCR, across risk-return profiles (concessional to market-priced). | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.4.8: Compile and synthesize findings from preceding activities into proposed strategy and roadmap for addressing conditions antecedent to attracting private sector investment finance to support “coral reef positive” market developments | CI has budgeted staff time and related occupancy costs to complete this deliverable.
Output 1.5: Detailed strategy and workplan to replicate key MPA and MPA finance innovations first developed in Raja Ampat to other locations within the Bird’s Head Seascape, the Lesser Sunda Seascape, and potentially other key geographies identified by partners, is developed and submitted with the full proposal. |  |  |  |  | Activity 1.5.1: Building from Activity 1.1.1, convene potential civil society partners in the Bird’s Head Seascape and the Lesser Sundas Seascape to ensure alignment and identify priorities and additional opportunities. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 0
[5 empty] | Activity 1.5.2: Identify key activities for the development and implementation of a sustainable financing plan and an ecotourism development plan for Cenderawasih Bay National Park. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.5.3: Prioritize potential locations and MPA management authorities for the replication of the Public Service Agency “BLUD” status and Raja Ampat MPA tourism fee system in the Bird’s Head Seascape and potentially in the Lesser Sundas. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.5.4: Identify priority existing (or potential) MPAs protecting resilient reefs within the Lesser Sunda Seascape for targeted conservation programing and blended finance mechanisms, including the Indonesia-Timor Leste transboundary Peace Park and candidate surf protected areas. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
Output 1.6: Initial scientific justification, strategy, and workplan for a dedicated workstream on mangrove/peat/seagrass protection, alternative livelihood development, and blue carbon financing potential is developed and submitted with the full proposal |  |  |  |  | Activity 1.6.1: Compile existing and as necessary develop additional detailed maps and analysis of globally significant irreplaceable blue carbon (including location, quantity and threat analysis), in the Bird’s Head Seascape, and other high potential geographies as relevant. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 28311.87
[5 empty] | Activity 1.6.2: Compile scientific evidence of the direct ecological link between mangrove and seagrass ecosystems with priority coral reefs, and the potential impacts of planned conversion of mangroves and coastal peat on specific reefs in the Bird’s Head Seascape, and other high potential geographies as relevant. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.6.3: Initial assessment of market (demand, supply side) for mangrove offsets, other blue carbon investments, and alternative livelihood options in the Bird’s Head Seascape. | CI has budgeted the costs for an external consultant to conduct the analysis, as well as staff time and related occupancy costs to oversee the contract deliverables.
[5 empty] | Activity 1.6.4: Conduct policy scoping analysis to assess readiness for domestic blue carbon implementation and potential carbon trading (for meeting national targets and/or voluntary carbon markets), including identifying relevant policy windows and levers and identifying appropriate legal counsel to conduct additional legal analysis of carbon rights and land tenure during project implementation. | CI has budgeted staff time and related occupancy costs to complete this deliverable.
[5 empty] | Activity 1.6.5: Commission an analysis of future-threat to blue carbon ecosystems in the Bird’s Head Seascape, using internationally respected methodologies approved by the Verified Carbon Standard, in order to build case for additionality of any mangrove conservation initiatives conducted in Bird’s Head Seascape. | CI has budgeted the costs for an external consultant to conduct the analysis, as well as staff time and related occupancy costs to oversee the contract deliverables.
Output 1.7: Proposed programme governance, staffing structure, and initial partner coalition designed |  |  |  |  | Activity 1.7.1: Develop proposed project governance and staffing structure to ensure effective and efficient oversite of the project and collaboration and coordination with partners. | CI has budgeted staff time and related occupancy costs to complete this deliverable. | 3007.49
| *Targets are cumulative. For details on these targets and other indicators, see Annex 2.2 Results Framework |  |  |  |  | Total | 87334.33

## D. Budget by Outcome -
BUDGET BY OUTCOME
Consevation International Planning Grant workplan for GFCR Indonesia Joint Program
Outcome | Output | Activity | Budget Lines | Organization | Unit quantity | Unit Cost (USD) | Duration | Time unit (Time units or Lump sum) | % Charged to Programme | UNDG Budget Category (1-7) |  | Narrative description of budget lines
GFCR
A. PROGRAMME OUTCOME COSTS
Outcome 1: Joint programme for Indonesia collaboratively designed and proposal submitted to the Global Fund for Coral Reefs
Output 1.1: Potential partners convened to contribute to project design
Activity 1.1.1: Hold initial partner dialogues with civil society partners working in target geographies to solicit input into project design and begin to aggregate potential ideas for the funding and project pipeline.
|  | 1.1.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.1.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.1.1: | [7 empty] | 0
Activity 1.1.2: Targeted outreach to specialist finance and investment professionals to inform design of blended financing approach(es) (see Activity 1.4.2 for additional detail)
|  | 1.1.2.1 |  |  |  | #REF! | 3 months | Monthly Unit | 0% |  | 0 | Activity budgeted in 1.4.2 which is a linked activity
|  | 1.1.2.2 |  |  |  | #REF! | 3 months | Monthly Unit | 0% |  | 0
|  |  | Sub-Total Activity 1.1.2: | [7 empty] | 0
Activity 1.1.3: Agree upon a mechanism for continued partner engagement in the project, including a mechanism to gather and vet additional potential investable and fundable projects as they emerge.
|  | 1.1.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.1.3.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.1.3: | [7 empty] | 0
Activity 1.1.4: Name of Activity
1.1.4.1
1.1.4.2
|  |  | Sub-Total Activity 1.1.4: | [7 empty] | 0
|  |  | Sub-Total Output 1.1: | [7 empty] | 0
Output 1.2: Project consultation conducted with relevant National, Provincial, and Regency Governments
Activity 1.2.1: Consult on project design with relevant agencies with the National Government, including but not limited to the Coordinating Ministry of Maritime and Investment Affairs, Ministry of Environment and Forestry Ministry of Maritime Affairs and Fisheries, Ministry of Finance, Ministry of National Development Planning (BAPPENAS), and the Peat and Mangrove Restoration Agency.
|  | 1.2.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.2.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.2.1: | [7 empty] | 0
Activity 1.2.2: Consult on project design with relevant governments in the Bird’s Head Seascape, possibly including but not limited to the West Papua Provincial Government, Regency Governments in Raja Ampat, Kaimana, FakFak, Tambrauw, South Sorong, Wondoma Bay, and Bintuni Bay.
|  | 1.2.2.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.2.2.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.2.2: | [7 empty] | 0
Activity 1.2.3: Consult on project design with relevant governments in the Lesser Sunda Seascape.
|  | 1.2.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.2.3.2 | Travel | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 5 | 2000 | Travel for CI Staff to travel within Indonesia to meet with project partners.
|  | 1.2.3.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.2.3: | [7 empty] | 2000
Activity 1.2.4: As part of Activities 1.2.1-1.2.3, specifically consult agencies, ministries and focal points related to economic development, finance, trade and investment, in order to identify policy and regulatory parameters related to investment in key verticals and to identify potential incentives, synergies and opportunities to facilitate private investment within existing legal, policy frameworks.
|  | 1.2.4.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.2.4.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.2.4: | [7 empty] | 0
Activity 1.2.5: If other geographies emerge through partner dialogues, CI or the relevant partner consult with relevant governments.
|  | 1.2.5.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.2.5.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.2.5: | [7 empty] | 0
|  |  | Sub-Total Output 1.2: | [7 empty] | 2000
Output 1.3: Negotiations for the Blue Abadi Debt for Nature Swap are progressing; the detailed opportunity and business case for GFCR investment is submitted with the full proposal.
Activity 1.3.1: As invited, participate in negotiations for the debt for nature swap between the Government of Indonesia, the Government of the United States, and CI and TNC for coral reef conservation in West Papua.
|  | 1.3.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 1890.99 | CI Staff time to directly contribute to project deliverables
|  | 1.3.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 114 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.3.1: | [7 empty] | 2004.99
Activity 1.3.2: Map the flow of proceeds (sources and uses) from Debt for Nature Swap investment and describe options for earmarking the GFCR proceeds within Blue Abadi to support local businesses with coral-positive business models, including building their technical capacity to access private investment.
|  | 1.3.2.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 1890.99 | CI Staff time to directly contribute to project deliverables
|  | 1.3.2.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 114 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.3.2: | [7 empty] | 2004.99
Activity 1.3.3: Compile any necessary additional documentation on Blue Abadi and/or the debt for nature swap mechanism for the Global Fund for Coral Reef joint programme proposal submission.
|  | 1.3.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 1890.99 | CI Staff time to directly contribute to project deliverables
|  | 1.3.3.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 114 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.3.2: | [7 empty] | 2004.99
|  |  | Sub-Total Output 1.3: | [7 empty] | 6014.97
Output 1.4: Blueprints of promising direct investment opportunities for coral reef positive economic development, including actionable business and finance and investment models, submitted with full proposal.
Activity 1.4.1: Commission landscape assessment and mapping of relevant financing and investment institutions, including domestic, regional, and international entities across both public and private sectors.
|  | 1.4.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.1.2 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 20000 | External consultant to conduct landscape assessment
|  | 1.4.1.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.1: | [7 empty] | 20000
Activity 1.4.2: In conjunction with landscape assessment, conduct targeted outreach with relevant financial sector institutions to identify new and existing relevant existing initiatives, and “coral reef positive” finance and investment ecosystem opportunities, gaps and synergies to inform design of blended financing approach (vehicles, instruments, etc.)
|  | 1.4.2.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.2.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.2: | [7 empty] | 0
Activity 1.4.3: Document design alternatives and key implementation partners and stakeholders
|  | 1.4.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.3.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.3: | [7 empty] | 0
Activity 1.4.4: Commission industry and market assessment(s) for coral reef positive small and mid-sized enterprises across relevant GFCR thematic priorities and verticals, with emphasis on but not exclusive to initial site priorities of the Bird's Head Seascape and Lesser Sunda Seascape.
|  | 1.4.4.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.4.2 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 3000 | External consultant to conduct market assessment for surf eco-tourism
|  | 1.4.4.3 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 12500 | External consultant to conduct industry and market assessment
|  | 1.4.4.4 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.4: | [7 empty] | 15500
Activity 1.4.5: Based on results of preliminary targeted industry and market analyses (see Activity 1.4.4), map key stakeholders across significant value chains (e.g. ecotourism, surf tourism, fisheries, aquaculture, restoration technology, water and waste management, clean energy, coastal agriculture, forestry, and other land use, etc.)
|  | 1.4.5.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.5.2 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 12500 | External consultant to conduct stakeholder and value-chain mapping
|  | 1.4.5.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.5: | [7 empty] | 12500
Activity 1.4.6: Time permitting, conduct initial targeted outreach to key industry and enterprise development leaders to identify opportunities for expanding “coral reef positive” enterprises and/or market activities at multiple scales (SME to industrial). This activity will be ongoing throughout the life of the project.
|  | 1.4.6.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.6.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.6: | [7 empty] | 0
Activity 1.4.7: Identify 3-5 potentially actionable market-based opportunities for early investment by GFCR, across risk-return profiles (concessional to market-priced).
|  | 1.4.7.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.7.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.7: | [7 empty] | 0
Activity 1.4.8: Compile and synthesize findings from preceding activities into proposed strategy and roadmap for addressing conditions antecedent to attracting private sector investment finance to support “coral reef positive” market developments
|  | 1.4.8.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.4.8.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.4.8: | [7 empty] | 0
|  |  | Sub-Total Output 1.4: | [7 empty] | 48000
Output 1.5: Detailed strategy and workplan to replicate key MPA and MPA finance innovations first developed in Raja Ampat to other locations within the Bird’s Head Seascape, the Lesser Sunda Seascape, and potentially other key geographies identified by partners, is developed and submitted with the full proposal.
Activity 1.5.1: Building from Activity 1.1.1, convene potential civil society partners in the Bird’s Head Seascape and the Lesser Sundas Seascape to ensure alignment and identify priorities and additional opportunities.
|  | 1.5.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.5.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.5.1: | [7 empty] | 0
Activity 1.5.2: Identify key activities for the development and implementation of a sustainable financing plan and an ecotourism development plan for Cenderawasih Bay National Park.
|  | 1.5.2.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.5.2.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.5.2: | [7 empty] | 0
Activity 1.5.3: Prioritize potential locations and MPA management authorities for the replication of the Public Service Agency “BLUD” status and Raja Ampat MPA tourism fee system in the Bird’s Head Seascape and potentially in the Lesser Sundas.
|  | 1.5.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.5.3.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.5.3: | [7 empty] | 0
Activity 1.5.4: Identify priority existing (or potential) MPAs protecting resilient reefs within the Lesser Sunda Seascape for targeted conservation programing and blended finance mechanisms, including the Indonesia-Timor Leste transboundary Peace Park and candidate surf protected areas.
|  | 1.5.4.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 0 | CI Staff time to directly contribute to project deliverables
|  | 1.5.4.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 0 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.5.4: | [7 empty] | 0
|  |  | Sub-Total Output 1.5: | [7 empty] | 0
Output 1.6: Initial scientific justification, strategy, and workplan for a dedicated workstream on mangrove/peat/seagrass protection, alternative livelihood development, and blue carbon financing potential is developed and submitted with the full proposal
Activity 1.6.1: Compile existing and as necessary develop additional detailed maps and analysis of globally significant irreplaceable blue carbon (including location, quantity and threat analysis), in the Bird’s Head Seascape, and other high potential geographies as relevant.
|  | 1.6.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 1532.85 | CI Staff time to directly contribute to project deliverables
|  | 1.6.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 247.29 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.6.1: | [7 empty] | 1780.14
Activity 1.6.2: Compile scientific evidence of the direct ecological link between mangrove and seagrass ecosystems with priority coral reefs, and the potential impacts of planned conversion of mangroves and coastal peat on specific reefs in the Bird’s Head Seascape, and other high potential geographies as relevant.
|  | 1.6.2.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 1532.85 | CI Staff time to directly contribute to project deliverables
|  | 1.6.2.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 247.29 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.6.2: | [7 empty] | 1780.14
Activity 1.6.3: Initial assessment of market (demand, supply side) for mangrove offsets, other blue carbon investments, and alternative livelihood options in the Bird’s Head Seascape.
|  | 1.6.3.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 613.14 | CI Staff time to directly contribute to project deliverables
|  | 1.6.3.2 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 10000 | External consultant to conduct blue carbon market assessment in Bird's Head Seascape
|  | 1.6.3.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 98.92 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.6.3: | [7 empty] | 10712.06
Activity 1.6.4: Conduct policy scoping analysis to assess readiness for domestic blue carbon implementation and potential carbon trading (for meeting national targets and/or voluntary carbon markets), including identifying relevant policy windows and levers and identifying appropriate legal counsel to conduct additional legal analysis of carbon rights and land tenure during project implementation.
|  | 1.6.4.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 5071.58 | CI Staff time to directly contribute to project deliverables
|  | 1.6.4.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 611.92 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.6.4: | [7 empty] | 5683.5
Activity 1.6.5: Commission an analysis of future-threat to blue carbon ecosystems in the Bird’s Head Seascape, using internationally respected methodologies approved by the Verified Carbon Standard, in order to build case for additionality of any mangrove conservation initiatives conducted in Bird’s Head Seascape.
|  | 1.6.5.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 306.57 | CI Staff time to directly contribute to project deliverables
|  | 1.6.5.2 | Contractual Services | CI | 1 | #REF! | 3 months | Lump Sum | 0% | 4 | 8000 | External consultant to conduct future-threat analyiss for blue carbon ecosystems in Bird's Head Seascape
|  | 1.6.5.3 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 49.46 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.6.5: | [7 empty] | 8356.03
|  |  | Sub-Total Output 1.6: | [7 empty] | 28311.87
Output 1.7: Proposed programme governance, staffing structure, and initial partner coalition designed
Activity 1.7.1: Develop proposed project governance and staffing structure to ensure effective and efficient oversite of the project and collaboration and coordination with partners.
|  | 1.7.1.1 | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 2836.49 | CI Staff time to directly contribute to project deliverables
|  | 1.7.1.2 | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 171 | Occupancy costs based on staff time related to project
|  |  | Sub-Total Activity 1.7.1: | [7 empty] | 3007.49
|  |  | Sub-Total Output 1.7: | [7 empty] | 3007.49
Sub-Total OUTCOME 1: | [10 empty] | 87334.33
Outcome 2:61:77A4061:9761:7861:7961:8061:8161:8261:8361:8461:8561:8661:8561:8661:8861:9061:9161:9061:9161:9261:9461:9661:9861:9161:9061:98
Output 2.1: Name of Output
Activity 2.1.1: Name of Activity
2.1.1.1
2.1.1.2
|  |  | Sub-Total Activity 2.1.1: | [7 empty] | 0
Activity 2.1.2: Name of Activity
2.1.2.1
2.1.2.2
|  |  | Sub-Total Activity 2.1.2: | [7 empty] | 0
|  |  | Sub-Total Output 2.1: | [7 empty] | 0
Output 2.2: Name of Output
Activity 2.2.1: Name of Activity
2.2.1.1
2.2.1.2
|  |  | Sub-Total Activity 2.2.1: | [7 empty] | 0
Activity 2.2.2: Name of Activity
2.2.2.1
2.2.2.2
|  |  | Sub-Total Activity 2.2.2: | [7 empty] | 0
Activity 2.2.3: Name of Activity
2.2.3.1
2.2.3.2
|  |  | Sub-Total Activity 2.2.3: | [7 empty] | 0
|  |  | Sub-Total Output 2.2: | [7 empty] | 0
Output 2.3: Name of Output
Activity 2.3.1: Name of Activity
2.3.1.1
2.3.1.2
|  |  | Sub-Total Activity 2.3.1: | [7 empty] | 0
|  |  | Sub-Total Output 2.3: | [7 empty] | 0
Output 2.4: Name of Output
Activity 2.4.1: Name of Activity
2.4.1.1
2.4.1.2
|  |  | Sub-Total Activity 2.4.1: | [7 empty] | 0
|  |  | Sub-Total Output 2.4: | [7 empty] | 0
Sub-Total OUTCOME 2: | [10 empty] | 0
Total PROGRAMME OUTCOME COSTS: | [10 empty] | 87334.33
B. PROGRAMME MANAGEMENT COSTS | [11 empty] | Narrative description of budget lines
Management and Operations
N/A | N/A | N/A | Staff and Personnel | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 1 | 5672.98 | CI Staff time to directly contribute to project deliverables
N/A | N/A | N/A | General Operating and Other Direct Cost | CI | 3 | #REF! | 3 months | Monthly Unit | 0% | 7 | 450.5 | Occupancy costs based on staff time related to project
N/A | N/A | N/A
N/A | N/A | N/A
N/A | N/A | N/A
N/A | N/A | N/A
N/A | N/A | N/A
|  |  | Sub-Total Management and Operations | [7 empty] | 6123.48
Communications and Learning
N/A | N/A | N/A | N/A during planning grant phase | [7 empty] | 0
N/A | N/A | N/A
N/A | N/A | N/A
N/A | N/A | N/A
N/A | N/A | N/A
|  |  | Sub-Total Communications and Learning | [7 empty] | 0
Evaluation
N/A | N/A | N/A | N/A during planning grant phase | [7 empty] | 0
N/A | N/A | N/A
|  |  | Sub-Total Evaluation | [7 empty] | 0
|  |  | TOTAL PROGRAMME MANAGEMENT COSTS: | [7 empty] | 6123.48
|  |  | TOTAL DIRECT PROGRAMME COSTS | [7 empty] | 93457.81
|  |  | Indirect Programme Support Costs (7%) | [6 empty] | 8 | 6542.0467
|  |  | TOTAL COSTS | [7 empty] | 99999.8567

## Staffing Notes (hidden)
Staffing Notes
LOE (Days)1
|  | CCenter | GFCR | Other | Comments
1 | Project Oversight
1.1 | Laure
1.2 | Meizani
2 | APFD Regional
2.1
2.2
2.3
2.4
2.5
3 | Indonesia
3.1
3.2
3.3
3.4
3.5
4 | Technical Advisory
4.1 | Rob Baigrie
4.2 | Jan Yoshioka | 2505 | 0 | 6 | Incl. (i) external consultancy management, oversight and deliverables review; (ii) relevant section proposal writing. Assumes Meizani/Rob to lead partner outreach and network development.
4.3 | Gracie White | 2505 | 0 | 4 | Incl. (i) supplemental research on relevant accelerators, incubators; (ii) targeted supplemental desktop review
4.4
4.5
Notes: | 1. LOE assuming March 1 - Apr 2 start and end