## Day 0
DAY 0
| Director | Coordinator | Co-Director | Housing Specialist | Hospitality Coordinator | Store Manager | Outer Realm/Rec Manager | Band | Stage Manager
BREAKFAST/COFFEE ON YOUR OWN IF TIME ALLOWS
8:00 | UNLOAD THE TRUCK
8:30
9:00
9:30
10:00
10:30
11:00
11:30
12:00 | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch
12:30
13:00 | Meet w/Venue if a.m. wasn't available | Meet w/Venue if a.m. wasn't available | Assist where needed | Help Setup Store | Meet w/Venue if a.m. wasn't available | Set up Store | Assist Production w/Stage Setup
13:30
14:00 | Oversee setup progress/Make adjustments as needed | Set up Check-In/ Inventory EC Case |  |  | Help Set up Check-In/Create Shopping List
14:30
15:00 | [6 empty] | Inventory Game Materials/Create Shopping List | Continue Stage Setup | Inventory Props/Create Shopping List
15:30
16:00
16:30
17:00 | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner
17:30
18:00 | WALMART RUN FOR ANYONE THAT NEEDS ITEMS
18:30
18:45 | Review signage placement/location |  | Assist where needed | Finalize Housing/Update Rosters | HUB Setup/Thank you Cards/Gift Bags/App/Small Groups | Merchandising/ Online Order Pack | Sort/Assemble/Repair | Runthroughs w/ Production | Runthroughs w/ Production
19:00
19:30 | Oversee Progress | Check In Prep
20:00
20:30
20:45
21:00
21:30 | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting
22:00
22:30
22:45
23:00

## Day 1
DAY 1
| Director | Coordinator | Co-Director | Housing Specialist | Hospitality Coordinator | Store Manager | Outer Realm/Rec Manager | Band | Stage Manager
8:00 |  | Check-In Set Up |  | Check-In Prep | Check-In Prep + HUB Set Up | Store Set-Up Finishing Touches | Set Up 9 Square & Other Welcome Games in the Zone | Final run-through/Sound Check | Finish Set Up, Sound Check, Run Throughs
8:30 | Prep ALM Room
9:00
9:30
10:00
10:30
11:00 | [6 empty] | Help pack Reg. Bags | Help pack Reg. Bags
11:30
12:00 | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch
12:30
13:00 | Check-In | Check-In | Check-In | Check - In | Check-In | Check-In |  | Big Room assistance | Prep Stage Props
13:30
14:00
14:30
15:00
15:30
16:00
16:30
17:00 | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner
17:30 |  |  |  |  | HUB | Store Open | Help with Store | Help with Store
18:00
18:30
18:45 | ALM | ALM | ALM | ALM | ALM |  | ALM
19:00
19:30 | Session | Session | Session | Session | Session /HUB | Session | Set up for Outer Realm | Session | Session
20:00
20:30 |  |  |  | Help Prep O.R. |  | Help Prep O.R.
20:45 |  |  |  | Help @ O.R. | Help @ O.R. | Help @ O.R. | O.R. | Help @ O.R. | Help @ O.R.
21:00
21:30 | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting
22:00
22:30
22:45 |  |  |  | Security | Security | Security | Security | Security | Security
23:00

## Day 2
DAY 2
| Director | Coordinator | Co-Director | Housing Specialist | Hospitality Coordinator | Store Manager | Outer Realm/Rec Mgr | Band | Stage Manager
7:00
7:30 | Breakfast: EC + HC | Breakfast: D + HC | Breakfast | Breakfast | Breakfast: D + EC | Breakfast | Breakfast | Breakfast | Breakfast
8:00 | ALM | ALM |  |  | ALM | Store Open | ALM | Help at store | Prep for Session
8:30 |  |  |  | HUB
9:00
9:30 | Session | Session | Session |  | HUB | Store Reset/Online Pack |  | Session | Session
10:00 |  |  |  | Housing | Session |  | Afternoon Prep
10:30 |  | Venue Check-In + Day 2 Report
11:00 | Production Meeting |  |  |  | HUB |  |  | Production Meeting | Production Meeting
11:30
12:00 | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch
12:30
13:00 |  | Bank Run |  | Help prep w/Rec. | Help prep w/Rec. | Help prep w/Rec. | Prep Dodgeball & Karaoke/Silent Disco
13:30 | KW Session |  | KW Session
14:00
14:30 |  | Office Hours |  |  |  |  | Dodgeball/Karaoke & Silent Disco | Help @ Dodgeball | Help @ Dodgeball
15:00 | Check on Rec/Check in with Churches |  |  | Help @ Karaoke/Silent Disco |  | Help @ Karaoke/Silent Disco
15:30
16:00 |  |  |  |  | Help @ Karaoke/Silent Disco
16:30
17:00 | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner
17:30
18:00 |  |  |  | Help @ Store |  | Store Open |  | Help @ Store
18:30 |  |  |  |  | HUB |  | Prep for O.R. |  | Session Prep
19:00 | Session | Session | Session | Session | Session | Session | Session | Session | Session
19:30
20:00 |  | Count Store & Offering |  |  | Count Offering
20:30 | [5 empty] | Count Store
20:45 |  |  |  |  | HUB
21:00 | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting
21:30
21:45 | Monitor O.R. | Monitor O.R. | Monitor O.R. | Help @ O.R. | Help @ O.R. | Help @ O.R. | Help @ O.R. | Help @ O.R. | Help @ O.R.
22:00
22:30
22:45 |  |  |  | Security | Security | Security | Security | Security | Security
23:00

## Day 3
DAY 3
| Director | Coordinator | Co-Director | Housing Specialist | Hospitality Coordinator | Store Manager | Outer Realm/Rec. Mgr. | Band | Stage Manager
7:00
7:30 | Breakfast: EC + HC | Breakfast: D + HC | Breakfast | Breakfast | Breakfast: D + EC | Breakfast | Breakfast | Breakfast | Breakfast
8:00 | ALM | ALM |  |  | ALM | Store Open | ALM | Help at store | Prep for Session
8:30 |  |  |  | HUB
9:00
9:30 | Session | Session | Session | Session | HUB | Store Reset/Online Pack |  | Session | Session
10:00 |  |  |  |  | Session |  | Prep for O.R.
10:30
11:00 | Production Meeting |  |  |  | HUB |  |  | Production Meeting | Production Meeting
11:30
12:00 | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch | Lunch
12:30
13:00 |  | Office Hours |  | Housing |  |  | Prep O.R.
13:30 | Monitor O.R. |  | Hang w/Churches |  |  |  | Outer Realm | Help @ O.R.
14:00
14:30 | [8 empty] | Help @ O.R.
15:00
15:30 |  | Monitor Karaoke/Silent Disco | Help @ Karaoke/Silent Disco |  | Karaoke/Silent Disco | Karaoke/Silent Disco |  |  | Karaoke/Silent Disco
16:00 | [6 empty] | Karoake/Silent Disco | Karaoke/Silent Disco
16:30
17:00 | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner
17:30
18:00 |  |  |  | Help @ Store |  | Store Open |  | Help @ Store
18:30 |  |  |  |  | HUB |  | Help @ Store |  | Session Prep
19:00 | Session | Session | Session | Session | Session | Session | Session | Session | Session
19:30
20:00 |  | Count Store & Offering |  |  | Count Offering
20:30 | [5 empty] | Count Store
20:45 |  |  |  |  | HUB
21:00 | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting
21:30
21:45
22:00
22:30
22:45 |  |  |  | Security | Security | Security | Security | Security | Security
23:00

## Day 4
DAY 4
| Director | Coordinator | Co-Director | Housing Specialist | Hospitality Coordinator | Store Manager | Outer Realm/Rec. Mgr. | Band | Stage Manager
7:00
7:30 | Breakfast: EC + HC | Breakfast: D + HC | Breakfast | Breakfast | Breakfast: D + EC | Breakfast | Breakfast | Breakfast | Breakfast
8:00 | ALM | ALM |  |  | ALM | Store Open | Help @ Store | Help at store | Prep for Session
8:30 |  |  |  | HUB
9:00
9:30 | Session |  | Session | Session | HUB | Store Reset/Online Pack/Inventory | Session | Session | Session
10:00 |  | Bank Run |  |  | Session
10:30
11:00 | Production Meeting |  |  |  | HUB |  |  | Production Meeting | Production Meeting
11:30
12:00 | EXTENDED REC
12:30
13:00
13:30
14:00
14:30
15:00
15:30 |  | Prep for Load Out |  |  | Prep for Load Out | Prep for Load Out | Prep for Load Out |  | Prep for Load Out
16:00
16:30
17:00 | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner | Dinner
17:30
18:00 |  |  |  | Help @ Store |  | Store Open |  | Help @ Store
18:30 |  |  |  |  | HUB |  | Help @ Store |  | Session Prep
19:00 | Session | Session/Count Decisions | Session/Count Decisions | Session/Count Decisions | Session/Count Decisions | Inventory Count | Session/Count Decisions | Session | Session
19:30
20:00
20:30 | [5 empty] | Count Decisions
20:45 |  |  |  |  | HUB
21:00 | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting | Team Meeting
21:30 |  | Count Store & Offering |  | Help Store Break Down | Count Store & Offering | Break Down Store | Stage Load Out
21:45
22:00 |  |  |  | Load Out
22:30
22:45 |  |  |  | Security | Security | Security | Security | Security | Security
23:00