## AS9100 Planner
AUGMINO AS9100 READINESS CHECKLIST, COST AND TIMELINE PLANNER
A single-tab planner for a shop deciding whether, and when, to start AS9100 certification. Full guide: augmino.com/blog/as9100-certification-indian-precision-shops-cost-timeline
SECTION 1: DOCUMENTATION TO HAVE IN PLACE BEFORE STAGE 1
Item | Done? | Notes
Document control system covering all quality records (not individual people's files or memory) | No
A history of internal audits, even informal ones | No
One named person who owns quality system responsibility day to day | No
A nonconformance log: issues tracked and root-caused, not just fixed quietly | No
ISO 9001 certification or a firm plan to pursue it first or alongside AS9100 | No
Leadership sign-off on realistic staff time for the process, not just registrar fees budgeted | No
Readiness score (live)
SECTION 2: TIMELINE, STAGE BY STAGE
Stage | Typical duration | Your target date
Gap analysis to Stage 1 readiness | Varies by starting point
Stage 1 to Stage 2 audit | 1-2 months
Stage 2 audit itself | 2-5 auditor-days
Nonconformance closure (if any) | Within 6 months of the closing meeting
Full process, no prior formal QMS | 9-12 months, start to certificate
Full process, already ISO 9001-certified | Roughly 6 months
Certificate validity | 3 years
Surveillance audits | Annual, 1-3 days each
SECTION 3: COST, CATEGORY BY CATEGORY
Cost category | Typical range (global, not India-specific) | Your quote
Gap analysis (optional) | Several thousand dollars
Registrar audit fees (Stage 1 + Stage 2), plus travel | $3,000-$10,000
Implementation (documentation, training, internal audit setup) | $8,000-$20,000
Total, first certification, small-to-mid shop | $10,000-$50,000
Three-year cycle, registrar fees only | $10,000-$20,000
Total entered so far (live)
Request quotes from at least two accredited registrars' India offices and fill in the right-hand column against this planning baseline. Confirm accreditation directly with the registrar before paying for anything.
SECTION 4: REGISTRAR SELECTION, QUESTIONS TO ASK BEFORE YOU SIGN
Question to ask the registrar | Why it matters
Is your AS9100 accreditation currently valid and in scope for our process category? | The certificate only counts if the registrar's own accreditation covers it
Are auditor travel and lodging charges included in the quoted fee? | A common cost that shows up later if not asked upfront
How many auditor-days will Stage 1 and Stage 2 each take? | Needed to schedule production around the audit realistically
What is the earliest available Stage 1 date? | Registrar backlogs vary and can add months on their own
What is the annual surveillance audit fee, separate from the initial certification fee? | This recurs every year of the three-year cycle, not a one-time cost
Pick a registrar only after all five answers check out. An accredited registrar will answer every one of these without hesitation.