## Overview
Legend
Activity performed in month
Text | Example input: note - these are example inputs based on requirements in the Solar for All terms and conditions and are not meant to be exhaustive of steps applicants must take
Introduction:
This Excel Workbook is an optional example for applicants to fill in and submit for their Program Timeline.
Instructions:
For each tab, below is a description of the steps an applicant should complete to finish the template. Applicants should add and subtract rows as needed.
- Choose the tab for your program, SFA recipients should use either the 'May start' or 'September start' example tab, based on project start date, as identified on the SF-424
- Delete the extra timeline tab that does not align with your program period of performance
- In Cell B3, Identify which planning period type you will use: Full/Partial/None
- In Row 4, Update the # of months applicants will plan to use for the planning period
- In Row 7, Update the planning period to end earlier if you will be using less than 12 months
- In column B, Pre-Award and Conditional Drawdown Period Activities, add additional subheaders to organize as needed, and fill in activities the program will complete in the implementation period; add a row for each activity.
- In column B, Program Planning Activities, add additional subheaders to organize as needed, fill in activities the program will complete in the program planning period; add a row for each activity; an activity could be a discrete piece of analysis needed to refine plans/strategies detailed in the Program Narrative; a specific engagement with an important stakeholder; a process like a Request for Proposals or hiring a program manager; and any other type of activity which would be helpful to complete before launching the program.
- In column B, Implementation Period, add additional subheaders to organize as needed, and fill in activities the program will complete in the implementation period; add a row for each activity.
- In column C and D, Include the anticipated state and completion date for each activity
- In columns E through BL, indicate with a colored cell when the activity will occur; consider whether the activity is repeated on some frequency (e.g., a quarterly briefing); consider indicated clearly in the Financial Assistance Strategy workplan when the program will begin offering financial assistance to customers
-Please note that the list of reporting and compliance activities is not comprehensive and it is the responsibility of the grantee to understand all of its compliance and reporting requirements.

## NJSFA Timeline- September Start
PRELIMINARY, PREDECISIONAL, CONFIDENTIAL. DRAFT – NOT FOR DISTRIBUTION
Source: BPU
NJ Solar for All Program Timeline
Planning Period Type Used: Full
Planning Period: 12 Months [1/1/2025-12/31/2025]
Period of Performance: 9/01/2024- 8/31/2029
Activity Type | time axis 2024-09-01 to 2029-12-01
Green indicates activities added from workplan to template |  |  | 2024-09-01: Pre-award and conditional drawdown period; 2025-01-01: Program Planning (12 Months); 2026-01-01: Project Deployment Period
|  |  | Period of Performance and Budget Year 1 | [11 empty] | Period of Performance and Budget Year 2 | [11 empty] | Period of Performance and Budget Year 3 | [11 empty] | Period of Performance and Budget Year 4 | [11 empty] | Period of Performance and Budget Year 5
Pre-Award and Conditional Drawdown Period Activities | Anticipated Start Date | Anticipated Completion Date | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Submit SFA detailed workplan and budget for approval within 90 days of award | 2024-07-22 | 2024-10-21 | bar: Period of Performance and Budget Year 1 Month 1 to Period of Performance and Budget Year 1 Month 2
Contract a Program Design & Implementation Consultant | 2025-01-01 | 2027-12-30 | bar: Period of Performance and Budget Year 1 Month 5 to Period of Performance and Budget Year 4 Month 4
Program Planning Activities |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Publish a full straw proposal to stress test design decisions with key stakeholders, including communities served | 2024-12-01 | 2025-02-27 | bar: Month 4 to Month 6
Develop, validate, and finalize household savings calculation to ensure 20% energy bill savings for multifamily + storage program, community solar program, and residential solar program | 2024-12-01 | 2025-03-31 | bar: Month 4 to Month 7
Develop, validate, and finalize monitoring/reporting and enforcement processes and mechanisms to ensure compliance with 20% energy bill savings requirement | 2024-12-01 | 2025-03-31 | bar: Month 4 to Month 7
Recruit and convene community-based organizations for the to-be-established NJSFA Advisory Council. Finalize members and membership structure. | 2024-12-01 | 2025-03-01 | bar: Month 4 to Month 7
Develop and align on a roadmap for community engagement and education activities | 2024-12-01 | 2025-04-01 | bar: Month 4 to Month 7
Align on new policies and requirements to serve LIDAC households and establish specific forms of technical support and modes of community outreach to LIDACs | 2024-12-01 | 2025-05-30 | bar: Month 4 to Month 9
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Develop monitoring and inspection mechanisms for workforce training providers | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Collaborate with NJDEP to explore whether NJBPU can invest a portion of its NJSFA funds into the NJ Community Solar PV Siting Tool | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Align on program metrics to track to ensure NJSFA programs are adequately serving diverse markets and communities | 2025-01-01 | 2025-03-31 | bar: Month 5 to Month 7
Collaborate with NJEDA to develop qualification criteria for the residential solar program RFP for solar financing providers | 2025-01-01 | 2025-06-30 | bar: Month 5 to Month 10
Perform initial analysis to identify solar-related workforce gaps and assess job quality of roles | 2025-01-01 | 2025-04-30 | bar: Month 6 to Month 8
Defining the guidelines of the Innovation Fund in terms of initiative criteria | 2025-02-01 | 2025-03-30 | bar: Month 6 to Month 7
Develop an initial understanding of solar workforce and skills gaps that the Innovation Fund could reasonably impact | 2025-02-01 | 2025-04-30 | bar: Month 6 to Month 8
Identify potential funding opportunities for interconnection, project siting, and permitting across several key innovative pilots | 2025-02-01 | 2025-04-30 | bar: Month 6 to Month 8
Finalize design of SFA Advisory Council, including its participants and key milestones | 2025-02-01 | 2025-03-01 | bar: Month 6
Design recycling, lifetime of assets term, and audits of assets plan | 2025-02-01 | 2025-09-30 | bar: Month 6 to Month 1
Finalize the design of technical assistance to developers to support customer acquisition, with focus on LIDAC households | 2025-03-01 | 2025-05-30 | bar: Month 7 to Month 9
Finalize the implementation technical assistance to developers to support customer acquisition, with focus on LIDAC households | 2025-03-01 | 2025-05-30 | bar: Month 7 to Month 9
Ideate, validate, and align use cases of NJDOL’s on-the-job training program with key stakeholders | 2025-03-01 | 2025-06-30 | bar: Month 7 to Month 10
Stand up a program monitoring function to track program performance against targets | 2025-03-01 | 2025-06-30 | bar: Month 7 to Month 10
Schedule group and bilateral meetings with stakeholder groups | 2025-03-01 | 2025-09-30 | bar: Month 7 to Month 1
Develop supplier and vendor diversity strategy for each program that focuses on returning benefits to businesses that are diverse-owned and/or located within LIDACs | 2025-03-01 | 2025-09-30 | bar: Month 7 to Month 1
Test potential for coordinating the multifamily + storage program being stood up with the Storage Incentive Program (SIP) that NJBPU is currently developing | 2025-04-01 | 2025-06-30 | bar: Month 8 to Month 10
Determine whether residential solar program will receive supplemental funding from EDA/Green Bank | 2025-04-01 | 2025-06-30 | bar: Month 8 to Month 10
Conduct stakeholder engagement with developers to make decisions on period of distribution of funds for storage for multifamily solar projects | 2025-04-01 | 2025-09-30 | bar: Month 8 to Month 1
Test incentive sizes and refine financial assistance for Community Solar Expansion (CSE) grant, Grid Capacity for Community Solar (GCCS) competitive grant, residential solar program, and multifamily solar + storage program, as well as other components of programs with developers and other key stakeholders | 2025-04-01 | 2025-09-30 | bar: Month 8 to Month 1
Conduct stakeholder engagement with developers to better understand workforce gaps and opportunities for LIDAC workers. | 2025-04-01 | 2025-09-30 | bar: Month 8 to Month 1
Develop and align on a draft MOU with NJEDA to enable transfer of funds to Green Bank for residential solar program | 2025-04-01 | 2025-12-31 | bar: Month 8 to Month 4
Develop and align on a draft MOU with NJDOL to enable transfer of funds to NJDOL for workforce development programs | 2025-04-01 | 2025-12-31 | bar: Month 8 to Month 4
Conduct ongoing stakeholder engagement across channels to boost awareness and maximize subscription to services, including after the planning period ends | 2025-04-01 | 2029-08-31 | bar: Month 8 to Month 12
Align on solar cooperative best practices to share with solar cooperatives once they are established | 2025-06-01 | 2025-06-30 | bar: Month 10
Conduct analyses to test market demand for community ownership of solar assets and convene stakeholders to determine whether community solar pilot will be made permanent in later years | 2025-06-01 | 2026-06-30 | bar: Month 10 to Month 10
Work with stakeholders to refine the key activities comprising the customer acquisition and management strategy for program-specific contexts | 2025-06-01 | 2025-07-31 | bar: Month 10 to Month 11
Coordinate directly with other utility and income-based assistance programs to educate, and where appropriate, auto-enroll NJ residents in community solar subscriptions | 2025-09-01 | 2029-08-31 | bar: Month 1 to Month 12
Submit Revised Workplan and Budget at end of Planning Period |  | 2025-12-31 | bar: Month 4
Project Deployment Period |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Partner with community-based organizations for feedback on engaging the populations they represent | 2025-03-01 | 2029-08-31
Partner with community-based organizations to educate residents on potential savings opportunities | 2025-03-01 | 2029-08-31
Partner with other income-qualifying programs to pre-qualify and educate potential customers | 2025-03-01 | 2029-08-31
Convene regular stakeholder meetings to gather input on SFA implementation and program outcomes | 2025-04-01 | 2029-07-30 | bar: Month 8; Month 11; Month 2; Month 5; Month 8; Month 11; Month 2; Month 5; Month 8; Month 11; Month 2; Month 5; Month 8; Month 11; Month 2; Month 5; Month 8; Month 11
Publish public maps of areas of the State that qualify for SFA funds | 2025-09-01 | 2029-08-31 | bar: Month 1; Month 1; Month 1; Month 1
Issue call for applications for Communty Solar Expansion Program | 2025-10-01 | bar: Month 2
Issue call for applications for enabling upgrades projects | 2025-10-01 | bar: Month 2
Disburse funding for all SFA programs as they are awarded | 2025-11-01 | 2029-08-31 | bar: Month 3 to Month 12
Enter into MOU with NJEDA for Residential Solar Program | 2025-12-01 | bar: Month 4
Enter into MOU with NJDOL for Workforce Development Program | 2025-12-01 | bar: Month 4
Issue call for applications for Community Solar Equity Pilot | 2026-01-01 | bar: Month 5
Conduct audits of all SFA programs | 2026-01-01 | 2029-08-31 | bar: Month 5 to Month 12
Reevaluation of NJSFA effectiveness and impact for funding reallocation | 2027-08-01 | 2027-12-31 | bar: Month 12 to Month 4
Reporting |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
MBE/WBE Reporting: EPA Form 5700-52A Annual Report Submitted (when the combined total of funds budgeted for procuring supplies, equipment, construction or services exceeds the Simplified Acquisition Threshold) |  | 10/30/2024, 10/30/2025, 10/30/2026, 10/30/2027, 10/30/2028, 10/30/2029 | bar: Month 2; Month 3; Month 2; Month 2; Month 2
Draft QMP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Draft QAPP and submit to EPA for Approval (within 90 days of the first amendment) | 2025-01-01 | 2025-03-30 | bar: Month 5 to Month 7
Submit Interim Federal Finacial Report (SF425) annually |  | [Add date specific to program]
Submit Final Federal Financial Report | 2029-08-31 | 2029-12-29 | bar: Month 12
July 1-December 31 2024 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2024-12-31 | 2025-01-30 | bar: Month 5
January 1-June 30 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-06-30 | 2025-07-30 | bar: Month 11
July 1-December 31 2025 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2025-12-31 | 2026-01-30 | bar: Month 5
January 1-June 30 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-06-30 | 2026-07-30 | bar: Month 10
July 1-December 31 2026 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2026-12-31 | 2027-01-30 | bar: Month 5
January 1-June 30 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-06-30 | 2027-07-30 | bar: Month 11
July 1-December 31 2027 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2027-12-31 | 2028-01-30 | bar: Month 5
January 1-June 30 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-06-30 | 2028-07-30 | bar: Month 11
July 1-December 31 2028 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2028-12-31 | 2029-01-30 | bar: Month 5
January 1-June 30 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-06-30 | 2029-07-30 | bar: Month 11
July 1-December 31 2029 Semi-annual performance report and semi-annual transaction-level and project-level data submitted | 2029-12-31 | 2030-01-30
Post-closeout program strategy Submitted Prior to Program Closout |  | 2029-08-30 | bar: Month 12
Final Report submitted | 2029-08-31 | 2029-12-29 | bar: Month 12
January 1-June 30 2030 Semi-annual performance report submitted | 2030-06-30 | 2030-07-30
July 1-December 31 2030 Semi-annual performance report submitted | 2030-12-31 | 2031-01-30
January 1-June 30 2031 Semi-annual performance report submitted | 2031-06-30 | 2031-07-30
July 1-December 31 2031 Semi-annual performance report submitted | 2031-12-31 | 2032-01-30
Review approved QMP annually |  | [Add date specific to program]
Review approved QAPP annually |  | [Add date specific to program]
Formulas:
Anticipated Completion Date = [Anticipated Start Date]+120