## Milestone Reporting Form Page 1
2020SREC Registration Program (SRP)
Milestone Reporting Form
For All Grid Supply Facilities and All Net Metered Facilities Greater Than 1 MW
| Initial Report Date: |  | OR | Report for Quarter Ending:
PROGRAM TERMS AND CONDITIONS
Registrants in the SREC Registration Program (SRP) must comply with all SRP terms and conditions, eligibility requirements and installation requirements, and submit all completed forms. This Milestone Reporting Form must be submitted by the Registrant as an initial report with the SRP Registration Packet and quarterly thereafter, including any extensions, if applicable, that may be granted to the initial SRP acceptance period, until the Final As-Built packet is submitted. Quarterly reports must be submitted to the SRP Processing Team at njreinfo@njcleanenergy.com within two weeks of the quarters ending March 31, June 30, September 30 and December 31.
INSTRUCTIONS FOR COMPLETING THIS FORM
The Milestone Reporting Form is required to be submitted for all Net Metered Facilities greater than 1 MW and all Grid Supply Facilities that have submitted a complete SRP Registration and been issued a SRP Acceptance letter. All Grid Supply Facilities must have received conditional approval through a board order from the New Jersey Board of Public Utilities (NJBPU).
Section B: | Please complete the chart, indicating whether each of the listed project milestones has been achieved. Where a milestone has been achieved, please insert the date it occurred in the Date Achieved column (it is not necessary to submit any supporting documentation); where a milestone has not been achieved, please insert the date that you expect it to occur in the Date Expected to Achieve column. Dates may be expressed as month and year; it is not necessary to identify a particular day. Please use the Comments section to elaborate on any of your responses.
Section C: | The Primary Contact (SREC Owner) and Premise Contact (if different from the SREC Owner) must sign the appropriate space(s).
Once this form is completed, it should be uploaded in the online portal as part of the SRP Registration Packet submission (if an initial report) or electronically to njreinfo@njcleanenergy.com (if a quarterly report).
NOTE: If the Change in Original SREC Ownership box is checked below, a copy of the most recent executed contract must be submitted to the SRP Processing Team.
SECTION A: PREMISE CONTACT AND PROJECT IDENTIFICATION
SRP Registration Number: |  |  | PJM Queue Number:
System Size (kW DC): |  | Original |  | Revised |  | (decrease only)
Name of Primary Contact(SREC Owner): |  |  |  |  | Change in Original SREC Owner
Name of Company or Organization:
Installation Address:
City, State, ZIP Code: |  | (City) |  | (State) |  | (ZIP Code)
Daytime Phone: |  |  |  | Email Address:
Name of Premise Contact (if different from SREC Owner):
Name of Company or Organization:
Address:
City, State, ZIP Code: |  | (City) |  | (State) |  | (ZIP Code)
Daytime Phone: |  |  |  | Email Address:

## Milestone Reporting Form Page 2
2020 SREC Registration Program(SRP)
Milestone Reporting Form
For All Grid Supply Facilities and All Net Metered Facilities Greater than 1 MW
SECTION B: PROJECT MILESTONES
Pursuant to the Clean Energy Act of 2018 (P.L. 2018, c. 17), the Board of Public Utilities must close the SRP to new applications upon the attainment of 5.1 percent of the kilowatt-hours sold in the State from solar electric power generators connected to the distribution system. Once that milestone is met, only projects that have commenced commercial operations prior to the market’s achievement of this milestone will be eligible for Solar Renewable Energy Certificates (SRECs). Projects that do not commence commercial operations prior to the market’s achievement of this milestone may not be eligible for SRECs. The Board is monitoring the progress of the market toward achieving this milestone and will determine when it has been achieved.
Milestone |  | Achieved (Y / N) | Date Achieved | Date Expected to Achieve
1 | Submitted interconnection application to EDC
2 | All required federal, state and local permits obtained
3 | Received interconnection application approval from EDC
4 | Mounting system installation has begun
5 | Mounting system installed
6 | Greater than 50% of solar panels installed
7 | All equipment installed, system testing complete and request sent to EDC to test and authorize operation of system
8 | EDC Authorization to Operate Approval
NOTE: If items #1-7 above have been achieved, what still remains to be completed to obtain the approval for the authorization to operate from the EDC?
SECTION C: CERTIFICATIONS
The undersigned warrants, certifies and represents that the information provided in this form is true and correct to the best of his or her knowledge.
I agree that this document and all notices and disclosures made or given relating to this document may be created, executed, delivered and retained electronically and that the electronic signatures appearing on this document and any related documents shall have the same legal effect for all purposes as a handwritten signature.
The information, statements, and documents I have provided in and with this document are true and accurate to the best of my knowledge. I am aware that if any of them are willfully false, I am subject to punishment.
Primary Contact (SREC Owner) |  | Premise Contact (if different from SREC Owner)
Signature: |  | Signature:
Print Name: |  | Print Name:
Date: |  | Date: