## Start Here
Cybersecurity Risk Assessment Template
SMEnode, version 1.0, 2026-10-13. Free to use and adapt. Not legal advice.
How to use it | Work left to right through the numbered tabs. Each tab is one step of the 5-step method in the SMEnode guide at smenode.com/blog/cybersecurity-risk-assessment.
Step 1 - 1 Assets | List what you're protecting: data, systems, services, suppliers. Give each a business value from 1 to 5 and an owner.
Step 2 - 2 Threats | For each important asset, name who or what could hurt it and the weakness that would let them.
Step 3 - 3 Risk Register | Write one risk per row. Pick Likelihood and Impact (1-5) from the scales below. Score and rating calculate themselves. The Matrix tab updates on its own.
Step 4 - 4 Treatment Plan | For every High or Critical risk, choose Mitigate, Transfer, Avoid or Accept. Give each action an owner and a due date. Accepted risks need a named person and a date.
Step 5 - 5 Summary + Review Log | The Summary tab counts risks by rating for your one-page report. Log every review in the Review Log, and re-run the assessment at least yearly or after a major change.
Canadian Obligations tab | A short checklist of Canadian rules that expect this work (PIPEDA, Quebec Law 25, OSFI B-13, CPCSC, Bill C-8) plus the Cyber Centre's 13 baseline controls. Confirm what applies to you with counsel.
Orange rows | Rows shaded orange and marked EXAMPLE show how a filled row looks. Delete them before you start.
Rating bands | Score = Likelihood x Impact (1 to 25). Low 1-4, Medium 5-9, High 10-16, Critical 20-25. Change the bands in the cells below if your board prefers others.
Band thresholds (editable)
Medium starts at score | 5
High starts at score | 10
Critical starts at score | 20
Likelihood scale
1 Rare | Not expected in the next 5 years
2 Unlikely | Could happen once in 2 to 5 years
3 Possible | About once a year, here or at peers our size
4 Likely | Several times a year
5 Almost certain | Monthly, or already happening (phishing attempts usually sit here)
Impact scale
1 Minimal | No personal information exposed, under 1 hour of disruption, no customer notices
2 Minor | Internal data only, part of a day lost, fixed by staff
3 Moderate | Some personal information or a key system down for about a day. Check whether the breach is reportable
4 Major | Breach with a real risk of significant harm (report to the OPC and notify people), multi-day outage, contract penalties
5 Severe | Large breach or weeks of disruption, regulator action, loss of major customers or the business at risk
Your $ bands | Add your own dollar thresholds here so every rater uses the same numbers:
Sources
NIST SP 800-30 Rev. 1, Guide for Conducting Risk Assessments (2012): csrc.nist.gov/pubs/sp/800/30/r1/final
Canadian Centre for Cyber Security, ITSP.10.033 RA controls (2026-03-31): cyber.gc.ca
Harmonized TRA Methodology (TRA-1), CSE and RCMP (2007): cyber.gc.ca/en/guidance/harmonized-tra-methodology-tra-1
Baseline Cyber Security Controls for Small and Medium Organizations v1.2: cyber.gc.ca

## 1 Assets
Step 1: What are you protecting?
One row per asset. Value 1-5 = how much the business would suffer if it were lost, leaked or down.
Asset ID | Asset | Type | Owner | Holds personal info? | Where it lives | Business value (1-5) | Notes
A-01 | EXAMPLE - Microsoft 365 mailboxes and OneDrive | System | IT manager | Yes | Cloud (Canada region) | 5 | Every staff account, client email, invoices
A-02 | EXAMPLE - Accounting system and bank portal | System | Controller | Yes | SaaS | 5 | Wire transfers approved here
A-03 | EXAMPLE - Managed IT provider remote access | Supplier | Ops lead | No | Vendor | 4 | Admin rights to every laptop

## 2 Threats
Step 2: What could go wrong?
Who or what could hurt an asset, and which weakness would let them. Use the vulnerability prompts in column G if you're stuck.
Threat ID | Threat | Source | Vulnerability (the weakness) | Asset IDs affected | Controls already in place | Vulnerability prompts
T-01 | EXAMPLE - Invoice or payment-redirect fraud by email | Criminal | No call-back check on changed bank details | A-01, A-02 | Spam filter | Is MFA on for every account, including admins and suppliers?
T-02 | EXAMPLE - Ransomware through a stolen remote login | Criminal | MFA not enforced on the vendor's remote tool | A-03 | Antivirus on laptops | Are operating systems and apps patched automatically?
T-03 | EXAMPLE - Supplier breach exposes our client data | Supplier | No security terms in the contract | A-03 | None | Are backups offline or immutable, and was a restore tested this year?
Do former staff and old vendor accounts still work?
Is anything exposed to the internet that shouldn't be (RDP, old VPN, admin pages)?
Would staff spot a fake invoice or a fake help desk call?
Do contracts with IT and cloud suppliers say who handles a breach?
Is personal information stored where you don't expect (shared drives, inboxes)?
Are laptops and phones encrypted?
Is there a written incident response plan with phone numbers?

## 3 Risk Register
Step 3: How likely, and how bad?
Pick Likelihood and Impact from the scales on Start Here. Score, rating and residual score calculate themselves.
Risk ID | Risk statement (If... then...) | Asset ID | Threat ID | Existing controls | Likelihood (1-5) | Impact (1-5) | Score | Rating | Treatment | Owner | Due date | Target likelihood | Target impact | Residual score | Status
R-01 | EXAMPLE - If a fraudster spoofs a supplier email, then we could wire a payment to the wrong account | A-02 | T-01 | Spam filter | 4 | 4 |  |  | Mitigate | Controller | 2026-11-15 | 2 | 4 |  | Open
R-02 | EXAMPLE - If the vendor's remote login is stolen, then ransomware could lock every laptop | A-03 | T-02 | Antivirus | 3 | 5 |  |  | Mitigate | IT manager | 2026-11-30 | 2 | 3 |  | In progress
R-03 | EXAMPLE - If our IT supplier is breached, then client personal information could leak | A-03 | T-03 | None | 2 | 4 |  |  | Transfer | Ops lead | 2027-01-31 | 2 | 3 |  | Open

## Matrix
Cyber risk assessment matrix (5 x 5)
Each cell counts the risks in the register at that likelihood and impact. It updates on its own.
Impact
|  | 1 Minimal | 2 Minor | 3 Moderate | 4 Major | 5 Severe
Likelihood | 5 Almost certain
4 Likely
3 Possible
2 Unlikely
1 Rare
Cell colours use the default bands (Low 1-4, Medium 5-9, High 10-16, Critical 20-25).

## 4 Treatment Plan
Step 4: What will you do about each risk?
One row per action. An accepted risk still gets a row: who accepted it, when, and when you'll look again.
Risk ID | Action | Control it maps to | Owner | Estimated cost (CAD) | Start | Due | Status | Accepted by (name, date) | Review again on
R-01 | EXAMPLE - Call-back on a known number before any change to supplier bank details; two approvers over a set amount | Cyber Centre baseline 3.6 (awareness) | Controller |  | 2026-10-20 | 2026-11-15 | Open
R-02 | EXAMPLE - Enforce MFA on the vendor remote tool; restrict it to named technicians | Baseline 3.5 (authentication), 3.10 (outsourced IT) | IT manager |  | 2026-10-20 | 2026-11-30 | In progress
R-03 | EXAMPLE - Add breach-notice and security terms at contract renewal; confirm cyber insurance covers supplier incidents | Baseline 3.10; OPC third-party draft guidance | Ops lead |  | 2026-11-01 | 2027-01-31 | Open

## 5 Summary
Step 5: One-page summary
Counts update from the register. Paste this tab into your board or insurer report.
Risks in the register
Critical
High
Medium
Low
Risks accepted
Risks with no owner
High or Critical still open
Highest score today
Highest residual score after treatment
Treatment actions logged
Treatment actions done
Assessment date:
Scope (what was in and out):
Method: SMEnode 5-step, 5x5 matrix, NIST SP 800-30 aligned
Prepared by:
Approved by (name, date):
Next review due:

## Canadian Obligations
Which Canadian rules want this work?
A starting checklist, not legal advice. Confirm what applies to your organisation with counsel. Checked 2026-10-13.
Rule | Applies to | What it expects from your risk work | Applies to us? | Evidence / where it lives
PIPEDA (federal) | Private-sector organisations handling personal information in commercial activity (outside provinces with their own law) | Safeguards that match the sensitivity of the data. Report breaches with a real risk of significant harm to the OPC and notify people. Keep a record of every breach of security safeguards for 2 years.
Quebec Law 25 (Private Sector Act) | Businesses handling personal information of people in Quebec | Keep a register of every confidentiality incident and give it to the CAI on request. Notify the CAI and people when there's a risk of serious injury. Privacy impact assessment for information-system projects involving personal information.
OSFI Guideline B-13 | Federally regulated financial institutions | Technology and cyber risk management, in force since 2024-01-01. Apply it in proportion to your size and risk profile.
CPCSC Level 1 | Suppliers bidding on select defence contracts | Self-attest to Level 1 criteria. Required at contract award in select contracts from summer 2026.
Bill C-8 / Critical Cyber Systems Protection Act | Designated operators in federally regulated critical sectors (telecom, finance, energy, transport) | Royal Assent 2026-06-15. The CCSPA part isn't in force yet and no operators are designated. Watch the Canada Gazette.
OPC draft guidance: third-party service providers | Any PIPEDA organisation using processors or IT suppliers | Draft of 2026-09-10, open for comment until 2026-12-04. Assess a provider's privacy and security before you sign, then monitor.
Contracts and cyber insurance | Everyone | Read your insurer's questionnaire and your largest customers' security clauses. They often ask for a dated risk assessment.
Cyber Centre baseline controls (organisations under 500 staff)
# | Control | Status | Notes
3.1 | Develop an incident response plan
3.2 | Automatically patch operating systems and applications
3.3 | Enable security software
3.4 | Securely configure devices
3.5 | Use strong user authentication
3.6 | Provide employee awareness training
3.7 | Back up and encrypt data
3.8 | Secure mobility
3.9 | Establish basic perimeter defences
3.10 | Secure cloud and outsourced IT services
3.11 | Secure websites
3.12 | Access control and authorization
3.13 | Secure portable media

## Review Log
Review log
Re-run the assessment at least once a year, and after any trigger: a new system, a merger, a breach, a new regulation or a big supplier change.
Date | Trigger | Reviewed by | What changed | Next review