## How to use
IT Roadmap Template - 3-year plan for Canadian businesses
By SMEnode (smenode.com). Free to use and adapt. Version 2026-09-30.
1. Write 3-5 business goals on the 'Goals' tab, in the board's own words.
2. Check the 'Canadian deadlines' tab. Any date that applies to you becomes a roadmap line.
3. Add every initiative to 'Roadmap register'. Every line needs a cost, an owner, a quarter and the risk if skipped.
4. Blue cells are inputs. Replace the two example rows with your own. Costs are in CAD; fill them with real quotes.
5. Pick a Decision for each line: Fund, Defer or Drop. Totals on 'Board summary' update automatically.
6. Put 2-3 rejected ideas on 'Not doing this year'. A plan that approves everything hasn't decided anything.
7. Year 1 by quarter, years 2-3 by half-year. Review the whole register every quarter.
Guide: https://smenode.com/blog/it-roadmap-for-business
Help building it: https://smenode.com/services/it-consulting/it-strategy
Tax note: the Productivity Mega Deduction (announced 2026-09-15) is draft legislation. Ask your accountant before relying on it.

## Goals
Goal ID | Business goal (board's words) | Target date | Measure of success | Executive owner
G1 | Open a second warehouse in 2027 | 2027-06 | Warehouse live with full IT on day one | COO
G2 | Pass the 2027 cyber insurance renewal without a premium jump | 2027-03 | Renewal accepted at current premium | CFO

## Roadmap register
ID | Initiative | Goal ID | Lane (Run/Protect/Grow) | Driver or deadline | Owner (a person) | Start quarter | End quarter | One-time cost (CAD) | Annual run cost (CAD) | Internal staff days | Depends on (ID) | Risk if skipped | Quebec PIA needed? (Y/N) | Decision (Fund/Defer/Drop) | Status | Notes
R-01 | Replace 40 Windows 10 PCs with Windows 11 devices | G1 | Run | Windows 10 ESU year 1 ends 2026-10-13 | Ops manager | Q4 2026 | Q1 2027 |  |  | 15 |  | Paying ESU each year (price doubles) or running unpatched PCs | N | Fund | Not started | Example row - replace
P-03 | MFA on every admin account | G2 | Protect | Insurance renewal 2027-03 | IT lead | Q1 2027 | Q1 2027 |  |  | 8 | R-05 | Higher premium or refused cover | N | Fund | Not started | Example row - replace

## Board summary
Board summary (calculated from 'Roadmap register')
Lane | Lines funded | One-time cost funded (CAD) | Annual run cost funded (CAD) | Lines deferred | One-time cost deferred (CAD) | Lines dropped
Run
Protect
Grow
Total
One-page view: list funded lines by quarter below (Run / Protect / Grow).
Period | Run | Protect | Grow
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
2028 H1
2028 H2
2029 H1
2029 H2

## Canadian deadlines
Date | What happens | Who it hits | Suggested roadmap line | Source (checked 2026-09-30)
2026-10-13 | Windows 10 commercial ESU year 1 ends. Year 2 US$122/device, year 3 US$244. ESU is cumulative. | Anyone still running Windows 10 | Replace or upgrade to Windows 11 | https://learn.microsoft.com/en-us/windows/whats-new/extended-security-updates
2026-06-15 (phased) | Bill C-8 Royal Assent. Critical Cyber Systems Protection Act comes into force in phases. | Finance, telecom, energy, transport operators; likely their suppliers | Security programme, incident reporting, supply-chain controls | https://www.canada.ca/en/public-safety-canada/news/2026/06/government-of-canada-strengthens-cyber-security-and-critical-infrastructure-with-royal-assent-of-bill-c8.html
In force since 2023-09-22 | Quebec private-sector Act s.3.3: privacy impact assessment required for any project to acquire, develop or overhaul an information system handling personal information. | Anyone with Quebec staff or customers | PIA step inside every system project | https://www.legisquebec.gouv.qc.ca/en/document/cs/P-39.1
2026-09-15 (proposed) | Productivity Mega Deduction: immediate expensing for most depreciable property acquired on or after this date. Draft legislation. | Taxable businesses | Buy vs subscribe decisions; confirm with your accountant | https://www.canada.ca/en/department-finance/news/2026/09/government-of-canada-introduces-new-productivity-mega-deduction-to-boost-canadas-advantage-as-the-most-competitive-g7-country-for-new-business-inve.html
2027-10-11 | vSphere / ESXi 8 end of general support (technical guidance to 2029-10-11). | Anyone running VMware on-premises | Upgrade, renew or migrate; decide by mid-2027 | https://endoflife.date/esxi
Your date | Cyber insurance renewal | You | Controls the insurer asks for (MFA, backups, EDR)
Your date | Major contract and licence renewals (Microsoft 365, firewall, ERP) | You | Renew, renegotiate or replace

## Not doing this year
Idea considered | Why not this year | Revisit when | Who asked for it
Replace practice management software | Stable, vendor supports it to 2029 | 2028 H1 | Partners
AI chatbot for clients | Data isn't clean enough yet | 2029 H1 | Marketing