| Project | Details | Responsibility (Staff, Board, Committee, Consultant, other) |  |  |  |  | Notes | Dates |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Staff | Board | Committees | Consultant | Other |  | Start | End |
| 2023 |  |  |  |  |  |  |  |  |  |
| Fundraising | Review all relevant and significant funding opportunities | ED makes decisions | Board recommends | All committees recommend |  |  |  | 01-Jan-23 | 31-Dec-28 |
|  | Equine health and wellness policy | Project and Event Coordinator | Board | Industry Committee |  |  |  | 01-Oct-23 | 31-Dec-24 |
| Evaluation | Organizational evaluation | Supported by ED | Board | Governance / Board Development Committee |  |  | every other year | 01-Oct-24 | 31-Dec-25 |
| Medication education |  | Project and Event Coordinator & Communication and Engagement Manager |  | Industry Committee |  |  |  | 01-Oct-23 | 31-Mar-24 |
| 2024 |  |  |  |  |  |  |  |  |  |
| Trail Rider program | Trail Rider Program: Information to committee for review | Membership Manager & Project and Event Coordinator |  | Recreation Committee |  |  |  | 01-Jan-24 | 30-Mar-24 |
|  | Trail Rider Program: Committee review complete |  |  | Recreation Committee |  |  |  | 01-Apr-24 | 30-Jun-24 |
| Board training and transition document etc. |  | Supported by ED | Board | Governance / Board Development Committee |  |  |  | 01-Jul-24 | 30-Jun-25 |
| Review Board and Committee complement |  | Supported by ED |  | Governance / Board Development Committee |  |  |  | 01-Jan-24 | 30-Sep-24 |
| Educate about health and wellness of equine (ongoing after) |  | Project and Event Coordinator & Communication and Engagement Manager |  | Industry Committee | Contractor / AB Bits |  |  | 01-Jul-24 | 31-Dec-24 |
| 2025 |  |  |  |  |  |  |  |  |  |
| Trail Rider Program: Promote |  | Communication and Engagement Manager |  | Recreation Committee |  |  |  | 01-Jan-25 | 30-Mar-25 |
| 2028 |  |  |  |  |  |  |  |  |  |
| Trail App |  | Membership Manager & Project and Event Coordinator |  | Recreation Committee |  |  |  | 01-Jan-28 | 31-Dec-28 |