## 1. Introduction
Action Register Template
This is a simple and effective template for tracking action items for boards or sub-committees.
Using this tool:
Tab 1: | This tab introduces the tool and how to get the most out of it.
Tab 2: | This is an example of the Action Register in practice. It explains the rationale for including different details.
Tab 3: | This is a blank template for you to use to develop your own action register.
Getting the most out of your action register:
- This tool can be customised to suit your needs.
- Consider what action item numbering format suits you best. We suggest identifying the board or sub-committee name (with initials), the month and year the action was first raised (##-## format), and a unique number for that item (-01, for the first item raised in that meeting, and so on). This is preferable from just numbering as eventually the numbers will get very high! It also helps ensure you're prioritising actions that have been on the 'to do' list for a long time. It also builds alignment in action reporting across different sub-committees.
- Make sure you include updates to your action descriptions in subsequent Board meetings, until the item is completed. This will assist in tracking progress.
- You can sort items by colour or by due date, so priority items are listed first.
- By keeping closed items at the bottom (or in a different tab if you prefer), you can still keep an active, easy access record of what has been achieved.
- There's no 'one size fits all' approach to the perfect action register! It needs to work for you and your board. But this is a great starting point to work out what works best for you!
Need help with your action register or other board administration issues?
Book a free 30-minute discussion and advisory consultation with Red Dearnley (they/them), Influence Global’s Managing Director and Principal Consultant. Go to https://calendly.com/influenceglobal or email contact@influenceglobal.net.
Action Register Template © 2022 by Influence Global is licensed under CC BY-NC-ND 4.0. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc-nd/4.0/

## 2. EXAMPLE_Action Register
Action Item No. | Date of Meeting | Agenda Item No. (when action first tabled) | Topic | Action (and context, as relevant) | Responsible | Due date | Progress | Status
EXPLAINER
Unique identifying number. You can pick any format that suits you, but we recommend: LetterMonthYear-Number (e.g. B1223-01) Letter = Signify which Board or sub-committee it relates to. e.g. B = Board. Month/Year = Shows how long the item has been open on the register. e.g. 0923 = September 2023. Number = Unique number of action item raised at that meeting. e.g -01 = First item raised. | ##-Mon-## | # | Title or summary of item | Precise wording of the required action and any relevant context to explain the action. If there are updates at subsequent meetings, these should be included in this section, so it is clear what incremental progrees or action has been taken. | Name, Role or initials of person who is responsible. | Agreed delivery date. | Drop down to demonstrate progress. Actions should be marked as Not Yet Started on submission into the register. | The status of the action item is either Open, Overdue or Closed. Even if completed between meetings, items should not be marked as closed until they are formally presented at the next meeting.
EXAMPLES
B1123-01 | 2023-11-01 | 5 | Skills matrix | Directors to review Skills Matrix and make any recommended updates to their skills portfolio. | All | 2023-12-01 | Not yet started | Open
B0923-03 | 2023-09-01 | 4.3 | Constitutional review | Seek legal advice on proposed amendment to Clause 42, to align with the Modern Rules. | CoSec | 2024-09-04 | In progress | Open
B0823-02 | 2023-08-01 | 3.1 | Strategic Plan KPIs | Management to reconsider appropriateness of KPI baselines and monitor trends - especially for items that are continually being exceeded. Bring recommendations to Board ahead of Strategic Plan review session. | CEO | 2024-02-01 | In progress | Open
0723-01 | 2023-07-01 | 2.2 | Risk register | Bring update report on mitigation strategies that are being implemented at operational level to address high-risk items. August 2023 update: CEO noted that the paper was in development. Will present at the next meeting. September 2023 update: CEO noted that the process of the review raised additional concerns that required immediate action (as presented in Agenda Item 4.5 of the September meeting). CEO has met with CoSec to mitigate immediate risk. The report will be tabled at the next meeting. | CEO | 2023-09-01 | In progress | Overdue
B0923-01 | 2023-09-01 | 4.2 | Delegations of Authority | Update financial delegations to align with revised risk appetite thresholds for planned/budgeted items. Present back to Board for noting at next meeting. | CoSec | 2023-10-01 | Complete | Closed
B0923-02 | 2023-09-01 | 3.2 | Annual Report | Proceed with development of Annual Report in current style and circulate final draft for approval prior to AGM distribution deadlines. | CEO | 2023-11-01 | Complete | Closed
B0823-02 | 2023-08-01 | 5 | Acting CEO arrangements | CEO to prepare recommendations for Acting CEO arrangements whilst on leave and discuss management and supervision requirements with the Chair. Present plans ahead of CEO leave. September 23 update: Chair and CEO have met and discussed arrangements for COO to be appointed Acting CEO. Planned discussions with COO about support needs during this period in the next few weeks. Handover meetings with Chair also scheduled. Will provide update at next Board meeting once plans are confirmed. | CEO/Chair | 2023-10-01 | Complete | Closed

## 3. TEMPLATE_Action Register
Action Item No. | Date of Meeting | Agenda Item No. (when action first tabled) | Topic | Action (and context, as relevant) | Responsible | Due date | Progress | Status

## Data validation
Status | Closed/Open
Not yet started | Open
In progress | Overdue
Complete | Closed
Cancelled