## Slide 1: Scaling strategy and action plan
11

## Slide 2: Strategic action plan
The tool helps you structure:
What needs to be strengthened (solution, uptake, enabling structures).
What actions are required to get there.
How scaling will happen in practice (pathways, roles, resources, engagement strategies, timelines, what to prepare).
It is both a planning tool for readiness and a launch plan for scaling.
What this tool is and why it matters
The scaling strategy and action plan is a practical tool that helps you translate your scaling ambition and assessment findings into a clear strategy and action plan. It builds directly on the scaling ambition and direction you defined earlier: what you want to scale, for whom, where, over what timeframe, and the key uncertainties you need to address.
Where the scaling ambition provides your initial strategic direction, this tool helps you define what must happen to make the ambition realistic, now that the pilot is complete and you have stronger evidence, results and insights.
This tool helps you identify the most important gaps, priorities, roles, resources, partnerships, risks, and next steps needed to move towards scaled impact. It brings these together in a practical and structured action plan that outlines your strategic direction, priorities, and concrete actions for scaling.

## Slide 3
When to use this tool
Early in Transition to Scale (Phase 1–2)
Purpose of this phase: helps you define a strategic plan for what needs to be prepared to become ready for scaling
Use the tool after your initial assessment to:
Translate identified gaps into strategic priorities
Define what needs to be built, tested, or strengthened
Create a directional plan for becoming scaling-ready
End of Transition to Scale (Phase 3)
Purpose of this phase: a refined, concrete action plan for moving into and executing scaling.
Use the tool again to:
Refine and finalise your scaling strategy and action plan
Confirm:
  Operational readiness.
  Roles and responsibilities.
  Resources and partnerships.
  Define concrete next steps for implementation at scale.
At this stage, the plan is:
More strategic and exploratory.
Focused on preparing for scale.
At this stage, the plan should be:
Clear, detailed, and actionable.
Aligned and agreed with key stakeholders.
Ready to guide the move into Stage 3: Scaling impact.

## Slide 4: How to use the tool
1
2
3
4
Start from your gaps and opportunities
Use the gaps identified in your scaling assessment:
What are the weakest or most critical elements?
What is holding back scaling today?
What strengths and opportunities must we maintain?
Define strategic direction and goals
Revisit your scaling ambition and define:
Your overall scaling goal (what success looks like).
What do you want to achieve by scaling?
What is your scaling pathway? How will you scale?
Time-based objectives: 2–3 years, 1 year and 3–6 months.
Success factors and potential gaps and uncertainties.
Translate into action
For each key gap:
What could we do to address it?
What actions or activities are needed?
What are realistic first steps?
How can we build on the strengths and opportunities to address them?
Structure actions across time horizons:
Short-term (3–6 months): quick wins, foundational steps.
Mid-term (1 year): strengthening and testing.
Long-term (2–3 years): scaling and institutionalisation.
Define implementation
For each action, clarify:
Timeline.
Roles and responsibilities.
Who else needs to be involved.
Keep it simple and practical: It’s just a template – adjust it as needed. Think of this as a working draft, not a final plan. Don’t be too comprehensive or detailed at the earlier phases. The goal is to:
Have a clear starting point and direction
Capture key goals, roles, activities, and practical steps
Cover both short- and long-term perspectives

## Slide 5: Core components of a strong scaling strategy
Mandatory components (must include)
These elements are consistently present in real scaling plans and are essential for long-term sustainability and implementation. Your scaling strategy and plan should include:
Scaling routes / pathways: How will you scale impact? For example, adoption, diffusion/improvement, partnerships, integration, replication, and what do you want to achieve?
Value creation model(s): How will the solution create and sustain value over time? Examples: business models, livelihood models, circular or ecosystem-based models.
Risk assessment and mitigation: What could prevent scaling?
Consider: regulatory barriers, adoption challenges, operational risks, ethical risks and humanitarian value.
Roles and partnerships: Who will play what role in scaling? How will partners contribute?
Essential elements for sustainable scale
At a minimum, your strategy should address:
Strategy – clear direction and priorities.
Financial viability – how scaling will be sustained.
Organisational setup – capacity and structure to deliver.
Key stakeholders – who adopts, enables, and supports.
Success factors and potential gaps/uncertainties.
+ Additional components (if relevant).
Depending on your solution, you may also include:
Communication and uptake strategy.
Support, training, and service systems.
Production and delivery mechanisms.
Legal and regulatory considerations.
Social and environmental responsibility.
Continuous improvement and learning.
These strengthen your ability to scale effectively but should be prioritised based on relevance.
What do we know, and what are we still assuming?
Before locking in any strategic choice, ask: what data do we actually have to back this, and what are we still assuming? Name the gaps. If any are essential, on impact, demand, costs or what partners and funders will require, build in a step to get that evidence before you move forward.

## Slide 6
What is our overall scaling goal? | Scale access to safe neonatal care in humanitarian and low-resource settings by making NeoSafe available in 500 health facilities across 10 countries by 2030, contributing to measurably reduced neonatal mortality. |  |  | 
Scaling pathway(s) | Primary: Government adoption through national health ministries. Secondary: UN agency procurement (UNICEF Supply Division). Supporting: NGO health programmes as early adopters and proof-of-concept channels. |  |  | 
What do we want to achieve? Objectives: | In 3–6 months…Finalise scaled manufacturing agreement. Complete regulatory registration in 3 pilot countries. Secure first procurement agreement with a UN agency. | In 1 year…Deployed in 50 facilities across 3 countries. 200 health workers trained. Cost-effectiveness data documented and ready for government and funder engagement. | In 2–3 years…Integrated into national health protocols in 5 countries. 200 facilities operational. 2 governments procuring through national health budgets. | In 4+ years…500 facilities, 10 countries. Solution self-sustaining through commercial and government procurement. Private partner manufacturing at scale without grant dependency.
Key uncertainties or gaps | Cost-per-unit at volume not yet confirmed. Regulatory pathways vary by country. Government procurement timelines unpredictable. Extent of local adaptation for different climates unclear. Evidence threshold required by institutional funders unknown. |  |  | 
Success factors and opportunities | Private partner has manufacturing capacity and export experience. Existing NGO and UN health networks in target countries. Strong pilot evidence from 3 sites. UNICEF Supply Division has expressed interest in procurement. |  |  | 
Objective / Gap | Actions & Activities | Timeline | Implementation (first steps) | Roles/ responsibilities & Partners & resources needed
Cost viability and manufacturing at scale not confirmed | Conduct production cost analysis at volume; negotiate pricing with manufacturer; explore local assembly options in target regions | 3–6 months | Private partner leads cost modelling; NGO/UN convenes supplier meeting; apply for bridge funding | Private partner (lead); NGO procurement team; Innovation Norway transition funding
Regulatory registration needed in priority countries before government adoption is possible | Map regulatory requirements in 5 priority countries; initiate WHO prequalification; engage local regulatory consultants per country | 6–12 months | WHO partner leads prequalification; assign country focal points; budget allocated for registration costs | WHO (prequalification lead); private partner (technical documentation); national Ministries of Health
Scaling model components Scaling pathways Value creation model(s) Financial model Organisational setup Key stakeholders and partnerships | Pathways: Government adoption (primary); UN/NGO procurement (bridge); local assembly franchise (long-term) Value creation: Improved neonatal outcomes; cost savings versus existing solutions; commercial value through growing humanitarian market Financial model: Grant-funded in transition; shifting to government + UN procurement; private partner revenues at scale Org setup: Joint steering committee (NGO + private partner); country implementation teams; training and support function Key stakeholders: Ministries of Health; UNICEF Supply Division; WHO; national NGO health partners; private investors for manufacturing scale-up |  |  | 
Risks and mitigation Key risks and mitigation strategies | Government procurement timelines too slow → maintain NGO/UN channel as parallel pathway Cost-per-unit too high for government budgets → subsidised transition pricing; explore cross-subsidy from commercial markets Local adaptation underestimated → modular design with adaptation protocol; test in 3 diverse contexts before full rollout |  |  | 
Indicators of progress How will we measure that we are on track? | Facilities with NeoSafe deployed (target: 50 in year 1) Cost-per-unit at volume confirmed Procurement agreements signed (government + UN) Health worker satisfaction and usage rates (quarterly) |  |  | 
Scaling direction for the frugal incubator “NeoSafe”
EXAMPLE

## Slide 7
What is our overall scaling goal? |  |  |  | 
Scaling pathway(s) |  |  |  | 
What do we want to achieve? Objectives: | In 3–6 months… | In 1 year… | In 2–3 years… | In 4+ years
Key uncertainties or gaps |  |  |  | 
Success factors and opportunities |  |  |  | 
Objective / Gap | Actions & Activities | Timeline | Implementation (first steps) | Roles/ responsibilities & Partners & resources needed
Scaling model components Scaling pathways Value creation model(s) Financial model Organisational setup Key stakeholders and partnerships |  |  |  | 
Risks and mitigation Key risks and mitigation strategies |  |  |  | 
Indicators of progress How will we measure that we are on track? |  |  |  | 
Scaling action plan
Scaling direction