## Slide 1: Adoption journey mapping
13
Engagement strategy – from awareness to sustained use

## Slide 2: Adoption journey mapping
What this tool is and why it matters
This tool helps you design how adopters, decision-makers, and partners move from initial awareness of your solution to actual implementation and sustained use at scale.
In Stage 3, scaling is no longer about proving the solution, it is about ensuring the right actors understand it, trust it, choose it, and successfully use it over time. Many solutions fail at this stage not because they lack impact, but because the pathway from awareness to adoption is unclear, too complex, or not actively supported based on the realities of the adopters or implementers.
This tool helps you map that pathway by identifying:
What needs to happen in each phase (build awareness → secure uptake → implementation → sustain use and improve)?
What activities, channels, and materials are needed to engage adopters?
What support is required to reduce risk, build trust, and enable successful use?
In short, it helps you move from “people know about our solution” to “people choose it, implement it, and continue using it at scale.”

## Slide 3
Expected outcomes
By using this tool, you will:
Map how adopters move through the 4 scaling phases.
Identify key activities and channels in each phase.
Define your “adoption kit” (materials needed to persuade and support).
Identify gaps in engagement, trust, or support.
Define concrete actions to increase adoption and sustained use.
When to use this tool
At the start of Stage 3, operationalise your scaling strategy.
When entering new contexts or working with new adopters.
When uptake is slower than expected.
To refine communication, engagement, and support strategies.

## Slide 4: Adoption & user channels
In humanitarian innovation, what are called “customer channels” in business are the ways you reach, engage, and support the people and organisations that decide to adopt, fund, implement or use your solution. These may include, for example: Adopters (e.g. NGOs, governments, agencies), decision-makers (e.g. programme managers, donors), partners (e.g. implementing organisations) and end-users (communities, frontline staff).
What are “adoption and user channels” in a humanitarian context?
Scaling requires more than a strong solution. It requires reaching the right actors, building their trust and understanding, and supporting decision-making and implementation. Channels define how people move from building awareness → secure uptake → implementation → sustain use and improve. Think of channels as the ways you engage people throughout this journey:
Awareness: How do people hear about your solution (e.g. networks, events, partners, referrals)? How do you build understanding and trust? How do they learn about, evaluate and believe in the value your solution could create for them (e.g. case studies, pilots, peer validation)?
Decision & uptake: How do they decide to adopt or fund your solution (e.g. meetings, proposals, demonstrations)?
Implementation & sustained use: How do you support them to use the solution successfully (e.g. training, onboarding, support systems)?
Why channels matter for scaling
Types of channels:
Direct → you engage directly (meetings, demos, trainings).
Partner-driven → others help you reach adopters or users (NGOs, agencies).
Network-based → trust spreads through communities and peers.

## Slide 5: How to use the tool
1
2
Select one key adopter persona
Choose one specific decision-maker or adopter persona (not a broad segment). If you have not already created them, do this before moving on to Step 2.
Ask:
Who is most likely to adopt first?
Who influences others to adopt?
Example: “Country-level WASH manager in an INGO in Somalia.”
Map their journey across the 4 phases
For your key adopter or user decision maker persona – work through each phase (Phase 7: Build awareness → Phase 8: Secure uptake → Phase 9: Implementation → Phase 10: Sustain use and improve) and define:
Adopter needs → What do they need to move forward?
Channels & activities → How do we reach and engage them?
Materials (adoption kit) → What do we show or provide?
Test actions → What small steps can we take now to test this?

## Slide 6: Stage 3 Scaling impact
Stage 3
Sustain & improve
Implement
Secure
uptake
Build awareness
Goal: Scaled
impact
How does your adopter find out you exist?
How do you raise awareness about your solution?
Goal: Get attention and interest.
How do adopters understand and compare what you offer? Hence, evaluate your value proposition.
How do you persuade them to adopt and use it?
Goal: Build trust and get a decision to adopt.
How do adopters successfully put your solution into practice in their context?
What do they need to integrate, use, and manage it in their day-to-day work?
Goal: Ensure smooth implementation and reduce barriers to use.
How do adopters continue using the solution over time, and what keeps it relevant and valuable?
How do you support learning, adaptation, and ongoing engagement?
Goal: Ensure continued use, ownership, and improvement over time.
4 Phases
Phase 7
Phase 8
Phase 9
Phase 10

## Slide 7: Selected early adopter or user persona
Select 1 early adopter customer profile to start with
Step 1
(not broad segments)
Out of our adopter or user segments who are our most likely early adopters?
People who could also influence others to buy/ use/ adopt our solution?
Who do we think will care most about our solution first?
Write here
Write here
Write here

## Slide 8: Build awareness
1 Adopter needs | 2 Channels & activities we could explore to reach them | 3 Materials (adoption kit) we could prepare | 4 Test actions we will start with Example: Share 1 post in a relevant network / Example 2: Present at 1 meeting
What would make them notice and care? What problem do they recognise? | Where do they spend time? How can we reach them? (e.g. networks, partners, events) | Simple explanation (1-pager, short pitch) Clear problem + value | Assign: Responsible person Timeline (e.g. within 2 weeks) Measure: Did we get responses, interest, follow-ups?
How does your adopter find out you exist?
How do you raise awareness about your solution?
Step 2
Goal: Get attention and interest.
Write here
Write here
Write here
Write here

## Slide 9: Secure uptake
How do adopters understand and compare what you offer? Hence, evaluate your value proposition.
How do you persuade them to adopt and use it?
Step 3
Goal: Build trust and get a decision to adopt.
1 Adopter needs | 2 Channels & activities we could explore to reach them | 3 Materials (adoption kit) we could prepare | 4 Test actions we will start with Example: Meet 3 potential adopters / Example 2: Run 1 demo session
What do they need to feel confident? What risks or doubts do they have? | Direct meetings, demos, workshops Partner introductions | Case studies Cost-benefit overview Pilot/demo results | Assign: Responsible person Timeline (e.g. within 1 month) Measure: Did they express interest? Did they request next steps or pilot?
Write here
Write here
Write here
Write here

## Slide 10: Implementation
How do adopters successfully put your solution into practice in their context?
What do they need to integrate, use, and manage it in their day-to-day work?
Step 4
Goal: Ensure smooth implementation and reduce barriers to use.
1 Adopter needs | 2 Channels & activities we could explore to reach them | 3 Materials (adoption kit) we could prepare | 4 Test actions we will start with Example: Pilot with 1 adopter Example 2: Run 1 training session
What do they need to implement successfully? What could go wrong? | Training sessions Onboarding support Regular check-ins | Implementation guide? Training materials? Support contacts? | Assign: Responsible person Timeline (e.g. within 1 month) Measure: Are they able to use the solution? Where do they struggle?
Write here
Write here
Write here
Write here

## Slide 11: Sustain & improve
How do adopters continue using the solution over time, and what keeps it relevant and valuable?
How do you support learning, adaptation, and ongoing engagement?
Step 5
Goal: Ensure continued use, ownership, and improvement over time.
1 Adopter needs | 2 Channels & activities we could explore to reach them | 3 Materials (adoption kit) we could prepare | 4 Test actions we will start with Example: Conduct 5 user feedback interviews / Example 2: Create 1 user group or forum
What keeps them using the solution? What would make them stop? | Follow-up meetings User communities Feedback loops | Feedback tools Updates / improvements Ongoing support | Assign: Responsible person Timeline (e.g. within 1 month) Measure: Are they still using the solution? Are they recommending it to others?
Write here
Write here
Write here
Write here