## Snag List
Greenbox Design Studio
Snag List Template
Room-wise defect log with severity, responsibility, photo reference and automatic status
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
ID | Room | Element | Defect observed | Severity | Responsibility | Photo ref | Raised | Target | Closed on | Status | Rectification cost (Rs)
S-01 | Living | TV unit | Left drawer fouls the side panel at full extension | Major | Carpentry | IMG_1042 | 12-Sep | 16-Sep | 16-Sep |  | 0
S-02 | Living | False ceiling | Cove shadow gap uneven, 8 mm to 18 mm along the dining edge | Major | Ceiling | IMG_1044 | 12-Sep | 17-Sep |  |  | 4200
S-03 | Living | Paint | Roller marks visible on the south wall in evening light | Minor | Painting | IMG_1047 | 12-Sep | 18-Sep |  |  | 3500
S-04 | Kitchen | Counter | Chip at the sink cut-out, 12 mm, front edge | Major | Stone | IMG_1051 | 12-Sep | 19-Sep |  |  | 6800
S-05 | Kitchen | Base unit | Bottle pull-out rubs the adjacent shutter | Minor | Hardware | IMG_1053 | 12-Sep | 16-Sep | 15-Sep |  | 0
S-06 | Kitchen | Backsplash | Grout line cracked above the hob | Minor | Tiling | IMG_1055 | 13-Sep | 18-Sep |  |  | 1800
S-07 | Master bed | Wardrobe | Sliding shutter jumps at the mid-point of the track | Critical | Hardware | IMG_1061 | 13-Sep | 15-Sep |  |  | 9500
S-08 | Master bed | Bedside | Soft-close not engaging on the right drawer | Minor | Hardware | IMG_1063 | 13-Sep | 17-Sep | 17-Sep |  | 0
S-09 | Master bath | Shower | Water ponds 40 mm from the trap after two minutes | Critical | Plumbing | IMG_1068 | 13-Sep | 16-Sep |  |  | 14500
S-10 | Master bath | Vanity | Mirror cabinet not level, 6 mm across the width | Minor | Carpentry | IMG_1070 | 13-Sep | 18-Sep |  |  | 900
S-11 | Bedroom 2 | Wardrobe | Loft shutter binds against the false ceiling drop | Major | Carpentry | IMG_1074 | 14-Sep | 19-Sep |  |  | 5600
S-12 | Bedroom 2 | Electrical | Bedside socket dead on the left side | Major | Electrical | IMG_1076 | 14-Sep | 15-Sep | 15-Sep |  | 0
S-13 | Common bath | WC | Flush plate loose in the wall recess | Minor | Plumbing | IMG_1079 | 14-Sep | 17-Sep |  |  | 1200
S-14 | Passage | Flooring | Three tiles hollow on tapping near the DB | Major | Tiling | IMG_1082 | 14-Sep | 20-Sep |  |  | 7400
S-15 | Balcony | Paint | Efflorescence patch below the chhajja drip | Major | Painting | IMG_1085 | 14-Sep | 21-Sep |  |  | 5200
S-16 | Whole flat | Cleaning | Protective film left on 11 handles and two glass panels | Minor | Site | IMG_1088 | 14-Sep | 15-Sep | 15-Sep |  | 0
TOTAL
GST @ 18%
Grand total (incl. GST)
Note: Severity drives sequence: Critical before handover, Major before final payment, Minor within the defects period.
Note: Column K is a formula. Fill a date in 'Closed on' and the status flips to Closed by itself.
Note: Rectification cost is what the item would cost you to fix if the contractor walks away. It is your negotiating figure.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com