## Budget
Greenbox Design Studio
Interior Budget Planner
Budget against committed against paid, by head, with live variance
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
Head | Budget (Rs) | Committed (Rs) | Paid to date (Rs) | Balance to pay (Rs) | Variance vs budget (Rs) | Variance % | Comment
Design and drawings | 90000 | 85000 | 85000 |  |  |  | Fixed fee, closed
Civil and demolition | 150000 | 204000 | 140000 |  |  |  | Extra wall found to be structural; rerouted
Electrical | 140000 | 148000 | 100000 |  |  |  | Nine extra points added at first fix
Plumbing and waterproofing | 160000 | 167000 | 167000 |  |  |  | Ponding test passed, paid in full
False ceiling | 55000 | 52500 | 30000 |  |  |  | Under budget, plain design chosen
Flooring and tiling | 130000 | 118000 | 118000 |  |  |  | Batch discount on vitrified tile
Painting | 110000 | 112000 | 60000 |  |  |  | Two extra coats on the west wall
Modular kitchen | 380000 | 348000 | 200000 |  |  |  | Laminate instead of acrylic on wall units
Kitchen hardware | 50000 | 52000 | 52000 |  |  |  | Tandem drawers upgraded
Countertop | 25000 | 21000 | 21000 |  |  |  | Quartz, 20 mm
Wardrobes | 230000 | 225000 | 120000 |  |  |  | Sliding in master, hinged in bedroom 2
Loose joinery | 170000 | 162000 | 90000 |  |  |  | TV, crockery, study, shoe unit
Bathroom fittings | 120000 | 141000 | 141000 |  |  |  | CP brand upgraded by the client
Appliances | 180000 | 174000 | 174000 |  |  |  | Hob, chimney, oven, dishwasher
Loose furniture and soft goods | 250000 | 118000 | 60000 |  |  |  | Sofa and beds ordered; curtains pending
Society, deposits and debris | 45000 | 52000 | 52000 |  |  |  | Deposit refundable at closeout
Contingency | 120000 | 0 | 0 |  |  |  | Hold until snag closure
TOTAL
GST @ 18%
Grand total (incl. GST)
Note: Committed means you have signed for it, whether or not you have paid. That is the number that predicts the final cost.
Note: Variance is shown against budget, not against the last revision. Revising the budget to match the spend hides the problem.
Note: Contingency is a head, not a comfort. Move money out of it explicitly and write the reason in column H.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com