## Change Request
Greenbox Design Studio
Change Request Form
Variation CR-004 worked as an example: additions, omissions and the revised contract value
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
Description | Unit | Qty | Rate (Rs) | Amount (Rs)
Additions requested by the client
Convert the second bedroom wardrobe from hinged to sliding | sq ft | 48 | 420
Add a pull-out pantry unit to the kitchen tall bay | nos | 1 | 28500
Add profile lighting to the crockery unit | rft | 5 | 1850
Upgrade master bedroom shutters from laminate to acrylic | sq ft | 64 | 640
Add a shoe drawer bank at the entrance | sq ft | 8 | 1650
Additions requested by the client — sub-total
Omissions agreed in exchange
Omit the study table in the second bedroom | rft | -4 | 7200
Omit the balcony decking | sq ft | -36 | 340
Reduce false ceiling in the passage to a plain band | sq ft | -22 | 125
Omissions agreed in exchange — sub-total
Time and preliminaries impact
Additional site days caused by this variation | days | 6 | 4200
Re-drawing and re-approval of the affected elevations | LS | 1 | 9500
Time and preliminaries impact — sub-total
Sub-total (ex-GST)
GST @ 18%
Grand total (incl. GST)
Note: Negative quantities are omissions; the sheet nets them off automatically.
Note: A variation must state its time impact as well as its cost impact. Six extra site days is a real cost.
Note: Both parties sign the form before the work is started, not after it is finished.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com