## Timeline
Greenbox Design Studio
Interior Project Timeline Template
A 14-week residential programme with dependencies, float and the value released at each task
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
Phase | Task | Trade | Start week | Duration (wks) | Finish week | Float (wks) | Depends on | Value at completion (Rs)
Pre-site | Measurement survey and existing-condition photography | Design | 1 | 1 |  | 0 | — | 0
Pre-site | Layouts, elevations and 3D views to client | Design | 1 | 2 |  | 0 | T1 | 185000
Pre-site | Material selection and sample approvals | Design | 2 | 2 |  | 1 | T2 | 92000
Pre-site | Society NOC, deposits and lift booking | Admin | 2 | 2 |  | 2 | — | 0
Enabling | Demolition, debris removal and site protection | Civil | 4 | 1 |  | 0 | T4 | 78000
Enabling | Masonry, plaster and levelling screed | Civil | 4 | 2 |  | 0 | T5 | 126000
First fix | Electrical chasing, conduit and wiring | Electrical | 5 | 2 |  | 0 | T6 | 148000
First fix | Plumbing lines, pressure test and waterproofing | Plumbing | 5 | 2 |  | 1 | T6 | 167000
First fix | Ponding test and photographic record | Plumbing | 7 | 1 |  | 0 | T8 | 0
Shell | False ceiling framing and boarding | Ceiling | 7 | 2 |  | 0 | T7 | 52500
Shell | Tiling, flooring and skirting | Tiling | 8 | 2 |  | 0 | T9 | 118000
Joinery | Factory manufacture of carcasses and shutters | Carpentry | 6 | 4 |  | 1 | T3 | 420000
Joinery | Carcass installation at site | Carpentry | 10 | 2 |  | 0 | T12 | 240000
Joinery | Shutter hanging, hardware and alignment | Carpentry | 12 | 1 |  | 0 | T13 | 155000
Finishing | Putty, primer and paint | Painting | 11 | 2 |  | 0 | T10 | 112000
Finishing | Counter templating, fabrication and fixing | Stone | 11 | 2 |  | 1 | T13 | 21000
Finishing | Second fix electrical, fixtures and switch plates | Electrical | 13 | 1 |  | 0 | T14 | 46000
Finishing | Sanitaryware, CP fittings and shower glass | Plumbing | 13 | 1 |  | 0 | T11 | 68000
Closeout | Deep clean and protective film removal | Site | 14 | 1 |  | 0 | T17 | 0
Closeout | Snagging walk, closure and handover documents | All | 14 | 1 |  | 0 | T19 | 62000
TOTAL
GST @ 18%
Grand total (incl. GST)
Note: Float of zero means the task is on the critical path. Four of them are, and they all involve carpentry.
Note: Column F is a formula. Change a start week or a duration and every finish date recalculates.
Note: A 14-week programme assumes 10am to 6pm society hours, six days a week. Add two weeks for a monsoon start.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com