## Move Plan
Greenbox Design Studio
Office Move Planning Template
Fit-out to first working day: a 16-week workstream plan with owners and budget
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
Workstream | Task | Owner | Start week | Duration (wks) | Finish week | Status | Budget (Rs)
Property | Lease signed, fit-out manual received and read | Admin lead | 1 | 1 |  | Done | 0
Property | Landlord drawing submission and approval | Design | 2 | 3 |  | Done | 0
Property | Fit-out deposit, insurance and contractor indemnity lodged | Finance | 2 | 1 |  | Done | 350000
Design | Base build survey and measured drawings | Design | 1 | 1 |  | Done | 60000
Design | Test fit, headcount plan and department adjacency | Design | 2 | 2 |  | Done | 145000
Design | Reflected ceiling plan and MEP coordination | Design | 4 | 2 |  | In progress | 120000
Fit-out | Partitions, glazing and ceiling | Contractor | 6 | 4 |  | Not started | 2850000
Fit-out | Electrical, data and lighting installation | Contractor | 7 | 4 |  | Not started | 1940000
Fit-out | HVAC modification, balancing and commissioning | MEP | 8 | 3 |  | Not started | 1260000
Fit-out | Flooring, painting and joinery | Contractor | 10 | 3 |  | Not started | 1480000
Statutory | Fire NOC coordination and detector relocation sign-off | Consultant | 9 | 3 |  | Not started | 185000
IT | Rack, patching, switch install and Wi-Fi survey | IT | 12 | 2 |  | Not started | 960000
IT | Circuit provisioning and cutover rehearsal | IT | 13 | 2 |  | Not started | 240000
Furniture | Workstation and chair order placed against the approved plan | Admin lead | 6 | 1 |  | Not started | 2150000
Furniture | Delivery, build and cleaning | Vendor | 13 | 2 |  | Not started | 0
Move | Asset tagging and crate allocation at the old office | Admin lead | 14 | 1 |  | Not started | 85000
Move | Building permissions, lift booking and security passes | Admin lead | 14 | 1 |  | Not started | 45000
Move | Physical move over a weekend, IT last out and first in | Vendor | 15 | 1 |  | Not started | 320000
People | Floor plan, seating allocation and induction communication | HR | 14 | 2 |  | Not started | 0
Closeout | Snagging, O&M handover and defects register opened | Design | 16 | 1 |  | Not started | 0
Closeout | Old premises reinstatement and deposit recovery | Admin lead | 16 | 2 |  | Not started | 480000
TOTAL
GST @ 18%
Grand total (incl. GST)
Note: Reinstatement of the old premises is the line most move plans forget. It is real and it is due at lease end.
Note: IT cutover rehearsal in week 13 is what makes the Monday after the move uneventful.
Note: Column F is a formula. Move a start week and the plan re-sequences itself.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com