## Payments
Greenbox Design Studio
Payment Schedule Format
Milestone-based payment plan tied to verifiable events, worked on a Rs 18,50,000 contract
+91 77387 66599 · greenboxdesignstudio.com · Free to use. This is a planning aid, not a quotation. Figures are indicative 2026 Mumbai bands, ex-GST unless stated.
Milestone | Verifiable trigger — what must exist before you pay | Stage % | Cumulative % | Amount (Rs) | Typical week
1 · Booking | Signed contract, signed BOQ and the full drawing set issued | 10 | 10 |  | Week 0
2 · Design freeze | All layouts, elevations and 3D views approved in writing; material selections closed | 15 | 25 |  | Week 2
3 · Site mobilisation | Society NOC in hand, site protection installed, demolition complete | 15 | 40 |  | Week 3
4 · First fix complete | Electrical and plumbing chased, tested and photographed before plaster | 15 | 55 |  | Week 5
5 · Joinery at site | Carcasses delivered and installed, shutters at the factory finishing stage | 20 | 75 |  | Week 8
6 · Finishing complete | Painting, flooring, ceiling and hardware done; power-on and water-on tested | 15 | 90 |  | Week 11
7 · Snag closure | Signed snag list closed, warranties and as-built drawings handed over | 5 | 95 |  | Week 12
8 · Retention release | Thirty days of occupancy with no unresolved defect | 5 | 100 |  | Week 16
TOTAL
GST @ 18%
Grand total (incl. GST)
Note: Replace 1850000 in column E with your own contract value; every amount and the total recalculate.
Note: Never pay against a calendar date. Pay against the evidence in column B — that is the whole design of this sheet.
Note: GST is payable on each invoice as it is raised, not in a single block at the end. The grand total is the all-in figure.
Free to copy and use on any project, with any contractor. Not a quotation. Greenbox Design Studio, Mumbai · +91 77387 66599 · greenboxdesignstudio.com