### 🎯 High-Level Readiness Goals

To ensure continuity of service, operations, payments, and compliance, your organization should be able to do the following by 1 November 2025:

- Understand the Act's principles and reporting obligations.

- Review and update your services and registration categories.

- Review and update your organization's information, outlets, services, and pricing in government systems.

- Update funding and payment processes to make claims and get paid.

- Update your business processes, training, and IT systems to reflect the changes.

- Communicate with existing participants and ensure they have new service agreements (where applicable).

- Work with your partner eco-system to ensure joint readiness.

### ✅ Your Digital Readiness Checklist

Here are the specific actions to tick off, organized by the document's timeline.

1. January to June 2025

- Item 1: Advise Local Network Advise your Local Network of any service transfers, combines, or openings to support deeming accuracy.

- Item 2: Submit Material Changes (Deeming) Submit any material changes and key personnel changes that could impact deeming (e.g., provider transfers) through the 'Manage Your Organisation' tile in GPMS .

- Item 3: Review Deeming Info Review your deeming information and registration categories, which were sent to providers in April 2025.

- Item 4: Review Digital Changes Guide Review the 'Guide to Digital Changes for Providers' and stay on top of updates. An updated version is expected by the end of August 2025.

- Item 5: Review Transition Guides Review the 'Support at Home Provider Transition Guide' and the 'Guide for Short-Term Restorative Care providers transitioning to the Restorative Care Pathway' .

- Item 6: Review Claiming Process Review documentation on the claiming process to understand new data and information sharing requirements for receiving payments .

- Item 7: Maintain GPMS Info Continue to maintain your provider information (contact details, user roles) within GPMS via the 'Manage Your Organisation' tile .

- Item 8: Engage IT Providers Engage your IT providers to prepare your ICT systems for the required changes.

- Item 9: Review Organisation Administrators Review your Organisation Administrator details in GPMS and the My Aged Care Service and Support Portal .

  - Note: CHSP/NATSIFACP providers must provide details of a staff member to be an Organisation Administrator with GPMS access from 3 November 2025 .

- Item 10: Prepare Financial/Reporting Processes Prepare your financial and reporting processes and systems for the transition to Support at Home.

- Item 11: Participate in Consultations Participate in relevant surveys and forums on the department's Consultation Hub site .

2. July to August 2025

- Item 12: Continue GPMS Updates Continue to ensure all provider information (contact details, user roles) is up to date in GPMS .

- Item 13: Submit Material Changes (General) Submit any new material changes and key personnel changes through the 'Manage Your Organisation' tile in GPMS .

- Item 14: Review Pricing Survey Review the outcomes of the Support at Home pricing survey in preparation for uploading your service prices .

- Item 15: Review ACPP Resources Review resources about the Aged Care Provider Portal (ACPP) on Services Australia's website to stay on top of claiming processes .

- Item 16: Assess Operational Impacts Assess the operational impacts that will result from digital changes, such as new claims submission processes.

- Item 17: Review GPMS Resources Review GPMS resources to prepare for digital changes. New training materials will be shared in the lead-up to 1 November 2025.

- Item 18: Assist HCP Recipients Assist your Home Care Package (HCP) care recipients in navigating the reforms and understanding what transitioning to Support at Home means for them.

- Item 19: Review Draft Forms Review the new draft interactive registration forms on the Commission's website. Final forms will be available from 1 November 2025.

- Item 20: Continue Review (Jan-June) Continue to review items from the January-June 2025 list (items 1-11) for any updates to links or guides.

3. September to October 2025

- Item 21: Train Workforce Provide training for your workforce on the technical changes to your provider's internal systems and government portals.

- Item 22: Access Guidance Materials Access and review the guidance materials on government system changes, including GPMS and the My Aged Care Service and Support Portal .

- Item 23: Upload Pricing Schedule Upload a PDF of your revised pricing schedule for the Support at Home services you will offer to the My Aged Care Service and Support Portal .

- Item 24: Set Up Authentication Ensure users of newly deemed provider organisations set up their authentication across government systems (GPMS and My Aged Care Service and Support Portal).

- Item 25: Prepare for GPMS Maintenance Be aware of and prepare for two major GPMS Scheduled Maintenances:

  - Maintenance 1: 11:15 PM (AEDT) Friday 17 Oct 2025 to midnight (AEDT) Sunday 19 Oct 2025.

  - Maintenance 2: 11:00 PM (AEDT) Thursday 30 Oct 2025 to 8:00 AM (AEDT) Monday 3 Nov 2025 .

- Item 26: Submit GPMS Changes (DEADLINE) Submit any material changes or key personnel changes in GPMS by 5:00 PM (AEDT) Friday 17 October 2025.

- Item 27: Update QFR Contacts (DEADLINE) Review and update your Provider Contacts in your Quarterly Financial Report (QFR) for Quarter 1 by 11:15 PM (AEDT) Friday 17 October 2025 .

- Item 28: Finalise Claims (DEADLINE) Ensure all claims and entry events are up to date before the ACPP maintenance:

  - Residential Providers: Submit by 24 October 2025.

  - Home Care Providers: Submit by 31 October 2025.

- Item 29: Discuss Contributions Work with your participants so they understand their required contributions when Support at Home begins. Indicative rates will be available in the ACPP from 1 October 2025.

- Item 30: Understand Claiming Requirements Understand the new Support at Home claiming requirements.

  - Note: Final October 2025 HCP claims must be submitted by 30 November 2025 to enable Support at Home claiming from 1 December 2025.

- Item 31: Continue Review (All) Continue to review all previous checklist items (1-20) for any updates .

- Item 32: Complete AT-HM Data Collection Complete the AT-HM Scheme data collection process for HCP care recipients transitioning to Support at Home. This process runs from October 2025 to February 2026.

4. For November 2025

- Item 33: Deploy Digital Changes Deploy your internal digital changes in preparation for the 1 November 2025 start date.

- Item 34: Implement Operational Changes Implement all operational and digital changes required to support the new Act's commencement.

- Item 35: Update Service Info (CRITICAL WINDOW)
 From 3-7 November 2025, you must verify and update your service and pricing information in the My Aged Care Service and Support Portal. This is a critical requirement. This includes:

  - Verifying and updating the services you deliver .

  - Updating pricing for your services.

  - Revalidating your service delivery area.

  - Confirming outlet names and descriptions.

- Item 36: Engage Recipients on Agreements Engage with transitioning HCP care recipients to discuss their care plans and enter into new Support at Home service agreements (or vary existing ones).

- Item 37: Develop API Solutions Talk to your software vendors or internal ICT teams to develop API solutions that can streamline reporting and claiming .

### ❗ Key Dates & System Downtimes

- Oct 17 (Fri): DEADLINE

  - Submit GPMS material/key personnel changes by 5:00 PM (AEDT).

  - Update QFR contacts by 11:15 PM (AEDT).

- Oct 17-19: GPMS Maintenance 1 System unavailable from 11:15 PM (AEDT) Fri 17th to midnight Sun 19th.

- Oct 24 (Fri): DEADLINE

  - Residential Aged Care providers must have claims and entry events up to date.

- Oct 30 - Nov 3: GPMS Maintenance 2 System unavailable from 11:00 PM (AEDT) Thurs 30th to 8:00 AM (AEDT) Mon 3rd .

- Oct 31 (Fri): DEADLINE

  - Home Care providers must have claims and entry events up to date.

- Oct 31 - Nov 1: ACPP Maintenance System unavailable from 6:00 PM (AEDT) Fri 31st to 12:00 PM (AEDT) Sat 1st.

- Nov 1 (Sat): New Aged Care Act starts.

- Nov 1-5: ACPP Read-Only Period The ACPP will be in read-only mode from 12:00 PM (AEDT) Sat 1st until at least 12:00 PM (AEDT) Wed 5th.

- Nov 3-7: CRITICAL ACTION WINDOW Providers must log in to the My Aged Care Service and Support Portal to verify and update service and pricing information.

- Nov 30 (Sun): DEADLINE

  - Final Home Care Package (HCP) claims for the October 2025 period must be submitted.

### ☎️ Support and Contact Information

#### General & Technical Support

- My Aged Care Helpline: For technical support and general information for providers, assessors, and hospital staff who use the My Aged Care Service and Support Portal and GPMS portal, call 1800 836 799.

- Website: For more information and updated support material, visit myagedcare.gov.au or use the My Aged Care Service and Support Portal.

#### Claims and Payments (Services Australia)

- Services Australia Enquiry Line: For help with aged care claims and payments, call 1800 195 206.

- Scope: This line can assist with supplement claims, Approved Provider forms, online claiming registrations, and transitional and respite care extensions.

#### GPMS (Government Provider Management System)

- General Enquiries: For general questions relating to GPMS, contact GPMS.project@health.gov.au.

- Specific Enquiries: This email can also be used for questions about:

  - Setting up your Organisation Administrator.

  - The scheduled maintenance periods.

#### Registration, Deeming, and Notifications

- Deeming Enquiries: For registration preview or deeming enquiries, email AgedCareRegModel@health.gov.au.

- Provider Notifications: If you have concerns about deferring submission of changes between 17 October and 1 November 2025, contact the Commission at providernotifications@agedcarequality.gov.au.

#### Other Contacts

- Local Network: You should engage with your Local Network contacts regarding any service transfers, combines, or openings.