## Slide 1: How to Estimate With Story Points

## Slide 2: Four Things to Understand about Story Points
Story points are relative
1

## Slide 3: Points Are Relative
Reading a 300-page book will take twice as long as reading a 150-page book.
  Assuming they generally the same type of books, etc.

## Slide 4: Points Are Relative
Walking or running two kilometers will take twice as long as walking/running one kilometer
  Assuming the same terrain, etc.
  Would an Olympic runner agree?
  Can you and the Olympian agree to estimate those as 10 and 20 then?

## Slide 5: An Exercise

## Slide 6: Four Things to Understand about Story Points
Story points are relative
The units are meaningless
1
2

## Slide 7: Units Are Meaningless
Estimating items as 50:100 is the same as estimating 10:20, 1:2 or even 0.1:0.2.
50:100
1:2
10:20
=
=

## Slide 8: Units Are Meaningless
The ratio is all that matters
Obviously integers are easier to deal with
A good way to avoid fractions is to set your scale so that {3, 5} or {4, 8} are used on typical small items for that project
:
:
:

## Slide 9: Four Things to Understand about Story Points
Story points are relative
The units are meaningless
Story points are about effort
1
2
3

## Slide 10
Experienced bricklayer 500 bricks / day
Apprentice 250 bricks / day
What happens if we ask them to estimate how long it will take to build a 2,000-brick wall?

## Slide 11
Experienced bricklayer 500 bricks / day
4
DAYS
8
DAYS
2,000 Brick Wall
4,000 Brick Wall
Apprentice 250 bricks / day
16
DAYS
8
DAYS

## Slide 12: Disagreeing or Agreeing?
How will the experienced bricklayer respond when the apprentice says the larger wall will take:
16 Days
Twice as long as the smaller wall

## Slide 13: Think in Hours, Speak in Points
Twice as long
8 hours
16 hours

## Slide 14: Four Things to Understand about Story Points
Story points are relative
The units are meaningless
Story points are about effort
Story points are a function of amount, risk, uncertainty, and complexity
1
2
3
4

## Slide 15
How long will it take to paint the fence around a house?
What would be useful to know about the fence?

## Slide 16
Amount of Work
Complexity
Risk & Uncertainty

## Slide 17: The Amount of Work
How long the fence is
How many different types of pages
How many guests are invited to the wedding
FENCE
WEBSITE
WEDDING

## Slide 18: Risk and Uncertainty
Not knowing what color to paint it
A screen or feature that hasn’t been designed
Not knowing yet how many guests will be invited
FENCE
WEBSITE
WEDDING

## Slide 19: Complexity
Painting a mural instead of a single color
A difficult calculation
A seating chart when some guests don’t like one another
FENCE
WEBSITE
WEDDING

## Slide 20: The Four Key Things
Story points are relative
The units are meaningless
Story points are about effort
Story points are a function of amount, risk, uncertainty, and complexity
1
2
3
4

## Slide 21: For More Information
Estimating with Story Points
with Mike Cohn
Learn more at: https://mtngo.at/esp

## Slide 22: License
This presentation is provided under the Creative Commons Attribution-ShareAlike 4.0 International (CC BY-SA 4.0)
You are free to:
Share — copy and redistribute the material in any medium or format
Adapt — remix, transform, and build upon the material for any purpose, even commercially.
Under the following terms:
Attribution — You must give appropriate credit, provide a link to the license, and indicate if changes were made. You may do so in any reasonable manner, but not in any way that suggests the licensor endorses you or your use.
ShareAlike — If you remix, transform, or build upon the material, you must distribute your contributions under the same license as the original.
This slide is a summary and not a substitute for the license at https://creativecommons.org/licenses/by-sa/4.0/legalcode