# Monitoring Biosand Filter Projects

October 2011

Manual

12, 2916 – 5th Avenue Calgary, Alberta, T2A 6K4, Canada

Phone: + 1 (403) 243-3285, Fax: + 1 (403) 243-6199

E-mail: cawst@cawst.org, Website: www.cawst.org

CAWST is a Canadian non-profit organization focused on the principle that clean water changes lives. Safe water and basic sanitation are fundamentals necessary to empower the world’s poorest people and break the cycle of poverty. CAWST believes that the place to start is to teach people the skills they need to have safe water in their homes.

CAWST transfers knowledge and skills to organizations and individuals in developing countries through education, training and consulting services. This ever expanding network can motivate individual households to take action to meet their own water and sanitation needs.

One of CAWST’s core strategies is to make knowledge about water common knowledge. This is achieved, in part, by developing and freely distributing education materials with the intent of increasing its availability to those who need it most. You should feel free to copy and distribute this document in any form, printed or electronic. If you wish to use any parts of this document in the creation of your own materials, please ensure that CAWST is properly acknowledged.

Please include our website address: www.cawst.org.

Feel free to include a link from your website to the CAWST website. Please do not host this document to download from your website as we will have updated versions from time to time. Please email us if you have any questions or feedback.

This document is open content and licensed under the Creative Commons Attribution Works 3.0 Unported License. To view a copy of this license, visit: http://creativecommons.org/licenses/by/3.0

You are free to:

- Share – to copy, distribute and transmit this document

- Remix – to adapt this document

Under the following conditions:

- Attribution. You must give credit to CAWST as the original source of the document

CAWST and its directors, employees, contractors, and volunteers do not assume any responsibility for and make no warranty with respect to the results that may be obtained from the use of the information provided.

#### Acronyms and Abbreviations

ACI	Aqua Clara International

BSF	Biosand filter

CAWST	Centre for Affordable Water and Sanitation Technology CHP	Community Health Promoter

cm	centimeters

HWTS	Household Water Treatment and Storage L	Litre

LFM	Logical Framework Model

Min	minutes

mL	millilitre

WASH	Water, Sanitation and Hygiene

#### Table of Contents

- Monitoring Biosand Filter Projects	1

- Logical Framework Model and Monitoring	5

- Indicators	9

- Establishing a Baseline	19

- Setting SMART Targets	21

- Collecting Information	23

  - What Information is Needed?	24

  - What is the Most Appropriate Method to Collect Information?	27

  - Questioning Techniques	30

  - Who Will Collect the Information?	32

  - When Should the Information be Collected?	34

  - How Will the Information be Managed?	35

  - Consider the Human Factor	37

- Analyzing and Making Improvements	39

  - Situational Analysis	41

  - Group Trends	44

  - Long Term Trends	49

- Communication	53

- Timeline and Growth	55

- Summary	59

References	60

# Monitoring Biosand Filter Projects

This guideline is to help implementers to plan out how to monitor their projects as well as tips on how to put it into action with growth, improvement and impact in mind. The main target audience for this set of resources is biosand filter project implementers and field staff. CAWST hopes to help organizations plan and use monitoring for success with the combination of this guide, a training program and consulting support.

The stages of developing a monitoring plan start with outlining the projects’ outputs, developing indicators, establishing a baseline and setting targets. Some projects may already have these stages already set if they were completed during the project design stage. If they are complete, it is recommended that they are reviewed with monitoring in mind. If they are not complete, the manual and training will help to develop these very important parameters of a project.

With the outputs, indicators, baseline and targets established, the monitoring forms are developed to collect relevant information in an appropriate and effective way. Once the information is collected, it needs to be analyzed to determine what is working, what is not working and what needs to be fixed. Improvements are then made to fix the identified problems and improve processes to prevent the problems from happening again. All of these results and improvements are then communicated to various stakeholders. Figure 1.1 below illustrates this process.

Throughout the manual, explanations and examples are used to illustrate how to plan and develop monitoring activities, processes and capacities. There is an emphasis on how to analyze, make improvements and communicate results as these are the stages of monitoring where many organizations have their greatest challenges. Administrative and operational challenges will also be discussed, such as resource, environmental and cultural considerations.

Throughout the guideline, case studies, lessons learned and CAWST experiences will be showcased for a broader perspective of monitoring successes and challenges that have helped to create this set of guidelines.

A fictional biosand filter project will be used as an example project in each section for continuity and a way to create a complete picture of the monitoring stages in action.

COMMUNICATION:

How, how often and to whom are the results communicated?

IMPROVEMENTS:

How can problems be fixed?

How can processes be improved to avoid the same problems in the future?

MONITORING FORMS:

Collecting necessary information

ANALYSIS:

What conclusions can be made from the information collected?

INFORMATION COLLECTION:

Methods and logistics

Figure 1.1: The Stages of a Building a Monitoring Plan and Putting into Action

PROJECT OUTPUTS

(short term expected results)

INDICATORS

Establishing a

BASELINE

Setting

SMART

targets

# Logical Framework Model and Monitoring

Key Messages:

- LFM is a project planning tool that can be used to guide the development of a monitoring plan

- Monitoring checks in with the outputs and activities of a project

The Logical Framework Model (LFM) is a project planning and management tool used mainly in the design, monitoring and evaluation of projects. When planning a project the LFM helps to give structure and direction to a project. It establishes long, medium and short term project goals with the details of what is going to be done to achieve them and how they will be measured.

The key components of a project are all connected and lead from one component to the next.

Outputs = Successful; Outcomes

Outputs and Outcomes = Successful;

Impact

OUTCOME

(mid-term expected results)

IMPACT

(long term expected results)

Figure 2.1: Key Components of the Logical Framework Model

Project activities = Successful;

Outputs

ACTIVITIES

(Day to day events to meet expected results)

OUTPUTS

(short term expected results)

Monitoring, using the LFM, helps to identify if the day to day activities are a success, or not, and why. This then allows the project to measure the success of the outputs. Therefore, in terms of the LFM, monitoring focuses on the outputs and day to day activities in order to determine how successfully they are being carried out and what can be improved upon. To clarify the components, Table 2.1 provides explanations and examples for each component of the LFM.

Table 2.1: Key Elements of the Logical Framework Model

| KEY ELEMENT | EXPLANATION | EXAMPLE |
| --- | --- | --- |
| Impact (Long term expected results) | Highest objective, impact or goal that this project, as well as other, intends to contribute. It refers to the long term effect of the project aims to have on the target community. | Community X has a reduction in diarrheal diseases, yearly clinic visits and medical expenses. |
| Outcome (Mid-term expected results) | The change in beneficiary situation, conditions or behaviours that contributes to the desired impact. It is medium term, for example 3-5 years. | Community X has installed biosand filters, is capable of operating and maintaining them and has improved hygiene and sanitation practices. |
| Outputs (Short term expected results) | Short term goals that direct project activities and when successfully achieved they contribute to the outcomes and impact. They are the tangible products or services to be delivered by the project. | Biosand filters are properly produced, installed and used. |
| Activities (Day to day events to meet expected results) | Specific actions that are carried out to accomplish the expected outputs. | - Biosand filter production - Filtration sand preparation - Filter installation - End user training - Follow up visits to biosand filter |

(CIDA, 2011 and WFP, unknown)

Outputs

MONITORING

Are we doing things right?

Activities

Figure 2.2: How Monitoring Fits into the Logical Framework Model

Impact

Outcomes

Figure 2.3 presents the example biosand filter project used throughout the manual as the basis for developing example monitoring activities and processes.

#### Figure 2.3: Case Example of a Biosand Filter Project LFM

Community X has a reduction in diarrheal diseases, yearly clinic visits and medical expenses

IMPACT

(Long term expected results)

###### OUTCOME

Community X has quality biosand filters, is capable of operating and maintaining them and has improved hygiene and sanitation practices.

(Mid-term expected results)

###### OUTPUTS

Post filter installation and WASH support for each household

Biosand filters are properly produced, installed and used

BSF End User training and WASH Awareness sessions delivered in the target community

(Short term expected results)

- Post installation household visit by BSF technician

- WASH follow up visits by Community Health Promoters

- BSF/WASH

awareness training

- End user training

- BSF production

- Filtration sand preparation

- Filter installation

- End user training

ACTIVITIES

(Day to day events)

# Indicators

Key Messages:

- Indicators are the details of the project that indicate whether or not it is successful

- Monitoring is planned to gather the information necessary to prove their success

- A combination of qualitative and quantitative indicators provide a more complete

picture of the project’s results

Monitoring is guided by indicators of the project’s outputs. The indicators determine what monitoring activities are necessary to measure success, to identify problems and make improvements on a day to day and week to week basis.

All indicators should be:

- Relevant to the project and to national standards

- Feasible to collect and easy to interpret

- Easy to track change over time.

Figure 3.1: Stage 1 in Developing a Monitoring Plan - Indicators

PROJECT OUTPUTS

(short term expected results)

Stage 1- INDICATORS

Establishing a

BASELINE

In a project that is designed with a logic model, there are two broad categories of indicators - process and impact. Process indicators help us to answer the question, “Am I doing things right?” For the purpose of monitoring, process indicators will be the most useful to specifically measure the outputs of the project objectives and activities and provide opportunity to make improvements along the way.

Impact indicators are developed to measure the outcomes and impact of a project by answering the question, “Am I doing the right things?” Impact indicators are commonly used when conducting an independent evaluation or during academic research, to show the longer-term health impacts or benefits to the community and therefore not to be used in monitoring.

Figure 3.2 below illustrates the difference between process and impact indicators.

Figure 3.2: Process vs. Impact Indicators in the Logical Framework Model

Refer to Figure 3.3 for explanations and examples of indicators for each of the levels of the LFM.

Shortest term and more depth, frequency and detail of information needed. Combine information collected during project activities and analyzed as a whole to prove success.

- # competent BSF technicians

- % filter boxes useable (production  installation)

- % appropriate sand sieve analysis

- % appropriate flow rate test (pre-installation)

- % accepted sand sets

- # filters properly installed

- % appropriate installation flow rate

ACTIVITIES

(Day to day events to meet expected results)

OUTPUTS

(short term expected results)

OUTCOME

(mid-term expected results)

Figure 3.3: Logical Framework Model and Indicators

Longer term and broad depth of information needed. Can combine information collected from output and activity indicators and analyzed as a whole to prove success.

- # of people reached with better water, hygiene and sanitation

- User perception of change in health

Logical Framework Model	Indicators	Examples

IMPACT

(long term expected results)

Longest-term and broad depth of information needed; No obvious link to specific activities.

- # of clinic/hospital visits by target families for water related diseases

To simplify things for the purposes of this set of guidelines and resources we will refer to process indicators as simply indicators, assuming they are the indicators of the outputs of the project and for use in monitoring.

Therefore, the indicators discussed in this manual are used to:

- Track progress towards the expected results of outputs

- Guide the development of the monitoring plan, monitoring forms, and the processes for analysis and making improvement.

When developing indicators, it is important to understand three key aspects:

  - Numbers only tell one part of what we hope is a great story. A more complete picture of success can be created and what improvements are needed by including qualitative and quantitative indicators.

Figure 3.4: Completing the Picture with Qualitative and Quantitative Results

Quantitative: # filters properly

installed

Qualitative: Satisfaction of end users

If all targeted end users have a filter and are happy with them = SUCCESS

  - More than one indicator is often needed to fully capture the level of success due to the number of things involved and blending qualitative and quantitative results.

Figure 3.5: Example Indicators to Measure Success of

OUTPUT #1

(short term)

INDICATORS

Filters properly produced, installed and used

Satisfaction off end users with BSF

% appropriate installation flow

% problems identified and unsolvable at installation

  - There is a trade-off between the ease with which some monitoring data is collected and its overall correlation with the project outputs.

For example, it is easy to measure the number of biosand filters produced and distributed, but to monitor the quality of the biosand filters and the actual household use of them requires more time and money. The quality and use, however, provide very useful information to know if the filters are actually operating properly and if the end user training is sufficient.

Once developed, look at each indicator and ask the following questions:

- Is it accurate? Is it always going to measure what is needed or could it be telling you something else?

- Is it cost-effective to collect the information?

- Does it give useful information for finding problems and making improvements to processes and capacity?

- Will the information be easily understood by stakeholders, including funders?

Refer to Tables 3.1 to see a complete list of indicators for key biosand filter project activities.

Table 3.1: Suggested Indicators for Biosand Filter Projects

| Outputs | Activities | Indicators (Usually calculated by management) | Necessary Information (Usually collected by BSF Technicians and CHPs) |
| --- | --- | --- | --- |
| Filters properly produced, installed and used | Biosand filter production | - # competent BSF technicians | - # BSF technicians validated as competent (male/female) |
|  |  | - % filter boxes useable (production  installation) | - # of completed filter boxes, numbered, recorded and made ready for delivery - # of filters rejected and returned by installation team - # of filter bodies rejected at production site - # filters taken for delivery and installation - # filters broken during transportation |
|  |  | - % appropriate sand sieve analysis | - # acceptable sand sieve analysis tests |
|  |  | - % appropriate flow rate test (pre-installation) | - # acceptable pre installation flow rate tests |
|  | Filtration sand preparation (sieving and washing) | - % accepted sand sets | - # sand sets (one filter of sand and gravel) prepared for delivery - # sand set rejected/returned by installation team |
|  | Filter installation | - # filters properly installed | - # of filter installations (with form signed) |
|  |  | - % appropriate installation flow rate | - # of filters with flow rates out of range (less than 0.3 or over 0.5 L/min) |
|  |  | - % problems identified and unsolvable at installation | - # of problems raised that could not be resolved at installation |
| BSF end user training and WASH | BSF/WASH awareness training | - # competent CHPs | - # CHPs validated as competent (male/female) |

| Outputs | Activities | Indicators (Usually calculated by management) | Necessary Information (Usually collected by BSF Technicians and CHPs) |
| --- | --- | --- | --- |
| awareness sessions delivered in the community |  | - # participants in WASH awareness session | - # WASH Awareness sessions delivered - # of participants (male/female) |
|  |  | - # households requesting biosand filters after WASH Awareness session - % households receiving biosand filters within 1 month of request | - # requests for biosand filters from non-BSF owners - # families confirmed to receive BSF from WASH sessions - # families waiting over 1 month for their filter post request |
|  |  | - % confidence of participants in putting their action plan item into practice at home | - # participants with confidence of their action plan - # of participants (male/female) |
|  |  | - Satisfaction of participants in WASH session | - # participants satisfied - Anecdotal affirmation of satisfaction |
|  | End user training | - # end users trained | - # of end users trained (male/female) |
| Post filter installation and WASH follow up for each household | Post installation household visit by BSF technician | - % filters used to unused after 1 month | - # of filter problems referred to technicians |
|  |  | - % end users competent in operation and maintenance | - # end users using and cleaning filters properly - # end users NOT using and cleaning filters properly |
|  |  | - % properly operated filters 1 month post installation | - # filters no longer being used consistently - # filters operating properly 1 month post installation |
|  |  | - # filter problems identified and solved | - # filters problems identified - # problems resolved |
|  |  | - # of BSF tech visits required after follow up visit | - # repair visits needed |

| Outputs | Activities | Indicators (Usually calculated by management) | Necessary Information (Usually collected by BSF Technicians and CHPs) |
| --- | --- | --- | --- |
|  |  | - % filters used to unused after 1 month | - # filters installed - # filters still used at post installation visit |
|  | WASH follow up household visit by Community Health Promoters | - Ratio of recommendations made during first household visit to last scheduled visit | - # households who had X# of WASH follow up visits |
|  |  | - % end users competent in operation and maintenance | - # end users operating and maintaining filters and parts properly |
|  |  | - Satisfaction of end users with BSF | - # end users satisfied with BSF - # of end users NOT satisfied with BSF |
|  |  | - % properly operated 3, and 12 months post installation | - # filters no longer being used consistently after 2 months, 6 months, 12 months |
|  |  | - % filter problems identified to problems solved | - # filter problems identified - # filter problems solved |
|  |  | - % household putting their action plan into action | - # households practicing their action item at each visit |
|  |  | - # hygiene and sanitation recommendations made by CHPs from visit to visit | - # the same WASH recommendations made by CHPs from visit to visit |

# Establishing a Baseline

Before starting a biosand filter project it is common to collect information on the current situation in the target community. The information collected is directly linked to the logical framework model of the project and established indicators. This information is what is called a baseline.

Figure 4.1: Stage 2 in Developing a Monitoring Plan

INDICATORS

Stage 2- Establishing a BASELINE

Setting

SMART

targets

Baseline information is normally collected in a similar manner to monitoring information and uses the same tools. The main purposes of establishing a baseline for a biosand filter project is to:

- Determine and describe the current WASH situation in the community and households:

  - What other forms of water treatment are commonly used in the area?

  - What are the main sources of water?

  - What is the level of WASH practices happening in the homes?

  - What is the standard of sanitation used by the household?

- Determine and describe the current situation at the biosand filter production site and installation processes:

  - What is the level of production success at the start?

  - What is the level of installation success?

- Provide a benchmark (i.e. a snapshot of the current situation), against which change can be assessed, focusing mainly on the variables that a WASH project may be intending to improve.

Based on the baseline information it is easier to set SMART targets (Section 5). Once both the baseline and targets are known, the actual information collected can be compared to illustrate for the team how far along the project has come and where it still needs to get to as shown in Figure 4.2 below.

Figure 4.2: Comparing Baseline, Actual and Target Results

Acceptable Key Operating Parameters - Visit 1

120

100

80

Percentage (%)  60

40

20

Baseline

Acceptable Target

0

Standing	Flow Rate	Daily Use	Diffuser

Water Level

Key Operating Parameters

As can be seen in Figure 4.2 above, the operating parameters are above the baseline, but still haven’t reached the target. An organization can then look at what is working and what is not working to keep moving them towards the targets.

# Setting SMART Targets

In the first stage of developing a monitoring plan, indicators are developed for the outputs of the project. The next stage is to set SMART targets for the indicators.

Figure 5.1: Stage 3 in Developing a Monitoring Plan – Setting SMART targets

Establishing a

BASELINE

Stage 3- Setting SMART

targets

MONITORING FORMS:

Collecting necessary

information

In order to measure success, each indicator needs to have targets that are SMART:

- Specific

- Measurable

- Achievable/Affordable

- Relevant/Reliable

- Time-bound

SMART targets are very project specific depending on the scale of the project, staff and budget. A few examples are given here, but the monitoring plan team will have to set SMART targets for their project.

To set SMART targets a few details are required: timeframe, what the quantitative or qualitative goals are, and what activity matches the indicator. See the Figure 5.2 below for setting SMART targets.

Figure 5.2: Steps to Create a SMART Target

% appropriate trial installation flow rate test results

Indicator

- 1 trial installation flow rate test per sand sorting session

- Minimum trial installation every 2nd day of washing

Project Specific Parameters (to help set targets)

Filtration sand with 100% acceptable flow rate with each trial installation

Trial Installation Flow Rate Test –

100% acceptable

Target

###### SMART

Target

More examples of SMART targets are shown in Table 5.1.

Table 5.1: Developing SMART Targets

| Example |  |  |  |
| --- | --- | --- | --- |
| Indicator | % filter boxes useable (production  installation) | % confidence of participants in putting their action plan item into practice at home | # hygiene and sanitation recommendations made by CHPs from visit to visit |
| Project Parameters | 5 molds, 6 work days, 3 staff, 7% acceptable breakage (production and installation) |  | 6 CHP visits per year (1 per 3 weeks for 3 months, 1 at 6 months, 1 at 12 months) |
| Target(s) | 28 filters per week | Increased confidence over time. 65% feel very confident 20% feel less than confident 15% feel no confidence | Reduction in recommendations necessary over time because the practices are in place. |
| SMART Target | 93% of filters produced are immediately useable for a total of 28 filters per week | 65% confidence that the participants can and will put their action plan item in to practice at home | 50% reduction in the number of hygiene and sanitation recommendations to households made |

# Collecting Information

Key Messages:

- Only collect information that is necessary to measure the indicators

- Use a combination of collection methods to have more reliable information

- Use effective questioning techniques to ensure reliability of the information collected

- Determine who will be the most

appropriate to collect information

- Organize the information collection into daily activities

- Determine how the information will be managed once it is collected

- Consider how culture, status, and the feelings and attitudes of collectors and respondents could affect reliability

- Determine the appropriate amount of resources, training and mentoring required to build the capacity of those collecting the information

After developing indicators and adding targets that are SMART, the next stage of monitoring is to collect the information that is necessary to determine if the targets are being met.

A number of factors need to be considered with the collection of information:

- What information is necessary to measure the success of the indicators?

- What is the most appropriate method to collect the information?

- What techniques need to be used to maintain reliability of the information?

- Who will be collecting the information?

- When should the information be collected?

- How will the information be managed after collection?

- What social and cultural considerations should be considered?

Setting

SMART

targets

Stage 4- INFORMATION COLLECTION:

Methods and logistics

Stage 4- MONITORING FORMS:

Collecting necessary information

Figure 6.1: Stage 4 in Developing a Monitoring Plan – Monitoring Forms and Information Collection

ANALYSIS:

What conclusions can be made from the information collected?

## What Information is Needed?

One of the challenges is determining what information is necessary to collect to determine the indicators and if the targets are being met. Often more information is collected than necessary. Collecting unnecessary information wastes time and resource, adding more costs to the project. It is important to discuss what information is necessary so that only useable questions are included in the monitoring forms.

To determine what information is necessary, it is critical to keep the indicators in mind. They are the guidelines to measure success, so the necessary information needs to help identify if the targets are being met or not.

CAWST’s monitoring forms have been developed based on the key indicators listed in Table

3.1. These forms can be used as a starting point for an organization to use as is or adjust them to fit the needs of the project. See Appendix A for a complete set of CAWST monitoring forms.

A biosand filter production monitoring form is analyzed in Table 6.1.1 to explain the rationale for the information to be collected.

Table 6.1.1: Rationale for Information on a Monitoring Form

Indicator = % filter boxes useable (production  installation)

##### Form #: 		Location: 		Date:

| Mold Number Used | Date Poured (day/ month/ year) | Filter Number | Initial Cracks or Leaks or | Fixed Cracks or Leaks or | Flow Rate When Empty (mL/min) if plugged | Water Level Below Diffuser or | Filter Useable or | Improvements Made |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To track if | To track | To track | To help | To help | To ensure that | To ensure | To track that | To track if there |
| there are | when it | the filter | track the | identify a | the filter was | that the tube | the filter has | were any |
| problems | was | from | filter | possible | okay before | length has | passed all | improvements |
| from | poured | produc- | production | future | installation in | been | the | that had to be |
| filters that | which | tion to | processes | problem if | case there are | checked | requirements | made to the |
| come out | will be | installa- |  | a filter is | flow rate | before | for | production |
| of a | tracked | tion |  | fixed | problems after | installation | installation | process |
| certain | with the |  |  |  | installation |  |  |  |
| mold | number |  |  |  |  |  |  |  |

Information to be Collected

Reason

**Note: When the Filter Useable data is tallied, a percentage will be calculated to identify the level of success for the performance indicator.

Technician Name: 		Supervisor Signature:

(To know which technician is in charge of this data and that the supervisor has seen the data page)

## What is the Most Appropriate Method to Collect Information?

The method use to collect information will depend on the type of information and where it needs to be collected. There are numerous options, but again it is important to keep it simple and consider the capacity of the individuals that will be required to collect the information.

Collection methods that can be used individually or in combination are:

    - Interview with questionnaire (i.e. individual or group)

    - Physical measurements (i.e. flow rate)

    - User demonstration (i.e. swirl and dump)

    - Group discussions (i.e. community meeting)

    - Direct observations (i.e. observe the presence of soap and wash stand)

The information in Table 6.2.1 needs to be collected from the household during a follow up visit. Therefore this information can be collected using the following methods:

    - Direct observations (e.g. observing if members of the family have red, swollen or discharge coming from their eye which is a sign of an infection)

    - Questioning the household members (e.g. you can ask questions like “How often has the

family experience diarrhea or stomach aches in the last week?”

Table 6.2.1: Information Collection Methods for Household Visit

| Does anyone in the home suffer from the following? |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| OR | Diarrhea | Stomach Ache | Skin Infection | Eye Infection | Other |

The information in Table 6.2.2 is available at the filter production site. Therefore this information can be collected using the following methods:

    - Direct observations (e.g. checking filters for numbers)

    - Physical measurement (e.g. testing the flow rate when empty)

    - Questioning the filter technicians at the site (e.g. Asking “Have you noticed any problems with Mold #2?”)

Table 6.2.2: Information Collection Methods for Filter Production

| Mold Number | Date Poured (day/ month/ year) | Filter Number | Initial Cracks or Leaks or | Fixed Cracks or Leaks or | Flow Rate When Empty (mL/min) if plugged | Water Level Below Diffuser or | Filter Useable or |
| --- | --- | --- | --- | --- | --- | --- | --- |

Based on the CAWST monitoring forms included in Appendix A, here are some suggested methods to collect the necessary information to complete the forms.

Table 6.2.3: Suggested Collection Methods for CAWST Monitoring Forms

| CAWST Monitoring Form | Collection Methods |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Interview with Questionnaire | Physical Measurements | User Demonstration | Group Discussions | Direct Observation |
| BSF Production |  |  |  |  |  |
| Sand Production |  |  |  |  |  |
| Sand Sieve Analysis |  |  |  |  |  |
| Test Installation |  |  |  |  |  |
| Lid/Diffuser Production |  |  |  |  |  |
| Installation |  |  |  |  |  |
| End User Training |  |  |  |  |  |
| WASH awareness session |  |  |  |  |  |
| Post- installation Visit |  |  |  |  |  |
| CHP Follow Up Visits |  |  |  |  |  |

Even if you use appropriate information collection methods, getting reliable information can be a challenge. There are a number of factors that can affect the results. Table 6.2.4 below is a list of common collection errors and how to prevent them.

Table 6.2.4: Common Errors in Collecting False Information and How to Prevent It

| Common Errors | Ways to Prevent Them |
| --- | --- |
| Interviewer bias or poor questioning technique (An interviewer can influence a response just by how the questions are asked) | BEFORE USE - Clarify the purpose of collecting the information - Clarify the correct units, whom to speak with and where, and the frequency of collection - Practice using the forms in house - Adjust forms to make it easier to avoid biases - Brainstorm possible problems that may occur. Agree on various ways to either avoid or deal with them should they arise. DURING USE - Use open questions - Pause or wait after asking the question to allow the respondent to think - Avoid leading statements after the question is asked - Ask the question in the same way every time - Repeat the question if necessary - Ask respondents to demonstrate what they know as much as possible (e.g. operation and maintenance of the filter) - Record responses accurately and consistently |
| Non-response bias (If many people do not respond to a certain question, the results are biased) | - Pre-test questions and how they are asked - Present questions clearly and confirm the interviewee has understood - Use local terms and language as much as possible - If there is consistent non-response, discuss as a group how to improve the question to get a response |
| Culture and status bias (Cultural pressures or status can affect answers if there is any sense that the respondent is on a different level than the interviewer) | - Consider cultural taboos, customs, sensitive topics, status (e.g. social, financial, age) when designing questions - Identify the questions that culturally the respondents may feel uncomfortable answering - Use appropriate language to help make the question easier for them to understand (For example, the word “diarrhea” is taboo in some cultures so a question can be reworded to use more appropriate terminology, like “uncomfortable in the gut area” instead) - For BSF Technicians and CHPs who conduct household visits, choose individuals that are as neutral as possible when it comes to status - See Section 4.3.6 for more information |

(Adapted from IFAD, 2001)

## Questioning Techniques

Questions are used every day in search of information and understanding. Although they seem simple, an effective question requires thought and design based on the desired response and the reliability that is needed. Keeping reliability in mind when designing a question ensures that key words are used in the question to get to the truth. The main design consideration for effective questions is that they are open ended for the respondent to reply, explain or elaborate, as opposed to closed questions that only require a yes or no response.

Figure 6.3.1: Designing Effective Questions for Reliable Responses

The household either does or doesn’t sediment

their inlet water before using the biosand filter.

Desired Reliable	 Response

Do you sediment your water before pouring it into the filter?

Yes.

Question 1 	

What, if anything, do you do to the water before it is poured into the filter?

They have to explain. If they can’t they most likely don’t do any form of sedimentation.

Question 2 	

A question can be effectively designed and yet the reliability of the question could be affected if it isn’t asked in an effective way. The following is a list of questioning techniques to ensure that questions remain effective when they are asked.

- Wait time

After asking the question, give the respondent time to think. The respondent’s brain needs a chance to process the question to be able to answer it. They might not respond right away, so wait patiently for them to respond. Watch their face and you will be able to tell if they are thinking or don’t understand.

- Avoid follow up statements or questions after the key question is asked

An effective question is more reliable when it is asked in a way that doesn’t lead to the desired response but is open for the truth. If a respondent doesn’t answer right away, the interviewer often continues to expand the question and falls into leading or closed questions. The expansion often makes it a leading question or more confusing.

For example an interviewer may start with an effective question and quickly add in a statement and another question while the respondent is trying to answer the first question. For example:

  - “What else do you do to your water to make is safer besides using the filter?”

  - “Like settling, boiling, chlorination, SODIS.”

  - “Do you do anything to your water before or after filtering?”

The first question is effective and allows the respondent to explain. The second leads them to name one of them whether they do it or not. The third gives them an out to say yes if they want to whether it is true or not.

- Repeat if necessary

If the facial expression of the respondent shows confusion, then ask them if they would like to hear the question again. Asking permission confirms whether they need it or not. They just might need more time to think.

- Ask the respondents to demonstrate as much as possible

Actions speak louder than words. If they are in fact doing something like washing their hands the way they are taught, then there will be soap and a water source set up. Ask to see it and for them to show you how they use it.

- Ask the question the same way every time to ensure reliability between houses and visits

To ensure reliability from house to house, visit to visit and for trend analysis, be consistent in how you ask the question and how you record the responses.

- Be conscious of how feedback is given to the respondents –

“In Cameroon and Haiti I have seen poor feedback leading to trouble with the end users. For example the flow rate was 0.6 mL/min instead of 0.4 mL/min and the monitoring agent said ‘Ah not good the flow rate is too fast.’ The end-user got scared and stopped using the filter.”

(Personal communication with O. Mills, CAWST) When problems are noted, record the information with no verbal or non-verbal indication of

judgement. If there is a problem (particularly with a filter) don’t scare them. Either mentally set a

plan to resolve it, resolve it immediately or explain that someone will be following up in the next couple of days.

## Who Will Collect the Information?

The most appropriate person to collect the information depends on the type of information and the collection method. It is also important that the people collecting the information can troubleshoot, problem solve and make on the spot improvements. Therefore, their connection to the activities being monitored and their capacity is an advantage in efficiency.

For example: As the biosand filter project starts up it will be easiest and most strategic to use the filter technicians as early on as possible. They would immediately start collecting the information needed to monitor the filter, diffuser and lid construction and sand preparation.

Depending on the size of the operation, it may be the same filter technicians that perform all of the monitoring from production to training to installation. Or it may be different technicians who monitor different activities.

Follow up visits to the households could be designated to Community Health Promoters. They will need to be competent on hygiene, sanitation and the operation and maintenance of the biosand filter. This will allow them to collect the information, as well as problem solve and make recommendations during their visits. The information collected during the household visits provides very important information for trend analysis and improvements to implementation processes.

Refer to Table 6.4.1 below for a complete list of roles and responsibilities.

Table 6.4.1: Definition of Monitoring Roles and Responsibilities

| Monitoring Roles | Monitoring Responsibilities |
| --- | --- |
| Project Manager | - Support a positive culture for monitoring - Check in with, encourage and mentor staff regularly - Review the monitoring plan regularly - Allocate resources appropriately - Support supervisors and review reports regularly |
| Supervisors | - Check in with, encourage and mentor staff regularly - Review the monitoring plan regularly - Look for large scale problems in long term trends - Present problems, resolutions and improvements to management - Participate in review and decision making processes |
| Trainers | - Train how to fill in the forms - Train how to ask questions in a way that doesn’t influence the answer - Conduct analysis, resolve problems and make improvements - Submit completed forms to data management team - Participate in review and decision making processes - Train end users in monitoring activities to be able to hand over the activities at project end |
| Technicians | - Record relevant information during production, installation, end user training, and post-installation follow up visits - Conduct analysis, resolve problems and make improvements - Communicate larger problems with team and supervisor - Submit completed forms to data management team, including actions made - Participate in review and decision making processes |
| Community Health Promoters (CHP) | - Interview and observe end users - Record relevant information during household visits - Conduct analysis, resolve problems and make improvements - Reeducate end users as required - Submit completed forms to data management team, including actions made - Participate in review and decision making processes |
| Data Management Team | - Organize and input completed forms - Analyze group and long term trends - Report on trends needing resolution - Track improvements made - Document process changes - Prepare reports for management - Participate in review and decision making processes |
| End Users | - Provide feedback to technicians and CHPs on technology and effectiveness of training sessions - Help and participate with monitoring activities to have capacity to take over at project end |

## When Should the Information be Collected?

For monitoring to be effectively integrated into the project, it needs to be part of the daily, weekly, and monthly operations plan. Scheduled time dedicated to monitoring will ensure the success of monitoring and therefore the project. As part of the planning process, the organization should create a schedule to fit in monitoring with the project activities. This will depend on the amount of staff that are involved, what the activities are, and how much time is needed to fulfill the responsibilities.

For example, Table 6.5.1 shows daily activities and monitoring for BSF Technicians who are producing filter boxes, preparing sand, building diffusers and lids.

Table 6.5.1: Example Daily Monitoring Schedule

| Time | Production Activities | Monitoring Activities |
| --- | --- | --- |
| 8:00 – 8:30am | Team meeting to discuss activities of the day. | Discuss possible solutions to problems that were identified the day before. |
| 8:30 – 10:30am | Demold filters and set to cure |  |
| 10:30 – 10:45am |  | Record observations of new filter boxes – filter number, leaks, date, etc. |
| 10:45 – 11:30am |  | Record observations of filter boxes that have cured for 7 days – fixed leaks, standing water level, flow rate when empty, ready for installation If problems are identified, then they are resolved on the spot if possible and noted to discuss during the following day team meeting |
| 12:30 – 2:30pm | Prepare molds and concrete, pour filters |  |
| 2:30 – 4:30pm | Alternate between sand sieving, sand washing or building diffusers or lids |  |
| 4:30 – 5:00pm |  | Sand sieve analysis or trial installation; record data into Sand Production Site or Lid and Diffuser Production forms |

As represented in the table above, monitoring activities are incorporated into the daily activities to make it easier for the BSF Technicians who are collecting the information.

Community Health Promoters

The following Table 6.5.2 shows what a weekly monitoring schedule could look like for BSF Technicians.

Table 6.5.2: Example Weekly Monitoring Schedule

| Day | Production and Monitoring Activities |
| --- | --- |
| 1 | Team meeting to discuss activities for the week and problems that were previously identified, filter production, sand preparation, diffuser and lid building with daily monitoring activities |
| 2 | Filter production, sand preparation, diffuser and lid building with daily monitoring activities |
| 3 | End user training day and installation preparations |
| 4 | Filter installation day |
| 5 | Post-installation visits and troubleshooting, prepare results for the Day 1 team meeting |

## How Will the Information be Managed?

Once information is collected it needs to be managed so that it can be used to fix problems and guide improvements. The information has to get to the right people in the right way. For example, once a Community Health Promoter (CHP) has done their follow up visits and filled in the forms, who needs to know that information and how does it get to them?

Information management is very project specific and needs to be developed by the stakeholders of the project. During this process it is important to consider:

- Who needs to be in the loop

- How they will be in the loop

- The logistics involved in each transfer of information

- How to make it as easy as possible.

Figure 6.6.1: Possible Flow of Information After Collection For Input and Analysis

Technicians

Data Management Team

Supervisors

Project Manager

Aqua Clara International (ACI), a biosand filter implementer in Kenya has developed a monitoring system that works for them. In this feedback loop, there are:

  - ACI staff who support the production and follow up processes

  - Community Health Promoters that are community members receiving a stipend for when they deliver training or do household visits

  - Entrepreneurial BSF technicians that are contracted to build and install the filters

Once a month, ACI staff will host a meeting with the CHPs working in the area. At each meeting the CHPs will give the ACI staff the monitoring forms they completed during the household visits, discuss successes and any problems that came up in the last month. The CHPs then receive new forms and a list of households that need a follow up visit from them.

The ACI staff brings the completed forms back to the office for review, input and analysis. If any problems (individual or group trend) are found, the information is passed on to the relevant persons. This process proved itself when for a period the CHPs were finding that the flow rate of many filters was too high.

This information was taken to the monthly BSF Technician meeting where ACI staff were able to do some re-education and discuss with the technicians how they were going to resolve the problem and improve their processes of sand washing. (The sand is pre- sieved for them by ACI.) See Figure 4.3.3 for Aqua Clara’s example flow of information.

Figure 6.6.2: Aqua Clara International Information Flow

Community Health Promoters hand in monitoring forms to ACI and discuss problems they noted.

ACI Monitoring Staff review, input and analyze the information.

BSF Technicians are informed when problems have been found and there is a discussion to fix the problems and process and capacity improvements made.

## Consider the Human Factor

Monitoring cannot be separated from issues of power, competition of resources or control over them.

(Morgan, 1997)

Even if the implementing organization has planned their monitoring as an opportunity for growth and improvement, monitoring checks in on activities and capacities of the individuals involved; and it can become very personal. People are proud and fear judgement.

Therefore, there are a number of human factors to consider that could, if ignored, very easily complicate the best of monitoring plans.

- Social and cultural practices and beliefs

“Where we have tried on a simple basis we find it hard to obtain trustworthy data because of the cultural screen that usually exists between questioner – even one from the project country – and the interviewee. There is a general inclination in these circumstances for interviewees to give positive answers [regardless if it is true or not]”.

(Safe Water International, 2011)

Understanding the local social and cultural context is very important when designing a project, as well as monitoring. Particularly with HWTS and sanitation, the project is designed around accessing locations that, for many, is kept very private. To enter into a home is a delicate matter, but to enter someone’s home with the hope to change how the home operates is even more delicate and challenging. As an organization, here are a few questions to discuss:

  - Are relationships required before the business of water and sanitation can be addressed or can the business start immediately? While planning it is important to find out what is acceptable and the customs for visiting someone’s home.

  - What are the general roles in the family structure? This is important to understand to make sure that you are training those that will actually be operating and maintaining the biosand filter or having an influence on the WASH practices of the household.

  - What cultural and social challenges does the local staff anticipate in monitoring biosand filters and WASH practices? Local knowledge is the greatest resource to use. Keeping these considerations in mind during the planning and implementation will likely prevent major problems along the way.

- Attitude and feeling of staff

Monitoring biosand filter projects checks in with processes and staff capacity to implement them. If it is set up to be judgemental, instead of an opportunity for learning and capacity building, then the staff will perform the monitoring activities with a different mind-set. Here are a few possible situations to consider:

  - Does the staff feel that they will be supported and encouraged to improve when they find problems? If so, they will more likely report the real findings. But, if they feel that they may get in trouble or possibly lose their job, they will more likely report the findings that make it look as if everything is fine when it actually isn’t. The real tragedy in this case is that the end users suffer the consequence.

  - Does the staff feel they are collecting information for a purpose? If there is no follow up to resolve problems, they may feel frustrated about wasting their time. If the problems aren’t solved then they can also lose face or their reputation with the end users.

  - Are the staff asking the end users or other staff questions in a non-judgemental, unbiased and supportive way? How questions are asked has a significant impact on how questions are answered. Practicing with those that are collecting the information is important to collect information that is unbiased and maintains reliability of the information collected.

During monitoring it is important to check in with the staff on a regular basis to determine their attitude towards the system. This is just as, if not more, important than checking if the forms are working.

- Attitude and feeling of respondents

It can also be a challenge to determine if the information end users are providing is accurate and honest. Here are a few questions to consider:

  - What is the reputation of other development organizations in the community?

  - Is there cultural pressure to tell you what they think you want to hear?

  - Do they feel supported after providing the information? If not, they may feel it is a waste of their time.

- Resources, training and mentoring

Implementing a biosand filter project is about building filters and installing them into households, but more importantly it is about building the people involved, from staff to end users. When planning for monitoring it is important to first determine what capacities will be required and what the gaps are. The following questions should be considered:

  - What training will be required to fill the gap in capacities?

  - What will mentorship look like after the training?

  - What resources (e.g. time, money, materials) will be required?

  - How much extra time should be added in case some of the staff require more support than anticipated?

  - How will you choose or hire the monitoring staff?

Key Messages:

- All information will be analyzed to identify problems

- Information can be analyzed as single pieces of information or combined in groups to show a group trend

- Group trends can be compared over time to notice long term trends

Once identified, the problems must be resolved and improvements made

Stage 5 ANALYSIS:

What conclusions can be made from the information collected?

Analyzing and Making Improvements

After collecting information, the next stages are to determine how the information is to be analyzed, and how improvements will be made to fix existing problems and avoid the same problems in the future.

Analysis is:

- Clarifying the information collected

- Understanding connections within the information about the project’s activities

- Arriving at conclusions as to the success of the activity or the need for improvement

Figure 7.1: Stage 5 and 6 in Developing a Monitoring Plan

INFORMATION COLLECTION:

Methods and logistics

COMMUNICATION:

How, how often and to whom are the results communicated?

Stage 6

IMPROVEMENTS:

How can problems be fixed?

How can processes be improved to avoid the same problems in the future?

1. Guide household through the swirl and dump procedure.

2. Retest the flow rate.

IMPROVEMENTS:

How can problems be fixed?

How can processes be improved to avoid the same problems in the future?

In monitoring, when someone looks at the information collected they can analyze it to come to a conclusion as to whether it is a problem or not. If something is a problem, then they can try to figure out why it is a problem or what caused it and what can be done to resolve it. Follow the example below in Figure 1.5.2.

Figure 7.2: Analyzing and Making Improvements for Flow Rate

- 150 mL/min Too slow for the

household

Flow rate

(< 400 mL/min)

ANALYSIS:

What conclusions can be made from the information collected?

It could be slow because of sediment built up on the top layer of sand.

3. If improved, ask household to show their source water to determine turbidity.

4. Discuss with household sedimentation options and why it is important to do so.

5. If not improved, request

technician follow up.

6. Make note of the actions taken. If frequent, tell supervisor.

## Situational Analysis

There are two main ways that the information can be used after it is collected:

- As information for an individual situation (i.e. a household, a specific filter, a specific batch of sand)

- As a collection of information that together communicates a trend (i.e. group of filters, group of households, multiple batches of sand)

Individual information is the information that indicates a success or a problem in a specific situation. It is like a snapshot in time of that one particular situation. When a problem is identified by an individual piece of information it is important to do the process of analysis, resolving the problem and improving before it becomes worse or causes other problems. They are like little fires that need to be put out along the way.

The problem can often be addressed at the time of collection. For example, a CHP doing a household visit finds out that the household only uses the filter every other day (Figure 1.4.3). The CHP can train the end users on the importance of using the filter at least once a day at that moment.

Figure 7.1.1: Situational Analysis of a Specific Filter

Used once a day?

The problem might have to be followed up at a later time. For example, a CHP determines that the flow rate is too fast (Figure 1.4.4). This is perhaps a problem that the CHP cannot resolve at the time and requests a technician to follow up and resolve the problem.

Figure 7.1.2: Situational Analysis of a Specific Filter

- 600 mL/min Too fast

Flow rate

(< 400 mL/min)

CHP notes down actions taken.

CHP can follow up with the household on the next visit by looking at the container and asking how it is going with their commitment.

Example 1: Situational Information Management – On the Spot

CHP notices and notes down the storage container is acceptable, but not clean.

| Storage container is acceptable and clean |  |
| --- | --- |

While they are there, the CHP mentors the household to use soap and safe water to clean it.

CHP asks the household how often they can commit to washing the storage container.

Household commits to 1/week and the CHP notes it down on the form.

FIXING THE PROBLEM	IMPROVING

CHP asks the household why it would be important to keep it clean. Household explains or CHP re-educates.

Demonstrated how to clean with soap and safe water. Will now wash once a week.

Cleaning Storage Container

Example 2: Situational Information Management - Follow Up

CHP notices and notes down the standing water level at 2 cm.

Standing water level 5 cm

5 cm

- 2 cm

The CHP has been taught that with this particular type of problem to pass the information on to the organization as soon as possible.

Key information about which filters need what problems resolved is passed on to the follow-up technicians.

Technicians organize Repair Day activities to include visits to resolve the problem filters.

During the visit, technicians find out that they have to remove some of the sand that was originally installed.

They caution the household that because some of the top biolayer has been removed to make sure they disinfect the water before drinking it for at least a week.

The technicians emphasize to the end users to call the number on their filter or tell the CHP on their next visit if problems continue.

FIXING THE PROBLEM

## Group Trends

If problems are only reviewed individually, a larger underlying problem may be missed. Therefore, it is important to determine trends in all the information collected. This is where individual pieces of information are tallied, organized and used to see a larger picture of what is going on, like a series of pictures put together and made into a movie to create a complete story.

Before trends can be analyzed, the information collected needs to be put into a format that is easy to see as a whole, otherwise it is just individual pieces of information. There are a few options for formats and methods of how to present the results.

- Tallying Information

if YES if NO

The first step is to use tally sheets where someone marks the information from the monitoring forms to a tally sheet and then counts the numbers up.

Figure 7.2.1: Operating Conditions Tally Sheet

Dates: 		Name of Recorder:

| Form # | Standing Water Level | Flow Rate | Daily Use | Diffuser |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| … |  |  |  |  |
| Total |  |  |  |  |
| % |  |  |  |  |

For example, by tallying the number of flow rates that are acceptable and unacceptable, it is easier to note what is happening for the whole group of filters. The amount of filters that have unacceptable flow rates requires a bigger discussion to determine why and what can be done to prevent this trend from both continuing with other filters.

- Graphing

Next, the tallied information can be graphed to visually show a trend of the information compared to other groups or to the baseline and target.

Figure 7.2.2: Trend Information for a Group of Filters

Biosand Filter Key Operating Parameters

% Filters

100

90

80

70

60

50

40

30

20

10

0

Acceptable

Key Operating Parameters

Comparisons can be made between collection periods to view long term trends. Section 7.3 will discuss long term trends in more detail.

- Analysis

Analysis involves coming to conclusions about what the information is saying about the success of an activity. When determining what the problem is and, how to resolve it, it is important to determine whether it is the process or the capacity that is affecting success. The key questions to ask are:

  - To what extent is the problem caused by how the activity is being done?

  - To what extent is the problem caused by the capacity of the person doing the activity?

  - To what extent is the problem caused by for reasons out of the scope of the project?

For example, if the filters bodies are cracked, perhaps the concrete mixture is not appropriate, or perhaps the technicians are not pouring the concrete correctly. By reviewing both process and capacity will ensure a better product in the end.

- Improvements are done a various levels and include fixing problems or making systematic changes to processes and capacity. They can be done at the time of situational analysis or after a review of the trend analysis. It is important that improvements are carried out quickly to fix what is not working, and to prevent the problem from getting worse, further problems arising, or end users to stop using the technology.

Fixing problems is best done as efficiently as possible once it has been identified. So, training the people collecting information to analyze and fix problems on the spot is strategic. Problems that can’t be resolved on the spot must be followed up with at a later time. Determining how that will be coordinated and who will do the follow up is part of integrating monitoring into project activities.

Regardless of whether it is a small problem or a big problem, every problem is an opportunity for learning. Identifying and fixing problems are opportunities for education or reemphasizing key ideas, regardless of whether it is a situational problem or a trend and whether the cause was due to process or capacity.

Making process and capacity improvements can range from simple to complex. It may require minor adjustments or major changes in how things are done or in the depth of training and mentorship needed. For example: A CHP helping a household reorganize space for a hand washing stand to reorganizing a sand preparation site to stop cross contamination of the gravel and sand. Decisions on the scale of improvements can be made by an individual or require input and approval from the team and/or supervisor. Determining these processes will also have to be determined by the organization.

Clean Water for Haiti, Haiti has the following system of organizing filter repairs that need

to be followed up on:

- On the Filter Follow Up form there is a section for ‘repairs’.

- During data input, if a filter is designated for repair, this filter is written up on the Filter Repairs form and put into a folder.

- At the beginning of the week, the Repair folder is reviewed and a group of filters are chosen for repair in a similar geographic area. The aim is to repair 10-12 filters in a day.

- Once the filters are identified, the staff call the filter owners to let them know which day the visit will be scheduled.

- The truck is prepared with everything needed to make the repairs.

- Often a few extra filters and all its components are included in the truck just in case

they need to change the filter.

See the following examples for analysis, identifying problems and suggested improvements.

Example 1: Group Trend Information Management

Data management staff tallies information to look for trends.

Standing Water Level - Visit 1

60

50

40

Percentage (%) 30

20

10

0

Less than 5 cm

More Than 5 cms 5 cms

Standing Water Level

Key Operating Parameters

Technicians and supervisor discuss why too much sand is being installed.

Because transportation is a problem, they decide as a team that they will return to those filters the next day (Day 5) to check the standing water level and make final adjustments.

Supervisor checks in with technician and CHP team to hear how the repairs went on the identified problem filters.

FIXING THE PROBLEM	IMPROVING

The tally below was highlighted as a possible problem since 9/20 or 45% of the filters have unacceptable standing water levels.

They figure out that they weren’t waiting to see what the standing water level was for the filters installed in the afternoon because their transportation was under pressure to be getting them back to the office.

During the next day of installations in the afternoon, they explain to the household that the filter is not to be used until they return to finish the installation process the next day.

Data management staff tallies the information and graphs to look for trends.

Storage Container - Visit 1

80

70

60

50

Percentage (%) 40

30

20

10

0

Unacceptable

Acceptable

Storage Type	Storage Clean

Key Operating Parameters

The tally below was highlighted as a possible problem since 68% of the storage containers were unacceptable and 62% are dirty.

Trainers and supervisor discuss how storage container maintenance is taught during

They figure out that even though the topic is supposed to be covered during both trainings, sometimes the trainers run out of time and don’t train on it.

The teams discuss three possible solutions: 1) Better time management to make sure it is covered; 2) Remove non-essential topics from the training program; 3) Train the end users during installation while they wait for the water to pass through the filter.

As a group they decide that it makes more sense to do the training during installation so that more people in the household will know about keeping it clean and why.

Supervisor checks in with CHP team to hear how the households are now maintaining the storage containers.

Example 2: Group Trend Information Management

###### FIXING THE PROBLEM	IMPROVING

## Long Term Trends

Information that is collected over time can be compared to the baseline information collected previously. By keeping track of trends over time it is possible to see the effect of success. If in each time period there are improvements made, then hopefully there is an improvement in the success over time as well. Looking at a long term trend will help to identify if the improvements have been effective or perhaps it will identify that there is an external influence causing problems. This accumulation of information is also useful for reporting to stakeholders and donors.

To present long term trends it is easiest to create either a bar graph (Figure 7.3.1) or line graph (Figure 7.3.2).

Figure 7.3.1: Bar Graph of Community X Long Term Flow Rate Trend

Percentage (%)

100

90

80

70

60

50

40

30

20

10

0

Fast Flow

Slow Flow Normal Flow

Visit 1	Visit 2	Visit 3	Visit 4

Post Installation Flow Rate

Figure 7.3.2: Line Graph of Community X Long Term Flow Rate Trend

Percentage (%)

100

90

80

70

60

50

40

30

20

10

0

Fast Flow

Slow Flow Normal Flow

Visit 1	Visit 2	Visit 3	Visit 4

Post Installation Flow Rate

As represented in both graphs above, the fast and slow flowing filters decreased over time and there was a marked increase in the number of filters that had normal flow rates. If an organization saw this they would know that processes are working to have more filters operating properly with appropriate flow rates. It would also indicate that there is still work to do if their target was to have 100% appropriate flow rates.

It is important to input this information as it is collected to be sure to address the problems that come up at that time. Waiting a year to the do long term trend analysis might be too long and several problems could have been noticed and fixed earlier. For example, comparing Visit 2 to Visit 3 information could possibly show that some problems needed to be resolved. When the Visit 4 information is collected the same thing will need to be done.

Example 1: Long Term Trend Management

Data management staff tallies the information each quarter as it becomes available and inputs the tally into the graph. At each quarter the trend can be analyzed and resolutions and improvements can be made.

By the end of the year, the information is in a format to see the long term trend, as shown in Figure 7.3.3.

Figure 7.3.3: Community Y Long Term Flow Rate Trend

80

70

60

50

Percentage (%) 40

30

20

Fast Flow

Slow Flow Normal Flow

10

0

Visit 1

Visit 2

Visit 3

Visit 4

Month of Monitoring Visit

The graph shows that the fast and slow flowing filters have stayed at high levels over time and there was a decrease in the number of filters that had normal flow rates. When the results are unacceptable in a long term trend, the analysis is more complex as there are more factors involved at this time in the project. It will require discussing the various factors with the team to determine what the underlying issue is and how to fix it. See Table 7.3.1 below for example factors and conclusions.

Table 7.3.1: Factors to Discuss and Example Conclusions for Community Y

| Factor | Example Conclusions |
| --- | --- |
| What has been already done to resolve the problem? | - Reinstall or trade some existing sand for fine sand to fast flowing filters - Re-educate end users on swirl and dump for plugged filters - Promote sedimentation during rainy season |
| What improvements were already made? | - Do sand sieve analysis every day - Do test installation with each new batch of sand - Ensure flow rate testing is done properly - Ensure swirl and dump is taught and taught properly |
| What outside factors could be influencing the results? | - Dry season for first 6 months of filter use so source water was clear - Rainy season started and the source water became turbid |
| What could be causing the problem to continue? | - Not enough follow up on the importance of sedimentation during the rainy season - Inadequate end user training on swirl and dump - Sand not washed enough |

Based on the discussion from the factors and conclusions above, the following analysis could occur:

Example Analysis:

FAST Flow	SLOW Flow	NORMAL Flow

Decreases after the first visit which means the filters were resolved as planned. There were just a few left to go back and do again.

The number was initially high. With more education on swirl and dump the number was reduced. But then the rains started, the water was more turbid and the filters were blocked. More education was needed.

Mirror of the slow flow numbers. The numbers got better, but then fell off again with the rainy season. The numbers are getting better, but still are not reaching the targets of 100% normal.

# Communication

Key Messages:

- Communication is essential to successful monitoring

- Communication must flow smoothly between all roles

- Communication format is determined by the audience and the type of information

- A communication plan must be developed by the organization

Communication is essential to successful monitoring.

“The main challenge is maintaining [monitoring] and having data that can be fed back into the operations. Often tons of data is gathered but never fed back or fed back too late. To ensure the findings are shared and operations adapted, the monitoring team should be in frequent communication with 1) Production team, 2) Training team and 3) Project management.”

(Personal communication, O. Mills, CAWST)

Information must be communicated to the right people so that the key stakeholders involved are up to date. Communication management should be discussed regularly within the organization. Part of the discussion is to determine: Who? When? How? How often? To who?

Communication is more than writing a report and handing it over to management.

Communication is sharing what was learned so that problems can be resolved and then sharing the results of those efforts. It is also about sharing the successes of a project to keep everyone motivated about the work. Supportive management and donors want to know when things are going right and also when they are going wrong. If they went wrong, what was done about it and how it is going at present?

There are a number of important details to include in communications.

- What were the problems identified

- How the problems need to be resolved

- When the problems have been resolved

- What improvements need to be carried out or have been carried out

Communications can be written or verbal, detailed or an overview of the key points. It depends on who is delivering the information and who the receiving audience is. It is important in communications to include project management and end users, not just those directly involved in the monitoring activities.

Figure 8.1 shows the flow of information between stakeholders once the information has been collected.

Community Health Promoters

Data Management Team

Supervisors

Trainers

Technicians

Project Manager

End Users

Figure 8.1: Possible Communication Flow of Collected Information and Actions

Community Health Promoters

Figure 8.2 shows all stakeholders that can be included once problems have been identified and/or resolved, all the way back to the end users.

Data Management Team

Trainers

Technicians

Project Manager

End Users

Supervisors

Figure 8.2: Possible Communication Flow of Trend Results and Actions

# Timeline and Growth

Key Messages:

- Monitoring is a set of processes and capacities that can be adjusted to meet the changing needs of the project

Monitoring needs to grow proportionally with the project. If monitoring starts with the project it must grow as the project moves towards being fully operational. This is also the case if the project decides to scale up, for example if a project grows from installing 500 filters to 8,000 filters in a year.

With natural project growth and scale up here are a few things to consider:

- Review what monitoring is tracking as some questions become less relevant over time

- Anticipate resource needs by mapping out growth (See Table 9.1 and 9.2)

Table 9.1 below is a project working towards being fully operational. The organization proposed to do a 1 month post installation follow up visits and 4 WASH follow up visits. As it progresses to being fully operational, the number of visits increases from 0 to 200 visits per month.

Table 9.2 is based on Clean Water for Haiti. They are fully operational at 200 filters per month. The table charts what their growth may have looked like to get to that level. Clean Water for Haiti focuses on filter follow up at 1, 3 and 12 months. This results in an average of 30 visits per day.

To plan for this growth, each organization must anticipate staffing needs, training and mentoring requirements, as well as logistics on how to accomplish the visits and keep it all organized. The more monitoring is integrated as the project grows, the more smoothly it should happen with increased assurance of success.

Table 9.1: Charting Growth and Monitoring Resource Needs – Example 1

| Month | Group of Filters Installed | Post Installation Visit month 1 | WASH Follow Up Visit month 2 | WASH Follow Up Visit month 4 | WASH Follow Up Visit month 6 | WASH Follow Up Visit month 12 | Total Visits in the Month | # Visits per Day (20 days/month) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | A |  |  |  |  |  | 0 |  |
| 2 | B | A |  |  |  |  | 40 | 2 |
| 3 | C | B | A |  |  |  | 80 | 4 |
| 4 | D | C | B |  |  |  | 80 | 4 |
| 5 | E | D | C | A |  |  | 120 | 6 |
| 6 | F | E | D | B |  |  | 120 | 6 |
| 7 | G | F | E | C | A |  | 160 | 8 |
| 8 | H | G | F | D | B |  | 160 | 8 |
| 9 | I | H | G | E | C |  | 160 | 8 |
| 10 | J | I | H | F | D |  | 160 | 8 |
| 11 | K | J | I | G | E |  | 160 | 8 |
| 12 | L | K | J | H | F |  | 160 | 8 |
| 13 | M | L | K | I | G | A | 200 | 10 |
| 14 | N | M | L | J | H | B | 200 | 10 |
| 15 | O | N | M | K | I | C | 200 | 10 |
| 16 | P | O | N | L | J | D | 200 | 10 |
| 17 | Q | P | O | M | K | E | 200 | 10 |
| 18 | R | Q | P | N | L | F | 200 | 10 |

A quick way to check the number of visits necessary is to multiply the number of filters to be installed per month by the number of visits planned per household. (# filters/month X # planned visits = 3 visits needed per month)

Table 9.2: Charting Growth and Monitoring Resource Needs – Example 2

| Month | Group of Filters Installed | Number of Filters in Group | Follow Up Visit 1 (Month 1) | Follow Up Visit 2 (Month 3) | Follow Up Visit 3 (Month 12) | Total Visits in the Month | # Visits per Day (20 days/month) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | A | 100 |  |  |  | 0 |  |
| 2 | B | 100 | A |  |  | 100 | 5 |
| 3 | C | 100 | B | A |  | 200 | 10 |
| 4 | D | 100 | C | B |  | 200 | 10 |
| 5 | E | 100 | D | C | A | 300 | 15 |
| 6 | F | 100 | E | D | B | 300 | 15 |
| 7 | G | 150 | F | E | C | 450 | 23 |
| 8 | H | 150 | G | F | D | 450 | 23 |
| 9 | I | 150 | H | G | E | 450 | 23 |
| 10 | J | 150 | I | H | F | 450 | 23 |
| 11 | K | 150 | J | I | G | 450 | 23 |
| 12 | L | 150 | K | J | H | 450 | 23 |
| 13 | M | 200 | L | K | I | 600 | 30 |
| 14 | N | 200 | M | L | J | 600 | 30 |
| 15 | O | 200 | N | M | K | 600 | 30 |
| 16 | P | 200 | O | N | L | 600 | 30 |
| 17 | Q | 200 | P | O | M | 600 | 30 |
| 18 | R | 200 | Q | P | N | 600 | 30 |

# Summary

- Keep the monitoring plan and scope small and manageable to start

- Be flexible – a plan is not set in stone

- Contact CAWST if you have any questions or need support at cawst@cawst.org

- There are great resources out there – look for them to increase your comfort with the subject

- Finally, just GET STARTED, there will never be a better moment than right now!

# References

Aqua Clara International, 2011. Personal communication.

Indicators: http://www.acdi-cida.gc.ca/acdi-cida/ACDI-CIDA.nsf/eng/NAT-92213444-N2H#perf

Larkin Simon. Introducing Evaluation – Guidelines on Assessment. Tearfund.

Logic Model with Definitions: http://www.acdi- cida.gc.ca/INET/IMAGES.NSF/vLUImages/Results-basedManagement/$file/RBM- LOGIC_MODEL-Def.pdf

Managing for Impact in Rural Development: A guide for project M & E, Section 1, 2001 www.ifad.org

Mills, O., 2011.CAWST. Personal communication.

Monitoring and Evaluations Guidelines, World Food Program http://www.wfp.org/content/monitoring-and-evalutation-guidelines http://documents.wfp.org/stellent/groups/public/documents/ko/mekb_module_7.pdf

Monitoring and Evaluation; RTI International; www.rti.org

Morgan. P., 1997, The Design and Use of Capacity Development Indicators. Hull: Policy Branch, CIDA

Results oriented Monitoring and Evaluation, A Handbook for Program Managers, Chapter 18 OESP UNDP (1997); http://www.undp.org/eo/documents/mae-toc.htm

Rolling, L., 2011. Clean Water for Haiti, Haiti. Personal communication.

Safe Water International, 2011. WHO Monitoring and Evaluation Manual feedback session.

Schuelert, Earwaker, Dow Baker, 2011. A Household Water Treatment Implementation Framework: Lessons Learnt From the Diversity of HWT Implementation Worldwide; WEDC.

Appendix A - CAWST Monitoring Forms

Table of Contents

BSF Production Monitoring Form	A-1

BSF Production: Tips and Guidelines for Use ......................................................................... A-2

Sand Preparation Monitoring Form ......................................................................................... A-3

Sand Preparation:Tips and Guidelines for Use ....................................................................... A-4

Diffuser and Lid Monitoring Form ............................................................................................ A-5

Sand Sieve Analysis Results................................................................................................... A-6

Trial Installation Flow Rate Results ......................................................................................... A-7

Trial Installation: Guidelines and Tips for Use ......................................................................... A-8

BSF Installation Monitoring Form ............................................................................................ A-9

BSF Installation: Tips and Guidelines for Use ....................................................................... A-10

Post Installation Follow Up Form........................................................................................... A-11

if acceptable if unacceptable

Participant Manual Appendix A

#### BSF Production Monitoring Form

##### Location: 		Date:

| Mold Number | Date Poured day/ month | Filter Number | No Leaks After Demolding or | 7 Days of Curing Time or | Filter Box Washed Out or | Empty Flow Rate or | Flow Rate (mL/ minute) | Water Level Below Diffuser or | Filter Ready for Installation or | Comments Or Recommended Actions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |

Technician Signature: 		Supervisor Signature: 		Date:

#### BSF Production: Tips and Guidelines for Use

|  | Mold Number | Date Poured (day/month) | Filter Number | No Leaks After Demolding or | 7 Days of Curing Time or | Filter Box Washed Out or |
| --- | --- | --- | --- | --- | --- | --- |
|  | Need to track in | This can help | This is to help | If there were no | If curing time is | This can help to track |
|  | case there are | identify if there | track a filter to | leaks then the | tracked, it helps to | if the production |
|  | problems with each | were problems | make sure if | processes and | ensure that the | processes are |
|  | of the filters that | with the | problems are | capacity of | necessary 7 days of |  |
| Tips and | comes out of this mold. | concrete that was mixed that | identified later all aspects of | technicians are acceptable. If leaks | curing is respected. |  |
| Guidelines |  | day. | the filters production can | were identified some analysis can be |  |  |
|  |  |  | be reviewed. | done to help |  |  |
|  |  |  |  | determine why and |  |  |
|  |  |  |  | help make |  |  |
|  |  |  |  | improvements. |  |  |

|  | Empty Flow Rate or | Flow Rate (mL/ minute) | Water Level Below Diffuser or | Filter Ready for Installation or | Comments Or Recommended Actions |
| --- | --- | --- | --- | --- | --- |
|  | Water should flow | Recording flow | Ensures that the | Tracks if filters are |  |
|  | freely our of outlet | rate ensures | outlet tube is the | ready to be |  |
| Tips and Guidelines | tube. Tracking empty filter flow rate ensures that | that the flow rate is acceptable. | right length. | delivered and installed. |  |
|  | the flow is free |  |  |  |  |
|  | before installation. |  |  |  |  |

#### Sand Preparation Monitoring Form

##### Form #: 		Location: 		Dates:

Use = acceptable or  = unacceptable

| Sieve Sizes | Sieve Set in Good Condition | Sand/Gravel Sieved Properly | Sieved Sand/Gravel Organics Free (Visual Inspection) | Gravel Washed Clean | Jar Test Result on Filtration Sand | Sand /Gravel Stored Properly | The Sand is Useable | The Gravel is Useable | Additional Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12 mm (½”) |  |  |  |  |  |  |  |  |  |
| 6 mm (¼”) |  |  |  |  |  |  |  |  |  |
| 1 mm (0.04”) |  |  |  |  |  |  |  |  |  |
| 0.7 mm (0.03”) |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |

##### Lead Technician: 		Manager Signature: 	 Date:

#### Sand Preparation:Tips and Guidelines for Use

| Sieve Set in Good Condition | Sand/Gravel Sieved Properly | Sieved Sand/Gravel Organics Free (Visual Inspection) | Gravel Washed Clean |
| --- | --- | --- | --- |
| This is to ensure that the sieve sets are not damaged which would affect the accuracy of sieving. | This refers to organization of sand preparation area. Prevention of cross contamination and size of sand and gravel are appropriate – ie no cross contamination. | To ensure that the prepared sand and gravel is organics free. This is difficult when the sand preparation area is out of doors. | To ensure the gravel is ready for installation. |

| Jar Test Result on Filtration Sand | Sand /Gravel Stored Properly | The Sand is Useable | The Gravel is Useable | Additional Comments |
| --- | --- | --- | --- | --- |
| To compare to trial | Checking in on | Overall, the sand is ready | Overall, the gravel is ready |  |
| installation tests. | processes of bagging | for installation. | for installation. |  |
|  | and storing of |  |  |  |
|  | materials. |  |  |  |

##### Location: 		 Dates:

Use to agree or  to disagree

#### Diffuser and Lid Monitoring Form

##### Location: 		 Dates:

Use to agree or  to disagree

| Lids Built Properly |  |
| --- | --- |
| Lids Fit Properly |  |
| Diffusers Fit Properly |  |
| Diffuser holes = 3 mm or less |  |
| Diffuser holes = 2.5 cm Spacing |  |

| Lids Built Properly |  |
| --- | --- |
| Lids Fit Properly |  |
| Diffusers Fit Properly |  |
| Diffuser holes = 3 mm or less |  |
| Diffuser holes = 2.5 cm Spacing |  |

Recommended actions to improve:

##### Lead Technician: 		 Supervisor Signature: 			 Date:

Recommended actions to improve:

##### Lead Technician: 		 Supervisor Signature: 			 Date:

#### Sand Sieve Analysis Results

| Test # | Test Date | Sand Source Location | Uniformity Coefficient (1.5-2.5) | Effective Size (0.15-0.20 mm) | Acceptable or | Action if Unacceptable? |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |

Technician Name: 		Supervisor Signature: 		Date:

#### Trial Installation Flow Rate Results

| Test # | Test Date | Sand Source | Delivery Date (Day/Month) | Number of Washes on Filtration Sand | Jar Test Result or | Test Installation Flow Rate (mL/min) | Flow Rate Result or |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |

Technician Name: 		Supervisor Signature: 		Date:

#### Trial Installation: Guidelines and Tips for Use

| Sand Source | Delivery Date (Day/Month) | Number of Washes on Filtration Sand | Jar Test Result or | Test Installation Flow Rate (mL/min) | Flow Rate Result or |
| --- | --- | --- | --- | --- | --- |
| To track where the | When it was | Tracking for finding | Indicate here | Trial installation to | Was the flow rate |
| sand came from. | delivered helps to | average of washes. | whether or not the | compare to jar test | acceptable? |
|  | know which batch | Helps to determine # | sand was jar tested | and other sand |  |
|  | the sand came in | of washes for | and if it was | parameters. |  |
|  | with. | appropriate jar | acceptable. This is |  |  |
|  |  | testing. | for comparison to |  |  |
|  |  |  | the trial installation. |  |  |
|  |  |  | If the jar test was |  |  |
|  |  |  | positive, but the |  |  |
|  |  |  | trial installation is |  |  |
|  |  |  | rejected then some |  |  |
|  |  |  | investigation needs |  |  |
|  |  |  | to happen to |  |  |
|  |  |  | determine why. |  |  |

if acceptable if unacceptable

BSF Installation Monitoring Form

__

Technician Name: 		Location: 		Date:

| Date Installed (day/ month) | Filter Number | Name of Household | Address and Phone Number of Household | Filter Location in House | Flow Rate (mL/ minute) | Flow Rate Acceptable or | Standing Water Level = 5 cm or | Problems Unresolvable at Install or | Swirl and Dump Demo (Tech, HH) or | # of Sand Sets Rejected |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL |  |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |

##### Technician Signature: 		Supervisor Signature: 		Date:

#### BSF Installation: Tips and Guidelines for Use

|  | Date Installed (day/ month) | Filter Number | Name of Household | Address and Phone Number of Household | Filter Location in House | Flow Rate (mL/ minute) |
| --- | --- | --- | --- | --- | --- | --- |
| Tips and Guidelines |  |  | Or name of key person who will be responsible for the filter | Or a general description of where the house is if it has no specified address. Or a note of how to best reach someone. | Important is case it has been moved and experiences problems after the move | Important to know exactly what the flow rate is for reference. |

|  | Flow Rate Acceptable or | Standing Water Level = 5 cm or | Problems Unresolvable at Install or | Swirl and Dump Demo or | # of Sand Sets Rejected |
| --- | --- | --- | --- | --- | --- |
| Tips and Guidelines | The acceptable range of flow rates must be determined as an organization. It must be an acceptable flow rate or else must be reinstalled. But this is to reinforce that it must in fact be acceptable at the time of installation. | If it is not at the recommended 5 cm record what it is at and why. | Were there problems that prevented the technicians from signing off on the filter? If so what were they and what was done about it. Installation team should have extra filters and materials but the problems should be noted for the production team | Was the swirl and dump demonstrated to the household by the technician? Did the household then demonstrate it to the technicians? This is a prompt to make sure the household is aware of how to maintain the filter if it gets plugged up. | If the flow rate is unacceptable the filter has to be reinstalled with another set of sand. It is important to track if sand is not appropriate and how many packs of it for the sand preparation team. |

#### Post Installation Follow Up Form

| Name of Technician or Community Health Promoter: |  |
| --- | --- |
| Date of visit: |  |
| Household Name: |  |
| Phone Number: |  |
| House address or Location: |  |
| Filter Number: | How long have you been using the filter? |
| How many people use the filter? | How many times to you pour water into the filter per day? |

| What is the source water that is poured into the filter? |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| OR | River | Open Well | Closed Well | Tap Stand | Pump |
| Besides the biosand filter, what other methods do you use to treat your water? |  |  |  |  |  |
| OR | No Treatment | Settling | Boiling | Chlorine | Other |
| Does anyone in the home suffer from the following? |  |  |  |  |  |
| OR | Diarrhea | Stomach Ache | Skin Infection | Eye Infection | Other |

| Operating Conditions |  |  |  |  |
| --- | --- | --- | --- | --- |
| OR | 5 cms Standing water level = 5 cms | Flow rate (<400 mL/min) | Used once a day? | Diffuser is in good condition |
|  |  | mL/min |  |  |
| OR | Sand is level | Source water is clear | Storage container is clean Type used?? | No leaks |
| End User Competence |  |  |  |  |
| Demo OR | \ Cleaning Filter Box | Swirl and Dump | Cleaning Diffuser | Cleaning Storage Container |
| Demo OR | BSF Operations |  |  |  |

Water, Sanitation and Hygiene (WASH) Follow Up Form

| Name of Community Health Promoter: |  |
| --- | --- |
| Household Name: |  |
| Phone Number: |  |
| House Address or Location: |  |
| Date of Visits: |  |
| Behaviour Now Goal By Next Visit |  |

| Does anyone in the home suffer from the following? |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| OR | Diarrhea | Stomach Ache | Skin Infection | Eye Infection | Other |
| How do you treat your water? |  |  |  |  |  |
| OR | No Treatment | Boiling | SODIS | Chlorine | Biosand Filter |

| How do you store your drinking water? |  |  |  |  |
| --- | --- | --- | --- | --- |
| OR | Protected | Unprotected | Tap | No Tap |
| When do you wash your hands? |  |  |  |  |
| OR | After the Toilet | Before Eating | Before Preparing Food | After Changing a Baby |

| Where do you defecate? |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| OR | Open Defecation | Buried | Dirty Latrine | Clean Latrine | Latrine with Hand Washing |
| How do you prevent disease transmission? |  |  |  |  |  |
| OR | Covered Food | Washing Food | Water Treatment | Use Latrine | Hand Washing |

Appendix B - CAWST Tally Sheets

Table of Contents

BSF Production	B-1

BSF Production Tally Sheet............................................................................................................... B-3

Sand Preparation Tally Sheet ............................................................................................................ B-4

Lid and Diffuser Tally Sheet............................................................................................................... B-5

Sand Sieve Analysis Tally Sheet ....................................................................................................... B-6

Trial Installation Flow Rate Tally Sheet.............................................................................................. B-7

BSF Installation Tally Sheet............................................................................................................... B-8

Post Installation .................................................................................................................................... B-9

Water Sources Tally Sheet .............................................................................................................. B-11

HWT Options Tally Sheet ............................................................................................................... B-12

Health Tally Sheet ........................................................................................................................... B-13

Operating Conditions Tally Sheet .................................................................................................... B-14

End User Competence Tally Sheet.................................................................................................. B-15

Wash Follow Up.................................................................................................................................. B-17

Health Tally Sheet ........................................................................................................................... B-19

HWT Options Tally Sheet ............................................................................................................... B-20

Filtered Water Storage Container Tally Sheet ................................................................................. B-21

Hand Washing Tally Sheet .............................................................................................................. B-22

Sanitation Tally Sheet..................................................................................................................... B-23 Preventing Disease Transmission Tally Sheet ................................................................................ B-24

BSF Production

BSF Production Tally Sheet

Dates: 	 Name of Recorder:	 Supervisor Signature:

| Form # | Total # on Form | No Leaks |  | Curing Time |  | Washed Box |  | Flow Rate |  | Water Level |  | Ready to Install |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |  |  |  |  |  |  |

Sand Preparation Tally Sheet

Dates: 	 Name of Recorder:	 Supervisor Signature:

| Form # | Total # on Form | Condition of Sieve Set |  | Sieved Sand Quality |  | Sieved Sand Organic Free |  | Gravel Washed Clean |  | Sand is Useable |  | Gravel is Useable |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |  |  |  |  |  |  |

Lid and Diffuser Tally Sheet

Dates: 		Name of Recorder:

| Form # | Lids Built Properly | Lids Fit Properly | Diffuser Fits Properly | Diffuser Holes 3mm or less | Diffuser Holes 1” Spacing |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Total |  |  |  |  |  |
| % |  |  |  |  |  |

Sand Sieve Analysis Tally Sheet

Dates: 	 Name of Recorder:	 Supervisor Signature:

| Form # | Total # on Form | Acceptable Sand Sieve Analysis |  |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |
| 6 |  |  |  |
| 7 |  |  |  |
| 8 |  |  |  |
| 9 |  |  |  |
| 10 |  |  |  |
| 11 |  |  |  |
| 12 |  |  |  |
| 13 |  |  |  |
| 14 |  |  |  |
| 15 |  |  |  |
| 16 |  |  |  |
| 17 |  |  |  |
| 18 |  |  |  |
| 19 |  |  |  |
| 20 |  |  |  |
| Totals |  |  |  |
| % |  |  |  |

Trial Installation Flow Rate Tally Sheet

Dates: 	 Name of Recorder:	 Supervisor Signature:

| Form # | Total # on Form | Jar Test |  | Acceptable Flow Rate |  |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Totals |  |  |  |  |  |
| % |  |  |  |  |  |

BSF Installation Tally Sheet

Dates:	Name of Recorder:	Supervisor Signature:

| Form # | Total # on Form | Acceptable Flow Rate |  | Standing Water Level = 5 cm |  | Problems at Installation |  | Swirl and Dump Demonstration |  | # Sand Sets Rejected |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |  |  |  |

Post Installation

if YES

if NO

Water Sources Tally Sheet

Dates: 		Name of Recorder:

| Form # | River | Open Well | Covered Well | Tap Stand | Pump |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Total |  |  |  |  |  |
| % |  |  |  |  |  |

if YES

if NO

HWT Options Tally Sheet

Dates: 		Name of Recorder:

| Form # | No Treatment | Settling | Boiling | Chlorination | Other |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Total |  |  |  |  |  |
| % |  |  |  |  |  |

|  |  |  |  |  |  | if YES if NO |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Form # | Diarrhea | Stomach Ache | Skin Infection | Eye Infection | Other |  |  |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |

Health Tally Sheet

Dates: 		Name of Recorder:

| Monitoring Biosand Filter Projects Operating Conditions Tally Sheet Dates: Name of Recorder: |  |  |  |  |  |  |  |  | if YES if NO |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Form # | Standing Water Level | Flow Rate | Daily Use | Diffuser | Sand Level | Turbidity | Storage Type | Storage Clean |  | Leaks |  |
| 1 |  |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  | if YES if NO |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Survey # | BSF Operations | Swirl and Dump | Diffuser Cleaning | Storage Cleaning | Filter Box Cleaning |  |  |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |

Monitoring Biosand Filter Projects End User Competence Tally Sheet

Dates: 		Name of Recorder:

Wash Follow Up

if YES if NO

Monitoring Biosand Filter Projects

Health Tally Sheet

Dates: 		Name of Recorder:

| Form # | Diarrhea | Stomach Ache | Skin Infection | Eye Infection | Other |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Total |  |  |  |  |  |
| % |  |  |  |  |  |

if YES

if NO

Monitoring Biosand Filter Projects

HWT Options Tally Sheet

Dates: 		Name of Recorder:

| Form # | No Treatment | Settling | Boiling | Chlorination | Biosand Filter |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
| 6 |  |  |  |  |  |
| 7 |  |  |  |  |  |
| 8 |  |  |  |  |  |
| 9 |  |  |  |  |  |
| 10 |  |  |  |  |  |
| 11 |  |  |  |  |  |
| 12 |  |  |  |  |  |
| 13 |  |  |  |  |  |
| 14 |  |  |  |  |  |
| 15 |  |  |  |  |  |
| 16 |  |  |  |  |  |
| 17 |  |  |  |  |  |
| 18 |  |  |  |  |  |
| 19 |  |  |  |  |  |
| 20 |  |  |  |  |  |
| Total |  |  |  |  |  |
| % |  |  |  |  |  |

if YES

if NO

Filtered Water Storage Container Tally Sheet

Dates: 		Name of Recorder:

| Form # | Protected | Unprotected | Tap | No Tap |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| 8 |  |  |  |  |
| 9 |  |  |  |  |
| 10 |  |  |  |  |
| 11 |  |  |  |  |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |
| 15 |  |  |  |  |
| 16 |  |  |  |  |
| 17 |  |  |  |  |
| 18 |  |  |  |  |
| 19 |  |  |  |  |
| 20 |  |  |  |  |
| Total |  |  |  |  |
| % |  |  |  |  |

if YES

if NO

Hand Washing Tally Sheet

Dates: 		Name of Recorder:

| Form # | After the Toilet | Before Eating | Before Preparing Food | After Changing a Baby |
| --- | --- | --- | --- | --- |
| 1 |  |  |  |  |
| 2 |  |  |  |  |
| 3 |  |  |  |  |
| 4 |  |  |  |  |
| 5 |  |  |  |  |
| 6 |  |  |  |  |
| 7 |  |  |  |  |
| 8 |  |  |  |  |
| 9 |  |  |  |  |
| 10 |  |  |  |  |
| 11 |  |  |  |  |
| 12 |  |  |  |  |
| 13 |  |  |  |  |
| 14 |  |  |  |  |
| 15 |  |  |  |  |
| 16 |  |  |  |  |
| 17 |  |  |  |  |
| 18 |  |  |  |  |
| 19 |  |  |  |  |
| 20 |  |  |  |  |
| Total |  |  |  |  |
| % |  |  |  |  |

|  |  |  |  |  |  | if YES if NO |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Form # | Open Defecation | Buried | Dirty Latrine | Clean Latrine | Clean Latrine with Hand Washing |  |  |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |

Sanitation Tally Sheet

Dates: 		Name of Recorder:

|  |  |  |  |  |  | if YES if NO |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Form # | Covered Food | Washing Food | Water Treatment | Use Latrine | Hand Washing |  |  |
| 1 |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |
| % |  |  |  |  |  |  |  |

Preventing Disease Transmission Tally Sheet

Dates: 		Name of Recorder:

Appendix C - CAWST Analysis Graphs

Table of Contents

BSF Production Graphs	C-1

Post Installation Follow Up Graphs ......................................................................................... C-3

WASH Follow Up Graphs........................................................................................................ C-6

BSF Production Graphs

Use the following graphs as examples or to input the information collected in the field.

Filter Production

% Filters

100

90

80

70

60

50

40

30

20

10

0

Baseline

Current

No Leaks

Curing

Time

Washed Flow Rate	Water

Box

Filter Features

Level

Ready to

Install

Diffuser and Lid Production

% Acceptable

100

90

80

70

60

50

40

30

20

10

0

Baseline

Current

Lids Built

Properly

Lids Fit	Diffuser Fits  Diffuser

Properly

Properly  Holes 3mm

or less

Diffuser

Hole Spacing 2.5cm

Options

Sand Preparation

100

80

60

Percentage (%)  40

20

0

Baseline

Current

Sieve Set	Sand	Sand

Condition	Quality	Organics

Free

Gravel

Washed Clean

Sand is	Gravel is

Useable	Useable

Parameters for Sand and Gravel

Acceptable Sand Sieve Analysis, Jar Test and Trial

Installation Results

100

90

80

70

60

Montly Percentages

(%)

50

40

30

20

10

0

Analysis

Jar Test

Trial Installation

January

February

Month

March

Installation

120

100

80

Percentage (%)  60

40

Percentage

20

0

Acceptable	Standing	Unresolvable	End User	Sand Sets

Flow Rate	Water Level	Problems

Swirl and

Dump Demo

Rejected

Installation Parameters

Post Installation Follow Up Graphs

Water Source for Filter Use

80

70

60

50

% Households 40

30

20

10

0

Baseline

Current

River	Uncovered	Covered	Tap Stand	Pump

Well	Well

Water Sources

Household Water Treatment Options

100

90

80

70

60

% Households

50

40

30

20

10

0

Baseline

Current

Options

Household Health

80

60

% Households 40

20

Baseline

Current

0

Diarrhea	Stomach

Ache

Skin	Eye Infection

Infection

Other

Health Complaints

Biosand Filter Key Operating Parameters

% Household

100

90

80

70

60

50

40

30

20

10

0

Acceptable

Key Operating Parameters

Biosand Filter End User Competence

90

80

70

60

% Households 40

30

20

10

0

50

Current

Cleaning Filter	Swirl and

Box	Dunp

Cleaning

Diffuser

Cleaning	BSF

Storage	Operations Container

Types of Sanitation

WASH Follow Up Graphs

Household Health

80

60

% Households 40

20

Baseline

Current

0

Diarrhea	Stomach

Ache

Skin	Eye Infection

Infection

Other

Health Complaints

Household Water Treatment Options

100

90

80

70

60

% Households

50

40

30

20

10

0

Baseline

Current

Options

Water Storage Containers

% Households

100

90

80

70

60

50

40

30

20

10

0

Baseline

Current

Uncovered	Covered	No Tap	Tap

Storage Container Features

Level on the Sanitation Ladder

70

60

50

40

% Households

30

20

10

0

Baseline

Current

Open	Buried	Dirty Latrine  Clean Latrine  Latrine with

Defecation	Hand Washing

Types of Sanitation

Key Times to Wash Hands

70

60

50

40

% Households

30

20

Baseline

Current

10

0

After the Toilet	Before Eating Before Preparing After Changing

Food	Babies

Hand Washing

Prevention of Disease Transmission Methods

70

60

50

40

% Households

30

20

10

0

Baseline

Current

Covered Food Washing Food	Water	Use Latrine  Hand Washing

Treatment

Prevention Method

Appendix D - Field Example Monitoring Forms

Fom Enstalasyon & Vizit

# kay :

Dat enstalasyon : (j/m/a) 		/	/		Met kay la : 		 Zòn : 	 Lokalite : 			 # Telefon :

Comment 1

and 2

Direksyon pou jwenn kay la :

Teknisyen : 	 Vitès : 	Ml/min Tib la dezenfekte, tout bagay fini : □

;

Vizit #1 (1 mwa)

Dat vizit : (j/m/a) 	/	/	 Teknisyen : 	 Vitès : 	 Ml/min (avan) 	 (apre)

Comment 3

Ou te tchecke : □ kouveti	□ boite filtè □plak difusyon □ nivo sab □ tube

Kondisyon filtè :

Si li bezwen ranje/remplace:

Comment 4

Dat filtè te ranjè/remplase: 	/	/	 Teknisyen: 	 Vitès: 	Ml/min

;

Vizit #2 (3 mwa)

Dat vizit : (j/m/a) 	/	/	 Teknisyen : 	 Vitès : 	 Ml/min (avan) 	 (apre)

Ou te tchecke : □ kouveti	□ boite filtè □plak difusyon □ nivo sab □ tube

Comment 5

Kondisyon filtè :

Si li bezwen ranje/remplace:

Dat filtè te ranjè/remplase: 	/	/	 Teknisyen: 	 Vitès: 	Ml/min

;

Vizit #3 (1 anè)

Dat vizit : (j/m/a) 	/	/	 Teknisyen : 	 Vitès : 	 Ml/min (avan) 	 (apre)

Comment 6

Ou te tchecke : □ kouveti	□ boite filtè □plak difusyon □ nivo sab □ tube

Kondisyon filtè :

Si li bezwen ranje/remplace:

Dat filtè te ranjè/remplase: 	/	/	 Teknisyen: 	 Vitès: 	Ml/min

Clean Water for Haiti, Pierre Payen, Haiti, 2011.

Comment 1

We designate a number for each filter. We prefer to use a system with the year, month, date, then filter number starting at 01. Eg. 11090203 would be a filter installed in 2011, in the month of September, on the 2nd

(02) and the 3rd (03) installed for that day. All filters installed in a delivery are then stapled together into a package for filing.

Comment 2

All of this info is collected on the initial installation day.

Comment 3

First follow up visit happens at one month after installation and all of this info is collected. If a filter needs repairs, needs more sand, diffusion

plate is broken etc, that’s indicated. When I enter the info into the data base I’ll use the repair sheet to indicate which filters need attention from the batch.

Comment 4

If a filter needs repairs it’s visited again, the work is done and then it’s

indicated here.

Comment 5

Second visit happens at 3 months after installation. Same process as before with repairs etc.

Comment 6

Third visit happens at one year after installation. If a filter has no issues at this point and the users understand the education we don’t see a need to continue visiting.

#### Filter Ki Bezwen Ranje/Remplasment

| # Filte | Pwoblem | Zon | Lokalite | Met filte | # Telefon | Fini |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |

#### Filter Ki Bezwen Ranje/Remplasment

| # Filte | Pwoblem | Zon | Lokalite | Met filte | # Telefon | Fini |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |

#### Filter Ki Bezwen Ranje/Remplasment

| # Filte | Pwoblem | Zon | Lokalite | Met filte | # Telefon | Fini |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |
|  |  |  |  |  |  | □ |

Aqua Clara International

##### PO Box 795-40202 Keroka

Safe Water System Order & Installation Report

Kisii: 0716-406-687; Eldoret: 0716-406-670

Purchaser Information

Purchaser Name (or school room):

Contact Phone:

Village:	Sublocation:

Number living in

Household:

Purchase Agreement

Water Source during Rains:

Date of Birth of Yougest Child:

Water Source during Dry Season:

| QUANTITY | DESCRIPTION | UNIT PRICE | TOTAL |
| --- | --- | --- | --- |
| Total |  |  |  |

- Filler (Sand/Ballast) Preparation & Transport. The purchaser agrees to arrange for the transport and preparation (sieving & washing) of the sand and ballast for their purchased filter. The Installer (CDO) agrees to properly train the purchasing household in these tasks, working alongside of them.

- Installation. The Installer (CDO) will be present to install the filter once filler is prepared. The installer will fully train the purchaser in proper filter care and use, as well as on related safe water storage techniques.

- Maintenance. Filters require simple maintenance. Included in the purchase price is a fee that covers the first maintenance visit. When the filter slows to 1 liter in five minutes or more, call the installer (CDO), who will come to conduct simple maintenance, training the purchaser in the process.

- Community Health Promoter Visit. ACI CHPs will visit the filter owner 1-2 months after the installation. They will re-train on filter use, safe water storage and related household hygiene.

Additional Filter Installation Information

Sold By (CDO): 	  Purchased By:

| Exact Date Installed | Standing water depth at installation | Flow rate at installation (pour 10 liters of water exactly, then time 1 liter) |
| --- | --- | --- |

| Filter Unit Number | Construction Site (School) | Installed by (CDO Name) | Installer Contact # (CDO Phone #) |
| --- | --- | --- | --- |

TODAYS DATE:

SHIP LUSAKA

BIOSAND FILTER FOLLOW-UP RECORD

### FILTER #: 	 INSTALLATION DATE:

### FOLLOW UP PERSONNEL:

### HOUSE #: 	 LOCATION:

### FILTER POSITION IN THE HOUSE:

### OWNER’S NAME:

### HAVE YOU CARRIED OUT SAND CLEANING?

### HOW OFTEN AND WHY?

#### IS CHLORINE BEING ADDED TO THE FILTERED WATER?(Explain why; 1capful

#### chlorine/20L or 20 drops Jik/ 20L)

### NUMBER OF USERS:	ADULTS: 	 CHILDREN:

### WHAT PROBLEMS HAVE YOU ENCOUNTERED WITH THE USE OR MAINTENANCE OF THE FILTER:

### WHERE IS WATER SOURCE:

#### HEALTH PROBLEMS (water related):	 Diarrhoea Frequency

####  Skin Infections

####  Stomach Aches

####  Eye Infections

### WATER VOLUME USED DAILY:

| Brochure Provided | Cracks or Leaks | Lid | Diffuser | Sand Level (5 cm) | Container Supplied | Flow Rate (400 ml/min) | Observed Swirl & Dump |
| --- | --- | --- | --- | --- | --- | --- | --- |

#### Note any changes or potential problems you observe:

Monitoring Form – Biosand Filter Project, Santa Barbara, Honduras

Community	 Municipality

Date

Filter #	 Name		# Persons who benefit

- Condition and Care of Filter

In daily use?	 if not, why?	Leaks?

Moved?	Flow rate	 sec./litre Filter level?	Sand level?     Sand height (14-15” “opt)

Sand added?

Depth of water ( 2 “ ideal)	 Pipes in place?	 if not, why	 Bucket use

  - Cleanliness: outside of filter	inside of filter	diffuser	pipes	bucket

How often clean the pipes and bucket?	Use purified water and soap or bleach?

  - Have they cleaned sand?	 if yes, why?	How many times

When last?	 Comments

  - Daily throughput (l.)	Timing of use 	Rest time between uses?

  - Water source: Tap	Storage tank	Well	Creek	Other

  - Turbidity of input water: Clear	Turbid (NTU est.)	Other

#### Care of Filtered Water

Storage of water: Jugs/bottles	Bucket 	Other containers	 closed	 open

Cleanliness of water containers?

Do you add bleach to the purified water?	 Use eyedropper/pencil	How many drops?

If no bleach, why?

- General

Any questions about managing the filter?

How do you like your filter?

How do you like the flavour of the filtered water: unchanged	better	cooler

Stomach problems? Didn’t have any	better now	no change

- Water Samples? 	Time of sampling	 Filter last used when?

Results: Filter (ecu/100ml) water in	 water out	Stored Water

Comments: