## Slide 1
Public Safety and Justice Facilities
TIBC OJS Subcommittee
November 6, 2023

## Slide 2: Agenda
    80 IAM 9 - Construction FI&R Funding Allocation Methodology Overview
    80 IAM 12 - PS&J Construction Site Assessment and Capital Investment (SA-CI) Program
    PS&J - Construction Updates
    PS&J SA-CI Status
    PS&J SA-CI FY 2022 and FY2023 Project List

## Slide 3: 80 IAM 9 - Construction FI&R Funding Allocation Methodology Overview
    The FI&R program prioritizes funding for projects to improve the conditions of facilities that are necessary to provide safe and functional facilities.
    The amount of (FY12X – FY23X) PS&J FI&R funding currently available is $27.5M.
    There are a lot of PS&J FI&R funds, but PS&J New Construction funds are much more limited.
    Your respective Agency and/or Region identifies, approves, and funds potential projects for Federally funded facilities.
    The Branch of PS&J Construction/FI&R has been established to build internal capacity so that we can focus on PS&J FI&R projects.

## Slide 4: 80 IAM 12 - PS&J Construction Site Assessment and Capital Investment (SA-CI) Program
Identifying eligible facilities
All BIA PS&J facilities will be considered
In the first quarter of each fiscal year (FY), OFPSM/DFMC will identify all PS&J facilities that have their Facility Condition Index (FCI) rated in “poor” condition.
Poor condition = FCI > 0.15
FCI = Total DM / CRV.
DM = deferred maintenance for the asset.
CRV = current replacement value for the asset.

## Slide 5: 80 IAM 12 - PS&J Construction Site Assessment and Capital Investment (SA-CI) Program
Ranking criteria for eligible facilities are considered in the order below:
1) the age of the facility
2) adherence to space requirements
3) operational impacts due to life safety and health issues
4) if the facilities were a re-use or renovation
Subsequently, the ranking criteria for Detention Center facilities only will also be considered in the order below:
5) inmate population and number of admissions
6) proximity to services
All facilities that are already being funded in a Replacement or Major FI&R project will be excluded from ranking in the SA-CI Program.

## Slide 6: 80 IAM 12 - PS&J Construction Site Assessment and Capital Investment (SA-CI) Program
The site project plans will result in one of four recommendations:
  a) Replace the facility;
  b) Replace/consolidate a limited number of buildings;
  c) Initiate a major renovation and/or focused facilities improvement & repair (FI&R); or
  d) Execute a combination of b & c above.
  The SA-CI program is a tool to assess the condition of facilities, the FY of the assessment is not associated with funding.
  Sites are still able to receive funding for FI&R projects without impacting their place on the SA-CI project list.
  105(l) Facility Lease Program may be an option
  Link to the 105(l) Technical Assistance Guidebook https://www.bia.gov/as-ia/ofpsm/brpl/105lp

## Slide 7: PS&J - Construction Status
 | Project | State | Beds | Type |  | Phase | ECD | Status
Detention Center Replacement | Hopi Detention | AZ | 60 | FAR |  | Design-Build | FY24 Q4 | Awarded March 2021, 66% complete.
 | Blackfeet Detention | MT | 45 | FAR |  | Design | FY26 Q3 | The design was awarded August 2022, the design is 64% complete.
 | Mescalero Detention | NM | 40 | FAR |  | Design-Build | FY24 Q4 | Awarded April 2022, 47% complete.
 | Sisseton-Wahpeton Oyate Detention | SD | 25 | PL 93-638 |  | Construction | FY25 Q3 | The Design-Build Construction was awarded September 30, 2023, 11% complete.
 | Turtle Mountain Detention | ND | 60 | PL 93-638 |  | Construction | FY26 Q1 | Awarded September 2020, 37% complete.
 | Quinault Detention | WA | 25 | FAR |  | Design | FY27 Q2 | The design was awarded July 2020, 40% design complete.
 | Window Rock Detention | AZ | 45 | FAR |  | Pre-Planning | TBD | The Planning and 20% Design are still to be awarded.
 | Warm Springs Detention | OR | 60 | FAR |  | Planning | FY28 Q2 | Planning was awarded August 2022, 45% complete.

## Slide 8: PS&J SA-CI Status
The PS&J Site Assessment - Capital Investment (SA-CI) program is a pilot program, initiated in FY2022, and modeled after the Education SA-CI program. The program coordinates New Construction, FI&R, and Quarters funding by generating site-level project plans. The SA-CI selection process considers the Facility Condition Index (FCI), age, detainee capacity and other factors. Once selected, locations are notified and provided an orientation, third-party assessment, DFMC led site visit, FIRB presentation and decision, which leads to the execution of the project.
All FY2022 Final Condition Assessments have been received from the contractor. Award of FY2023 Condition Assessments contract is anticipated by FY2024 Q2.
 | Year | Sites Selected | Orientations Completed | Third Party Assessments Completed | DFMC Site-visit | FIRB Presentation and Decision
 | FY 2022 | 5 | 5 | 5 | 5 | 0
 | FY 2023 | 2 | 0 | 0 | 0 | 0

## Slide 9: PS&J SA-CI FY 2022 and FY2023 Project List
SA-CI (PS&J) - FY 2023 | Region | State
1. Northern Cheyenne (Lame Deer Detention Center) | Rocky Mountain | MT
2. Wind River Adult Detention Center | Rocky Mountain | WY

## Slide 10
THANK YOU!
Michael Wischnewski: Deputy Director, Office of Facilities, Property and Safety Management
Michael.Wischnewski@bia.gov